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[bookmark: _Hlk120113180]ENMIENDAS AL PROGRAMA DE TRABAJO DEL PNUMA 
PARA EL AÑO 2022








OBSERVACIONES Y RECOMENDACIONES DE LA SECRETARÍA
[bookmark: _Hlk120287426]El PNUMA solicita al Comité Ejecutivo aprobar la suma de 4.645.044 $EUA, más gastos de apoyo de 370.914 $EUA, para las enmiendas al programa de trabajo para el año 2022 que se indican en el Cuadro 1. Se adjunta al presente documento la comunicación presentada por el PNUMA.
Cuadro 1: Enmiendas al programa de trabajo del PNUMA para el año 2022
	País
	Actividad o Proyecto
	Monto solicitado ($EUA)
	Monto recomendado ($EUA)

	SECCIÓN A: ACTIVIDADES RECOMENDADAS PARA APROBACIÓN GENERAL

	[bookmark: _Hlk117865714]A1: Renovación de proyectos de fortalecimiento institucional (FI)

	Belice
	Renovación de proyecto de FI (fase XI)
	98.176
	98.176

	Botswana
	Renovación de proyecto de FI (fase VI)
	100.061
	100.061

	Brunei Darussalam
	Renovación de proyecto de FI (fase VIII)
	89.600
	89.600

	Côte d’Ivoire
	Renovación de proyecto de FI (fase X)
	136.115
	136.115

	Djibouti
	Renovación de proyecto de FI (fase VIII)
	85.000
	85.000

	El Salvador
	Renovación de proyecto de FI (fase VI)
	85.000
	85.000

	Fiji
	Renovación de proyecto de FI (fase XIII)
	85.000
	85.000

	Kirguistán
	Renovación de proyecto de FI (fase XI)
	148.262
	148.262

	República Democrática Popular Lao
	Renovación de proyecto de FI (fase XI)
	85.000
	85.000

	Mauritania
	Renovación de proyecto de FI (fase VIII)
	85.000
	85.000

	Mozambique
	Renovación de proyecto de FI (fase X)
	103.424
	103.424

	Perú
	Renovación de proyecto de FI (fase VI)
	170.893
	170.893

	Seychelles
	Renovación de proyecto de FI (fase X)
	85.000
	85.000

	Sierra Leona
	Renovación de proyecto de FI (fase IX)
	109.824
	109.824

	República Unida de Tanzanía (la)
	Renovación de proyecto de FI (fase VIII)
	85.000
	85.000

	Viet Nam
	Renovación de proyecto de FI (fase XIV)
	152.289
	152.289

	Total A1
	1.703.644
	1.703.644

	A2: Asistencia técnica para la elaboración de informes de verificación del consumo de HCFC

	Brunei Darussalam
	Informe de verificación, etapa II del PGEH
	30.000
	30.000

	Cabo Verde
	Informe de verificación, etapa II del PGEH 
	30.000
	30.000

	Comoras 
	Informe de verificación, etapa II del PGEH
	30.000
	30.000

	Malawi
	Informe de verificación, etapa II del PGEH 
	30.000
	30.000

	Paraguay
	Informe de verificación, etapa II del PGEH 
	30.000
	30.000

	Rwanda
	Informe de verificación, etapa II del PGEH 
	30.000
	30.000

	Togo
	Informe de verificación, etapa II del PGEH
	30.000
	30.000

	Uganda
	Informe de verificación, etapa II del PGEH
	30.000
	30.000

	República Unida de Tanzanía (la)
	Informe de verificación, etapa II del PGEH
	30.000
	30.000

	Zambia
	Informe de verificación, etapa II del PGEH 
	30.000
	30.000

	Subtotal A2
	300.000
	300.000

	Gastos de apoyo
	39.000
	39.000

	Total A2
	339.000
	339.000

	A3: Elaboración de proyectos relativos a planes de aplicación de la Enmienda de Kigali (KIP) KIP

	Cabo Verde
	Elaboración de un KIP KIP (etapa I)
	130.000
	130.000

	Comoras (las)
	Elaboración de un KIP (etapa I)
	100.000
	100.000

	Congo (el) a
	Elaboración de un KIP (etapa I)
	51.000
	51.000

	Côte d’Ivoire b
	Elaboración de un KIP (etapa I)
	133.000
	133.000

	Gabón b
	Elaboración de un KIP (etapa I)
	133.000
	133.000

	Guinea-Bissau b
	Elaboración de un KIP (etapa I)
	91.000
	91.000

	Mongolia
	Elaboración de un KIP (etapa I)
	130.000
	130.000

	Santa Lucía b
	Elaboración de un KIP (etapa I)
	90.000
	90.000

	República Unida de Tanzanía (la)b
	Elaboración de un KIP (etapa I)
	91.000
	91.000

	Zimbabwe c
	Elaboración de un KIP (etapa I)
	119.000
	119.000

	Subtotal A3
	1.068.000
	1.068.000

	 Gastos de apoyo
	138.840
	138.840

	Total A3
	1.206.840
	1.206.840

	A4: Elaboración de proyectos relativos a un plan regional de aplicación de la Enmienda de Kigali

	12 Países insulares del Pacífico
	Elaboración de un plan regional de aplicación de la Enmienda de Kigali (etapa I) en Islas Cook, Kiribati, Islas Marshall, Micronesia (Estados Federados de), Nauru, Niue, Palau, Samoa, Islas Salomón, Tonga, Tuvalu y Vanuatu
	780.000
	780.000

	Subtotal A4
	780.000
	780.000

	 Gastos de apoyo
	95.800
	95.800

	Total A4
	875.800
	875.800

	SECCIÓN B: ACTIVIDADES RECOMENDADAS PARA CONSIDERACIÓN INDIVIDUAL

	B1. Asistencia técnica 

	Global
	Articulación entre encargados de oficinas del ozono y autoridades nacionales en materia de eficiencia energética en apoyo de los objetivos de la Enmienda de Kigali
	[bookmark: _Hlk118012807]793.400
	*

	Subtotal B1
	793.400
	*

	 Gastos de apoyo
	97.274
	*

	Total B1
	890.674
	*

	Total A1, A2, A3, A4 y B1
	4.645.044
	3.851.644

	Gastos de apoyo para A1, A2, A3, A4 y B1
	370.914
	273.640

	Total general
	5.015.958
	4.125.284


a Con la ONUDI como principal organismo de ejecución.
b Con la ONUDI como organismo cooperante.
c Con el PNUD como organismo cooperante.
* Recomendado para consideración individual.

SECCIÓN A: ACTIVIDADES RECOMENDADAS PARA APROBACIÓN GENERAL
[bookmark: _Hlk117865673]A1: Renovación de proyectos de fortalecimiento institucional
Descripción del proyecto
El PNUMA presentó sendas solicitudes de financiamiento para la renovación de los proyectos de fortalecimiento institucional de los países que se indica en la sección A1 del Cuadro 1. Los proyectos se detallan en el Anexo I al presente documento.
Observaciones de la Secretaría
La Secretaría analizó las solicitudes de renovación de 16 proyectos de fortalecimiento institucional presentadas por el PNUMA a nombre de los respectivos Gobiernos a la luz de las pautas y decisiones relativas a admisibilidad y niveles de financiamiento. Las solicitudes se confrontaron con los planes de trabajo de fortalecimiento institucional de la fase anterior, con los datos del programa país y del artículo 7, con el último informe de ejecución del plan de gestión para la eliminación de HCFC (PGEH), con el informe de avance presentado por el organismo de ejecución, y con las correspondientes resoluciones de la Reunión de las Partes. Se constató que todos los países han presentado los datos de sus programas país para el año 2021, que han dado cumplimiento a las metas de control previstas en el Protocolo de Montreal, y que su consumo anual de HCFC no excede el máximo permitido en el Acuerdo con el Comité Ejecutivo. De conformidad con la decisión 74/51 e), las solicitudes presentadas contenían además indicadores de desempeño para las actividades previstas en la siguiente fase de cada proyecto.
Recomendación de la Secretaría
La Secretaría recomienda la aprobación general de las solicitudes de renovación de proyectos de fortalecimiento institucional para Belice, Botswana, Brunei Darussalam, Côte d’Ivoire, Djibouti, El Salvador, Fiji, Kirguistán, la República Democrática Popular Lao, Mauritania, Mozambique, Perú, Seychelles, Sierra Leona, la República Unida de Tanzanía y Viet Nam, al nivel de financiamiento que se indica en la sección A1 del Cuadro 1 anterior. El Comité Ejecutivo podrá estimar oportuno remitir a los respectivos Gobiernos las observaciones que se formulan en el Anexo II al presente documento.
A2: Asistencia técnica para la elaboración de informes de verificación del consumo de HCFC
Descripción del proyecto
El Comité Ejecutivo solicitó a los organismos bilaterales y de ejecución considerar, en las enmiendas a sus respectivos programas de trabajo a presentar a la 91ª reunión, los fondos necesarios para la elaboración de los informes de verificación de ciertos países del artículo 5. El PNUMA, en su calidad de principal organismo de ejecución, solicita financiamiento para los informes de verificación correspondientes a la etapa II de los PGEH de Brunei Darussalam, Cabo Verde, las Comoras, Malawi, Paraguay, Rwanda, Togo, Uganda, la República Unida de Tanzanía y Zambia.[footnoteRef:2] [2:  Decisión 90/33.] 

Observaciones de la Secretaría
La Secretaría constata que los montos solicitados concuerdan con lo aprobado para similares propósitos en reuniones anteriores y recuerda que los informes de verificación se deben presentar al menos 10 semanas antes de la reunión del Comité Ejecutivo en que se solicite el siguiente tramo de financiamiento del PGEH.
Recomendación de la Secretaría
La Secretaría recomienda la aprobación general de los fondos solicitados para elaborar los informes de verificación correspondientes a la etapa II de los PGEH de Brunei Darussalam, Cabo Verde, las Comoras, Malawi, Paraguay, Rwanda, Togo, Uganda, la República Unida de Tanzanía y Zambia, al nivel de financiamiento que se indica en la sección A2 del Cuadro 1 anterior, en el entendido de que dichos informes serán presentados al menos 10 semanas antes de la reunión del Comité Ejecutivo en que se solicite el siguiente tramo de financiamiento del PGEH.
A3: Elaboración de proyectos relativos a planes de aplicación de la Enmienda de Kigali (KIP)
Descripción del proyecto
El PNUMA solicitó fondos para preparar la etapa I del plan de aplicación de la Enmienda de Kigali (KIP) en tres países del artículo 5 en calidad de organismo de ejecución designado; de otros seis países en calidad de principal organismo de ejecución, con la ONUDI como cooperante en cinco de ellos y el PNUD como cooperante en uno; y de un país del artículo 5 en calidad de cooperante con la ONUDI como principal organismo de ejecución, según se muestra en la sección A3 del Cuadro 1 anterior. En las enmiendas a sus respectivos programas de trabajo para el año 2022,[footnoteRef:3] el PNUD, en su calidad de organismo cooperante en Zimbabwe, solicita 51.000 $EUA más gastos de apoyo de 3.570 $EUA, en tanto que la ONUDI, en calidad de principal organismo de ejecución en el Congo y de cooperante en Côte d’Ivoire, Gabón, Guinea-Bissau, Santa Lucía y la República Unida de Tanzanía, solicita 351.000 $EUA más gastos de apoyo de 24.570 $EUA. [3:  UNEP/OzL.Pro/ExCom/90/32 y UNEP/OzL.Pro/ExCom/90/34.] 

Observaciones de la Secretaría
La Secretaría analizó las solicitudes en base a las pautas de financiamiento para planes de aplicación de la Enmienda de Kigali (KIP) contenidas en la decisión 87/50, a las iniciativas propuestas y a su nexo con las actividades de apoyo y demás proyectos relativos a los HFC en los respectivos países. Utilizando el formulario para planes de aplicación de la Enmienda, el PNUMA, como organismo de ejecución principal o designado, describió las actividades involucradas en la elaboración de las estrategias transversales para los planes de aplicación de la Enmienda de Kigali de Cabo Verde, las Comoras, Côte d’Ivoire, Gabón, Guinea-Bissau, Mongolia, Santa Lucía, la República Unida de Tanzanía y Zimbabwe, adjuntando para cada país los datos de consumo de HFC y sus mezclas. Entre las actividades de preparación de proyectos contempladas para estos nueve países se cuentan un estudio y recopilación de datos de consumo de HFC por país; un análisis del uso de HFC y sus alternativas; estudios del marco legislativo y de políticas sectoriales; una recopilación de datos y análisis de las capacidades del sector servicio técnico; una evaluación de las necesidades de capacitación y equipamiento; el desarrollo de una estrategia transversal de reducción de los HFC; reuniones consultivas con las contrapartes, y reuniones de validación de datos. Además de lo indicado, en algunos países se agregaron actividades de análisis de las necesidades y capacidades de las estructuras de aduanas, comercio y fiscalización; consideraciones sobre integración de la perspectiva de género; un análisis de las normas y códigos actuales y por desarrollar, incluyendo respecto de refrigerantes inflamables y criterios mínimos de eficiencia energética; análisis del sistema de reciclaje y regeneración; elaboración de las primeras políticas y normas de regulación de los HFC y sus correspondientes planes de comunicación, y el desarrollo de estrategias respecto de las tecnologías ecoenergéticas existentes en el mercado.
El PNUMA aclaró que la preparación de las estrategias transversales para los KIP de cada país se sustentará en las actividades de apoyo previamente realizadas que sirvieron de punta de lanza para la reducción de los HFC y contribuyeron a la ratificación de la Enmienda de Kigali.
Tras el análisis, la Secretaría constató que los nueve países donde el PNUMA es el organismo de ejecución principal o designado han ratificado la Enmienda de Kigali;[footnoteRef:4] que todos han manifestado por escrito su intención de adoptar prontas medidas tendientes a la reducción de los HFC y que el financiamiento solicitado es concordante con la decisión 87/50 c). [4:  Fecha de ratificación (o aceptación) de la Enmienda Kigali: Cabo Verde (28 de octubre de 2020), las Comoras (16 de noviembre de 2017), Côte d’Ivoire (29 de noviembre de 2017), Gabón (28 de febrero de 2018), Guinea‑Bissau (22 de octubre de 2018), Mongolia (27 de julio de 2022), Santa Lucía (2 de noviembre de 2021) y la República Unida de Tanzanía (25 de marzo de 2022) y Zimbabwe (18 de octubre de 2022).] 

[bookmark: _Hlk104444546]La ONUDI, en calidad de principal organismo de ejecución, describió en las enmiendas a su programa de trabajo las actividades que requerirá la preparación del KIP del Congo, indicando además los costos correspondientes y las observaciones de la Secretaría al respecto.[footnoteRef:5] [5:  UNEP/OzL.Pro/ExCom/90/34.] 

Recomendación de la Secretaría
La Secretaría recomienda la aprobación general de los fondos solicitados para elaborar los planes de aplicación de la Enmienda de Kigali de Cabo Verde, las Comoras, Congo, Côte d’Ivoire, Gabón, Guinea-Bissau, Mongolia, Santa Lucía, la República Unida de Tanzanía y Zimbabwe, al nivel de financiamiento que muestra la sección A3 del Cuadro 1 anterior.
A4: Elaboración de proyectos relativos a un plan regional de aplicación de la Enmienda de Kigali
Descripción del proyecto
En calidad de organismo de ejecución designado, y según se indica en la sección A4 del Cuadro 1 anterior, el PNUMA presentó una solicitud relativa a la elaboración de la etapa I del plan regional de aplicación de la Enmienda de Kigali de los Países Insulares del Pacífico, por un monto total de 780.000 $EUA más gastos de apoyo de 95.800 $EUA. El Cuadro 2 muestra el consumo base de HCFC en cada país.
Cuadro 2. Consumo base de HCFC para financiamiento, Países Insulares del Pacífico
	País
	Base de comparación
(tons. PAO)

	
	

	Islas Cook 
	0.10

	Kiribati
	0.10

	Islas Marshall 
	0.20

	Micronesia (Estados Federados de)
	0.20

	Nauru
	0.00

	Niue
	0.00

	Palau
	0.20

	Samoa
	0.30

	Islas Salomón
	2.00

	Tonga
	0.10

	Tuvalu
	0.10

	Vanuatu
	0.30

	Total
	3.60



La presentación entrega los datos de consumo de HFC y sus mezclas en el período 2016-2021 para 10 países (Islas Cook, Kiribati, Islas Marshall, Estados Federados de Micronesia, Niue, Palau, Samoa, Tonga, Tuvalu y Vanuatu); Nauru e Islas Salomón no cuentan con información para el período 2019-2021. Las actividades de elaboración de proyectos incluyen una evaluación de necesidades y el desarrollo de una estrategia transversal de reducción de los HFC; un estudio y recopilación de datos de consumo de HFC por país; un análisis del uso de HFC y sus alternativas; reuniones de validación de datos con contrapartes, y talleres y coordinación regionales. El detalle de la propuesta figura en la presentación sobre enmiendas al programa de trabajo del PNUMA para el año 2022 adjunta al presente documento.
Observaciones de la Secretaría
La Secretaría analizó la solicitud en base a las pautas de financiamiento para planes de aplicación de la Enmienda de Kigali (KIP) contenidas en la decisión 87/50, a las iniciativas propuestas y a su nexo con las actividades de apoyo y demás proyectos relativos a los HFC en los respectivos países. Utilizando el formulario para planes de aplicación de la Enmienda, el PNUMA, como organismo de ejecución principal o designado, describió las actividades involucradas en la elaboración de una estrategia transversal para el KIP de los Países Insulares del Pacífico. El PNUMA explicó que la etapa I tendrá carácter regional, fórmula que en países de similares características ha dado buenos resultados como método de intercambio de experiencias y mejores prácticas de ejecución de los PGEH. La elaboración del plan regional considera un conjunto de iniciativas nacionales a cargo de cada país y de otras de tipo regional a cargo del PNUMA, las que se centrarán principalmente en un proceso de consultas entre países orientado a alcanzar una visión conjunta de las actividades previstas y de los resultados que se espera lograr en las etapas de elaboración y ejecución.
Tras el análisis, la Secretaría constató que los 12 países han ratificado la Enmienda de Kigali;[footnoteRef:6] que todos han manifestado por escrito su intención de adoptar prontas medidas tendientes a la reducción de los HFC, y que el financiamiento solicitado para la elaboración del KIP regional es 450.000 $EUA menor a la cifra que cada país habría recibido por separado según la decisión 87/50 c). [6:  Fecha de ratificación (o aceptación) de la Enmienda de Kigali: Islas Cook (22 de agosto de 2019), Kiribati (26 de octubre de 2018), Islas Marshall (15 de mayo de 2017), Estados Federados de Micronesia (12 de mayo de 2017), Nauru (3 de noviembre de 2022), Niue (24 de abril de 2018), Palau (29 de agosto de 2017), Samoa (23 de marzo de 2018), Islas Salomón (23 de mayo de 2022), Tonga (17 de septiembre de 2018), Tuvalu (21 de septiembre de 2017) y Vanuatu (20 de abril de 2018).] 

Recomendación de la Secretaría
La Secretaría recomienda la aprobación general de los fondos solicitados para elaborar el KIP regional de los Países insulares del Pacífico, al nivel de financiamiento que se indica en la sección A4 del Cuadro 1 anterior.
SECCIÓN B: ACTIVIDADES RECOMENDADAS PARA CONSIDERACIÓN INDIVIDUAL
B1: Asistencia técnica
Global:	 Articulación entre encargados de oficinas del ozono y autoridades nacionales en materia de eficiencia energética en apoyo de los objetivos de la Enmienda de Kigali

Descripción del proyecto
Según se muestra en la sección B1 del Cuadro 1, el PNUMA solicitó financiamiento para un proyecto global de asistencia técnica en la suma de 793.400 $EUA más gastos de apoyo de 92.274 $EUA.
Este proyecto se orienta a satisfacer la necesidad, expresada por los países del artículo 5, de disponer de una plataforma de fortalecimiento de capacidades para contrapartes vinculadas al ozono y la energía en temas relativos a la Enmienda de Kigali. Esta plataforma operaría en base a la articulación a través de las redes regionales de los encargados de oficinas del ozono con las autoridades nacionales en materia de eficiencia energética, con miras a fortalecer las capacidades y la cooperación en el cumplimiento de los objetivos de la Enmienda de Kigali. Esta actividad de articulación permitiría a las oficinas nacionales del ozono (ONO) entender de mejor manera las políticas, programas y proyectos de eficiencia energética (p. ej., normas mínimas, programas de etiquetado, políticas sectoriales), al tiempo de fortalecer la comprensión por parte de las autoridades nacionales en materia de eficiencia energética de los requisitos y objetivos de cumplimiento del Protocolo de Montreal.
La propuesta se construye en base a los resultados de un proyecto anterior financiado por otro mecanismo[footnoteRef:7] con apoyo del Programa de Asistencia al Cumplimiento (PAC) del PNUMA, iniciativa que permitió fortalecer las capacidades de participantes de países del artículo 5 respecto de sus respectivos programas y reforzó (y en algunos casos, impulsó) los procesos de consulta nacionales respecto del nexo entre ozono y eficiencia energética. [7:  El Programa de Kigali para la Refrigeración Eficiente, actualmente denominado Clean Cooling Collaborative.] 

El proyecto consta de cuatro partes: El componente I comprende la identificación de los principales participantes en talleres y una evaluación de necesidades por región a fin de determinar la información que los países necesitan para trabajar con las contrapartes en el diseño de temarios para talleres. El componente II consistirá en talleres de dos días de duración realizados inmediatamente a continuación de las reuniones regionales que sostendrán en 2023 y 2024 los encargados de ONO con las autoridades nacionales en materia de eficiencia energética y los coordinadores de mecanismos financieros nacionales,[footnoteRef:8] a fin de comprometerlos en el logro de los objetivos de Kigali. El componente III, por su parte, considera el desarrollo o intercambio de materiales de fortalecimiento de capacidades sobre eficiencia energética y refrigerantes de bajo PCA según las necesidades que determinen los encargados de las ONO y las autoridades nacionales en materia energética, en tanto que el componente IV se ocupará del seguimiento y evaluación del proyecto. [8:  Se refiere a los entes coordinadores operativos de mecanismos financieros tales como el FMAM y el FVC.] 

El proyecto se implementaría en dos fases; la presente solicitud de financiamiento se refiere sólo a la primera, a ejecutar en el período 2023-2024. El financiamiento de la segunda fase se solicitaría en el ejercicio 2024 para su ejecución en 2025 y 2026, según los resultados de la primera fase. Se plantea cubrir algunas partidas con el presupuesto para redes regionales contemplado en el programa de trabajo 2023‑2024 del PAC, según se indica en el Cuadro 3.
Cuadro 3. Propuesta presupuestaria para asistencia técnica al proyecto de articulación
	Descripción
	Personas
	Costo ($EUA)

	
	
	Fase 1
2022
	Fase 2
2024

	Encargados nacionales de oficinas del ozono - viajes y viáticos*
	147
	0
	0

	Autoridades nacionales en materia de eficiencia energética - viajes y viáticos
	147
	286.020
	286.020

	Entes coordinadores de mecanismos financieros nacionales - viajes y viáticos
	147
	286.020
	286.020

	Organismos regionales de eficiencia energética - viajes y viáticos
	20
	39.200
	39.200

	Colaboradores y especialistas - viajes y viáticos
	20
	79.200
	79.200

	Arriendo de recintos, logística e interpretación simultánea*
	10
	0
	0

	Experto técnico de apoyo a la entrega de proyectos
	1
	102.960
	102.960

	Materiales de fortalecimiento de capacidades *
	—
	0
	0

	Total por año
	
	793.400
	793.400

	Total general
	
	1.586.800


* Con cargo al presupuesto para redes regionales contemplado en el programa de trabajo 2023-2024 del PAC.

Observaciones de la Secretaría
La Secretaría solicitó al PNUMA explicar qué valor agregaría el proyecto de articulación de redes regionales a la luz de la experiencia recogida en talleres de articulación anteriores y de cómo dichas experiencias se tuvieron en cuenta para formular la propuesta; por qué los talleres no podrían hacerse como parte de las actividades sobre redes regionales del PAC; qué se espera lograr en cuanto a institucionalizar la colaboración con las autoridades en materia energética de países del artículo 5, y qué beneficios aportaría esta iniciativa a las resoluciones del Comité Ejecutivo relacionadas directamente con la asistencia a países de bajo consumo para fortalecer la colaboración con organismos e instituciones en materia de promover la eficiencia energética.[footnoteRef:9] La Secretaría también preguntó sobre el financiamiento solicitado y cómo se armoniza con el presupuesto del PAC. [9:  Coordinación y colaboración entre las ONO y las autoridades y entidades del ramo a fin de que los refrigerantes de bajo PCA se consideren en los planes de refrigeración y eficiencia energética, lo que comprende desde normas mínimas de eficiencia energética y, donde corresponda, programas de etiquetado y prueba, hasta normas para equipos de refrigeración, climatización y bomba de calor (decisión 89/6 b) iii)).] 

En respuesta, el PNUMA explicó que aunque los anteriores talleres de articulación proporcionaron un marco inicial para el diálogo y la cooperación entre las ONO y las autoridades en materia energética, éstos no generaron mecanismos formales de coordinación, dado que en ese entonces la mayoría de los países aún no había ratificado la Enmienda de Kigali y por ende no existía un compromiso reglamentario de eliminar los HFC. El PNUMA subrayó que el proyecto fortalecerá las relaciones iniciadas en talleres y actividades de apoyo, señalando haber recogido algunas de las experiencias del proyecto anterior e identificado vacíos que el propuesto apunta a resolver. Entre éstos, cabe mencionar la necesidad de fortalecer la colaboración institucional en materia de eficiencia energética y gestión de refrigerantes; la capacitación y desarrollo de capacidades para demostrar las ventajas de los equipos ecoenergéticos; un mejor diseño de políticas públicas que garantice la integración de los tipos de refrigerante en las normas mínimas de eficiencia energética; apoyar una infraestructura que asegure la aplicación y fiscalización de las normas de eficiencia energética y las exigencias de la Enmienda de Kigali; respaldar la adopción por parte del mercado de equipos ecoenergéticos de bajo PCA a través de demostrar sus ventajas, e incentivar un compromiso de cooperación permanente entre los encargados de las ONO y las contrapartes a cargo de temas energéticos.
El PNUMA explicó asimismo que, para optimizar los costos, los talleres se realizarían de forma inmediatamente consecutiva a las reuniones de las redes regionales y que sólo se solicita el adicional necesario para costear la participación de las autoridades en materia energética, costo que no podría ser solventado por el PAC sin afectar la asistencia general que presta a los países. Dado que el proyecto está pensado como plataforma de fortalecimiento de capacidades e intercambio de información, no se prevé expresamente alcanzar ningún tipo de compromiso específico; sin embargo, al igual que en las reuniones de redes, se espera poder adoptar recomendaciones, incluso aunque no sean vinculantes, y que los países participantes opten por comprometerse voluntariamente con medidas específicas a las que se dará seguimiento a través de las redes regionales.
En cuanto al efecto sobre las decisiones del Comité Ejecutivo, especialmente respecto de países de bajo consumo, el PNUMA aclaró que los talleres permitirían a las ONO identificar oportunidades para concretar proyectos y actividades de eficiencia energética relativas a sustancias controladas e interactuar con contrapartes nacionales en materia de eficiencia energética en apoyo al sector de servicio técnico. Esto hará que las ONO estén en mejores condiciones para proponer proyectos de eficiencia energética y para coordinarse con sus contrapartes en materia de eficiencia energética durante las etapas de desarrollo y ejecución.
El PNUMA redujo el presupuesto solicitado de 975.420 $EUA a 793.400 $EUA tras racionalizar el costo de días extras para la ONO, los costos de uso del recinto de reunión y los costos de desarrollar materiales de extensión y fortalecimiento de capacidades. El PNUMA actualizó la propuesta a fin de incluir los elementos señalados por la Secretaría y las modificaciones al presupuesto. El detalle figura en la presentación adjunta al presente documento.
Recomendación de la Secretaría
El Comité Ejecutivo podrá estimar oportuno considerar la aprobación del proyecto global de asistencia técnica denominado Articulación entre encargados de oficinas del ozono y autoridades nacionales en materia de eficiencia energética en apoyo de los objetivos de la Enmienda de Kigali (fase I: 2023-2024) en la suma de 793.400 $EUA más gastos de apoyo de 92.274 $EUA, en el entendido de que:
(a) El PNUMA presentará a la última reunión del Comité Ejecutivo del año 2023 un informe parcial sobre el avance del proyecto mencionado en el párrafo 29 como parte del informe sobre la marcha de las actividades del Programa de Asistencia al Cumplimiento (PAC);
(b) La segunda fase del proyecto se presentará a la segunda reunión del año 2024 exclusivamente como parte del presupuesto del PAC, y deberá incluir un informe final en el que se detallen las experiencias recogidas durante la primera fase; y
(c) Todo saldo remanente de la primera fase deberá ser reintegrado al Fondo Multilateral a más tardar en la segunda reunión del año 2025.
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INSTITUTIONAL STRENGTHENING PROJECT PROPOSALS[footnoteRef:10] [10:  Data as at December 2021 are based on document UNEP/OzL.Pro/ExCom/91/15.] 
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Belize: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-99
	88,500

	Phase II:
	Jul-03
	76,700

	Phase III:
	Jul-05
	76,700

	Phase IV:
	Nov-07
	76,700

	Phase V:
	Nov-09
	76,700

	Phase VI:
	Apr-12
	76,700

	Phase VII:
	May-14
	76,700

	Phase VIII
	May-16
	98,176

	Phase IX
	Jun-18
	98,176

	Phase X:
	Jul-21
	98,176

		Total:
	843,228

	Amount requested for renewal (phase XI) (US $):
	98,176

	Amount recommended for approval for phase XI (US $): 
	98,176

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XI to the Multilateral Fund (US $):
	98,176

	Date of approval of country programme:
	1999

	Date of approval of HCFC phase-out management plan:
	2010

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	2.8

	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	0.52

	Annex E (methyl bromide)
	0.00

		Total:
	0.52

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	2,262,369

	Amount disbursed (as at December 2021) (US $):
	1,736,418

	ODS to be phased out (as at June 2022) (ODP tonnes):
	25.5

	ODS phased out (as at December 2021) (ODP tonnes):
	24.7



1. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	334,354

	(b)
	Institutional strengthening:
	843,228

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,084,787

		Total:
	2,262,369

	(d)
	HFC activities funded from additional voluntary contributions
	0


Progress report
Despite the challenges of the COVID-19 pandemic, the National Ozone Unit (NOU) of Belize maintained support for public awareness campaigns, strengthened the legislative framework, as well as improved communication and involvement of other public and private organizations during phase X of the institutional strengthening (IS) project. Belize also commenced implementation of the first tranche of stage II of its HCFC phase-out management plan (HPMP) and worked towards completion of stage I. During the phase, the NOU continued to: submit Article 7 and country programme data to the respective Secretariats; monitor and prevent illegal trade in ODS; monitor data collection, analysis, and submission; provide comprehensive public education and awareness; and maintain stakeholder confidence, support and buy-in. Belize fully achieved 33 out of 37 performance indicators and four were partially achieved, due to delays caused by the COVID-19 pandemic.
Plan of action
For the upcoming phase, the Government of Belize will continue to support activities relating to the phase-out of HCFCs and efforts towards the ratification of the Kigali Amendment. With the lessons learned during the COVID-19 pandemic, the NOU has developed new tools that will support implementation, including the ability to host more virtual events and activities. The following actions will be undertaken during the new phase: continuing good coordination of the NOU, strengthening the existing legal framework by formalizing the inclusion of HFCs into the licensing system, and sharing more information regarding the Kigali Amendment, promoting the transition to low-GWP alternatives and implementation of the National Cooling Plan; coordinating and monitoring programme activities under the HPMP; continuing to promote HCFC recovery and recycling and good practices in the refrigeration servicing sector; continuing to strictly enforce the licensing and quota system to prevent the illegal trade of ODS; and implementing public awareness campaigns through mass media and print media. The NOU will also supervise the implementation of the HPMP, maintain timely submission of Article 7 and country programme data, and will participate in Montreal Protocol-related meetings, either in person or virtually.
Botswana: Renewal of institutional strengthening 
	Summary of the project and country profile

	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul. 1994
	90,200

	Phase II:
	Dec. 2003
	78,173

	Phase III:
	Nov. 2007
	78,173

	Phase IV:
	Dec. 2012
	78,173

	Phase V:
	May-16
	100,061

		Total:
	424,780

	Amount requested for renewal (phase VI) (US $):
	100,061

	Amount recommended for approval for phase VI (US $): 
	100,061

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VI to the Multilateral Fund (US $):
	100,061

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan:
	2015

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	11.0

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.2

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	5.42

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	5.42

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	2,490,750

	Amount disbursed (as at December 2021) (US $):
	1,502,257

	ODS to be phased out (as at June 2022) (ODP tonnes):
	12.08

	ODS phased out (as at December 2021) (ODP tonnes):
	8.00



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	720,000

	(b)
	Institutional strengthening:
	424,780

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,345,970

		Total:
	2,490,750

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
Although it began with an initial delay, phase V of the IS project was implemented according to plan. During the reporting period, the National Ozone Office (NOO) of Botswana enforced the ODS regulations through implementation of the licensing and quota system; and embarked on awareness-raising programmes, trained Customs officers, clearing agents, and refrigeration technicians. Botswana also began amending its ODS Regulation to incorporate the provisions of the Kigali Amendment in its draft legal framework on controlled substances under the Montreal Protocol. Botswana fully achieved 12 out of 16 performance indicators selected for the phase and the remaining four were partially achieved.
Plan of action
During the upcoming phase, the country will commit to implement its action plan to ensure sustained compliance with Montreal Protocol. The NOO will continue with the training programme for technicians in the refrigeration sector as well as training of newly recruited and remaining customs officers to support the implementation and enforcement of ODS regulations including control measures of HCFCs.The NOO will also continue with its awareness-raising programme through mass media, non-governmental organizations (NGOs), workshops, and distribution of materials such as brochures, pamphlets and others to the industry and other stakeholders, at Gantsi Agricultural shows, school visits and during gatherings for national celebrations and commemorations.
Brunei Darussalam: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-98
	80,000

	Phase II:
	Jul-04
	70,000

	Phase III:
	Jul-12
	70,000

	Phase IV:
	Nov-14
	70,000

	Phase V:
	May-16
	89,600

	Phase VI:
	Dec-18
	89,600

	Phase VII:
	Dec-20
	89,600

		Total:
	558,800

	Amount requested for renewal (phase VIII) (US $):
	89,600

	Amount recommended for approval for phase VIII (US $): 
	89,600

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	89,600

	Date of approval of country programme:
	1998

	Date of approval of HCFC phase-out management plan (stage I):
	2012

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	6.1

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	3.75

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	3.75

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	1,989,900

	Amount disbursed (as at December 2021) (US $):
	1,505,432

	ODS to be phased out (as at June 2022) (ODP tonnes):
	69.4

	ODS phased out (as at December 2021) (ODP tonnes):
	67.3



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	143,000

	(b)
	Institutional strengthening:
	558,800

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,288,100

		Total:
	1,989,900

	(d)
	HFC activities funded from additional voluntary contributions
	150,000


Progress report
During phase VII of the IS project, Brunei Darussalam was in compliance with its ODS phase-out obligations. The NOU continued enforcing its HCFC licensing and quota system through the application permit system; all imports are recorded in the national single window system. Brunei Darussalam also submitted its country programme and Article 7 data reports in a timely manner, following close cooperation between the NOU and the Royal Customs and Excise Department. In addition, the NOU continued the enforcement of the labelling system for HCFC cylinders. The NOU also actively coordinated the implementation of stage I of the HPMP, preparations for stage II of the HPMP, and the enabling activities project for HFC phase-down. The NOU also organized several activities to raise awareness of the public and end-users on the HCFC phase‑out, actively joined the regional and global meetings on the Montreal Protocol and promoted gender inclusion during the implementation of the phase. Of the 26 performance indicators proposed for the phase, 21 were fully achieved, four were partially achieved, and one was not achieved.
Plan of action
During the upcoming phase, the NOU will continue with the following activities: enforcement of the licensing and quota system for HCFC and HFC import/export through the electronic system; regularly conducting data collection and reconciliation for HCFC and HFC import/export statistics to ensure timely and accurately submission of Article 7 and country programme data; continued implementation of the labeling requirement for HCFC cylinders; working with other relevant stakeholders to enact specific regulation on control of ODS; continued and enhanced information dissemination to the target groups including celebration of World Ozone Day; promotion of international and regional cooperation on the implementation of the Montreal Protocol and ratification of the Kigali Amendment.
[bookmark: _Hlk118298282]Côte d’Ivoire: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-94
	122,810

	Phase II:
	Nov-98
	81,800

	Phase III:
	Jul-04 and Apr-06
	106,340

	Phase IV:
	Nov-07
	106,340

	Phase V:
	Dec-10
	106,340

	Phase VI:
	Dec-12
	106,340

	Phase VII
	Nov-14
	106,340

	Phase VIII:
	Dec-16
	136,115

	Phase IX:
	May-19
	136,115

		Total:
	1,008,540

	Amount requested for renewal (phase X) (US $):
	136,115

	Amount recommended for approval for phase X (US $): 
	136,115

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	136,115

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan (stage I):
	2012

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a) Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b) Annex C, Group I (HCFCs) (average 2009-2010)
	63.8

	(c) Annex E (methyl bromide) (average 1995-1998)
	8.1

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a) Annex B, Group III (methyl chloroform)
	0.00

	(b) Annex C, Group I (HCFCs)
	35.84

	(c) Annex E (methyl bromide)
	0.00

		Total:
	35.84

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	6,950,387

	Amount disbursed (as at December 2021) (US $):
	3,038,378

	ODS to be phased out (as at June 2022) (ODP tonnes):
	489.69

	ODS phased out (as at December 2021) (ODP tonnes):
	210.09



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved 
(US $)

	(a)
	Investment projects:
	3,785,957

	(b)
	Institutional strengthening:
	1,008,540

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	2,155,890

		Total:
	6,950,387

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase IX of the IS project for Côte d’Ivoire, the NOU collected ODS import data from the Customs department and subsequently submitted country programme and Article 7 data to the Fund and Ozone Secretariats, respectively. The NOU also held annual meetings with the National Ozone Committee to ensure coordination with other stakeholders. Meetings were also held with the refrigeration association and the major importers and consumer’s association. The NOU also supervised the training of refrigeration and air-conditioning technicians, and training of customs officers; held awareness-raising activities including the dissemination of information to consumers and importers on the availability of HCFC alternatives, information on ODS, and Montreal Protocol-related decisions; celebrated International Ozone Day and participated in regional network and Montreal Protocol meetings. Côte d’Ivoire fully achieved 18 out of 20 performance indicators selected for the phase, one was not achieved, and one could not be assessed. 
Plan of action
For the upcoming phase, the NOU is planning the following activities: continuing information dissemination and awareness-raising; coordinating the implementation of stage I of the HPMP; promoting the licensing and quota system and its enforcement, and providing information about annual quota to importers; putting into place the technician certification programme; continuing monitoring and evaluation activities; organizing annual stakeholder workshops to raise awareness on low‑GWP HCFC alternatives; and collecting and timely reporting of data to the Ozone and Multilateral Fund Secretariats.
Djibouti: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-02
	90,000

	Phase II:
	Apr-06
	78,000

	Phase III:
	Apr-09
	60,000

	Phase IV:
	Jul-11
	60,000

	Phase V:
	Jul-13
	60,000

	Phase VI:
	May-15
	60,000

	Phase VII:
	Jun-18
	85,000

	Total:
	493,000

	Amount requested for renewal (phase VIII) (US $):
	85,000

	Amount recommended for approval for phase VIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	2002

	Date of approval of HCFC phase-out management plan:
	2012

	
	

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)  Annex C, Group I (HCFCs) (average 2009-2010)
	

	(c)	Annex E, (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)  Annex C, Group I (HCFCs)
	0.34

	(c)  Annex E, (methyl bromide)
	0.00

		Total:
	0.34

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	1,590,263

	Amount disbursed (as at December 2021) (US $):
	1,260,332

	ODS to be phased out (as at June 2022) (ODP tonnes):
	21.24

	ODS phased out (as at December 2021) (ODP tonnes):
	21.40



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	147,000

	(b)
	Institutional strengthening:
	493,000

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	950,263

		Total:
	1,590,263

	(d)
	HFC activities funded from additional voluntary contributions
	50,000



Progress report
The NOU of Djibouti continued implementation of phase VII of its IS project. During the phase, the NOU coordinated activities under the HPMP; ODS import data was collected from the Customs department and subsequently Article 7 and country programme data were submitted to the Ozone and Fund Secretariats, respectively; stakeholders’ annual meetings were held with the National Ozone Committee, and also with the major importers and consumers association; and training sessions for service technicians and customs enforcement officers were organized. Awareness-raising activities held during the cycle included the dissemination of information on HCFC to schools, consumers and importers, on the availability of HCFC alternatives, information on laws and regulations such as the ban on import of HCFC‑based equipment, and celebration of International Ozone Day. Djibouti participated in regional network meetings, and also in Montreal Protocol meetings where it took part in various negotiations. 15 out of 15 performance indicators selected for the phase were rated as fully achieved. Djibouti ratified the Kigali Amendment in July 2022.
Plan of action
During phase VIII of the IS project, the NOU is planning the following activities: continuing information dissemination and awareness-raising; coordinating the implementation of stage I of the HPMP; promoting the licensing and quota system and its enforcement, and providing information about the annual quota to importers; continuing monitoring and evaluation activities; organizing annual stakeholder workshops to raise awareness on low-global warming potential HCFC alternatives; collecting and reporting data to the Ozone and Fund Secretariats; and undertaking the communication at national level on why the country has ratified the Kigali Amendment; and encouraging women to be more active in different activities related to the Montreal Protocol programmes and activities.
El Salvador: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	May-97
	66,900

	Phase II:
	Dec-00
	44,600

	Phase III:
	Nov-02
	57,980

	Phase IV:
	Dec-04
	60,000

	Phase V:
	Jul-07
	30,000

	Phase VI:
	Nov-08
	30,000

	Total:
	289,480*

	Amount requested for renewal (phase IX) (US $):
	85,000

	Amount recommended for approval for phase IX (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1997

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a) Annex A Group I (CFCs) (average 1995-1997)
	306.5

	(b) Annex A Group II (Halons) (average 1995-1997)
	0.7

	(c) Annex B Group II (Carbon tetrachloride) (average 1998-2000)
	0.0

	(d) Annex B Group III (Methyl chloroform) (average 1998-2000)
	0.0

	(e) Annex C, Group I (HCFCs) (average 2009-2010)
	11.7

	(f) Annex E (Methyl bromide) (average 1995-1998)
	1.4

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a) Annex A Group I (CFCs) 
	0.00

	(b) Annex A Group II (Halons) 
	0.00

	(c) Annex B Group II (Carbon tetrachloride) 
	0.00

	(d) Annex B Group III (Methyl chloroform) 
	0.00

	(e) Annex C, Group I (HCFCs) 
	3.97

	(f) Annex E (Methyl bromide) 
	0.00

		Total:
	3.97

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	4,103,911

	Amount disbursed (as at December 2021) (US $):
	3,348,347

	ODS to be phased out (as at June 2022) (ODP tonnes):
	378.3

	ODS phased out (as at December 2021) (ODP tonnes):
	373.1


* Excluding US $245,000 approved for phase VII (US $142,500) and phase VIII (US $102,500) and incorporated into stage I of the HPMP for El Salvador.

Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	1,689,506

	(b)
	Institutional strengthening:
	289,480

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	2,124,925

		Total:
	4,103,911

	(d)
	HFC activities funded from additional voluntary contributions
	0



Progress report
Phase VIII of the IS project for El Salvador was approved in December 2016 and implemented as part of stage I of the HPMP. During the reporting period, the NOU coordinated the activities for the implementation of the HPMP, submitted Article 7 and country programme data; organized trainings, including in-person workshops on the safe use and handling of hydrocarbons as a refrigerant in commercial freezers and capacity building for the customs and enforcement officers; and public meetings were organized to inform the wider public on the progress in the project’s implementation. El Salvador organized different campaigns and activities for Ozone Day celebrations, such as in the year 2021 celebrations were organized together with local universities. Additionally, the NOU participated in the regional and global meetings of the Montreal Protocol, both in person and virtually. El Salvador ratified the Kigali Amendment on 13 September 2021. The NOU rated all 20 performance indicators as fully achieved.
Plan of action
In preparation for stage II of its HPMP, El Salvador adopted the approach to request IS funding outside the HPMP. During the upcoming phase, El Salvador will continue activities such as revision of ODS legislation to fulfill the Kigali Amendment requirements and development of national capacities to allow the efficient implementation of all its provisions. It will focus on the early adoption of the tariff headings established in the Seventh Amendment of the Harmonized System and strengthening of the HFC licenses and permits system, including the definition of the quota. The NOU will continue the training of technicians in the RAC servicing sector, the training of customs officers and foster partnership with public and private sector stakeholders to comply with El Salvador’s phase-out and reporting obligations under the Montreal Protocol. The NOU will continue timely submission of Article 7 and country programme data to the Ozone and Fund Secretariats, respectively. The NOU will actively engage in regional and international meetings, workshops and events supporting the work of the Montreal Protocol.   
Fiji: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-94
	65,890

	Phase II:
	Nov-99
	43,930

	Phase III:
	Jul-02
	57,000

	Phase IV:
	Dec-04 & Nov-05
	60,000

	Phase V:
	Nov-06
	60,000

	Phase VI:
	Nov-08
	60,000

	Phase VII:
	Jul-10
	60,000

	Phase VIII:
	Jul-12
	60,000

	Phase IX:
	May-14
	60,000

	Phase X:
	Dec-16
	85,000

	Phase XI:
	Dec-18
	85,000

	Phase XII:
	Dec-20
	85,000

		Total:
	781,820

	Amount requested for renewal (phase XIII) (US $):
	85,000

	Amount recommended for approval for phase XIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1993

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.00

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	5.73

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.70

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	0.14

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	0.14

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	2,411,145

	Amount disbursed (as at December 2021) (US $):
	1,635,998

	ODS to be phased out (as at June 2022) (ODP tonnes):
	33.0

	ODS phased out (as at December 2021) (ODP tonnes):
	32.2



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	365,500

	(b)
	Institutional strengthening:
	781,820

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,263,825

		Total:
	2,411,145

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase XII of the IS project for Fiji, the ODS Unit worked closely with the Fiji Customs and Revenue Services and Biosecurity Authority in the control and management of trade and consumption of HCFCs, HFCs and methyl bromide (QPS use) and through the licensing/permitting system. The NOU also conducted iPIC consultations with other NOUs of importing/exporting countries and submitted its country programme and Article 7 data. The NOU worked in close collaboration with all key stakeholders in the implementation of all Multilateral Fund-funded activities [OK?] during the cycle. The NOU organized and delivered the 2021 World Ozone Day celebration and participated in the regional network meetings. Following the ratification of the Kigali Amendment, the ODS Act was amended in 2020 to put in place mandatory controls for HFCs and its blends. The licensing system has been implemented since 1 January 2021.Among 26 performance indicators proposed for this phase, 22 were rated as fully achieved, three as partially achieved and one as not achieved.
Plan of action
The plan of action for phase XIII of the IS project will include: implementing the HCFC licensing and quota system; implementing the HFC licensing system and establishment of HFC quota criteria; timely submission of Article 7 and country programme data reports; active engagement of stakeholders in the implementation of the Montreal Protocol; coordination with stakeholders for implementation of stage II of the HPMP; organization of the World Ozone Day celebrations and development of awareness materials; and participation in regional and international meetings relating to the Montreal Protocol. Gender mainstreaming will also be integrated into implementation of the next phase of the IS project.
Kyrgyzstan: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-02
	133,650

	Phase II:
	Dec-04
	115,830

	Phase III:
	Nov-06
	115,830

	Phase IV:
	Jul-08
	115,830

	Phase V:
	Jul-10
	115,830

	Phase VI:
	Dec-12
	115,830

	Phase VII:
	Nov-14
	115,830

	Phase VIII:
	Dec-16
	148,262

	Phase IX:
	Jun-18
	148,262

	Phase X:
	Dec-20
	148,262

		Total:
	1,273,416

	Amount requested for renewal (phase XI) (US $):
	148,262

	Amount recommended for approval for phase XI (US $): 
	148,262

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XI to the Multilateral Fund (US $):
	148.262

	Date of approval of country programme:
	2002

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	4.1

	(c)	Annex E (methyl bromide) (average 1995-1998)
	14.2

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0

	(b)	Annex C, Group I (HCFCs)
	0

	(c)	Annex E (methyl bromide)
	0

		Total:
	0

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	4,065,143

	Amount disbursed (as at December 2021) (US $):
	3,423,088

	ODS to be phased out (as at June 2022) (ODP tonnes):
	88.71

	ODS phased out (as at December 2021) (ODP tonnes):
	88.40



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	769,800

	(b)
	Institutional strengthening:
	1,273,416

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	2,021,927

		Total:
	4,065,143

	(d)
	HFC activities funded from additional voluntary contributions
	95,000



Progress report
During phase X of the IS project, the Ozone Centre of Kyrgyzstan updated the regulatory system to control HCFCs and HFCs; reported Article 7 and country programme data; and produced and distributed a code of good practice for the refrigeration and air-conditioning sector to service companies and technicians through the Public Association of Refrigeration Technicians. Kyrgyzstan also completed implementation of the third tranche of stage II of its HPMP in December 2021. The Ozone Centre also held a meeting of the Steering Committee, several meetings with the industry association and training workshops for customs officers and refrigeration technicians were conducted. As part of the awareness campaigns for children and youth, a variety of information and awareness materials were produced and disseminated. Out of 27 performance indicators, 23 were fully achieved during the reporting period and four were partially achieved.
Plan of action
The action plan for the next phase focuses on continued coordination and support to the development of the National Cooling Plan on HFC phase-down and implementation of the preparation of the national Kigali HFC implementation plan (KIP). It will also implement the HFC phase-down activities project to facilitate the preparation of the national country programme. These activities will include the development of an HFC quota system, enforcement of the import/export licensing and HFC system, updating national legislations in accordance with the requirements of the Eurasian Economic Union, training and certification of service technicians, training of enforcement officers, public awareness raising, and upgrading the capacity of technical training institutes. The Ozone Centre will work closely with the industry association and other relevant stakeholders to address the challenges of introduction of climate‑friendly alternatives to the local market and the training of technicians on the safe use of flammable, high-pressure and toxic refrigerants. The Ozone Centre will also promote gender equality and women’s empowerment through planned activities.
Lao People’s Democratic Republic: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-01
	66,000

	Phase II:
	Jul-04
	57,200

	Phase III:
	Nov-06
	60,000

	Phase IV:
	Nov-08
	60,000

	Phase V:
	Jul-10
	60,000

	Phase VI:
	Jul-12
	60,000

	Phase VII:
	May-14
	60,000

	Phase VIII:
	May-16
	85,000

	Phase IX:
	Jun-18
	85,000

	Phase X:
	Jun-20
	85,000

		Total:
	678,200

	Amount requested for renewal (phase XI) (US $):
	85,000

	Amount recommended for approval for phase XI (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XI to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	2001

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	2.3

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	0.82

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	0.82

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	2,783,188

	Amount disbursed (as at December 2021) (US $):
	1,913,412

	ODS to be phased out (as at June 2022) (ODP tonnes):
	32.14

	ODS phased out (as at December 2021) (ODP tonnes):
	16.30



Summary of activities and funds approved by the Executive Committee:
	Summary of activities
	Funds approved (US $)

	(a)
	Investment projects:
	791,503

	(b)
	Institutional strengthening:
	678,200

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,313,485

		Total:
	2,783,188

	(d)
	HFC activities funded from additional voluntary contributions
	95,000



Progress report
During phase X of the IS project, Lao People’s Democratic Republic continued to enforce its HCFC licensing system and put an HFC licensing system in place from 1 January 2021. In late 2022, there was a change of focal point for Montreal Protocol activities to the Department of Climate Change which also necessitated the establishment of a new NOU team. Despite a change in licensing authority, the NOU worked closely with the Ministry of Industry and Commerce to issue import licenses of HCFC and HFC based on quotas set by the NOU. Lao People’s Democratic Republic submitted its 2020 and 2021 country programme and Article 7 data reports to the Fund and Ozone Secretariats, respectively. The NOU worked closely with the Refrigeration and Air-conditioning Servicing Technician Association (RASTA) to support implementation of activities, such as training, providing feedback on the industry perspective as well as coordination and outreach to its members. The NOU also coordinated the HPMP implementation and completed activities under the enabling activities project for HFC phase-down; included gender mainstreaming in implementation of the Montreal Protocol activities; and organized public awareness-raising activities for the Montreal Protocol; and joined the regional and global meetings on the Montreal Protocol. Among the 22 performance indicators proposed for the phase, 16 were rated as fully achieved, five as partially achieved and one as not achieved.
Plan of action
During the upcoming phase, the NOU will focus on building capacity of the new NOU team to continue its mandate to comply with country obligations and continue implementation of other ongoing Multilateral Fund projects. The activities to be implemented under the phase include: working closely with the Ministry of Industry and Commerce to enforce the HCFC/HFC licensing system; continuation of mandatory labelling requirements for HCFC cylinders and at least semi-annual joint inspection of refrigerants in the domestic market through the institutionalized Joint Inspection Team; data collection and reconciliation for ODS and HFC import-export statistics to ensure timely submission of Article 7 and country programme data reporting; coordination with stakeholders for the implementation of Montreal Protocol activities as well as HPMP implementation and KIP preparation; ensuring the continuity of information dissemination to the target groups; and promoting international and regional cooperation on the implementation of the Montreal Protocol. All planned activities will integrate gender mainstreaming.  
Mauritania: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Sep-94
	38,874

	Phase II:
	Mar-01
	25,900

	Phase III:
	Jul-04
	33,670

	Phase IV:
	Jul-06
	60,000

	Phase V:
	Apr-09
	60,000

	Phase VI:
	Jun-18
	85,000

	Phase VII:
	Dec-20
	85,000

		Total:
	388,444

	Amount requested for renewal (phase VIII) (US $):
	85,000

	Amount recommended for approval for phase VIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan:
	2017

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	20.5

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	13.12

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	13.12

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at June 2022) (US $):
	1,905,139

	Amount disbursed (as at December 2021) (US $):
	1,273,467

	ODS to be phased out (as at June 2022) (ODP tonnes):
	18.3

	ODS phased out (as at December 2021) (ODP tonnes):
	16.4



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	388,444

	(b)
	Institutional strengthening:
	350,000

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,166,695

		Total:
	1,905,139

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
Under phase VII of the IS project, Mauritania’s NOU collected ODS import data from the Customs department and subsequently submitted country programme and Article 7 data to the Fund and Ozone Secretariats, respectively. To ensure coordination with other stakeholders, annual meetings were held with the National Ozone Committee and meetings were also held with the refrigeration association and the major importers and consumer’s association. The NOU supervised training of refrigeration and air conditioning technicians and training of customs officers. Awareness-raising activities included the dissemination of information to consumers and importers on the availability of HCFC alternatives, information on ODS, and Montreal Protocol-related decisions. Mauritania celebrated International Ozone Day and participated in regional network and Montreal Protocol meetings. Work progressed towards the ratification of the Kigali Amendment, which is expected in late 2022. The country fully achieved 14 out of 17 performance indicators during the phase, with one indicator partially achieved, one was not achieved, and one not assessed.
Plan of action
During the upcoming phase, the NOU is planning the following activities: continuing information dissemination and awareness-raising; coordinating the implementation of stage I of the HPMP; promoting the licensing and quota system and its enforcement, and providing information about annual quota to importers; continuing monitoring and evaluation activities; organizing annual stakeholder workshops to raise awareness on low-global warming potential HCFC alternatives; and collecting and reporting of data to the Ozone and Fund Secretariats. 
Mozambique: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Dec-94
	92,400

	Phase II:
	Dec-03
	80,080

	Phase III:
	Nov-06
	80,800

	Phase IV:
	Apr-09
	80,800

	Phase V:
	Jul-11
	80,800

	Phase VI:
	Jul-13
	80,800

	Phase VII
	May-16
	103,424

	Phase VIII:
	Dec-18
	103,424

	Phase IX:
	Jun-20
	103,424

		Total:
	805,952

	Amount requested for renewal (phase X) (US $):
	103,424

	Amount recommended for approval for phase X (US $): 
	103,424

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	103,424

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.00

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	8.69

	(c)	Annex E (methyl bromide) (average 1995-1998)
	3.40

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	2.21

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	2.21

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	2,941,788

	Amount disbursed (as at December 2021) (US $):
	1,977,557

	ODS to be phased out (as at June 2022) (ODP tonnes):
	28.13

	ODS phased out (as at December 2021) (ODP tonnes):
	9.60



Summary of activities and funds approved by the Executive Committee:
	Summary of activities
	Funds approved (US $)

	(a)
	Investment projects:
	859,015

	(b)
	Institutional strengthening:
	805,952

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,276,821

		Total:
	2,941,788

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase IX of the IS project for Mozambique, the NOU enforced the ODS regulations through the implementation of licensing and quota system; embarked on an awareness-raising program; and trained Customs officers, clearing agents, border control police, and refrigeration technicians. Mozambique incorporated the provisions of the Kigali Amendment into its draft legal framework on controlled substances under the Montreal Protocol, which is in the final stages for enactment.
Plan of action
During the upcoming phase, Mozambique will endeavor to implement its action plan to ensure sustained compliance with the Montreal Protocol. The NOU will continue with the training programme for the technicians in the refrigeration sector; training of newly recruited and current customs officers to support the implementation and enforcement of ODS regulations; awareness-raising programme through mass media, NGOs, workshops, and distribution of awareness materials to the industry and other stakeholders. The country will also prepare for the phase-down of HFCs as per the Kigali Amendment and the implementation of the KIP.
Peru: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-95
	154,000

	Phase II:
	Nov-99
	102,700

	Phase III:
	Jul-02
	133,510

	Phase IV:
	Dec-12
	133,510

	Phase V:
	Nov-17
	170,893

		Total:
	694,613

	Amount requested for renewal (phase VI) (US $):
	170,893

	Amount recommended for approval for phase VI (US $): 
	170,893

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VI to the Multilateral Fund (US $):
	170,893

	Date of approval of country programme:
	1995

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)  Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)  Annex C, Group I (HCFCs) (average 2009-2010)
	26.9

	(c)  Annex E, (methyl bromide) (average 1995-1998)
	1.3

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)  Annex B, Group III (methyl chloroform)
	0.00

	(b)  Annex C, Group I (HCFCs)
	9.39

	(c)  Annex E, (methyl bromide)
	0.00

		Total:
	9.39

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	8,124,330

	Amount disbursed (as at December 2021) (US $):
	6,080,070

	ODS to be phased out (as at June 2022) (ODP tonnes):
	547.4

	ODS phased out (as at December 2021) (ODP tonnes):
	501.4



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	5,315,322

	(b)
	Institutional strengthening:
	694,613

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	2,114,395

		Total:
	8,124,330

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase V of the IS project for Peru, the NOU/Environmental Directorate ensured that the licensing and quota system was in place and that Article 7 and country programme data were submitted in a timely manner. The Environmental Directorate implemented multiple actions to comply with the HPMP and continued with actions to maintain controls on regulated substances under the Montreal Protocol. Among other actions, the team of the Environmental Directorate was responsible for: coordination of ODS import/export controls with Customs and other enforcement authorities; data cross-checking and timely submission of reports to the Ozone Secretariat and the Multilateral Fund Secretariat; conducting awareness rising activities among, suppliers, end-users and general public; training activities for the service sector promoting good practices in refrigeration and the certification of technicians, as well as training of customs officers. The NOU fully achieved all performance indicators selected for the phase.
Plan of action
The NOU will focus on the following activities during the upcoming phase: implementation of an electronic system for granting authorizations and update it for improved communication with customs authorities to assure an effective implementation of control measures; early adoption of the tariff headings established in the Seventh Amendment of the Harmonized System of the World Customs Organization and continued application and implementation of an effective quota and licensing system; maintaining regular coordination with the ministries of energy and mines, among others to build synergies with other national policies, particularly in the areas of climate change and energy efficiency; continuing cooperation with training centers for the refrigeration and air-conditioning sector to improve the education received by refrigeration technicians and engineers; carrying out tasks to prepare for the phase-down of HFCs and to ensure compliance with the first stages of KIP; continuing implementation and supervision of the HPMP and the development of HFC phase-down strategies which are designed in way to involve all relevant stakeholders (importers, exporters, distributors, technicians, and end-users); and continuation of public awareness activities amongst the wider public and important stakeholder such as refrigeration and air‑conditioning service technicians which include the dissemination of information via the institutional website of the Ministry and the organization of the World Ozone and Refrigeration Day.
Seychelles: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-94
	31,900

	Phase II:
	Jul-00
	21,267

	Phase III:
	Dec-04
	60,000

	Phase IV:
	Nov-07
	60,000

	Phase V:
	Apr-11
	60,000

	Phase VI:
	Jul-13
	60,000

	Phase VII:
	Nov-15
	85,000

	Phase VIII:
	Jun-18
	85,000

	Phase IX:
	Jun-20
	85,000

		Total:
	548,167

	Amount requested for renewal (phase X) (US $):
	85,000

	Amount recommended for approval for phase X (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	1.4

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.0

	(e)	Annex C, Group I (HCFCs)
	0.0

	(f)	Annex E (methyl bromide)
	0.0

		Total:
	0.0

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	1,837,774

	Amount disbursed (as at December 2021) (US $):
	1,311,937

	ODS to be phased out (as at June 2022) (ODP tonnes):
	4.18

	ODS phased out (as at December 2021) (ODP tonnes):
	2.80



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	733,000

	(b)
	Institutional strengthening:
	548,167

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	556,607

		Total:
	1,837,774

	(d)
	HFC activities funded from additional voluntary contributions
	95,000



Progress report
During phase IX of the IS project, the NOU of Seychelles implemented several activities under the IS and HPMP, including: enforced the ODS regulations through the implementation of licensing authority, which controls the importation of refrigerant-dependent equipment, and bars import of unwanted or banned ODS and ODS dependent appliances; embarked on an awareness-raising programme; trained customs officers, port authorities, refrigeration technicians; and conducted a media workshop to raise awareness on ozone protection and role of stakeholders. The NOU also participated in the activities of the African Network for Ozone Officers. Seychelles fully achieved 22 out of 26 performance indicators that were selected for the phase and the remaining four were partially achieved.  
Plan of action
During the upcoming phase, the NOU will continue with the training of technicians in the refrigeration and air-conditioning servicing sector, training of customs officers and environment inspectors, and the fostering of partnerships with public and private sector stakeholders to comply with Seychelles’ phase-out and reporting obligations under the Montreal Protocol. The NOU will continue with its awareness-raising programme through media workshops, NGOs, symposiums and distribution of materials such as newspapers, brochures, and pamphlets to the industry and other stakeholders. Work will also continue on preparation for the KIP and the requirements of the Kigali Amendment.
Sierra Leone: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02 & Dec-03
	111,800

	Phase II:
	Nov-05 & Mar-07
	96,890

	Phase III:
	Apr-08
	85,800

	Phase IV:
	Jul-10
	85,800

	Phase V:
	Apr-13
	85,800

	Phase VI:
	Nov-15
	109,824

	Phase VII:
	Dec-18
	109,824

	Phase VIII:
	Jun-20
	109,824

		Total:
	795,562

	Amount requested for renewal (phase IX) (US $):
	109,824

	Amount recommended for approval for phase IX (US $): 
	109,824

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	109,824

	Date of approval of country programme:
	2003

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	1.7

	(c)	Annex E (methyl bromide) (average 1995-1998)
	2.6

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	0.56

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	0.56

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	2,497,795

	Amount disbursed (as at December 2021) (US $):
	1,698,483

	ODS to be phased out (as at June 2022) (ODP tonnes):
	80.32

	ODS phased out (as at December 2021) (ODP tonnes):
	71.10



Summary of activities and funds approved by the Executive Committee:
	Summary of activities
	Funds approved (US $)

	(a)
	Investment projects:
	277,000

	(b)
	Institutional strengthening:
	795,562

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,425,233

		Total:
	2,497,795

	(d)
	HFC activities funded from additional voluntary contributions
	95,000



Progress report
During phase VIII of the IS project for Sierra Leone, the NOU was involved in many activities centered on awareness creation, training and capacity building of refrigeration technicians, importers, customs and other law enforcement officers and implementation of various phase-out plans. A licensing system is in place and functioning for importation of refrigerants and information was disseminated on HCFC phase-out and the promotion of acceptable refrigerant alternatives. Training of refrigeration technicians, customs and law enforcement officers were conducted for HCFC phase-out. The NOU maintained a high level of cooperation with stakeholders and the public on phase-out process, and created a good working relationship with government bodies, industry associations and other relevant stakeholders involved in the implementation of ODS phase-out activities. Sierra Leone fully achieved 16 out of 17 performance indicators selected for the current phase and one was partially met.
Plan of action
[bookmark: _Hlk118393610]For the upcoming phase, the NOU aims to maintain compliance with the control measures established by the Montreal Protocol on ODS and to implement programmes and strategies aimed at achieving gradual phase out of HCFCs, especially through strengthening networking between relevant institutions. The NOU will: continue the strengthening of the licensing and quota system for HCFC import; update the database of all importers and exporters of HCFCs on a yearly basis; coordinate the allocation of HCFC licenses and quotas; organize two meetings to analyze and evaluate annual quotas; and conduct inspection visits to monitor distribution of HCFCs to check compliance with the quotas allocated for that particular year. In addition, support and regular monitoring and review for enforcement of existing policies and regulations for controlling HCFCs and other ODS will continue. The NOU will carry out important public awareness activities such training workshops, television and radio discussions, and printing of brochures. The NOU will also coordinate and monitor programme activities under the HPMP, ensure the integration of Montreal Protocol objectives into environmental policy and regulations, and carry out training of relevant personnel concerned with the phase-out process. The country will also continue on preparation for the KIP and the requirements of the Kigali Amendment.
United Republic of Tanzania (the): Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Oct-96
	66,000

	Phase II:
	Dec-04
	57,200

	Phase III:
	Nov-06
	60,000

	Phase IV:
	Apr-09
	60,000

	Phase V:
	Apr-12
	60,000

	Phase VI:
	May-14
	60,000

	Phase VII:
	May-19
	85,000

		Total:
	448,200

	Amount requested for renewal (phase VIII) (US $):
	85,000

	Amount recommended for approval for phase VIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1996

	Date of approval of HCFC phase-out management plan (stage I):
	2012

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)  Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)  Annex C, Group I (HCFCs) (average 2009-2010)
	1.7

	(c)  Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(a)  Annex B, Group III (methyl chloroform)
	0.00

	(b)  Annex C, Group I (HCFCs)
	0.90

	(c)  Annex E (methyl bromide)
	0.00

		Total:
	0.90

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	3,927,316

	Amount disbursed (as at December 2021) (US $):
	2,963,917

	ODS to be phased out (as at June 2022) (ODP tonnes):
	361.7

	ODS phased out (as at December 2021) (ODP tonnes):
	292.5



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	1,988,587

	(b)
	Institutional strengthening:
	448,200

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,490,529

		Total:
	3,927,316

	(d)
	HFC activities funded from additional voluntary contributions
	95,000



Progress report
During phase VII of the IS project for the United Republic of Tanzania, the NOU implemented ODS regulations through the enforcement of the licensing and quota system and the country established a unit for implementing the licensing and quota system for control of ODS import/export. The NOU embarked on an awareness-raising programme, trained customs officers, and refrigeration technicians and organized meetings with refrigeration association; provided supplementary technician training on good service practices; participated in national and international meetings on ozone issues; and celebrated the International Ozone Day. The United Republic of Tanzania participated in regional network and Montreal Protocol meetings during the phase. The NOU fully achieved 16 out of 16 performance indicators selected for the current phase.
Plan of action
During the upcoming phase, the NOU will continue the training programme for technicians in the refrigeration sector; and training of newly recruited and current customs officers to support the implementation and enforcement of ODS regulations, including control measures of HCFCs. The NOU will continue the awareness-raising programme through mass media, NGOs, workshops, and distribution of materials such as newspapers, brochures, pamphlets and others to the industry and other stakeholders. The NOU will also continue with preparation for the KIP and the requirements of the Kigali Amendment.
Viet Nam: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-95
	137,280

	Phase II:
	Jul-99
	91,520

	Phase III:
	Mar-01
	91,520

	Phase IV:
	Jul-03
	118,976

	Phase V:
	Jul-05
	118,976

	Phase VI:
	Jul-07
	118,976

	Phase VII:
	Apr-09
	118,976

	Phase VIII:
	Apr-11
	118,976

	Phase IX:
	Dec-12
	118,976

	Phase X:
	Nov-14
	118,976

	Phase XI:
	Dec-16
	152,289

	Phase XII:
	Dec-18
	152,289

	Phase XIII:
	Dec-20
	152,289

		Total:
	1,610,019

	Amount requested for renewal (phase XIV) (US $):
	152,289

	Amount recommended for approval for phase XIV (US $): 
	152,289

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XIV to the Multilateral Fund (US $):
	 152,289

	Date of approval of country programme:
	1996

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)  Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.2

	(b)  Annex C, Group I (HCFCs) (average 2009-2010)
	221.2

	(c)  Annex E (methyl bromide) (average 1995-1998)
	136.5

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(a)  Annex B, Group III (methyl chloroform)
	0.00

	(b)  Annex C, Group I (HCFCs)
	141.79

	(c)  Annex E (methyl bromide)
	0.00

		Total:
	141.79

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at June 2022) (US $):
	25,076,277

	Amount disbursed (as at December 2021) (US $):
	16,993,150

	ODS to be phased out (as at June 2022) (ODP tonnes):
	905.8

	ODS phased out (as at December 2021) (ODP tonnes):
	865.8



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	19,311,744

	(b)
	Institutional strengthening:
	1,610,019

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	4,154,514

		Total:
	25,076,277

	(d)
	HFC activities funded from additional voluntary contributions
	250,000



Progress report
During phase XIII of the IS project for Vietnam, the NOU continued to enforce the HCFC quota and licensing system and put into place an HFC licensing system; submitted Article 7 data and country programme implementation reports to the Ozone and Fund Secretariats, respectively; worked closely with national stakeholders and industry to gain their support on implementation of Montreal Protocol activities; and coordinated the implementation of stage II of the HPMP and preparation of the KIP. The Ozone Day celebration activities were organized with the launch of Regional Ozone2Climate Art Contest, for which Viet Nam had a significant number of applications. The NOU also actively participated in the global and regional meetings on the Montreal Protocol. Of the 19 performance indicators selected for the phase, 18 were rated as fully achieved and one was partially achieved.
Plan of action
During the upcoming phase, the NOU will implement a number of activities with an emphasis on enforcing the quota and licensing system for HFCs and blends given that Viet Nam has ratified the Kigali Amendment. These activities include: implementation and enforcement of the HCFC and HFC quota and licensing system; regularly conducting data collection and reconciliation for HCFC and HFC import/export statistics to ensure timely submission of Article 7 and country programme data; coordination with stakeholders for the implementation of Montreal Protocol activities, such as the HPMP and KIP; ensuring the continuity of information dissemination to target groups; and promoting international and regional cooperation on the implementation of the Montreal Protocol. All planned activities will integrate gender mainstreaming.
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Anexo II
PROYECTO DE OPINIONES PRELIMINARES DEL COMITÉ EJECUTIVO EN CUANTO A LA RENOVACIÓN DE LOS PROYECTOS DE FORTALECIMIENTO INSTITUCIONAL PRESENTADOS ANTE LA 91ª REUNIÓN

Belice
1. Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Belice (fase XI), el Comité Ejecutivo observa con satisfacción que el Gobierno de Belice ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para los años 2014 a 2020 del programa país y del artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata además que Belice ha cumplido en tiempo y forma con el calendario de eliminación de HCFC, que cuenta con un sistema operativo y estructurado de licencias y cuotas de importación de HCFC, y que el plan de gestión para la eliminación de HCFC (PGEH) se sigue ejecutando pese a las dificultades impuestas por la pandemia del Covid-19. El Comité también reconoce que Belice ha adoptado medidas para ratificar la Enmienda de Kigali y manifiesta su confianza en que durante el próximo bienio seguirá implementando los proyectos y políticas que le permitan cumplir con las siguientes medidas de control previstas en el Protocolo de Montreal y el Acuerdo suscrito con el Comité Ejecutivo.
Botswana
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Botswana (fase VI), el Comité Ejecutivo observa con satisfacción que el Gobierno de Botswana ha informado los datos del programa país y del artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata la implementación de un sistema de licencias y cuotas, de actividades de sensibilización y de entrega de información y la capacitación de personal aduanero y técnicos en refrigeración, todo lo cual ha sido fundamental para frenar el consumo de HCFC. El Comité reconoce con satisfacción que en septiembre de 2020 el país ratificó la Enmienda de Kigali y expresa su expectativa de que durante el próximo bienio el Gobierno siga implementando actividades de eliminación de HCFC en un marco de estrecha colaboración entre la ONO y las contrapartes locales a fin de preparar al país para alcanzar la reducción del 67,5 por ciento en el consumo de HCFC que debe cumplir a más tardar el 1º de enero de 2025.
Brunei Darussalam
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Brunei Darussalam (fase VII), el Comité Ejecutivo observa con satisfacción que el Gobierno de Brunei Darussalam ha transmitido a las Secretarías del Ozono y del Fondo, respectivamente, los datos para los años 2020 y 2021 del artículo 7 y del programa país que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité reconoce que el país cuenta con un sólido sistema de licencias y cuotas de control del comercio de HCFC y que el sistema de licencias para HFC se mantiene operativo a la espera de que estas sustancias se agreguen a la norma vigente. El Comité constata además la activa participación del país en la red regional y los pasos dados hacia la ratificación de la Enmienda de Kigali. Por consiguiente, el Comité manifiesta su confianza en que durante el próximo bienio Brunei Darussalam seguirá implementando las actividades que le permitan cumplir con las siguientes metas del Protocolo de Montreal, garantizando la integración de la perspectiva de género en la ejecución de las actividades del Protocolo de Montreal.
Côte d’Ivoire
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Côte d’Ivoire (fase X), el Comité Ejecutivo observa con satisfacción que el Gobierno de Côte d’Ivoire ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos del programa país y del artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata además que Côte d’Ivoire ha adoptado medidas para eliminar el consumo de HCFC, destacándose la imposición de controles a la importación de SAO por medio de un sistema de licencias y cuotas y de la capacitación de personal aduanero y técnicos en refrigeración. El Comité reconoce los esfuerzos de Côte d’Ivoire por reducir el consumo de HCFC y manifiesta su confianza en que durante el próximo bienio seguirá implementando las actividades que le permitan cumplir y mantenerse en cumplimiento con las obligaciones contraídas en virtud del Protocolo de Montreal.
Djibouti
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Djibouti (fase VIII), el Comité Ejecutivo observa con satisfacción que el Gobierno de Djibouti ha transmitido a la Secretaría del Ozono los datos para los años 2020 y 2021 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata además que Djibouti ha adoptado importantes medidas para eliminar el consumo de HCFC, reconoce con satisfacción la ratificación de la Enmienda de Kigali en julio de 2022 y, por consiguiente, manifiesta su confianza en que durante el próximo bienio Djibouti seguirá implementando actividades de eliminación de HCFC y dará inicio a las actividades de reducción de los HFC.
El Salvador
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para El Salvador (fase IX), el Comité Ejecutivo observa con satisfacción que el país ha dado cumplimiento a la obligación de informar los datos del artículo 7 y eliminar HCFC contraída en virtud el Protocolo de Montreal, y que cuenta con un sistema operativo de licencias de importación y exportación de SAO y de cuotas de HCFC. El Comité constata además que El Salvador transmitió de manera oportuna a la Secretaría del Fondo los datos del programa país, que ha capacitado a técnicos en refrigeración, que ha asegurado el respaldo de las contrapartes a través de reuniones de coordinación y que ha hecho conciencia pública sobre la importancia de proteger la capa de ozono. El Comité reconoce con satisfacción la ratificación de la Enmienda de Kigali en septiembre de 2021 y manifiesta su confianza en que El Salvador seguirá implementando actividades de eliminación de HCFC y proyectos de fortalecimiento institucional y que presentará de manera eficaz un plan de aplicación de la Enmienda de Kigali que le permita cumplir con las metas de eliminación de HCFC y reducción de HFC.
Fiji
[bookmark: _Hlk119229020]Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Fiji (fase XIII), el Comité Ejecutivo observa con satisfacción que el Gobierno de Fiji ha transmitido a las Secretarías del Ozono y del Fondo, respectivamente, los datos para los años 2020 y 2021 del artículo 7 y programa país que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata que Fiji cuenta con un sistema operativo de licencias y cuotas de HCFC y que el PGEH ha sido implementado de manera eficaz y oportuna. El Comité también constata con satisfacción que Fiji, tras ratificar la Enmienda de Kigali el 16 de junio de 2020, dispuso el control obligatorio de los HFC a partir del 1º de enero de 2021. El Comité destaca asimismo la permanente interacción del país con las principales partes del Protocolo de Montreal a nivel nacional, la organización de actividades de sensibilización y de celebración del Día Internacional del Ozono y su activa participación en las redes regionales. Por consiguiente, el Comité manifiesta su confianza en que durante el próximo bienio el Gobierno de Fiji seguirá implementando las actividades que le permitan cumplir con las obligaciones contraídas en virtud del Protocolo de Montreal y teniendo en cuenta la integración de la perspectiva de género.
Kirguistán
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Kirguistán (fase XI), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Ozono y del Fondo, respectivamente, los datos del artículo 7 y programa país que indican haber dado cumplimiento al plan acelerado de eliminación total de HCFC antes de lo previsto en el cronograma de control del Protocolo de Montreal. Por consiguiente, el Comité manifiesta su confianza en que durante el próximo bienio el Gobierno de Kirguistán consolidará la eliminación lograda y dará inicio a la elaboración y ejecución del plan de aplicación de la Enmienda de Kigali.
República Democrática Popular Lao
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para la República Democrática Popular Lao (fase XI), el Comité Ejecutivo observa con satisfacción que el Gobierno ha transmitido a las Secretarías del Ozono y del Fondo, respectivamente, los datos para los años 2020 y 2021 del artículo 7 y programa país que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité reconoce que el país cuenta desde el 1º de enero de 2021 con un sistema de licencias de HFC y constata asimismo el cambio producido en el ente coordinador nacional a cargo de las funciones de la ONO, por lo que insta al PNUMA a seguir colaborando con el país durante el período de transición a fin de garantizar las operaciones de la ONO y de otras actividades financiadas por el Fondo Multilateral que permitan al país cumplir con las metas fijadas en el Protocolo de Montreal.
Mauritania
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Mauritania (fase VIII), el Comité Ejecutivo observa con satisfacción que el Gobierno de Mauritania ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para los años 2014 a 2020 del programa país y del artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata además que Mauritania ha adoptado medidas para eliminar el consumo de HCFC, en especial la imposición de controles a la importación de SAO por medio de un sistema de licencias y cuotas y de capacitar a personal aduanero y técnicos en refrigeración. El Comité reconoce asimismo los esfuerzos de Mauritania por reducir el consumo de HCFC y manifiesta su confianza en que durante el próximo bienio seguirá implementando las actividades que le permitan cumplir y mantenerse en cumplimiento con las obligaciones contraídas en virtud del Protocolo de Montreal.
Mozambique
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Mozambique (fase X), el Comité Ejecutivo observa que el Gobierno de Mozambique transmitió a las Secretarías del Ozono y del Fondo, respectivamente, los datos del artículo 7 y programa país que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité reconoce además las medidas adoptadas por Mozambique para eliminar el consumo de SAO, en especial la imposición de controles a la importación por medio de un sistema de licencias y cuotas y de capacitar a personal aduanero y técnicos en refrigeración. Por consiguiente, el Comité manifiesta su confianza en que durante el próximo bienio Mozambique seguirá implementando las políticas y proyectos que le permitan cumplir con las obligaciones contraídas en virtud del Protocolo de Montreal.
Perú
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para el Perú (fase VI), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Ozono y del Fondo, respectivamente, los datos del artículo 7 y programa país que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata que el Perú cuenta con un sistema operativo de licencias de importación y exportación de SAO y de cuotas de HCFC, que se ha esforzado por fortalecer las capacidades de las autoridades aduaneras, que ha asegurado el respaldo de sus contrapartes por medio de reuniones de coordinación, que ha participado en talleres regionales y globales y que ha hecho conciencia sobre la importancia de proteger la capa de ozono. El Comité reconoce con satisfacción que el 7 de agosto de 2019 el Perú ratificó la Enmienda de Kigali y manifiesta su confianza en que seguirá implementando actividades de eliminación de HCFC y proyectos de fortalecimiento institucional y que dará inicio de manera eficaz a la elaboración y ejecución de un plan de aplicación de la Enmienda de Kigali que le permita cumplir con las metas de eliminación de HCFC y reducción de HFC.
Seychelles
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Seychelles (fase X), el Comité Ejecutivo observa que el país ha transmitido a las Secretarías del Ozono y del Fondo, respectivamente, los datos para los años 2020 y 2021 del artículo 7 y programa país que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité reconoce las medidas adoptadas por Seychelles para prohibir la importación de HCFC y manifiesta su confianza en que durante el próximo bienio el país consolidará la eliminación total de HCFC lograda antes de lo previsto en el cronograma de reducción del Protocolo de Montreal y que dará inicio a la reducción de HFC que estipula la Enmienda de Kigali.
Sierra Leona
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Sierra Leona (fase IX), el Comité Ejecutivo observa que el país ha transmitido a las Secretarías del Ozono y del Fondo, respectivamente, los datos del artículo 7 y programa país para el año 2021 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata además que Sierra Leona ha adoptado medidas para eliminar el consumo de HCFC y controlar la importación de SAO por medio de un sistema de licencias y cuotas y de capacitar a personal aduanero y a técnicos en refrigeración. Por consiguiente, el Comité manifiesta su confianza en que durante el próximo bienio el país seguirá implementando las políticas y proyectos que le permitan cumplir con las obligaciones contraídas en virtud del Protocolo de Montreal.
República Unida de Tanzanía 
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para la República Unida de Tanzanía, el Comité Ejecutivo observa con satisfacción que Tanzanía ha transmitido los datos del artículo 7 y programa país que indican haber cumplido en tiempo y forma con las medidas de control de los HCFC previstas en el Protocolo de Montreal. El Comité también constata el compromiso del Gobierno de mantener a largo plazo la supervisión, información y verificación de las SAO eliminadas. Por consiguiente, el Comité manifiesta su confianza en que Tanzanía seguirá implementando las actividades de eliminación de HCFC que le permitan alcanzar la reducción del 67,5 por ciento en el consumo de HCFC que debe cumplir a más tardar el 1º de enero de 2025.
Viet Nam
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Viet Nam (fase XIV), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Ozono y del Fondo, respectivamente, los datos del artículo 7 y programa país que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité reconoce que Viet Nam cuenta con un sistema estructurado de licencias y cuotas de importación y exportación de HCFC, que ha establecido un sistema de licencias de importación y exportación de HFC, y que contempla introducir un sistema de cuotas HFC a partir del 1º de enero de 2024. Por consiguiente, el Comité manifiesta su confianza en que Viet Nam seguirá implementando las políticas y proyectos que le permitan cumplir con las metas fijadas en el Protocolo de Montreal.
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