| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/93/30 10 November 2023 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-third Meeting

Montreal, 15-19 December 2023

Item 8(d)(v) of the provisional agenda

THE WORLD BANK Business plan for 2024–2026

# Introduction

# This document presents the World Bank business plan for 2024–2026 and includes the planned activities for the reduction of controlled substances under the Montreal Protocol during the period 2024-2026. The narrative of the World Bank’s business plan for 2024–2026 is attached to the present document.

# This document consists of the following sections:

- Planned activities during the period 2024–2026

- Secretariat’s comments

- Proposed adjustments by the Secretariat

- Performance indicators

- Recommendation

I.	Planned activities during the period 2024–2026

# Table 1 sets out, by year, the value of activities included in the World Bank’s business plan.

Table 1. Resource allocation in the World Bank business plan for 2024–2026 (US $)* – as submitted

| Description | 2024 | 2025 | 2026 | Total (2024–2026) | Total after 2026 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 1,256,763 | 5,350,000 | 4,494,000 | 11,100,763 | 0 |
| Approved HCFC production phase-out management plans (HPPMPs) | 23,232,000 | 0 | 0 | 23,232,000 | 0 |
| HPMP stage III | 0 | 6,169,737 | 10,700,000 | 16,869,737 | 17,279,605 |
| HCFC activities subtotal | 24,488,763 | 11,519,737 | 15,194,000 | 51,202,500 | 17,279,605 |
| HFC activities |  |  |  |  |  |
| Kigali HFC implementation plan (KIP) stage I | 3,210,000 | 6,021,488 | 16,538,270 | 25,769,758 | 23,156,284 |
| HFC activities subtotal | 3,210,000 | 6,021,488 | 16,538,270 | 25,769,758 | 23,156,284 |
| Other activities |  |  |  |  |  |
| Pilot project for energy efficiency – investment | 428,000 | 0 | 0 | 428,000 | 0 |
| National inventories of banks of waste-controlled substances – project preparation (PRP) | 0 | 214,000 | 0 | 214,000 | 0 |
| Other activities subtotal | 428,000 | 214,000 | 0 | 642,000 | 0 |
| Standard activities |  |  |  |  |  |
| Core unit | 1,759,375 | 1,771,691 | 1,784,092 | 5,315,158 | 0 |
| Institutional strengthening (IS) | 982,829 | 0 | 0 | 982,829 | 0 |
| Standard activities subtotal | 2,742,204 | 1,771,691 | 1,784,092 | 6,297,988 | 0 |
| Total | 30,868,968 | 19,526,916 | 33,516,363 | 83,912,246 | 40,435,889 |

* Including agency support costs where applicable.

# II.	Secretariat’s comments

II.1	HCFC activities

# Stage III of HPMPs

# A total of US $34.15 million is planned for stage III of HPMPs for two countries (Thailand and Viet Nam), including US $16.87 million for 2024–2026 and US $17.28 million for the period after 2026. Inclusion of stage III of HPMPs in the business plan including project preparation is allowed for countries for which stage II of the HPMP had been approved and which had a reduction target beyond 2024 (decision 88/34(d)).

II.2	HFC-related activities

Stage I of KIPs

# Decision 84/46(g) allowed inclusion of KIPs in the business plan only for countries that had ratified the Kigali Amendment. A total of US $48.93 million is included for stage I of KIPs for four countries (Indonesia, Malaysia, Thailand, and Viet Nam), including US $25.77 million for 2024–2026 and US $23.16 million for the period after 2026. One of these countries (Thailand) has not yet ratified the Kigali Amendment.

II.3	Other activities

Pilot projects for energy efficiency (decision 91/65)

# A total of US $428,000 is included in the business plan under the funding window for pilot projects for energy efficiency (decision 91/65) for 2024–2026 for two countries (Malaysia and Viet Nam).

Project preparation for national inventories of banks of waste-controlled substances (decision 91/66)

# A total of US $214,000 is included in the business plan for the preparation of national inventories of banks of waste-controlled substances (decision 91/66) for 2024–2026 for two countries (Malaysia and Thailand).

# II.4	Core unit costs

# The core unit costs are expected to increase at an annual rate of 0.7 per cent as agreed.

III.	Proposed adjustments by the Secretariat

# The adjustments to the World Bank business plan for 2024–2026 were based on relevant decisions of the Executive Committee. In reviewing the revised business plan of the World Bank for 2024–2026, the Secretariat noted that the following adjustments were not included:

Table 2. Adjustments to the World Bank business plan for 2024–2026 (US $)* – as proposed by the Secretariat

| Adjustment | 2024–2026 | After 2026 |
| --- | --- | --- |
| KIPs pursuant to decision 84/46(g) | (8,560,000) | (10,700,000) |

* Including agency support costs where applicable.

# Table 3 presents the results of the Secretariat’s proposed adjustments to the World Bank business plan for 2024–2026, which are also addressed in the context of the consolidated business plan of the Multilateral Fund for 2024–2026.

Table 3. Resource allocation in the World Bank’s adjusted business plan for 2024–2026 (US $)*

| Description | 2024 | 2025 | 2026 | Total (2024–2026) | Total after 2026 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HPMPs | 1,256,763 | 5,350,000 | 4,494,000 | 11,100,763 | 0 |
| Approved HPPMPs | 23,232,000 | 0 | 0 | 23,232,000 | 0 |
| HPMP stage III | 0 | 6,169,737 | 10,700,000 | 16,869,737 | 17,279,605 |
| HCFC activities subtotal | 24,488,763 | 11,519,737 | 15,194,000 | 51,202,500 | 17,279,605 |
| HFC activities |  |  |  |  |  |
| KIP stage I | 3,210,000 | 2,811,488 | 11,188,270 | 17,209,758 | 12,456,284 |
| HFC activities subtotal | 3,210,000 | 2,811,488 | 11,188,270 | 17,209,758 | 12,456,284 |
| Other activities |  |  |  |  |  |
| Pilot project for energy efficiency – investment | 428,000 | 0 | 0 | 428,000 | 0 |
| National inventories of banks of waste-controlled substances – PRP | 0 | 214,000 | 0 | 214,000 | 0 |
| Other activities subtotal | 428,000 | 214,000 | 0 | 642,000 | 0 |
| Standard activities |  |  |  |  |  |
| Core unit | 1,759,375 | 1,771,691 | 1,784,092 | 5,315,158 | 0 |
| IS | 982,829 |  |  | 982,829 | 0 |
| Standard activities subtotal | 2,742,204 | 1,771,691 | 1,784,092 | 6,297,988 | 0 |
| Total | 30,868,968 | 16,316,916 | 28,166,363 | 75,352,246 | 29,735,889 |

* Including agency support costs where applicable.

IV.	Performance indicators

# The World Bank submitted performance indicators pursuant to decision 71/28 in its business plan narrative. The Secretariat informed the World Bank of the targets shown in table 4.

Table 4. Performance indicators for the World Bank for 2024

| Type of indicator | Short title | Calculation | 2024 target |
| --- | --- | --- | --- |
| Planning-- Approval | Tranches approved | Number of tranches approved vs. those planned* | 4 |
| Planning-- Approval | Projects/activities approved | Number of projects/activities approved vs. those planned (including project preparation activities) | 4 |
| Implementation | Funds disbursed | Based on estimated disbursement in progress report | US $18,164,125 |
| Implementation | ODS phase-out | ODS phase-out for the tranche when the next tranche is approved vs. those planned per business plans* | 5,446.1 ODP tonnes |
| Implementation | Project completion for activities | Project completion vs. planned in progress reports for all activities (excluding project preparation) | 1 |
| Administrative | Speed of financial completion | The extent to which projects are financially completed 12 months after project completion | 90% |
| Administrative | Timely submission of project completion reports | Timely submission of project completion reports vs. those agreed | 0 |
| Administrative | Timely submission of progress reports | Timely submission of progress reports and business plans and responses unless otherwise agreed | On time |

- * The targets of an agency would be reduced “if it could not submit a tranche owing to another cooperating agency or lead agency” or “if the HPMP submitted for consideration by the Executive Committee was not approved as a result of factors beyond the control of the national ozone unit and the agency”.

V.	Recommendation

# The Executive Committee may wish:

## To note the World Bank business plan for 2024–2026, contained in document UNEP/OzL.Pro/ExCom/93/30; and

## To approve the performance indicators for the World Bank as set out in table 4 of document UNEP/OzL.Pro/ExCom/93/30.

UNEP/OzL.Pro/ExCom/93/1

A draft business plan for 2024–2026 of the World Bank was discussed at the Inter-agency coordination meeting (IACM) held in Montreal from 3 to 5 October 2023. The business plan contained in this document has addressed the issues raised at the meeting.

The World Bank’s 2024 core unit costs will be considered at the 93rd meeting (UNEP/OzL.Pro/ExCom/93/95).

UNEP/OzL.Pro/ExCom/93/25