| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/86/23 17 February 2021 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-sixth Meeting

Montreal, 2-6 November 2020

Postponed to 8-12 March 2021

UPDATE ON THE STATUS OF IMPLEMENTATION OF

THE 2020–2022 CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND

- Introduction

# This document consists of:

## Part I:		An update on the status of the implementation of the 2020–2022 business plans

## Part II:		Resource allocation for the 2018–2020 triennium

Recommendation

Annex I:	HFC phase-down activities submitted to the 86th meeting

## PART I:	UPDATE ON THE STATUS OF THE IMPLEMENTATION OF THE 2020–2022 BUSINESS PLANS

# At its 84th meeting, the Executive Committee endorsed the 2020–2022 consolidated business plan of the Multilateral Fund. In response to decision 84/46, the Secretariat adjusted the consolidated 2020–2022 business plan, as shown in Table 1.

Table 1. Resource allocation of the adjusted 2020–2022 consolidated business plans of the Multilateral Fund (US $)

| Description | 2020 | 2021 | 2022 | Total |
| --- | --- | --- | --- | --- |
| Required for compliance |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 77,761,219 | 60,230,083 | 21,862,803 | 159,854,105 |
| HPMP stage I | 346,137 | 0 | 500,000 | 846,137 |
| HCFC production project preparation (PRP) – stage I | 80,250 | 0 | 0 | 80,250 |
| HCFC production – stage I | 0 | 1,070,000 | 2,140,000 | 3,210,000 |
| HPMP PRP – stage II | 411,990 | 359,950 | 0 | 771,940 |
| HPMP stage II | 12,157,841 | 10,246,509 | 6,632,513 | 29,036,863 |
| HCFC production – stage II | 23,496,000 | 23,496,000 | 23,496,000 | 70,488,000 |
| HPMP PRP – stage III | 1,043,888 | 1,110,400 | 181,900 | 2,336,188 |
| HPMP stage III | 1,178,282 | 3,548,717 | 3,407,844 | 8,134,843 |
| HPMP verification | 588,600 | 588,600 | 588,600 | 1,765,800 |
| Required for compliance subtotal | 117,064,207 | 100,650,260 | 58,809,660 | 276,524,127 |
| HFC activities |  |  |  |  |
| HFC – enabling activities | 315,650 | 160,500 | 0 | 476,150 |
| HFC – investment | 1,819,000 | 0 | 0 | 1,819,000 |
| HFC phase-down plan – investment | 0 | 0 | 7,290,497 | 7,290,497 |
| HFC phase-down plan – PRP | 6,019,506 | 1,291,622 | 208,650 | 7,519,778 |
| HFC activities subtotal | 8,154,156 | 1,452,122 | 7,499,147 | 17,105,425 |
| Standard activities |  |  |  |  |
| Institutional strengthening (IS) | 11,574,486 | 9,858,118 | 11,574,486 | 33,007,090 |
| Compliance Assistance Programme | 11,095,078 | 11,427,930 | 11,770,768 | 34,293,775 |
| Core unit | 5,961,294 | 6,002,878 | 6,044,669 | 18,008,841 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 6,337,243 | 6,581,920 | 6,732,483 | 19,651,646 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |
| Standard activities subtotal | 35,468,101 | 34,370,846 | 36,622,406 | 106,461,352 |
| Total | 160,686,464 | 136,473,227 | 102,931,213 | 400,090,904 |
| Funding distribution by agency |  |  |  |  |
| Australia | 282,500 | 0 | 0 | 282,500 |
| France | 692,895 | 0 | 0 | 692,895 |
| Germany | 3,187,624 | 3,303,874 | 1,503,388 | 7,994,886 |
| Italy | 264,840 | 0 | 0 | 264,840 |
| Japan | 29,832 | 0 | 0 | 29,832 |
| UNDP | 49,827,593 | 14,434,927 | 18,556,104 | 82,818,624 |
| UNEP | 30,421,444 | 20,629,157 | 20,102,612 | 71,153,213 |
| UNIDO | 33,722,686 | 28,248,878 | 18,205,684 | 80,177,248 |
| World Bank | 34,831,207 | 33,295,871 | 31,392,342 | 99,519,420 |
| All (China) | 0 | 28,890,000 | 5,350,000 | 34,240,000 |
| HPMP verification | 588,600 | 588,600 | 588,600 | 1,765,800 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 6,337,243 | 6,581,920 | 6,732,483 | 19,651,646 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |

* Funding for the preparation of HPMP verification reports for low-volume-consuming countries is approved by the Executive Committee on an annual basis.

Status of implementation of the 2020 business plans

# The total funding available for 2020 amounts to US $325,299,217. Of this amount, US $87,131,937 has been approved at the intersessional approval processes for the 85th meeting (IAP-85) and the 86th meeting (IAP-86). In addition, activities amounting to US $26,036,792 would be considered at the postponed 86th meeting. If funding requests for all project proposals submitted to the 86th meeting are approved, a balance of US $47,517,735 would be available from the 2020 business plan, as shown in Table 2. The list of project proposals submitted to the 86th meeting is contained in Annex I to the present document.

Table 2. 2020 consolidated business plan, approvals at the IAP-85 and IAP-86, project submissions to the postponed 86th meeting, and balance (US $)*

| Budget items | Total value in business plan | Approvals at the IAP-85 | Approvals at the IAP-86 | Activities submitted to the postponed 86th meeting | Total | Balance (above)/below |
| --- | --- | --- | --- | --- | --- | --- |
| Bilateral agencies | 4,457,691 | 115,120 | 4,463,140 | 339,000 | 4,917,260 | (459,569) |
| UNDP | 49,827,593 | 17,110,701 | 21,652,587 | 1,254,040 | 40,017,328 | 9,810,265 |
| UNEP | 30,421,444 | 3,117,082 | 17,888,196 | 1,038,470 | 22,043,748 | 8,377,696 |
| UNIDO | 33,722,686 | 12,378,137 | 5,887,571 | 17,852,661*** | 36,118,369 | (2,395,683) |
| World Bank | 34,831,207 | 2,211,703 | 1,735,000 | 267,500 | 4,214,203 | 30,617,004 |
| HPMP verification | 588,600 | 33,900 | 538,800 |  | 572,700 | 15,900 |
| Subtotal (agencies) | 153,849,221 | 34,966,643 | 52,165,294 | 20,751,671 | 107,883,608 | 45,965,613 |
| Secretariat/Executive Committee/Monitoring and Evaluation (excluding Canadian counterpart)** | 6,337,243 |  |  | 4,785,121 | 4,785,121 | 1,552,122 |
| Treasurer | 500,000 |  |  | 500,000 | 500,000 | 0 |
| Subtotal (standard costs) | 6,837,243 | 0 | 0 | 5,285,121 | 5,285,121 | 1,552,122 |
| Total | 160,686,464 | 34,966,643 | 52,165,294 | 26,036,792 | 113,168,729 | 47,517,735 |

* Including core unit costs.

** As per the provisional statement of accounts.

*** Submission for the HFC-23 by-product project in Argentina ranged between US $11,627,690 and US $63,843,690. However, US $11,627,690 was used for the analysis.

# The value of activities submitted to the postponed 86th meeting is US $20,751,671 (including US $20,374,686 for HFC-related activities and two projects on HFC-23 emission controls), of which US $17,453,416 is associated with project proposals not included in the 2020 business plan.

# Project proposals with a value of US $67,346,261 that were included in the 2020 business plan, were not submitted to the 86th meeting. These proposals have been included in the Consolidated business plan of the Multilateral Fund for 2021–2023.

# Forward commitments

# The total amount for existing forward commitments for multi-year agreements for the period 2020 to 2031 is US $288.53 million, taking into account approvals at the IAP-85 and IAP-86, as shown in Table 3.

Table 3. Forward commitments (2020–2031) (US $000)

| Description | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approved in principle | 62,971 | 70,519 | 25,977 | 47,114 | 9,060 | 34,504 | 31,775 | 2,328 | 223 | 754 | 2,456 | 57 | 287,737 |
| Tranches submitted to the postponed 86th meeting | 377 |  |  | 270 |  | 142 |  |  |  |  |  |  | 789 |
| Total | 63,348 | 70,519 | 25,977 | 47,384 | 9,060 | 34,646 | 31,775 | 2,328 | 223 | 754 | 2,456 | 57 | 288,527 |

## PART II: RESOURCE ALLOCATION FOR THE 2018–2020 TRIENNIUM

# The resources approved by the Parties to the Montreal Protocol for the 2018–2020 triennium amount to US $540,000,000. Taking into account the total funding approvals in 2018, 2019 and 2020, interest accrued, paid contributions from non-Article 5 Parties, the gain/loss of the fixed exchange rate mechanism, and the provisional data on the Secretariat/Executive Committee/Treasurer expenditures, the cash available as of 31 December 2020 is US $297,664,828.

# If funding requests for all project proposals submitted to the postponed 86th meeting are approved at the total value of US $20,751,671, the carry-over for the 2018–2020 triennium would be US $276,913,157, as shown in Table 4.

Table 4. Resource allocation for the 2018–2020 triennium

| Description |  | Amount (US $) |
| --- | --- | --- |
| Balance available as of 31 December 2020 | (a) | 297,664,828 |
| Project submissions to the postponed 86th meeting | (b) | 20,751,671 |
| Balance | (c = a-b) | 276,913,157 |

# RECOMMENDATION

# The Executive Committee may wish to note:

## The update on the status of implementation of the 2020–2022 consolidated business plan of the Multilateral Fund as contained in document UNEP/OzL.Pro/ExCom/86/23; and

## That the total value of activities submitted to the postponed 86th meeting amounts to US $20,751,671 (including US $20,374,686 for HFC-related activities), of which US $17,453,416 is associated with project proposals not included in the 2020 business plan.

Annex I

HFC PHASE-DOWN ACTIVITIES SUBMITTED TO THE 86TH MEETING

| Country | Agency | Type | Sector | Project title | Amount reviewed (US $) | Support costs reviewed (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Albania | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 31,500 | 4,095 |
| Albania | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 63,500 | 4,445 |
| Argentina* | UNIDO | INV | PRO | Control and phase-out of HFC-23 emissions in production of HCFC-22 at FIASA | 10,867,000 | 760,690 |
| Armenia | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 19,500 |
| Bhutan | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 10,000 | 700 |
| Bhutan | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 75,000 | 9,750 |
| Burkina Faso | Germany | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 19,500 |
| Costa Rica | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 10,500 |
| Cuba | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 10,500 |
| Ghana | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 105,000 | 7,350 |
| Ghana | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 45,000 | 5,850 |
| Jordan | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 10,500 |
| Kyrgyzstan | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 60,000 | 4,200 |
| Kyrgyzstan | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 25,000 | 3,250 |
| Lao People's Democratic Republic (the) | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 10,000 | 700 |
| Lao People's Democratic Republic (the) | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 75,000 | 9,750 |
| Lebanon | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 10,500 |
| Malaysia | World Bank | PRP | PHA | Preparation of an HFC phase-down plan | 250,000 | 17,500 |
| Maldives | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 10,000 | 700 |
| Maldives | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 75,000 | 9,750 |
| Mauritius | Germany | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 19,500 |
| Mexico | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 90,000 | 6,300 |
| Mexico | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 35,000 | 4,550 |
| Mexico | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 125,000 | 8,750 |
| Mexico* | UNIDO | INV | PRO | Control and phase-out of HFC-23 emissions in production of HCFC-22 at Quimobasicos | 4,799,230 | 335,946 |
| Montenegro | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 85,000 | 5,950 |
| Niger (the) | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 10,500 |
| Nigeria | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 137,000 | 9,590 |
| Nigeria | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 58,000 | 7,540 |
| North Macedonia | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 85,000 | 5,950 |
| Peru | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 10,500 |
| Qatar | UNEP | TAS | PHA | HCFC phase-out management plan (stage II, first tranche) | 139,500 | 18,135 |
| Qatar | UNIDO | INV | PHA | HCFC phase-out management plan (stage II, first tranche) | 205,000 | 14,350 |
| Senegal | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 60,000 | 7,800 |
| Senegal | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 25,000 | 1,750 |
| South Africa | UNIDO | PRP | PHA | Preparation of an HFC phase-down plan | 100,000 | 7,000 |
| Sudan (the) | UNIDO | PRP | REF | Preparation for conversion of HFC-134a (or R-410a) to R-290 in the manufacture of air-conditioning units at J.M. Group/Mina factory | 30,000 | 2,100 |
| Turkmenistan | UNEP | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 19,500 |
| Uruguay | UNDP | PRP | PHA | Preparation of an HFC phase-down plan | 150,000 | 10,500 |

# * As originally submitted. For Argentina, submission ranged between US $11,627,690 and US $63,843,690. However, US $11,627,690 was used for the analysis.

Due to coronavirus disease (COVID-19)

These activities include: 103 HCFC-related activities for 56 countries (US $57.19 million), 43 HFC-related activities for 33 countries (US $3.48 million) and 40 IS activities (US $6.68 million).

UNEP/OzL.Pro/ExCom/86/25

Decision XXIX/1