| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/85/37/Corr.1 12 May 2020 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-fifth Meeting

Montreal, 25-29 May 2020

Postponed to 19-22 July 2020*

# Corrigendum

- PROJECT PROPOSAL: MALAWI

# This document is issued to:

- Add paragraph 31(bis) as follows:

31(bis).	Stage II of the HPMP for Malawi included three funding tranches, the first in 2020 together with the approval of the overall stage II, the second tranche in 2025, and the third and final tranche in 2030. Noting the lengthy time between tranches, it was agreed to redistribute the overall funding in four tranches (i.e., in 2020, 2023, 2026 and 2030), as shown in the revised Appendix-2A below. The funding for the first tranche was agreed at US $280,000 to be completed by December 2022, with funding levels of the following proposed activities:

## Strengthening enforcement and monitoring of ODS regulations and related policies (UNEP) (US $35,000) (UNIDO) (US $20,000);

## Development of RAC technical standards (UNEP) (US $40,000);

## Promotion of green procurement of RAC systems (US $20,000);

## Establishment of a certification scheme, capacity building of RAC technicians and upgrade of national codes of practice for servicing RAC systems (US $70,000);

## Strengthening the centres of excellence and technical assistance (UNIDO) (US $80,000); and

* Due to coronavirus disease (COVID-19)

## Monitoring and evaluation (UNEP) (US $15,000) for personnel and consultants (US $5,000); travel and compliance monitoring visits (US $5,000), and consultative workshops (US $5,000).

- In paragraph 36, replace “US $340,650” with “US $312,400” and “US $133,800” with “US $105,550”;

- In paragraph 38(e), replace “US $340,650” with “US $312,400”; “US $205,000” with “US $180,000”; and “US $26,650” with “US $23,400”; and

- In Annex I, replace Appendix-2A with the following:

APPENDIX 2-A: THE TARGETS, AND FUNDING

| Row | Particulars | 2020 | 2021-2022 | 2023 | 2024 | 2025 | 2026 | 2027-2029 | 2030 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Montreal Protocol reduction schedule of Annex C, Group I substances (ODP tonnes) | 7.02 | 7.02 | 7.02 | 7.02 | 3.51 | 3.51 | 3.51 | 0.27 | n/a |
| 1.2 | Maximum allowable total consumption of Annex C, Group I substances (ODP tonnes) | 7.02 | 7.02 | 7.02 | 7.02 | 3.51 | 3.51 | 3.51 | 0.00 | n/a |
| 2.1 | Lead IA (UNEP) agreed funding (US $) | 180,000 | 0 | 140,000 | 0 | 0 | 65,000 | 0 | 65,000 | 450,000 |
| 2.2 | Support costs for Lead IA (US $) | 23,400 | 0 | 18,200 | 0 | 0 | 8,450 | 0 | 8,450 | 58,500 |
| 2.3 | Cooperating IA (UNIDO) agreed funding (US $) | 100,000 | 0 | 100,000 | 0 | 0 | 0 | 0 | 0 | 200,000 |
| 2.4 | Support costs for Cooperating IA (US $) | 9,000 | 0 | 9,000 | 0 | 0 | 0 | 0 | 0 | 18,000 |
| 3.1 | Total agreed funding (US $) | 280,000 | 0 | 240,000 | 0 | 0 | 65,000 | 0 | 65,000 | 650,000 |
| 3.2 | Total support costs (US $) | 32,400 | 0 | 27,200 | 0 | 0 | 8,450 | 0 | 8,450 | 76,500 |
| 3.3 | Total agreed costs (US $) | 312,400 | 0 | 267,200 | 0 | 0 | 73,450 | 0 | 73,450 | 726,500 |
| 4.1.1 | Total phase-out of HCFC-22 agreed to be achieved under this Agreement (ODP tonnes) |  |  |  |  |  |  |  |  | 7.02 |
| 4.1.2 | Phase-out of HCFC-22 to be achieved in the previous stage (ODP tonnes) |  |  |  |  |  |  |  |  | 3.78 |
| 4.1.3 | Remaining eligible consumption for HCFC-22 (ODP tonnes) |  |  |  |  |  |  |  |  | 0.0 |

# *Date of completion of stage I as per stage I Agreement: 31 December 2021