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	INFORME SOBRE SALDOS Y DISPONIBILIDAD DE RECURSOS


Introducción
El presente documento resume los ajustes financieros indicados por los organismos bilaterales y de ejecución en acuerdo con la Secretaría. Según lo dispuesto en las decisiones 28/7 y 56/2 c), se incluyen datos estadísticos[footnoteRef:2] sobre todo proyecto con saldos a su haber a los 12 o más meses de terminado e informa los saldos a reintegrar en virtud de decisiones del Comité Ejecutivo (en el presente documento, proyectos terminados “según decisión”). El documento aborda además la recomendación de la Oficina de Servicios de Supervisión Interna (OSSI) sobre cierre financiero de proyectos (decisión 88/1 d)), indica el nivel de recursos en efectivo de que dispone el Comité según el documento Situación de las contribuciones y los desembolsos[footnoteRef:3] conforme a la decisión 41/92 b), y presenta una recomendación. Los montos que obran en poder de los organismos bilaterales y de ejecución por concepto de proyectos terminados y terminados según decisión constan en los Anexos I y II, respectivamente, en tanto que el Anexo III muestra los fondos reintegrados por dichos organismos por concepto de proyectos terminados, terminados según decisión y financiados por contribuciones voluntarias adicionales. [2:  Basados en el formato de presentación de informes elaborado de conformidad con la decisión 31/2.]  [3: UNEP/OzL.Pro/ExCom/90/3.

] 

Fondos a reintegrar a la 90ª reunión
Según muestra el Cuadro 1, el total de fondos a reintegrar por parte de los organismos de ejecución asciende a la suma de 3.360.846 $EUA.


Cuadro 1. Fondos a reintegrar a la 90ª reunión por parte de organismos de ejecución ($EUA)
	Organismo
	Costo de proyectos
	Gastos de apoyo
	Costos totales

	PNUD
	2.156.038
	161.346
	2.317.384

	PNUMA
	(17.118)
	23.719
	6.601

	ONUDI
	968.631
	68.230
	1.036.861

	Total
	3.107.551
	253.295
	3.360.846


Fondos retenidos por organismos bilaterales y de ejecución
El Cuadro 2 muestra los saldos retenidos por los organismos de ejecución por concepto de proyectos terminados, terminados según decisión y financiados por contribuciones voluntarias adicionales. El Anexo I explica las demoras en el desembolso de montos comprometidos o en el reintegro de montos no comprometidos, en tanto que el Anexo II remite a las decisiones del Comité Ejecutivo sobre demoras en el reintegro de fondos transcurrido un año del término del proyecto.
Cuadro 2. Saldos retenidos por organismos de ejecución por concepto de proyectos terminados, terminados según decisión y financiados por contribuciones voluntarias adicionales (incluye gastos de apoyo)
	Año de término
	PNUD
	PNUMA
	ONUDI
	Total

	
	Cantidad
	$EUA
	Cantidad
	$EUA
	Cantidad
	$EUA
	Cantidad
	$EUA

	Proyectos terminados hace más de dos años

	2018
	
	
	1
	23.215
	
	
	1
	23.215

	2019
	
	
	1
	31.296
	1
	46.514
	2
	77.810

	1º ene. - 31 may. 2020
	2
	31.206
	
	
	
	
	2
	31.206

	Subtotal
	2
	31.206
	2
	54.511
	1
	46.514
	5
	132.231

	Proyectos terminados hace menos de dos años

	1º jun. - 31 dic. 2020
	4
	14.520
	9
	455.895
	4
	989.199
	17
	1.459.614

	Subtotal
	4
	14.520
	9
	455.895
	4
	989.199
	17
	1.459.614

	Total 
	6
	45.726
	11
	510.406
	5
	1.035.713
	22
	1.591.845

	Proyectos terminados según decisión (en curso)

	
	1
	119.016
	3
	240.643
	15
	3.473.032
	19
	3.832.691

	Total general
	7
	164.742
	14
	751.049
	20
	4.508.745
	41
	5.424.536



Saldos en poder de organismos bilaterales

Japón mantuvo a su haber un saldo de 50.059 $EUA, cifra que incluye gastos de apoyo, por concepto de un proyecto terminado durante el año 2020.
Seguimiento a la decisión 88/1 d)

Durante la 88ª reunión, en el marco de la auditoría realizada por la OSSI al Fondo Multilateral, el Comité Ejecutivo solicitó a la Secretaría, a la Tesorería y a los organismos bilaterales y de ejecución dar cumplimiento a la Recomendación Nº 5 de la OSSI en cuanto a implementar el plan de acción orientado a resolver los retrasos en concretar el cierre financiero de proyectos más allá del plazo de doce meses fijado por el Comité, e informar al respecto en la correspondiente documentación (decisión 88/1 d)). En tal sentido, el 12 de noviembre de 2021 la Secretaría despachó a los organismos bilaterales y de ejecución un recordatorio oficial en cuanto a implementar rigurosamente todos los elementos del plan de acción establecido durante la 28ª reunión, ceñirse a lo dispuesto en las decisiones posteriores, y concretar el cierre financiero de todos los proyectos antes del vencimiento del plazo de doce meses, recomendación que reiteró durante la reunión de coordinación interinstitucional efectuada el 31 de marzo y 1º de abril de 2022. Para fines de cumplimiento, la Secretaría hizo llegar a los organismos de ejecución la nómina de los proyectos terminados con saldos a su haber durante el año 2020 y anteriores, recordándoles informar constantemente cualquier problema relativo a cierre financiero a fin de poder adoptar medidas de manera oportuna. Las estadísticas con que cuenta la OSSI muestran que el PNUD ha hecho el cierre financiero de todos los proyectos terminados durante los años 2018 y 2019 y que se ha comprometido a cerrar otros 10 tramos de proyectos plurianuales. Respecto de lo recomendado en la auditoría, el PNUMA alcanza un nivel de cumplimiento del 96 por ciento y se ha comprometido a cerrar otros cuatro proyectos; la ONUDI ha cerrado 38 proyectos y se ha comprometido a cerrar otros nueve, en tanto que el Banco Mundial no mantiene saldos retenidos por este concepto. En vista de lo anterior, la OSSI acordó dar por cumplida la observación sobre cierres financieros demorados más allá del plazo de doce meses fijado por el Comité.
Disponibilidad de recursos

Al 5 de mayo de 2022, el documento Situación de las contribuciones y los desembolsos muestra un saldo disponible de 424.470.206 $EUA, en tanto que el total reintegrado a la 90ª reunión por los organismos de ejecución asciende a la suma de 3.360.846 $EUA. En consecuencia, el nivel total de recursos disponibles para aprobación durante la 90ª reunión alcanza a la cifra de 427.831.052 $EUA.
Observaciones de la Secretaría
Se recuerda a los organismos bilaterales y de ejecución que los saldos provenientes de proyectos terminados según decisión y terminados hace un año o más deben ser reintegrados a la brevedad al Fondo Multilateral.
Al 2 de junio de 2022 se habían presentado a la 90ª reunión proyectos y actividades por un monto total de 18.550.280 $EUA, por lo que se cuenta con recursos suficientes para solventar las aprobaciones previstas.
Recomendación

El Comité Ejecutivo podrá estimar oportuno:
Tomar nota de:

i) El informe sobre saldos y disponibilidad de recursos que recoge el documento UNEP/OzL.Pro/ExCom/90/4;
ii) Que el nivel neto de fondos que los organismos de ejecución reintegran a la 90ª reunión asciende a un total de 3.360.846 $EUA, cifra consistente en 2.156.038 $EUA más gastos de apoyo de 161.346 $EUA que reintegra el PNUD; (17.118) $EUA más gastos de apoyo de 23.719 $EUA que reintegra el PNUMA, y 968.631 $EUA más gastos de apoyo de 68.230 $EUA que reintegra la ONUDI;
iii) Que el PNUD mantenía a su haber saldos de 31.206 $EUA, incluyendo gastos de apoyo, por concepto de dos proyectos terminados hace más de dos años, y de 119.016 $EUA, incluyendo gastos de apoyo, por concepto de un proyecto terminado por decisión del Comité Ejecutivo;
iv) Que el PNUMA mantenía a su haber saldos de 54.511 $EUA, incluyendo gastos de apoyo, por concepto de dos proyectos terminados hace más de dos años, y de 240.643 $EUA, incluyendo gastos de apoyo, por concepto de tres proyectos terminados por decisión del Comité Ejecutivo; y
v) Que la ONUDI mantenía a su haber saldos de 46.514 $EUA, incluyendo gastos de apoyo, por concepto de un proyecto terminado hace más de dos años, y de 3.473.032 $EUA, incluyendo gastos de apoyo, por concepto de 15 proyectos terminados por decisión del Comité Ejecutivo;
Solicitar:
A los organismos bilaterales y de ejecución, proceder al desembolso o cancelación de los fondos comprometidos y no comprometidos que ya no se precisen para proyectos terminados o para aquellos terminados por decisión del Comité Ejecutivo, y reintegrar los saldos respectivos a la 91ª reunión;
Al PNUD, proceder al desembolso o cancelación de sus compromisos respecto de los restantes dos proyectos terminados hace más de dos años y reintegrar los saldos respectivos a la 91ª reunión;

Al PNUMA, proceder al desembolso o cancelación de sus compromisos respecto de los restantes dos proyectos terminados hace más de dos años y reintegrar los saldos respectivos a la 91ª reunión; y

A la ONUDI, proceder al desembolso o cancelación de sus compromisos respecto del restante proyecto terminado hace más de dos años.
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Los documentos previos al período de sesiones del Comité Ejecutivo del Fondo Multilateral para la Aplicación del Protocolo de Montreal no van en perjuicio de las decisiones que el Comité pudiera adoptar después de la emisión de los mismos.
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Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

	Code
	Project title
	Date completed (Actual)
	Approved funding plus adjustments as of 31 December 2020 (US $)
	Funds disbursed as of 90th meeting (US $)
	Balances committed as per 90th meeting (US $)
	Balances not-committed as per 90th meeting (US $)
	Support cost on balances committed and not committed as per 90th meeting (US $)
	Why any balances could not be returned?
	When they could be returned?
	Project subject to decision

	UNDP

	COS/PHA/83/INV/59
	HCFC phase-out management plan (stage I, fifth tranche)
	Dec-20
	56,000
	47,445
	8,555
	
	642
	
	
	

	FIJ/PHA/77/INV/31
	HCFC phase-out management plan (stage I, third tranche)
	Dec-19
	59,850
	48,708
	11,142
	
	1,003
	
	
	

	FIJ/PHA/82/TAS/35
	Verification report on the implementation of the HCFC phase-out management plan
	Dec-20
	30,000
	27,859
	2,141
	
	193
	The updated status will be reported to the 91st meeting for Fiji once the open commitment is closed /disbursed
	
	

	GUY/PHA/75/INV/28
	HCFC phase-out management plan (stage II, first tranche)
	Dec-19
	159,750
	141,936
	17,814
	
	1,247
	
	
	

	SRL/PHA/82/PRP/52
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	40,000
	38,157
	1,843
	
	129
	
	
	

	SRL/PHA/82/TAS/51
	Verification report on the implementation of the HCFC phase-out management plan
	Dec-20
	30,000
	29,067
	933
	
	84
	The project balances are currently fully disbursed and projects financially closed. 
 

	
	

	TOTAL UNDP
	
	
	
	
	42,429
	
	3,297
	
	
	

	

	UNEP

	ASP/REF/76/DEM/59
	Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II)
	Dec-19
	375,000
	342,491
	     27,696 
	
	        3,600 
	
	
	83/37(c) and 85/18(b)

	BZE/PHA/82/PRP/36
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	20,000
	5,000
	     15,000 
	
	        1,950 
	
	
	

	GAM/PHA/82/PRP/34
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	20,000
	5,000
	     15,000 
	
	        1,950 
	
	
	

	GLO/SEV/84/TAS/350
	Compliance Assistance Programme: 2020 budget
	Dec-20
	8,899,977
	6,029,262
	   259,175 
	
	       20,734 
	
	
	

	KUW/REF/75/TAS/29
	Comparative analysis of three not-in-kind technologies for use in central air-conditioning (feasibility study for district cooling)
	Jun-18
	27,223
	6,679
	     20,544 
	
	        2,671 
	
	
	82/24(c)(ii) and 83/38(b)

	NIC/SEV/81/INS/35
	Renewal of institutional strengthening project (phase IX: 7/2018-6/2020)
	Dec-20
	85,000
	68,000
	     17,000 
	
	               - 
	
	
	

	RWA/PHA/81/PRP/29
	Preparation of a HCFC phase-out management plan (stage II)
	Nov-20
	22,000
	7,000
	     15,000 
	
	        1,950 
	
	
	

	SAU/PHA/68/TAS/18
	HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan)
	Dec-20
	43,150
	17,134
	     25,880 
	
	        3,206 
	
	
	86/16(f)(i)

	UGA/PHA/82/PRP/24
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	20,000
	44
	     19,956 
	
	        2,594 
	
	
	

	ZAM/PHA/83/PRP/38
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	20,000
	5,000
	     15,000 
	
	        1,950 
	
	
	

	ZIM/PHA/83/PRP/59
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-20
	40,000
	5,000
	     35,000 
	
	        4,550 
	
	
	

	TOTAL UNEP
	
	
	
	
	   465,251
	
	45,155       
	
	
	

	UNIDO[footnoteRef:4] [4:  2: Financial completion initiated; 3: Financial completion to be initiated after settlement of all pending issues; 4: Project is ongoing and extension is in discussion] 


	JOR/REF/81/INV/103
	Conversion of large commercial unitary roof top air-conditioning units of up to 400kW manufacturing facility from HFC (R134a, R407c, R410a) to propane R290 as refrigerant at Petra Engineering Industries Co.
	Jun-20
	1,637,610
	1,524,521
	113,089
	
	7,916
	4
	
	

	MOG/PHA/84/TAS/14
	Verification report on the implementation of the HCFC phase-out management plan
	Dec-20
	30,000
	21,661
	8,339
	
	751
	2
	
	

	SAU/PHA/72/INV/21
	HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan)
	Dec-20
	2,693,674
	2,052,598
	641,076
	
	44,875
	2
	
	86/17(i)(i)

	SAU/REF/76/DEM/28
	Demonstration project on promoting HFO-based low-global warming potential refrigerants for air-conditioning sector in high ambient temperatures
	Dec-20
	1,300,000
	1,138,176
	161,824
	
	11,328
	3
	
	83/33(c), 85/17(c) and 88/27(c)

	SOA/PHA/71/INV/05
	HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan)
	Dec-19
	2,042,620
	1,999,149
	43,471
	
	3,043
	3
	
	

	TOTAL UNIDO
	
	
	
	
	967,799
	
	67,913
	
	
	

	
	
	
	
	
	
	
	
	
	
	

	JAPAN
	
	
	
	
	
	
	
	
	
	

	CPR/PHA/77/TAS/582
	HCFC phase-out management plan (stage II, first tranche) (refrigeration and air-conditioning servicing sector plan and enabling component)

	Dec-20

	80,000

	35,700
	44,300
	
	5,759

	The balance is fully committed to the partner pending financial reporting. 
	The implementing partner has confirmed that they will provide the financial report by the date of ExCom 91 to enable   financially complete the project.
	

	TOTAL JAPAN
	
	
	
	
	44,300
	
	5,759
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Annex II
COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS
	Code
	Project title
	Financial date of completion per decision
	Approved funding plus adjustments as of 31 December 2020 (US $)
	Funds disbursed as of
90th meeting (US $)
	Balances committed as per 90th  meeting (US $)
	Balances not- committed as per 90th  meeting (US $)
	Support cost on balances committed and not-committed as per 90th  meeting (US $)
	Why any balances could not be returned?
	When they could be returned?
	Project subject to decision

	UNDP

	BRA/DES/72/DEM/305 
	Pilot demonstration project on ODS waste management and disposal 
	Dec-23 
	1,490,600 
	1,379,370

	111,230

	
	7,786

	
	
	79/18(c)(i) and 81/24(e)(ii) 

	TOTAL UNDP
	
	
	
	
	111,230
	
	7,786
	
	
	

	

	UNEP

	BAH/PHA/84/TAS/36

	HCFC phase-out management plan (stage I, third and fourth tranches) (policy, refrigeration servicing, monitoring and verification)

	91st meeting

	180,000

	70,000

	   110,000 

	
	14,300
	
	
	88/45(b)


	SAU/PHA/68/TAS/16
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring)
	87th meeting
	233,674
	182,206
	32,350
	
	4,007
	
	
	86/16(f)(i)

	SAU/PHA/77/TAS/32
	HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring)
	87th meeting
	130,400
	50,589
	71,170
	
	8,816
	
	
	86/16(f)(i)

	TOTAL UNEP
	
	
	
	
	213,520
	
	27,123
	
	
	

	UNIDO

	BHA/PHA/80/INV/25
	HCFC phase-out management plan (stage I, third tranche)
	Dec-23
	35,828
	15,823
	20,005
	
	1,800
	
	
	88/40(a)

	BRA/PHA/75/INV/311
	HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector)
	90th meeting
	1,674,275
	1,427,334
	44,841
	


	3,139
	
	
	88/61(a)(iii)

	CPR/PHA/64/INV/513
	HCFC phase-out management plan (room air-conditioner manufacturing sector plan) (stage I, first tranche)
	Dec-22
	36,430,000
	36,429,917
	83
	
	6
	
	
	84/68(d)(i) and 86/33(d)

	CPR/PHA/71/INV/536
	HCFC phase-out management plan (stage I, third tranche) (room air-conditioner manufacturing sector plan)
	Dec-22
	8,495,000
	8,494,893
	107
	
	8
	
	
	84/68(d)(i) and 86/33(d)

	CPR/PHA/75/INV/564
	HCFC phase-out management plan (stage I, fifth tranche) (room air-conditioner manufacturing sector plan)
	Dec-22
	11,250,000
	11,274,379
	(24,379)
	
	(1,706)
	
	
	84/68(d)(i) and 86/33(d)

	GLO/REF/80/DEM/344
	Global chiller replacement project (Argentina)
	Dec-21
	808,438
	121,667
	686,771
	
	51,508
	
	
	82/21(d)

	IRA/PHA/86/INV/246
	HCFC phase-out management plan (stage II, third tranche) (foam sector)
	
	524,000
	0
	148,299
	
	10,381
	
	
	

	IRQ/PHA/58/INV/09
	National phase-out plan (first tranche)
	Dec-18
	4,353,530
	3,998,281
	355,249
	
	26,644
	2
	91
	71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c)

	PHI/PHA/83/INV/104
	HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector)
	89th Meeting
	736,129
	95,414
	442,442
	
	30,971
	
	
	87/19(c)

	PHI/PHA/83/TAS/105
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	89th Meeting
	273,894
	132,310
	141,584
	
	9,911
	
	
	87/19(c)

	SAU/FOA/62/INV/13
	Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Al-Watania Plastics
	89th Meeting
	1,103,578
	585,281
	518,297
	
	38,872
	
	
	86/17(i)(i)

	SAU/PHA/72/INV/20
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring)
	87th Meeting
	270,000
	235,670
	34,330
	
	2,403
	2
	91
	86/17(i)(i)

	SAU/PHA/75/INV/24
	HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan)
	87th Meeting
	1,100,000
	655,813
	444,187
	
	31,093
	2
	91
	86/17(i)(i)

	SAU/PHA/77/INV/31
	HCFC phase-out management plan (stage I, fourth tranche) (polyurethane foam sector plan)
	87th Meeting
	989,600
	576,629
	412,971
	
	28,908
	
	
	86/17(i)(i)

	SOM/PHA/77/INV/12
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector)
	Second meeting in 2023
	141,500
	128,129
	13,371
	
	936
	
	
	88/40(a)

	TOTAL UNIDO
	
	
	
	
	3,238,159

	
	234,873
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Annex III

DETAILS ON COMPLETED PROJECTS, BY-DECISION AND PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES AND BILATERAL AGENCIES

	Code
	Project title
	Project costs returned (US $)
	Agency support costs (US $)
	Total (US $)

	BHU/PHA/76/TAS/26
	HCFC phase-out management plan (third tranche)
	641
	58
	699

	BRA/SEV/75/INS/314
	Extension of institutional strengthening project (phase VIII: 12/2015-11/2017)
	5,511
	386
	5,896

	COS/PHA/81/PRP/58
	Preparation of a HCFC phase-out management plan (stage II)
	1,117
	78
	1,196

	COS/SEV/80/INS/56
	Extension of institutional strengthening project (phase XII: 1/2018-12/2019)
	5,398
	378
	5,776

	CUB/PHA/68/INV/50
	HCFC phase-out management plan ( stage I, second tranche) (phase-out of HCFC-141b contained in formulated polyols in the foam sector)
	1,665
	125
	1,790

	EGY/PHA/68/INV/117
	HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in the polyurethane foam sector)
	70,928
	5,320
	76,248

	EGY/PHA/82/INV/139
	HCFC phase-out management plan (stage I, third tranche) (phase-out of HCFC-141b in the polyurethane foam sector)
	118,460
	8,884
	127,344

	GHA/PHA/81/PRP/44
	Preparation of a HCFC phase-out management plan (stage II)
	230
	16
	246

	GHA/SEV/82/INS/47
	Extension of the institutional strengthening project (phase XIII: 1/2018-12/2020)
	607
	42
	649

	IDS/PHA/71/TAS/200
	HCFC phase-out management plan (project management and coordination) (stage I, second tranche)
	159,291
	11,947
	171,238

	IDS/PHA/76/INV/208
	HCFC phase-out management plan (stage I, third tranche) (refrigeration and air-conditioning sector)
	267,832
	20,087
	287,919

	IDS/SEV/80/INS/212
	Extension of institutional strengthening project (phase XI: 1/2018-12/2019)
	3,891
	272
	4,163

	IND/SEV/76/INS/467
	Extension of institutional strengthening project (phase X: 4/2016-3/2018)
	52
	4
	56

	MEX/PHA/71/INV/168
	HCFC phase-out management plan (stage I, third tranche) (foam sector plan for systems houses and local customers)
	314,646
	23,598
	338,244

	MEX/PHA/75/INV/178
	HCFC phase-out management plan (stage I, fifth tranche) (foam sector plan for systems houses and local customers)
	1,122,503
	84,188
	1,206,691

	MEX/REF/81/INV/187
	Conversion of domestic refrigeration manufacturing facility from HFC-134a to isobutane as a refrigerant and conversion of compressors manufacturing facility from HFC-134a-based to isobutane-based at Mabe Mexico
	5,237
	367
	5,603

	MLI/PHA/76/INV/38
	HCFC phase-out management plan (stage I, third tranche)
	14,107
	1,058
	15,165

	NEP/PHA/75/INV/35
	HCFC phase-out management plan (stage I, second tranche)
	2,684
	242
	2,926

	PAR/PHA/74/INV/34
	HCFC phase-out management plan (stage I, second tranche)
	1,858
	139
	1,997

	SRL/SEV/82/INS/53
	Extension of the institutional strengthening project (phase XII: 1/2019-12/2020)
	99
	7
	106

	URU/SEV/80/INS/70
	Extension of institutional strengthening project (phase XII: 1/2018-12/2019)
	295
	21
	316

	VEN/SEV/77/INS/135
	Renewal of institutional strengthening project (phase XIII: 1/2017-12/2018)
	2,099
	147
	2,246

	ZIM/PHA/83/PRP/58
	Preparation of a HCFC phase-out management plan (stage II)
	8,565
	600
	9,165

	[bookmark: _Hlk5787459]Total completed projects
	
	2,107,715
	157,963
	2,265,678

	PAN/PHA/76/INV/44

	HCFC phase-out management plan (stage II, first tranche) (foam sector)
	43,153

	3,021

	46,174

	Total “by decision” projects
	
	43,153

	3,021

	46,174

	[bookmark: _Hlk103677519]COS/SEV/80/TAS/01+

	Enabling activities for HFC phase-down

	5,170
	362
	5,532

	Total “additional voluntary contributions” projects
	
	5,170
	362
	5,532

	TOTAL UNDP
	
	2,156,038
	161,346
	2,317,384

	
	
	
	
	

	ASP/PHA/81/PRP/61
	Development of stage II of HCFC phase-out management plans for PIC countries through regional approach
	   129,990 
	     16,899 
	   146,888 

	ECU/PHA/85/TAS/73
	HCFC phase-out management plan (stage I, fifth tranche)
	    (10,000)
	     (1,300)
	    (11,300)

	ECU/PHA/86/TAS/74
	HCFC phase-out management plan (stage II, first tranche)
	    (24,000)
	     (3,120)
	    (27,120)

	ECU/SEV/83/INS/71
	Extension of institutional strengthening project (phase VII: 7/2019-6/2021)
	  (226,305)
	              - 
	  (226,305)

	ELS/PHA/65/TAS/28
	HCFC phase-out management plan (stage I, first tranche)
	       8,258 
	          290 
	       8,548 

	KUW/PHA/52/TAS/10
	Terminal phase-out management plan for Annex A Group I substances (first tranche)
	     60,820 
	       7,907 
	     68,727 

	LAO/PHA/74/TAS/27
	HCFC phase-out management plan (stage I, second tranche)
	     11,000 
	       1,430 
	     12,430 

	LAO/PHA/82/TAS/32
	Verification report on the implementation of the HCFC phase-out management plan
	       6,308 
	          820 
	       7,128 

	MOL/SEV/77/INS/36
	Extension of the institutional strengthening project (phase IX: 1/2017-12/2018)
	          708 
	              - 
	          708 

	MON/PHA/82/TAS/28
	Verification report on the implementation of the HCFC phase-out management plan
	           58 
	             8 
	           66 

	NAM/SEV/79/INS/24
	Extension of institutional strengthening project (phase IX: 7/2017-6/2019)
	     20,000 
	              - 
	     20,000 

	QAT/PHA/65/TAS/17
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector)
	       6,045 
	          786 
	       6,831 

	Total completed projects
	
	    (17,118)

	     23,719 
	       6,601 

	TOTAL UNEP
	
	    (17,118)

	     23,719 
	       6,601 

	
	
	
	
	

	BAH/PHA/84/PRP/38
	Preparation of a HCFC phase-out management plan (stage II)
	154
	11
	165

	BEN/PHA/84/PRP/39
	Preparation of a HCFC phase-out management plan (stage II)
	106
	7
	113

	BOL/PHA/86/INV/49
	HCFC phase-out management plan (stage I, fifth tranche)
	58
	5
	63

	ECU/PHA/85/INV/72
	HCFC phase-out management plan (stage I, fifth tranche)
	1,686
	127
	1,812

	EQG/PHA/82/INV/14
	HCFC phase-out management plan (stage I, third and fourth tranches)
	1,695
	153
	1,848

	ERI/PHA/84/PRP/18
	Preparation of a HCFC phase-out management plan (stage II)
	15
	1
	16

	GRN/PHA/77/INV/23
	HCFC phase-out management plan (stage I, second tranche)
	711
	64
	775

	KUW/REF/84/PRP/38
	Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sector)
	78,239
	5,477
	83,715

	MDN/PHA/84/INV/42
	HCFC phase-out management plan (phase I, ninth tranche)
	38
	3
	41

	MOR/PHA/65/INV/68
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector)
	433
	32
	465

	MOR/PHA/68/INV/69
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector)
	615
	46
	661

	NER/PHA/82/TAS/34
	Verification report on the implementation of the HCFC phase-out management plan
	231
	21
	252

	OMA/PHA/75/INV/32
	HCFC phase-out management plan (stage II, first tranche)
	557
	39
	596

	OMA/PHA/82/INV/37
	HCFC phase-out management plan (stage II, second tranche)
	87
	6
	93

	OMA/PHA/86/INV/43
	HCFC phase-out management plan (stage II, third tranche)
	664
	46
	710

	PAK/PHA/76/TAS/95
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	5,645
	395
	6,040

	QAT/PHA/73/PRP/21
	Preparation of a HCFC phase-out management plan (stage II)
	347
	24
	372

	RWA/PHA/77/INV/27
	HCFC phase-out management plan (stage I, third tranche)
	233
	21
	254

	RWA/PHA/81/PRP/30
	Preparation of a HCFC phase-out management plan (stage II)
	808
	57
	865

	SAU/PHA/68/INV/17
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring)
	(6,628)
	(464)
	(7,092)

	SIL/PHA/76/INV/31
	HCFC phase-out management plan (stage I, third tranche)
	1,090
	98
	1,188

	SOA/PHA/67/TAS/04
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring)
	4,409
	308
	4,717

	STL/PHA/82/PRP/31
	Preparation of a HCFC phase-out management plan (stage II)
	83
	6
	89

	TUN/PHA/84/INV/78
	HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector)
	4,797
	336
	5,132

	TUR/SEV/80/INS/109
	Extension of institutional strengthening project (phase VIII: 12/2017-11/2019)
	5,082
	356
	5,438

	URT/PHA/76/INV/35
	HCFC phase-out management plan (stage I, second tranche)
	103
	9
	113

	YUG/PHA/84/INV/51
	HCFC phase-out management plan (stage I, fourth tranche)
	301
	23
	324

	YUG/SEV/80/INS/48
	Extension of institutional strengthening project (phase VI: 12/2017-11/2019)
	3,014
	211
	3,225

	Total completed projects
	
	104,572

	7,418
	111,990

	BRA/PHA/75/INV/311
	HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector)
	202,100
	14,147
	216,247

	EGY/PHA/82/INV/140
	HCFC phase-out management plan (stage I, third tranche) (enabling activities in the refrigeration and air-conditioning sector)
	1,987
	149
	2,136

	IRA/PHA/86/INV/246
	HCFC phase-out management plan (stage II, third tranche) (foam sector)
	375701
	26299
	402,000

	IRQ/REF/57/INV/07
	Replacement of refrigerant CFC-12 with isobutane and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigerators and chest freezers at Light Industries Company
	63,547
	4,766
	68,313

	PHI/PHA/83/INV/104
	HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector)
	198,273
	13,879
	212,152

	SAU/PHA/75/INV/25
	HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing and monitoring)
	1134
	79
	1,213

	Total “by decision” projects
	
	842,742

	59,320
	902,062

	[bookmark: _Hlk103676966]CMR/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	676
	47
	724

	GAM/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	53
	4
	57

	LEB/REF/81/INV/03+
	Conversion from HFC-134a and HFC-404A to R-600a and R-290 in domestic refrigeration at Lematic Industries
	13,984
	979
	14,963

	PRC/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	159
	11
	171

	SUD/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	344
	24
	369

	YUG/SEV/80/TAS/01+
	Enabling activities for HFC phase-down

	6,100
	427
	6,528

	Total “additional voluntary contributions” projects
	
	21,318
	1,492
	22,810

	TOTAL UNIDO
	
	968,631
	68,230
	1,036,861
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Introducción


 


1.


 


El


 


presente


 


documento


 


resume


 


los ajustes financieros


 


indicados 


por 


los organismos bilaterales


 


y 


de ejecución 


en acuerdo con


 


la Secretaría


.


 


Según 


lo dispuesto 


en 


las 


decisiones 28/7 y 56/2 c)


, 


se 


i


ncluye


n


 


datos


 


estadísticos


2


 


sobre todo proyecto


 


con 


saldos 


a su haber 


a los 


12 


o más 


meses 


de terminado


 


e 


informa 


los


 


saldos a reintegrar


 


en virtud de


 


decisiones


 


del 


Comité Ejecutivo 


(


en el presente documento


, 


proyectos


 


terminados 


“según decisión”


).


 


El


 


documento


 


aborda 


además 


la 


recomendación 


de la 


Oficina de Servicios 


de Supervisión Inter


na (OSSI) 


sobre cierre financiero


 


de


 


proyectos


 


(


decisión


 


88/1


 


d)


),


 


i


ndica 


el nivel de 


recursos 


en efectivo de que dispone el 


Comité 


según el documento 


Situación de las contribuciones y los 


desembolsos


3


 


conforme a la decisión


 


41/92


 


b)


, y presenta 


un


a recomendación


.


 


Los


 


montos que obran en 


poder de


 


los 


organismos bilaterales y de


 


ejecución


 


por concepto de


 


proyectos terminados y 


terminados 


según decisión


 


constan en los 


Anexo


s


 


I


 


y


 


II


,


 


respectivamente


, en tanto que e


l 


Anexo


 


III


 


muestra 


los 


fondos


 


reintegrados


 


por


 


dichos


 


organismos 


por concepto de 


proyectos 


terminado


s


, 


terminados 


según 


decisión


 


y


 


financiados por 


contribuciones


 


voluntarias


 


adicionales


.


 


Fondos a reintegrar


 


a la 9


0


ª reunión


 


2.


 


Segú


n 


muestra el Cuadro 1


, el total de fondos


 


a reintegrar por parte de los organismos de 


ejecución


 


asciende a 


la suma de 


3.360.846


 


$EUA


.
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Basados en el formato de 


presentación de informes elaborado de conformidad con la decisión 31/2.
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            INFORME SOBRE SALDOS Y DISPONIBILIDAD DE RECURSOS       Introducción   1.   El   presente   documento   resume   los ajustes financieros   indicados  por  los organismos bilaterales   y  de ejecución  en acuerdo con   la Secretaría .   Según  lo dispuesto  en  las  decisiones 28/7 y 56/2 c) ,  se  i ncluye n   datos   estadísticos
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