| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/92/16 10 May 2023 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-second Meeting

Montreal, 29 May to 2 June 2023

Item 9(d) of the provisional agenda

projects recommended for individual consideration

# This document provides summary information on the projects and activities submitted to the 92nd meeting that are recommended for individual consideration. Table 1 presents a summary of these requests.

Table 1: Requests recommended for individual consideration

| Projects and activities | No. of countries | No. of funding requests | Amount recommended (US $) | Amount in principle (US $) |
| --- | --- | --- | --- | --- |
| Stage II/III of HPMPs | 2* | 5 | 4,809,185 | 17,473,556 |
| Tranches of approved HPMPs | 2 | 5 | 4,185,278 |  |
| Verification of compliance of selected LVC countries with their HPMP Agreements | 16 | 16 | 540,000 |  |
| Stage I of KIPs | 2 | 2 | 2,061,641 | 5,032,428 |
| HFC-related investment project | 1 | 1 | 156,797 |  |
| Preparation for KIPs and/or investment-related activities | 1 | 2 | 184,960.00 |  |
| Preparation for a pilot project on energy efficiency | 1 | 1 | 33,900; $3,900.00. |  |
| Total |  | 32 | 11,971,761 |  |

*One new stage (Burkina Faso) includes additional activities to maintain energy efficiency in the servicing sector (decision 89/6)

Note: Funding amounts include agency support costs.

# Tables 2-4 provide more information on projects and activities recommended for individual consideration including non-investment activities included in the work programmes of UNDP, UNEP, UNIDO and the bilateral cooperation document, requests for new stages II and III of HCFC phase-out management plans (HPMPs), tranche requests under stages I, II and III of HPMPs, requests for stage I of Kigali HFC implementation plans (KIPs), and one HFC phase-down stand-alone investment project, as presented in the respective country project proposals.

Table 2: Non-investment activities recommended for individual consideration

| Country | Project title | Implementing agencies | Document # | Issue |
| --- | --- | --- | --- | --- |
| Technical assistance |  |  |  |  |
| Benin | Verification report | UNEP | 92/18 | Contingent on the consideration of the list of countries selected for compliance verification contained in document UNEP/OzL.Pro/ExCom/92/13 |
| Bhutan | Verification report | UNEP | 92/18 |  |
| Democratic Republic of the Congo | Verification report | UNEP | 92/18 |  |
| Eritrea | Verification report | UNEP | 92/18 |  |
| Ethiopia | Verification report | UNEP | 92/18 |  |
| Fiji | Verification report | UNDP | 92/17 |  |
| Liberia | Verification report | UNEP | 92/18 |  |
| Namibia | Verification report | Germany | 92/14 |  |
| Niger (the) | Verification report | UNIDO | 92/19 |  |
| Palau | Verification report | UNEP | 92/18 |  |
| Papua New Guinea | Verification report | Germany | 92/14 |  |
| Saint Vincent and the Grenadines | Verification report | UNEP | 92/18 |  |
| Samoa | Verification report | UNEP | 92/18 |  |
| Seychelles | Verification report | Germany | 92/14 |  |
| Solomon Islands | Verification report | UNEP | 92/18 |  |
| Tonga | Verification report | UNEP | 92/18 |  |
| Preparatory |  |  |  |  |
| Guatemala | Preparation of the KIP | UNIDO/UNEP | 92/19 | Instrument of ratification for the Kigali Amendment has not been deposited yet |
| India | Preparation for a pilot project on energy efficiency in line with decision 91/65 | Germany | 92/14 | Component manufacturing industry linked to future HFC phase-down in the KIP |

Table 3: Multi-year agreement requests recommended for individual consideration

| Country | Stage / Tranche | Implementing agencies | Document # | Issue |
| --- | --- | --- | --- | --- |
| Requests for stage II or III of HPMPs |  |  |  |  |
| Burkina Faso | Stage II | UNEP/UNIDO | 92/22 | All technical and cost issues resolved |
| Indonesia | Stage III | UNDP | 92/29 | All technical and cost issues resolved |
| Tranche requests under stage I or II of HPMPs |  |  |  |  |
| Argentina | Stage II, third tranche | UNIDO/Italy | 92/21 | HCFC consumption exceeding the annual target in 2022. Extension of the duration of the stage |
| Suriname | Stage I, fourth tranche | UNEP/UNIDO | 92/38 | Implementation issues related to strengthening the licensing and quota system for HCFCs. Extension of the duration of the stage |
| Requests for stage I of KIPs |  |  |  |  |
| Cameroon | Stage I | UNIDO | 92/23 | Absence of cost guidelines, starting point and template Agreement |
| Costa Rica | Stage I | UNDP | 92/24 | Absence of cost guidelines, starting point and template Agreement |

Table 3. Stand-alone projects recommended for individual consideration

| Country | Project title | Implementing agency | Document | Issue |
| --- | --- | --- | --- | --- |
| HFC investment projects |  |  |  |  |
| Mexico | Conversion of the manufacturing of commercial refrigerators from HFC-134a to propane at Friocima | UNDP | 92/34 | Absence of cost guidelines for HFC phase-down |

UNEP/OzL.Pro/ExCom/92/1