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INFORME SOBRE SALDOS Y DISPONIBILIDAD DE RECURSOS


Introducción
Este documento presenta una síntesis de los ajustes financieros indicados por los organismos de ejecución y bilaterales conforme a lo acordado por la Secretaría. Incluye datos estadísticos[footnoteRef:2] de todos los proyectos con saldos que se han retenido durante más de 12 meses después de la terminación del proyecto, de conformidad con lo estipulado en las decisiones 28/7 y 56/2 c). Se ocupa de los saldos que habrán de devolverse de los proyectos como seguimiento a las decisiones pertinentes (mencionados como proyectos "por decisión" en el presente documento). Indica también el nivel de recursos de que dispone el Comité Ejecutivo en efectivo según lo registrado en el documento sobre la situación de las contribuciones y los desembolsos,[footnoteRef:3] como se estipula en la decisión 41/92 b), y presenta una recomendación. Las cantidades que los organismos de ejecución mantienen para los proyectos terminados y para los proyectos de contribuciones voluntarias adicionales se indican en el anexo I y el anexo II. En el anexo III se presentan los fondos devueltos por los organismos bilaterales y de ejecución de proyectos terminados, por decisión y de contribuciones voluntarias adicionales. [2: Los datos presentados se basan en el formato de presentación de informes que se ha elaborado en respuesta a la decisión 31/2]  [3: UNEP/OzL.Pro/ExCom/95/3] 

Fondos que se han de devolver a la 95a reunión
Los fondos totales que han de devolverse ascienden a USD 3.337.269, que consisten en USD 3.334.669 por los organismos de ejecución y USD 2.600 por los organismos bilaterales, provenientes de proyectos terminados, y de contribuciones voluntarias adicionales, como se muestra en los cuadros 1 y 2.
Cuadro 1. Fondos que han de devolver los organismos de ejecución a la 95a reunión (USD)
	Organismo
	Costo del proyecto
	Gastos de apoyo al organismo
	Costo total 

	PNUD
	49.738
	3.589
	53.327

	PNUMA*
	1.795.410
	143.021
	1.938.431

	ONUDI
	567.175
	41.415
	608.590

	Banco Mundial
	620.456
	113.865
	734.321

	Total
	3.032.779
	301.890
	3.334.669


* Los fondos devueltos por el PNUMA incluyen USD401.361, más USD 27.217 en concepto de gastos de apoyo al organismo, para tres proyectos que se transferirán según se indica en el cuadro 5.

	Agency
	Project cost
	Agency support cost
	Total 

	Japan
	2,301
	299
	2,600


Cuadro 2. Fondos que han de devolver los organismos bilaterales a la 95ª reunión (USD)
Fondos en poder los organismos de ejecución y los organismos bilaterales
El total de los fondos retenidos asciende a USD 6.417.445 (USD 6.413.350 por los organismos de ejecución y USD 4.096 por un organismo bilateral), como se muestra en los cuadros 3 y 4.
Table 3. Saldos de proyectos terminados y proyectos financiados con contribuciones voluntarias adicionales en poder de los organismos de ejecución (incluidos gastos de apoyo a los organismos)
	Año de terminación
	PNUD
	ONUDI
	Total

	
	Número
	USD
	Número
	USD
	Número
	USD

	Proyectos terminados hace más de dos años

	2020
	1
	40.434
	0
	0
	1
	40.434

	2021
	2
	8.518
	4
	2.315.225
	6
	2.323.743

	1 de enero a
31 de oct. de 2022
	2
	13.091
	2
	24.101
	4
	37.192

	Sub-total
	5
	62.043
	6
	2.339.326
	11
	2.401.369

	Proyectos terminados hace menos de dos años

	1 de Nov a  
31 de dic. 2022
	3
	102.335
	5
	95.212
	8
	197.547

	2023
	31
	2.670.188
	22
	1.048.301
	53
	3.718.489

	Sub-total
	34
	2.772.523
	27
	1.143.513
	61
	3.916.036

	[bookmark: _Hlk179366560]Total
	39
	2.834.566
	33
	3.482.839
	72
	6.317.405

	Proyectos financiados con contribuciones voluntarias adicionales

	
	0
	0
	3
	95,945
	3
	95,945

	Total general
	39
	2.834.566
	36
	3.578.784
	75
	6.413.350



Cuadro 4. Saldo de un proyecto terminado en poder de un organismo bilateral
	Organismo
	Códido del proyecto
	Año completado
	Saldo comprometido (USD)

	
	
	
	Saldo del proyecto
	Saldo para los gastos de apoyo al organismo
	Total

	España
	MEX/PHA/81/TAS/190
	2023
	3.674
	421
	4,096






Transferencia de proyectos 
De conformidad con la decisión 93/14 c), los saldos remanentes de los siguientes proyectos para el plan de gestión de eliminación de HCFC (PGEH) para Afganistán se transferirán del PNUMA a la ONUDI:[footnoteRef:4] [4:  Véase también el documento UNEP/OzL.Pro/ExCom/95/20 relativo a los informes sobre proyectos con requisitos específicos de presentación de informes sin cuestiones pendientes. ] 

AFG/PHA/85/TAS/27 (etapa I, cuarto tramo) – USD 28.453 más los gastos de apoyo al organismo de USD 3.699. La transferencia a la ONUDI supondría una reducción de los gastos de apoyo al organismo de USD 2.561;
AFG/PHA/85/TAS/29 (etapa II, primer tramo) – USD 180.908 más los gastos de apoyo al organismo de USD 23.518. La transferencia a la ONUDI supondría una reducción de los gastos de apoyo al organismo de USD 16.282.
Además, Afganistán solicitó la transferencia de fondos para la extensión del proyecto de fortalecimiento institucional (fase X) del PNUMA a la ONUDI[footnoteRef:5] como se muestra a continuación:  [5:  Carta de fecha 8 de julio de 2024 de la Agencia Nacional de Protección del Medio Ambiente de Afganistán y véase también el documento UNEP/OzL.Pro/ExCom/95/37 sobre las enmiendas al programa de trabajo de la ONUDI para 2024.] 

AFG/SEV/87/INS/31 – USD 192.000, no incluidos los gastos de apoyo al organismo. La transferencia a la ONUDI supondría un incremento de los gastos de apoyo al organismo de USD 13.440.
El cuadro 5 presenta información detallada sobre los saldos que han de transferirse. El Comité Ejecutivo podría considerar oportuno aprobar estas solicitudes.
Cuadro 5. Saldos de proyectos para Afganistán que han de transferirse
	[bookmark: _Hlk182847938]Título del proyecto
	Proyecto nº.
	Devolución 
	Transferencia

	
	
	Al Fondo Multilateral
	Al Organismo

	
	
	Del 
	Saldo 
	Gasto de apoyo a programas
	A
	Saldo
	Gasto de apoyo a programas

	Etapas I y II del plan de gestión de la eliminación de los HCFC

	AFG/PHA/85/TAS/27
	PNUMA
	28.453
	3.699
	ONUDI
	 28.453 
	 2.561 

	
	AFG/PHA/85/TAS/29
	PNUMA
	180.908
	23.518
	ONUDI
	 180.908 
	 16.282 

	Extensión del proyecto de fortalecimiento institucional 
	AFG/SEV/87/INS/31
	PNUMA
	192.000
	-
	ONUDI
	 192.000 
	 13.440 

	Total
	 
	 401.361
	 27.217 
	 
	 401.361 
	 32.283 


Disponibilidad de recursos
El documento sobre la situación de las contribuciones y los desembolsos indica un saldo disponible de USD 577.336.286 al 23 de octubre de 2024. El saldo total devuelto por los organismos de ejecución y bilaterales a la 95ª reunión asciende a USD 2.908.691, excluyendo la cantidad de USD 428.578 devuelta por el PNUMA que ha de transferirse a la ONUDI. Por consiguiente, el nivel total de los recursos disponibles para aprobaciones en la 95ª reunión asciende a USD 580.244.977. 


Comentarios de la Secretaría
La Secretaría recordó a los organismos de ejecución que los saldos de los proyectos terminados con un año de anterioridad o más y los proyectos financiados con contribuciones voluntarias adicionales deberían devolverse al Fondo Multilateral tan pronto como fuera posible. 
Teniendo en cuenta que el nivel total de fondos para proyectos y actividades presentados a la 95ª reunión asciende a USD 135.939.008, se cuenta con suficientes recursos disponibles para la aprobación prevista en la reunión. 
Recomendación
El Comité Ejecutivo puede estimar oportuno:
Tomar nota del:
El informe sobre saldos y disponibilidad de recursos que recoge el documento UNEP/OzL.Pro/ExCom/95/4;
Que el nivel neto de fondos que los organismos de ejecución reintegran a la 95ª reunión es de USD 2.906.091, de los cuales USD 49.738, más USD 3.589 en concepto de gastos de apoyo al organismo que reintegra el PNUD; USD 1.394.049, más USD 115.804 en concepto de gastos de apoyo al organismo que reintegra el PNUMA;[footnoteRef:6] USD 567.175, más USD 41.415 en concepto de gastos de apoyo al organismo que reintegra la ONUDI; y USD 620.456, más USD 113.865 en concepto de gastos de apoyo al organismo que reintegra el Banco Mundial.  [6:  La cantidad no incluye los fondos devueltos por el PNUMA por valor de USD 401.361, más los gastos de apoyo al organismo por valor de USD 27.217, para tres proyectos que se transferirán a la ONUDI, como se indica en el cuadro 5.] 

Que el PNUD mantenía a su haber saldos de USD 62.043, incluyendo gastos de apoyo al organismo, por concepto de cinco proyectos terminados hace más de dos años; 
Que la ONUDI mantenía a su haber saldos de USD 2.339.326, incluyendo gastos de apoyo al organismo, por concepto de seis proyectos terminados hace más de dos años; USD 95.945, incluyendo gastos de apoyo al organismo, por concepto de tres proyectos financiados con las contribuciones voluntarias adicionales hechas por un grupo de países donantes para financiar actividades de apoyo inmediato para la reducción de HFC; 
Que el PNUMA devuelva en la 95ª reunión los saldos de las etapas I y II del plan de gestión de la eliminación de los HCFC (PGEH) y del proyecto de fortalecimiento institucional para Afganistán por un importe de USD 401.361, más los gastos de apoyo al organismo por valor de USD 27.217, que consisten en:
USD 28.453, más USD 3.699 en concepto de gastos de apoyo al organismo, con cargo al cuarto tramo de la etapa I del PGEH (AFG/PHA/85/TAS/27);
USD 180.908, más los gastos de apoyo al organismo por un valor de USD 23.518 del primer tramo de la etapa II del PGEH (AFG/PHA/85/TAS/29);
USD 192.000 de la extensión del proyecto de fortalecimiento institucional (fase X) (AFG/SEV/87/INS/31); 
Que el Gobierno de Japón devuelva USD 2.600, incluidos los gastos de apoyo a un proyecto;
Solictar:
Al PNUD y a la ONUDI proceder al desembolso o la cancelación de los fondos comprometidos que no fueron necesarios para los proyectos terminados, y devolver los saldos conexos a la 96ª reunión; 
Al PNUD y a la ONUDI proceder al desembolso o la cancelación de los compromisos de los proyectos terminados hace más de dos años, y devolver los saldos respectivos a la 96ª reunión; 
A la ONUDI proceder al desembolso o la devolución a la 96ª reunión de los saldos de los proyectos financiados con las contribuciones voluntarias adicionales; 
Al Tesorero; que transfiera a la ONUDI, en la 95ª reunión, los fondos devueltos para los proyectos mencionados en el subpárrafo a) v) anterior, para su ejecución, por un importe de USD 401.361, más los gastos de apoyo al organismo de USD 32.283, que consisten en:
USD 28.453, más los gastos de apoyo al organismo de USD 2.561 con cargo al cuarto tramo de la etapa I del PGEH P (AFG/PHA/85/TAS/27);
USD 180.908, más los gastos de apoyo al organismo de USD 16.282 con cargo al primer tramo de la etapa II del PGEH (AFG/PHA/85/TAS/29); 
USD 192.000, más los gastos de apoyo al organismo de USD 13.440 de la extensión del proyecto de fortalecimiento institucional (fase X) (AFG/SEV/87/INS/31); y
A la Tesorería, verificar con el Gobierno de Japón el reintegro en efectivo de la suma de USD 2.600 mencionada en el subpárrafo a) vi) anterior. 
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Los documentos previos al período de sesiones del Comité Ejecutivo del Fondo Multilateral para la Aplicación del Protocolo de Montreal no van en perjuicio de cualquier decisión que el Comité Ejecutivo pudiera adoptar después de la emisión de los mismo.
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Annex I
COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AND BILATERAL AGENCIES FOR COMPLETED PROJECTS
	Code
	Project title
	Date completed (Actual)
	Approved funding plus adjustments as of 
31 Dec 2023
(US $)
	Funds disbursed as of 
95th meeting (US $)
	Balances committed as per 
95th meeting (US $)
	Balances not-committed as per 
95th meeting (US $)
	Support cost on balances committed and not committed as per
95th meeting (US $)
	Why any balances could not be returned?
	When they could be returned?
	Project subject to decision

	UNDP

	ANG/PHA/79/INV/19
	HCFC phase-out management plan (stage II, first tranche)
	Aug-22
	450,000
	443,189
	6,811
	
	477
	
	
	

	BRA/PHA/88/PRP/330
	Preparation of HCFC phase-out management plan (stage III) (Overarching)
	Dec-23
	40,000
	31,233
	8,767
	
	614
	
	
	

	BZE/SEV/85/TAS/37
	Enabling activities for HFC phase-down
	Oct-22
	55,000
	49,576
	5,424
	
	380
	
	
	

	COL/SEV/88/INS/115
	Extension of institutional strengthening project (phase XIII: 12/2021-11/2023)
	Dec-23
	352,768
	328,161
	24,607
	
	1,723
	
	
	

	COS/SEV/88/INS/64
	Extension of institutional strengthening project (phase XIV: 1/2022-12/2023)
	Dec-23
	179,857
	170,446
	9,411
	
	659
	
	
	

	EGY/PHA/79/TAS/132
	HCFC phase-out management plan (stage II, first tranche) (project management and monitoring)
	Dec-22
	75,000
	67,871
	7,129
	
	499
	
	
	

	EGY/PHA/84/INV/144
	HCFC phase-out management plan (stage II, second tranche) (extruded polystyrene foam sector)
	Dec-23
	1,761,750
	1,471,691
	290,059
	
	20,304
	
	
	

	GHA/KIP/87/PRP/51
	Preparation of Kigali HFC implementation plan
	Aug-23
	130,000
	81,220
	48,780
	
	3,415
	
	
	

	GHA/PHA/87/INV/50
	HCFC phase-out management plan (stage II, first tranche)
	Dec-23
	459,820
	442,121
	17,699
	
	1,239
	
	
	

	HAI/SEV/84/TAS/23
	Enabling activities for HFC phase-down
	Dec-21
	95,000
	90,311
	4,689
	
	328
	
	
	

	IDS/PHA/76/TAS/210
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	Dec-23
	2,203,114
	1,829,259
	373,855
	
	26,170
	
	
	

	IDS/PHA/87/PRP/216
	Preparation of HCFC phase-out management plan (stage III) (Overarching)
	Dec-23
	90,000
	65,168
	24,832
	
	1,738
	
	
	

	IND/PHA/87/PRP/487
	Preparation of HCFC phase-out management plan (stage III) (refrigeration sector)
	Aug-23
	150,000
	89,924
	60,076
	
	4,205
	
	
	

	IRA/PHA/90/INV/262
	HCFC phase-out management plan (stage II, fourth tranche) (PMU)
	Dec-23
	92,000
	69,877
	22,123
	
	1,549
	
	
	

	IRA/PHA/92/INV/264
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector)
	Dec-23
	93,017
	0
	93,017
	
	6,511
	
	
	

	IRA/PHA/92/INV/265
	HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration sector)
	Dec-23
	145,255
	0
	145,255
	
	10,168
	
	
	

	IRA/SEV/86/INS/249
	Extension of the institutional strengthening project (phase XIII: 4/2021-3/2023)
	May-23
	222,094
	178,036
	44,058
	
	3,084
	
	
	

	KAM/KIP/88/PRP/40
	Preparation of Kigali HFC implementation plan
	Dec-23
	35,000
	19,678
	15,322
	
	1,073
	
	
	

	KYR/KIP/87/PRP/45
	Preparation of Kigali HFC implementation plan
	Aug-23
	91,000
	74,690
	16,310
	
	1,142
	
	
	

	KYR/PHA/90/TAS/47
	Verification report on the implementation of stage II of the HCFC phase-out management plan
	Jul-23
	30,000
	0
	30,000
	
	2,700
	
	
	

	LAO/PHA/86/INV/38
	HCFC phase-out management plan (stage II, first tranche)
	Dec-23
	107,000
	86,720
	20,280
	
	1,825
	
	
	

	LEB/SEV/86/INS/96
	Extension of the institutional strengthening project (phase XII: 4/2021-3/2023)
	Dec-23
	198,515
	157,610
	40,905
	
	2,863
	
	
	

	MAL/PHA/84/INV/191
	HCFC phase-out management plan (stage II, second tranche) (polyurethane foam sector)
	Dec-23
	1,703,922
	1,651,948
	51,974
	
	3,638
	
	
	

	MAL/PHA/84/TAS/186
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector)
	Dec-23
	627,053
	174,875
	452,178
	
	31,653
	
	
	

	MAL/PHA/88/INV/193
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector and management and coordination)
	Dec-23
	154,900
	39,789
	115,111
	
	8,058
	
	
	

	MAL/SEV/88/INS/192
	Extension of institutional strengthening project (phase XIV: 1/2022-12/2023)
	Dec-23
	357,760
	296,772
	60,988
	
	4,269
	
	
	

	MEX/KIP/87/PRP/195
	Preparation of Kigali HFC implementation plan
	Aug-23
	85,000
	62,950
	22,050
	
	1,544
	
	
	

	NIR/PHA/81/TAS/148
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	Dec-22
	1,077,113
	1,063,456
	13,657
	
	956
	
	
	

	NIR/PHA/81/TAS/150
	HCFC phase-out management plan (stage II, first tranche) (project management and coordination)
	Dec-22
	165,000
	90,146
	74,854
	
	5,240
	
	
	

	NIR/PHA/88/INV/162
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector)
	Dec-23
	977,407
	962,333
	15,074
	
	1,055
	
	
	

	PAN/PHA/83/PRP/49
	Preparation of a HCFC phase-out management plan (stage III)
	Jun-21
	60,000
	56,728
	3,272
	
	229
	
	
	

	PAR/KIP/87/PRP/42
	Preparation of Kigali HFC implementation plan
	Aug-23
	170,000
	154,838
	15,162
	
	1,061
	
	
	

	PER/KIP/87/PRP/59
	Preparation of Kigali HFC implementation plan
	Sep-23
	190,000
	167,346
	22,654
	
	1,586
	
	
	

	PER/PHA/85/INV/57
	HCFC phase-out management plan (stage II, second tranche)
	Jun-23
	233,400
	194,591
	38,809
	
	2,717
	
	
	

	SWA/KIP/87/PRP/33
	Preparation of Kigali HFC implementation plan
	Aug-23
	30,000
	3,000
	27,000
	
	1,890
	
	
	

	TRI/PHA/86/INV/38
	HCFC phase-out management plan (stage II, first tranche)
	Dec-23
	498,756
	413,693
	85,063
	
	5,954
	
	
	

	TRI/SEV/88/INS/41
	Extension of the institutional strengthening project (phase XI: 12/2021-12/2023)
	Dec-23
	85,000
	82,010
	2,990
	
	209
	
	
	

	URU/PHA/77/INV/67
	HCFC phase-out management plan (stage II, first tranche) (foam sector)
	Dec-20
	100,000
	62,211
	37,789
	
	2,645
	
	
	

	URU/PHA/82/INV/72
	HCFC phase-out management plan (stage II, second tranche) (foam sector)
	Dec-23
	422,889
	122,736
	300,153
	
	21,011
	
	
	94/13(a)(iii)

	TOTAL UNDP
	
	
	
	
	2,648,187
	
	186,379
	
	
	



	UNIDO[footnoteRef:7] [7:  Outstanding obligations to be paid, funds will be returned with next balance list.] 


	ALG/SEV/84/TAS/83
	Enabling activities for HFC phase-down
	Jun-22
	150,000
	142,499
	7,501
	
	525
	1
	96
	

	BKF/PHA/84/PRP/41
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-23
	20,000
	19,207
	793
	
	55
	1
	96
	

	CMR/KIP/88/PRP/49
	Preparation of Kigali HFC implementation plan
	Dec-23
	190,000
	188,245
	1,755
	
	123
	1
	96
	

	CPR/PHA/88/INV/607
	HCFC phase-out management plan (stage II, fourth tranche) (extruded polystyrene foam sector plan)
	Dec-23
	4,400,000
	3,960,000
	440,000
	
	30,800
	1
	96
	

	GAB/PHA/79/INV/34
	HCFC phase-out management plan (stage I, third tranche)
	Dec-22
	119,900
	60,409
	59,491
	
	5,354
	1
	96
	

	GUA/PHA/91/TAS/61
	Verification report on the implementation of stage II of the HCFC phase-out management plan
	Dec-23
	30,000
	29,899
	101
	
	9
	1
	96
	

	GUI/PHA/86/PRP/37
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-23
	10,000
	9,999
	1
	
	0
	n.a.
	96
	

	IRQ/PHA/58/INV/09
	National phase-out plan (first tranche)
	Jun-21
	4,353,530
	2,398,765
	1,954,765
	
	146,607
	1
	96
	71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c) 

	IRQ/PHA/74/INV/23
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector)
	Dec-21
	230,000
	66,856
	163,144
	
	12,236
	1
	96
	

	IVC/PHA/84/INV/45
	HCFC phase-out management plan (stage I, third tranche)
	Dec-22
	460,000
	449,046
	10,954
	
	767
	1
	96
	90/32(a)

	JOR/PHA/77/INV/101
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	Dec-23
	227,686
	227,444
	242
	
	17
	1
	96
	

	JOR/PHA/84/TAS/107
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector, project management and coordination)
	Dec-23
	294,122
	280,486
	13,636
	
	954
	1
	96
	

	LEB/REF/88/PRP/99
	Project preparation for HFC-related project in the manufacturing sector at Lematic Industries to convert the production of residential air-conditioning from R-410A to R-290
	Dec-23
	30,000
	24,155
	5,845
	
	409
	1
	96
	

	LIB/PHA/75/INV/36
	HCFC phase-out management plan (stage I, first tranche) (foam sector)
	Dec-23
	943,094
	713,112
	229,982
	
	16,099
	1
	96
	93/23(c) 

	LIB/SEV/85/INS/44
	Renewal of the institutional strengthening project (phase VI: 7/2020-6/2022)
	Jun-23
	174,164
	166,234
	7,930
	
	555
	1
	96
	

	MDN/SEV/88/INS/48
	Extension of the institutional strengthening project (phase VII: 12/2021-11/2023)
	Dec-23
	169,404
	158,932
	10,472
	
	733
	1
	96
	

	MEX/PHA/73/INV/174
	HCFC phase-out management plan (stage II, first tranche) (cleaning agent phase-out in refrigeration servicing sector)
	Jun-23
	673,009
	672,892
	117
	
	8
	1
	96
	

	MEX/PHA/81/INV/189
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector)
	Dec-23
	2,139,719
	2,142,290
	-2,571
	
	-180
	n.a.
	96
	

	MOZ/PHA/66/INV/23
	HCFC phase-out management plan (stage I, first tranche)
	Dec-22
	75,000
	72,133
	2,867
	
	258
	1
	96
	

	MOZ/PHA/83/INV/31
	HCFC phase-out management plan (stage I, third and fourth tranches)
	Jun-23
	85,000
	75,322
	9,678
	
	871
	1
	96
	

	NER/PHA/84/INV/39
	HCFC phase-out management plan (stage I, second tranche)
	Dec-22
	90,000
	76,492
	13,508
	
	946
	1
	96
	

	NER/PHA/88/INV/41
	HCFC phase-out management plan (stage I, third tranche)
	Dec-22
	20,000
	19,002
	998
	
	70
	1
	96
	

	NIC/PHA/86/INV/40
	HCFC phase-out management plan (stage II, first tranche)
	Dec-23
	100,092
	98,549
	1,543
	
	108
	1
	96
	

	PHI/PHA/83/INV/104
	HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector)
	Dec-23
	537,856
	345,899
	191,957
	
	13,436
	1
	96
	87/19(c) 

	PHI/PHA/83/TAS/105
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	Dec-23
	273,894
	233,872
	40,022
	
	2,802
	1
	96
	87/19(c) 

	PHI/PHA/88/PRP/108
	Preparation of HCFC phase-out management plan (stage III) (Overarching)
	Dec-23
	70,000
	69,762
	238
	
	17
	1
	96
	

	SEN/PHA/85/INV/41
	HCFC phase-out management plan (stage I, third tranche)
	Dec-21
	50,000
	18,910
	31,090
	
	2,332
	1
	96
	

	SEN/PHA/85/PRP/43
	Preparation of a HCFC phase-out management plan (stage II)
	Jun-22
	20,000
	4,977
	15,023
	
	1,052
	1
	96
	

	SOA/PHA/91/INV/16
	HCFC phase-out management plan (stage I, fifth tranche) (refrigeration servicing, custom training and monitoring)
	Dec-23
	178,760
	157,305
	21,455
	
	1,502
	1
	96
	94/9(b)

	SOM/PHA/88/INV/16
	HCFC phase-out management plan (stage I, third tranche)
	Jun-23
	40,000
	34,494
	5,506
	
	385
	1
	96
	88/40(a)

	SYR/REF/62/INV/103
	Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group
	Dec-21
	1,465,361
	1,460,663
	4,698
	
	352
	1
	96
	

	TKM/PHA/86/INV/17
	HCFC phase-out management plan (stage II, first tranche)
	Dec-23
	165,000
	164,864
	137
	
	10
	1
	96
	

	ZAM/PHA/77/INV/33
	HCFC phase-out management plan (stage I, third tranche)
	Jun-23
	70,000
	69,311
	689
	
	62
	1
	96
	

	TOTAL UNIDO
	
	
	
	
	3,243,565
	
	239,274
	
	
	

	SPAIN
	
	
	
	
	
	
	
	
	
	

	MEX/PHA/81/TAS/190
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector)

	Dec-23

	1,070,000

	1,066,326

	3,674

	
	421

	
	
	

	TOTAL SPAIN
	
	
	
	
	3,674
	
	421
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Annex II
COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS
	CODE
	Project title
	Approved funding plus adjustments as of 
31 December 2023 (US $) 
	Funds disbursed as of 
95th meeting (US $)
	Balances committed as per 
95th meeting (US $)
	Balances not- committed as per 
95th meeting (US $)
	Support cost on balances committed and not-committed as per 
95th meeting (US $) 
	Why any balances could not be returned?
	When they could be returned?

	UNIDO[footnoteRef:8] [8:  Outstanding obligations to be paid, funds will be returned with next balance list.] 


	ARG/REF/81/INV/01+
	Conversion project for replacement of HFC-134a with isobutane (R-600a)/propane (R-290)-based refrigerant in the manufacture of domestic and commercial refrigeration equipment at Briket, Bambi and Mabe-Kronen
	1,840,755
	1,597,406
	2,622
	
	184
	1
	96

	ARG/SEV/81/TAS/02+
	Enabling activities for HFC phase-down
	250,000
	164,539
	85,461
	
	5,982
	1
	96

	VEN/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	250,000
	248,415
	1,585
	
	111
	1
	96

	TOTAL UNIDO
	
	
	
	89,668
	
	6,277
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Annex III
DETAILS ON COMPLETED, BY DECISIONS AND ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AND BILATERAL AGENCIES
	Code
	Project title
	Project costs returned (US $)
	Agency support costs (US $)
	Total (US $)

	UNDP
	
	
	
	

	ANG/PHA/84/TAS/22
	Verification report on the implementation of the HCFC phase-out management plan
	411
	37
	448

	BGD/SEV/81/TAS/52
	Enabling activities for HFC phase-down
	10,751
	753
	11,504

	CHI/SEV/87/INS/204
	Extension of the institutional strengthening project (phase XIV: 7/2021-6/2023)
	574
	40
	614

	CUB/PHA/82/PRP/61
	Preparation of a HCFC phase-out management plan (stage II)
	2,087
	146
	2,233

	DOM/PHA/83/PRP/68
	Preparation of a HCFC phase-out management plan (stage III)
	3,290
	230
	3,520

	FIJ/PHA/86/INV/38
	HCFC phase-out management plan (stage I, fourth tranche)
	4,942
	445
	5,387

	IDS/PHA/76/INV/211
	HCFC phase-out management plan (stage II, first tranche) (firefighting sector)
	14,922
	1,045
	15,967

	IND/SEV/88/INS/491
	Extension of institutional strengthening project (phase XIII: 12/2021-11/2023)
	2,941
	206
	3,147

	JAM/PHA/81/PRP/38
	Preparation of a HCFC phase-out management plan (stage II)
	6,499
	455
	6,954

	SRL/SEV/86/INS/57
	Extension of the institutional strengthening project (phase XIII: 1/2021-12/2022)
	3,221
	225
	3,446

	TRI/PHA/82/PRP/36
	Preparation of a HCFC phase-out management plan (stage II)
	100
	7
	107

	[bookmark: _Hlk179363021]Total completed projects
	
	49,738

	3,589

	53,327

	TOTAL UNDP
	
	49,738

	3,589

	53,327

	UNEP
	
	
	
	

	AFG/PHA/85/TAS/27
	HCFC phase-out management plan (stage I, fourth tranche)
	28,453
	3,699
	32,151

	AFG/PHA/85/TAS/29
	HCFC phase-out management plan (stage II, first tranche)
	180,908
	23,518
	204,426

	AFG/SEV/87/INS/31
	Extension of institutional strengthening project (phase X: 1/2022-12/2023)
	192,000
	0
	192,000

	ALB/KIP/87/PRP/44
	Preparation of Kigali HFC implementation plan
	1,633
	212
	1,846

	ALB/PHA/85/TAS/42
	HCFC phase-out management plan (stage II, first tranche)
	1,346
	175
	1,521

	ASP/PHA/85/TAS/62
	HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche)
	9,702
	1,261
	10,964

	BAH/PHA/88/TAS/40
	HCFC phase-out management plan (stage II, first tranche) (servicing sector)
	73
	9
	82

	BAH/PHA/88/TAS/42
	HCFC phase-out management plan (stage II, first tranche) (PMU)
	49
	6
	55

	BDI/PHA/86/TAS/41
	Verification report on the implementation of stage I of the HCFC phase-out management plan
	205
	27
	232

	BHA/PHA/88/TAS/31
	HCFC phase-out management plan (stage I, fourth tranche)
	-4,504
	-585
	-5,089

	BKF/SEV/87/INS/45
	Extension of the institutional strengthening project (phase XIV: 7/2021-6/2023)
	1
	0
	1

	BOT/PHA/82/TAS/22
	HCFC phase-out management plan (stage I, second tranche)
	-181
	-23
	-204

	BOT/PHA/88/TAS/28
	Verification report on the implementation of stage II of the HCFC phase-out management plan
	205
	27
	232

	CHI/KIP/88/PRP/208
	Preparation of Kigali HFC implementation plan
	12,675
	1,648
	14,323

	CHI/PHA/76/TAS/191
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	15,183
	1,974
	17,157

	CHI/PHA/85/TAS/199
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector)
	567
	74
	641

	COI/PHA/84/PRP/30
	Preparation of a HCFC phase-out management plan (stage II)
	26
	3
	29

	COL/PHA/84/TAS/107
	HCFC phase-out management plan (stage II, third tranche) (technical assistance in policies formulation and implementation)
	26,575
	3,455
	30,029

	COL/PHA/88/TAS/112
	HCFC phase-out management plan (stage II, fourth tranche)
	447
	58
	505

	GAB/PHA/84/PRP/39
	Preparation of a HCFC phase-out management plan (stage II)
	485
	63
	548

	GAB/SEV/87/INS/40
	Extension of the institutional strengthening project (phase XI: 7/2021-6/2023)
	50
	0
	50

	GAM/PHA/88/TAS/43
	Verification report on the implementation of stage II of the HCFC phase-out management plan
	205
	27
	232

	GBS/SEV/87/INS/28
	Extension of the institutional strengthening project (phase VII: 7/2021-6/2023)
	16
	0
	16

	GHA/KIP/87/PRP/53
	Preparation of Kigali HFC implementation plan
	410
	53
	463

	GHA/PHA/87/TAS/52
	HCFC phase-out management plan (stage II, first tranche)
	459
	60
	519

	GLO/SEV/91/TAS/361
	Compliance Assistance Programme: 2023 budget
	1,192,987
	95,439
	1,288,426

	GUI/PHA/85/TAS/33
	HCFC phase-out management plan (stage I, third tranche)
	205
	27
	232

	GUI/PHA/86/PRP/38
	Preparation of a HCFC phase-out management plan (stage II)
	7,880
	1,024
	8,904

	GUY/PHA/86/TAS/34
	Verification report on the implementation of the HCFC phase-out management plan
	9,850
	1,281
	11,131

	HON/PHA/86/TAS/52
	HCFC phase-out management plan (stage II, first tranche)
	240
	31
	271

	IVC/PHA/84/PRP/46
	Preparation of a HCFC phase-out management plan (stage II)
	463
	60
	523

	MEX/KIP/87/PRP/197
	Preparation of Kigali HFC implementation plan
	2,168
	282
	2,450

	MEX/PHA/90/TAS/201
	HCFC phase-out management plan (stage II, fourth tranche)
	3,377
	439
	3,816

	MLW/KIP/88/PRP/50
	Preparation of Kigali HFC implementation plan
	460
	60
	520

	MLW/PHA/91/TAS/53
	Verification report on the implementation of stage II of the HCFC phase-out management plan
	205
	27
	232

	NIC/PHA/88/TAS/46
	Verification report on the implementation of stage II of the HCFC phase-out management plan
	6,071
	789
	6,860

	NIR/KIP/87/PRP/157
	Preparation of Kigali HFC implementation plan
	430
	56
	486

	PAK/SEV/81/TAS/97
	Enabling activities for HFC phase-down
	2,580
	181
	2,761

	PER/PHA/85/TAS/58
	HCFC phase-out management plan (stage II, second tranche)
	3,823
	497
	4,320

	PHI/SEV/87/INS/107
	Extension of institutional strengthening project (phase XIII: 1/2022-12/2023)
	2,908
	0
	2,908

	STK/PHA/82/TAS/22
	Verification report on the implementation of the HCFC phase-out management plan
	982
	128
	1,110

	STP/PHA/81/PRP/28
	Preparation of a HCFC phase-out management plan (stage II)
	8
	1
	9

	SUR/PHA/81/TAS/26
	HCFC phase-out management plan (stage I, third tranche)
	1,250
	163
	1,413

	SUR/PHA/83/PRP/29
	Preparation of a HCFC phase-out management plan (stage II)
	4,950
	644
	5,594

	YEM/SEV/73/INS/43
	Extension of the institutional strengthening project (phase VIII: 1/2015-12/2016)
	14
	0
	14

	ZAM/PHA/91/TAS/45
	Verification report on the implementation of stage II of the HCFC phase-out management plan
	205
	27
	232

	ZIM/PHA/88/TAS/64
	Verification report on the implementation of stage II of the HCFC phase-out management plan
	205
	27
	232

	Total completed projects
	
	1,708,250
	136,920
	1,845,170

	ANG/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	(1,750)
	(123)
	(1,873)

	BRU/SEV/82/TAS/01+
	Enabling activities for HFC phase-down
	30,188
	2,113
	32,301

	DMI/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	10,000
	700
	10,700

	NAU/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	(8,278)
	(579)
	(8,857)

	STL/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	38,000
	2,660
	40,660

	SYR/SEV/83/TAS/01+
	Enabling activities for HFC phase-down
	19,000
	1,330
	20,330

	Total “additional voluntary contributions” projects
	
	87,160
	6,101
	93,261

	TOTAL UNEP
	
	1,795,410
	143,021
	1,938,431

	UNIDO
	
	
	
	

	AFG/PHA/77/INV/20
	HCFC phase-out management plan (stage I, second tranche)
	512
	46
	558

	ALB/PHA/85/INV/41
	HCFC phase-out management plan (stage II, first tranche)
	108
	9
	117

	ARG/PHA/79/INV/180
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	3,200
	224
	3,424

	ARG/PHA/80/TAS/185
	HCFC phase-out management plan (stage II, first tranche) (management and coordination)
	2,911
	204
	3,115

	BHE/PHA/86/TAS/38
	Verification report on implementation of stage I of the HCFC phase-out management plan
	9,094
	818
	9,912

	BOL/KIP/87/PRP/52
	Preparation of Kigali HFC implementation plan
	4,594
	321
	4,915

	BOT/PHA/75/INV/18
	HCFC phase-out management plan (stage I, first tranche)
	9,859
	690
	10,549

	BOT/PHA/82/INV/21
	HCFC phase-out management plan (stage I, second tranche)
	29,918
	2,094
	32,013

	CHI/PHA/76/TAS/189
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	173
	12
	185

	CHI/PHA/81/TAS/196
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector)
	3,923
	274
	4,197

	CHI/PHA/85/TAS/200
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector)
	2,123
	149
	2,272

	ECU/KIP/87/PRP/76
	Preparation of Kigali HFC implementation plan
	5,810
	407
	6,217

	ECU/PHA/86/INV/75
	HCFC phase-out management plan (stage II, first tranche)
	8,363
	586
	8,949

	ECU/SEV/87/INS/77
	Extension of institutional strengthening project (phase VII: 7/2019-6/2021)
	974
	68
	1,042

	EGY/PHA/84/TAS/145
	HCFC phase-out management plan (stage II, second tranche) (air-conditioning sector)
	3,494
	245
	3,738

	GLO/REF/80/DEM/344
	Global chiller replacement project (Argentina)
	253,768
	19,033
	272,801

	HON/PHA/86/INV/50
	HCFC phase-out management plan (stage II, first tranche)
	879
	61
	941

	KUW/PHA/66/INV/21
	HCFC phase-out management plan (stage I, first tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company)
	10,247
	769
	11,016

	KUW/PHA/74/INV/24
	HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector phase-out: Kuwait polyurethane Industry Co.; Kirby Building Systems, technical assistance to spray foam users and other small users)
	7,558
	529
	8,088

	KUW/PHA/74/INV/25
	HCFC phase-out management plan (stage I, second tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company)
	429
	30
	460

	KUW/PHA/88/INV/45
	HCFC phase-out management plan (stage I, fourth tranche) (extruded polystyrene foam sector phase-out)
	72,516
	5,076
	77,592

	LIB/FOA/82/PRP/41
	Preparation for HCFC phase-out investment activities (stage II) (foam sector)
	436
	31
	467

	LIB/PHA/75/INV/37
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector)
	12,538
	878
	13,416

	MAG/PHA/84/PRP/33
	Preparation of a HCFC phase-out management plan (stage II)
	1,023
	72
	1,094

	MEX/PHA/77/INV/183
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector)
	199
	14
	213

	MEX/PRO/86/INV/194
	Control and phase-out of HFC-23 emissions in production of HCFC-22 at Quimobasicos
	301
	21
	322

	MLW/KIP/88/PRP/51
	Preparation of Kigali HFC implementation plan
	1,878
	131
	2,009

	MLW/PHA/85/INV/48
	HCFC phase-out management plan (stage II, first tranche)
	4,748
	427
	5,175

	MOG/PHA/88/TAS/18
	Verification report on the implementation of stage II of the HCFC phase-out management plan
	4,410
	397
	4,807

	NIC/KIP/87/PRP/45
	Preparation of Kigali HFC implementation plan
	1,615
	113
	1,728

	NIR/PHA/83/PRP/153
	Preparation of a HCFC phase-out management plan (stage III)
	762
	53
	815

	OMA/SEV/86/INS/42
	Renewal of institutional strengthening support (phase VIII: 12/2020-11/2022)
	8,339
	584
	8,923

	PAK/FOA/84/INV/103
	Phase-out of HCFC-142b/HCFC-22 from the manufacturing of extruded polystyrene at Symobl Industries, Lahore
	1,100
	77
	1,177

	RWA/PHA/86/INV/35
	HCFC phase-out management plan (stage II, first tranche)
	711
	64
	775

	SOA/FOA/67/INV/03
	HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan)
	8,098
	567
	8,665

	SOA/PHA/76/INV/10
	HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan)
	3,398
	238
	3,636

	SOA/PHA/83/TAS/13
	HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring)
	1,455
	102
	1,557

	SOM/PHA/77/INV/12
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector)
	2,662
	186
	2,849

	SYR/KIP/88/PRP/109
	Preparation of Kigali HFC implementation plan
	3,210
	225
	3,435

	TKM/PHA/88/TAS/19
	Verification report on the implementation of stage II of the HCFC phase-out management plan
	81
	7
	89

	TUR/SEV/84/INS/110
	Extension of institutional strengthening project (phase IX: 12/2019-11/2021)
	24,482
	1,713
	26,195

	Total completed projects
	
	511,900
	37,546
	549,446

	MOR/SEV/81/TAS/01+
	Enabling activities for HFC phase-down

	55,275

	3,869

	59,144


	Total “additional voluntary contributions” projects
	
	55,275

	3,869

	59,144


	TOTAL UNIDO
	
	567,175
	41,415
	608,590

	WORLD BANK
	
	
	
	

	GLO/SEV/91/TAS/362
	Core unit budget (2023)
	
	70,433
	70,433

	IDS/PHA/88/INV/218
	HCFC phase-out management plan (stage II, third tranche) (foam sector)
	14,628
	1,024
	15,652

	VIE/EEF/93/PRP/89
	EE project at an AC enterprise will not go forward
	30,000
	2,100
	32,100

	VIE/PHA/91/INV/82
	Savings after closing the Stage II HPMP. Slightly adjusted after WB-Viet Nam project financial closure (with $269 more disbursed than reported in the 2023 PR).
	575,828
	40,308
	616,136


	Total completed projects
	
	620,456
	113,865
	734,321

	Total WORLD BANK
	
	620,456
	113,865
	734,321

	JAPAN
	
	
	
	

	VIE/PHA/87/INV/79
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector)
	2,301
	299
	2,600

	TOTAL JAPAN
	
	2,301
	299
	2,600
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