| NACIONES UNIDAS |  | EP |
| --- | --- | --- |
|  | Programa de las Naciones Unidas para el Medio Ambiente | Distr. GENERAL UNEP/OzL.Pro/ExCom/95/4 19 de noviembre de 2024 ESPAÑOL ORIGINAL: INGLÉS |

COMITÉ EJECUTIVO DEL FONDO MULTILATERAL
 PARA LA APLICACIÓN DEL
 PROTOCOLO DE MONTREAL
Nonagésima quinta reunión

Montreal, 4 - 8 de diciembre de 2024

Punto 4 b) del orden del día provisional

# INFORME SOBRE SALDOS Y DISPONIBILIDAD DE RECURSOS

# Introducción

# Este documento presenta una síntesis de los ajustes financieros indicados por los organismos de ejecución y bilaterales conforme a lo acordado por la Secretaría. Incluye datos estadísticos de todos los proyectos con saldos que se han retenido durante más de 12 meses después de la terminación del proyecto, de conformidad con lo estipulado en las decisiones 28/7 y 56/2 c). Se ocupa de los saldos que habrán de devolverse de los proyectos como seguimiento a las decisiones pertinentes (mencionados como proyectos "por decisión" en el presente documento). Indica también el nivel de recursos de que dispone el Comité Ejecutivo en efectivo según lo registrado en el documento sobre la situación de las contribuciones y los desembolsos, como se estipula en la decisión 41/92 b), y presenta una recomendación. Las cantidades que los organismos de ejecución mantienen para los proyectos terminados y para los proyectos de contribuciones voluntarias adicionales se indican en el anexo I y el anexo II. En el anexo III se presentan los fondos devueltos por los organismos bilaterales y de ejecución de proyectos terminados, por decisión y de contribuciones voluntarias adicionales.

# Fondos que se han de devolver a la 95a reunión

# Los fondos totales que han de devolverse ascienden a USD 3.337.269, que consisten en USD 3.334.669 por los organismos de ejecución y USD 2.600 por los organismos bilaterales, provenientes de proyectos terminados, y de contribuciones voluntarias adicionales, como se muestra en los cuadros 1 y 2.

# Cuadro 1. Fondos que han de devolver los organismos de ejecución a la 95a reunión (USD)

| Organismo | Costo del proyecto | Gastos de apoyo al organismo | Costo total |
| --- | --- | --- | --- |
| PNUD | 49.738 | 3.589 | 53.327 |
| PNUMA* | 1.795.410 | 143.021 | 1.938.431 |
| ONUDI | 567.175 | 41.415 | 608.590 |
| Banco Mundial | 620.456 | 113.865 | 734.321 |
| Total | 3.032.779 | 301.890 | 3.334.669 |

* Los fondos devueltos por el PNUMA incluyen USD401.361, más USD 27.217 en concepto de gastos de apoyo al organismo, para tres proyectos que se transferirán según se indica en el cuadro 5.

| Agency | Project cost | Agency support cost | Total |
| --- | --- | --- | --- |
| Japan | 2,301 | 299 | 2,600 |

Cuadro 2. Fondos que han de devolver los organismos bilaterales a la 95ª reunión (USD)

# Fondos en poder los organismos de ejecución y los organismos bilaterales

# El total de los fondos retenidos asciende a USD 6.417.445 (USD 6.413.350 por los organismos de ejecución y USD 4.096 por un organismo bilateral), como se muestra en los cuadros 3 y 4.

Table 3. Saldos de proyectos terminados y proyectos financiados con contribuciones voluntarias adicionales en poder de los organismos de ejecución (incluidos gastos de apoyo a los organismos)

| Año de terminación | PNUD |  | ONUDI |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Número | USD | Número | USD | Número | USD |
| Proyectos terminados hace más de dos años |  |  |  |  |  |  |
| 2020 | 1 | 40.434 | 0 | 0 | 1 | 40.434 |
| 2021 | 2 | 8.518 | 4 | 2.315.225 | 6 | 2.323.743 |
| 1 de enero a 31 de oct. de 2022 | 2 | 13.091 | 2 | 24.101 | 4 | 37.192 |
| Sub-total | 5 | 62.043 | 6 | 2.339.326 | 11 | 2.401.369 |
| Proyectos terminados hace menos de dos años |  |  |  |  |  |  |
| 1 de Nov a 31 de dic. 2022 | 3 | 102.335 | 5 | 95.212 | 8 | 197.547 |
| 2023 | 31 | 2.670.188 | 22 | 1.048.301 | 53 | 3.718.489 |
| Sub-total | 34 | 2.772.523 | 27 | 1.143.513 | 61 | 3.916.036 |
| Total | 39 | 2.834.566 | 33 | 3.482.839 | 72 | 6.317.405 |
| Proyectos financiados con contribuciones voluntarias adicionales |  |  |  |  |  |  |
|  | 0 | 0 | 3 | 95,945 | 3 | 95,945 |
| Total general | 39 | 2.834.566 | 36 | 3.578.784 | 75 | 6.413.350 |

Cuadro 4. Saldo de un proyecto terminado en poder de un organismo bilateral

| Organismo | Códido del proyecto | Año completado | Saldo comprometido (USD) |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Saldo del proyecto | Saldo para los gastos de apoyo al organismo | Total |
| España | MEX/PHA/81/TAS/190 | 2023 | 3.674 | 421 | 4,096 |

# Transferencia de proyectos

# De conformidad con la decisión 93/14 c), los saldos remanentes de los siguientes proyectos para el plan de gestión de eliminación de HCFC (PGEH) para Afganistán se transferirán del PNUMA a la ONUDI:

## AFG/PHA/85/TAS/27 (etapa I, cuarto tramo) – USD 28.453 más los gastos de apoyo al organismo de USD 3.699. La transferencia a la ONUDI supondría una reducción de los gastos de apoyo al organismo de USD 2.561;

## AFG/PHA/85/TAS/29 (etapa II, primer tramo) – USD 180.908 más los gastos de apoyo al organismo de USD 23.518. La transferencia a la ONUDI supondría una reducción de los gastos de apoyo al organismo de USD 16.282.

# Además, Afganistán solicitó la transferencia de fondos para la extensión del proyecto de fortalecimiento institucional (fase X) del PNUMA a la ONUDI como se muestra a continuación:

## AFG/SEV/87/INS/31 – USD 192.000, no incluidos los gastos de apoyo al organismo. La transferencia a la ONUDI supondría un incremento de los gastos de apoyo al organismo de USD 13.440.

# El cuadro 5 presenta información detallada sobre los saldos que han de transferirse. El Comité Ejecutivo podría considerar oportuno aprobar estas solicitudes.

Cuadro 5. Saldos de proyectos para Afganistán que han de transferirse

| Título del proyecto | Proyecto nº. | Devolución |  |  | Transferencia |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Al Fondo Multilateral |  |  | Al Organismo |  |  |
|  |  | Del | Saldo | Gasto de apoyo a programas | A | Saldo | Gasto de apoyo a programas |
| Etapas I y II del plan de gestión de la eliminación de los HCFC | AFG/PHA/85/TAS/27 | PNUMA | 28.453 | 3.699 | ONUDI | 28.453 | 2.561 |
|  | AFG/PHA/85/TAS/29 | PNUMA | 180.908 | 23.518 | ONUDI | 180.908 | 16.282 |
| Extensión del proyecto de fortalecimiento institucional | AFG/SEV/87/INS/31 | PNUMA | 192.000 | - | ONUDI | 192.000 | 13.440 |
| Total |  |  | 401.361 | 27.217 |  | 401.361 | 32.283 |

Disponibilidad de recursos

# El documento sobre la situación de las contribuciones y los desembolsos indica un saldo disponible de USD 577.336.286 al 23 de octubre de 2024. El saldo total devuelto por los organismos de ejecución y bilaterales a la 95ª reunión asciende a USD 2.908.691, excluyendo la cantidad de USD 428.578 devuelta por el PNUMA que ha de transferirse a la ONUDI. Por consiguiente, el nivel total de los recursos disponibles para aprobaciones en la 95ª reunión asciende a USD 580.244.977.

# Comentarios de la Secretaría

# La Secretaría recordó a los organismos de ejecución que los saldos de los proyectos terminados con un año de anterioridad o más y los proyectos financiados con contribuciones voluntarias adicionales deberían devolverse al Fondo Multilateral tan pronto como fuera posible.

# Teniendo en cuenta que el nivel total de fondos para proyectos y actividades presentados a la 95ª reunión asciende a USD 135.939.008, se cuenta con suficientes recursos disponibles para la aprobación prevista en la reunión.

Recomendación

# El Comité Ejecutivo puede estimar oportuno:

## Tomar nota del:

### El informe sobre saldos y disponibilidad de recursos que recoge el documento UNEP/OzL.Pro/ExCom/95/4;

### Que el nivel neto de fondos que los organismos de ejecución reintegran a la 95ª reunión es de USD 2.906.091, de los cuales USD 49.738, más USD 3.589 en concepto de gastos de apoyo al organismo que reintegra el PNUD; USD 1.394.049, más USD 115.804 en concepto de gastos de apoyo al organismo que reintegra el PNUMA; USD 567.175, más USD 41.415 en concepto de gastos de apoyo al organismo que reintegra la ONUDI; y USD 620.456, más USD 113.865 en concepto de gastos de apoyo al organismo que reintegra el Banco Mundial.

### Que el PNUD mantenía a su haber saldos de USD 62.043, incluyendo gastos de apoyo al organismo, por concepto de cinco proyectos terminados hace más de dos años;

### Que la ONUDI mantenía a su haber saldos de USD 2.339.326, incluyendo gastos de apoyo al organismo, por concepto de seis proyectos terminados hace más de dos años; USD 95.945, incluyendo gastos de apoyo al organismo, por concepto de tres proyectos financiados con las contribuciones voluntarias adicionales hechas por un grupo de países donantes para financiar actividades de apoyo inmediato para la reducción de HFC;

### Que el PNUMA devuelva en la 95ª reunión los saldos de las etapas I y II del plan de gestión de la eliminación de los HCFC (PGEH) y del proyecto de fortalecimiento institucional para Afganistán por un importe de USD 401.361, más los gastos de apoyo al organismo por valor de USD 27.217, que consisten en:

USD 28.453, más USD 3.699 en concepto de gastos de apoyo al organismo, con cargo al cuarto tramo de la etapa I del PGEH (AFG/PHA/85/TAS/27);

USD 180.908, más los gastos de apoyo al organismo por un valor de USD 23.518 del primer tramo de la etapa II del PGEH (AFG/PHA/85/TAS/29);

USD 192.000 de la extensión del proyecto de fortalecimiento institucional (fase X) (AFG/SEV/87/INS/31);

### Que el Gobierno de Japón devuelva USD 2.600, incluidos los gastos de apoyo a un proyecto;

## Solictar:

### Al PNUD y a la ONUDI proceder al desembolso o la cancelación de los fondos comprometidos que no fueron necesarios para los proyectos terminados, y devolver los saldos conexos a la 96ª reunión;

### Al PNUD y a la ONUDI proceder al desembolso o la cancelación de los compromisos de los proyectos terminados hace más de dos años, y devolver los saldos respectivos a la 96ª reunión;

### A la ONUDI proceder al desembolso o la devolución a la 96ª reunión de los saldos de los proyectos financiados con las contribuciones voluntarias adicionales;

### Al Tesorero; que transfiera a la ONUDI, en la 95ª reunión, los fondos devueltos para los proyectos mencionados en el subpárrafo a) v) anterior, para su ejecución, por un importe de USD 401.361, más los gastos de apoyo al organismo de USD 32.283, que consisten en:

USD 28.453, más los gastos de apoyo al organismo de USD 2.561 con cargo al cuarto tramo de la etapa I del PGEH P (AFG/PHA/85/TAS/27);

USD 180.908, más los gastos de apoyo al organismo de USD 16.282 con cargo al primer tramo de la etapa II del PGEH (AFG/PHA/85/TAS/29);

USD 192.000, más los gastos de apoyo al organismo de USD 13.440 de la extensión del proyecto de fortalecimiento institucional (fase X) (AFG/SEV/87/INS/31); y

### A la Tesorería, verificar con el Gobierno de Japón el reintegro en efectivo de la suma de USD 2.600 mencionada en el subpárrafo a) vi) anterior.

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 Dec 2023 (US $) | Funds disbursed as of 95th meeting (US $) | Balances committed as per 95th meeting (US $) | Balances not-committed as per 95th meeting (US $) | Support cost on balances committed and not committed as per 95th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| ANG/PHA/79/INV/19 | HCFC phase-out management plan (stage II, first tranche) | Aug-22 | 450,000 | 443,189 | 6,811 |  | 477 |  |  |  |
| BRA/PHA/88/PRP/330 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | Dec-23 | 40,000 | 31,233 | 8,767 |  | 614 |  |  |  |
| BZE/SEV/85/TAS/37 | Enabling activities for HFC phase-down | Oct-22 | 55,000 | 49,576 | 5,424 |  | 380 |  |  |  |
| COL/SEV/88/INS/115 | Extension of institutional strengthening project (phase XIII: 12/2021-11/2023) | Dec-23 | 352,768 | 328,161 | 24,607 |  | 1,723 |  |  |  |
| COS/SEV/88/INS/64 | Extension of institutional strengthening project (phase XIV: 1/2022-12/2023) | Dec-23 | 179,857 | 170,446 | 9,411 |  | 659 |  |  |  |
| EGY/PHA/79/TAS/132 | HCFC phase-out management plan (stage II, first tranche) (project management and monitoring) | Dec-22 | 75,000 | 67,871 | 7,129 |  | 499 |  |  |  |
| EGY/PHA/84/INV/144 | HCFC phase-out management plan (stage II, second tranche) (extruded polystyrene foam sector) | Dec-23 | 1,761,750 | 1,471,691 | 290,059 |  | 20,304 |  |  |  |
| GHA/KIP/87/PRP/51 | Preparation of Kigali HFC implementation plan | Aug-23 | 130,000 | 81,220 | 48,780 |  | 3,415 |  |  |  |
| GHA/PHA/87/INV/50 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 459,820 | 442,121 | 17,699 |  | 1,239 |  |  |  |
| HAI/SEV/84/TAS/23 | Enabling activities for HFC phase-down | Dec-21 | 95,000 | 90,311 | 4,689 |  | 328 |  |  |  |
| IDS/PHA/76/TAS/210 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-23 | 2,203,114 | 1,829,259 | 373,855 |  | 26,170 |  |  |  |
| IDS/PHA/87/PRP/216 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | Dec-23 | 90,000 | 65,168 | 24,832 |  | 1,738 |  |  |  |
| IND/PHA/87/PRP/487 | Preparation of HCFC phase-out management plan (stage III) (refrigeration sector) | Aug-23 | 150,000 | 89,924 | 60,076 |  | 4,205 |  |  |  |
| IRA/PHA/90/INV/262 | HCFC phase-out management plan (stage II, fourth tranche) (PMU) | Dec-23 | 92,000 | 69,877 | 22,123 |  | 1,549 |  |  |  |
| IRA/PHA/92/INV/264 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Dec-23 | 93,017 | 0 | 93,017 |  | 6,511 |  |  |  |
| IRA/PHA/92/INV/265 | HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration sector) | Dec-23 | 145,255 | 0 | 145,255 |  | 10,168 |  |  |  |
| IRA/SEV/86/INS/249 | Extension of the institutional strengthening project (phase XIII: 4/2021-3/2023) | May-23 | 222,094 | 178,036 | 44,058 |  | 3,084 |  |  |  |
| KAM/KIP/88/PRP/40 | Preparation of Kigali HFC implementation plan | Dec-23 | 35,000 | 19,678 | 15,322 |  | 1,073 |  |  |  |
| KYR/KIP/87/PRP/45 | Preparation of Kigali HFC implementation plan | Aug-23 | 91,000 | 74,690 | 16,310 |  | 1,142 |  |  |  |
| KYR/PHA/90/TAS/47 | Verification report on the implementation of stage II of the HCFC phase-out management plan | Jul-23 | 30,000 | 0 | 30,000 |  | 2,700 |  |  |  |
| LAO/PHA/86/INV/38 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 107,000 | 86,720 | 20,280 |  | 1,825 |  |  |  |
| LEB/SEV/86/INS/96 | Extension of the institutional strengthening project (phase XII: 4/2021-3/2023) | Dec-23 | 198,515 | 157,610 | 40,905 |  | 2,863 |  |  |  |
| MAL/PHA/84/INV/191 | HCFC phase-out management plan (stage II, second tranche) (polyurethane foam sector) | Dec-23 | 1,703,922 | 1,651,948 | 51,974 |  | 3,638 |  |  |  |
| MAL/PHA/84/TAS/186 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Dec-23 | 627,053 | 174,875 | 452,178 |  | 31,653 |  |  |  |
| MAL/PHA/88/INV/193 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector and management and coordination) | Dec-23 | 154,900 | 39,789 | 115,111 |  | 8,058 |  |  |  |
| MAL/SEV/88/INS/192 | Extension of institutional strengthening project (phase XIV: 1/2022-12/2023) | Dec-23 | 357,760 | 296,772 | 60,988 |  | 4,269 |  |  |  |
| MEX/KIP/87/PRP/195 | Preparation of Kigali HFC implementation plan | Aug-23 | 85,000 | 62,950 | 22,050 |  | 1,544 |  |  |  |
| NIR/PHA/81/TAS/148 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-22 | 1,077,113 | 1,063,456 | 13,657 |  | 956 |  |  |  |
| NIR/PHA/81/TAS/150 | HCFC phase-out management plan (stage II, first tranche) (project management and coordination) | Dec-22 | 165,000 | 90,146 | 74,854 |  | 5,240 |  |  |  |
| NIR/PHA/88/INV/162 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Dec-23 | 977,407 | 962,333 | 15,074 |  | 1,055 |  |  |  |
| PAN/PHA/83/PRP/49 | Preparation of a HCFC phase-out management plan (stage III) | Jun-21 | 60,000 | 56,728 | 3,272 |  | 229 |  |  |  |
| PAR/KIP/87/PRP/42 | Preparation of Kigali HFC implementation plan | Aug-23 | 170,000 | 154,838 | 15,162 |  | 1,061 |  |  |  |
| PER/KIP/87/PRP/59 | Preparation of Kigali HFC implementation plan | Sep-23 | 190,000 | 167,346 | 22,654 |  | 1,586 |  |  |  |
| PER/PHA/85/INV/57 | HCFC phase-out management plan (stage II, second tranche) | Jun-23 | 233,400 | 194,591 | 38,809 |  | 2,717 |  |  |  |
| SWA/KIP/87/PRP/33 | Preparation of Kigali HFC implementation plan | Aug-23 | 30,000 | 3,000 | 27,000 |  | 1,890 |  |  |  |
| TRI/PHA/86/INV/38 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 498,756 | 413,693 | 85,063 |  | 5,954 |  |  |  |
| TRI/SEV/88/INS/41 | Extension of the institutional strengthening project (phase XI: 12/2021-12/2023) | Dec-23 | 85,000 | 82,010 | 2,990 |  | 209 |  |  |  |
| URU/PHA/77/INV/67 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Dec-20 | 100,000 | 62,211 | 37,789 |  | 2,645 |  |  |  |
| URU/PHA/82/INV/72 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | Dec-23 | 422,889 | 122,736 | 300,153 |  | 21,011 |  |  | 94/13(a)(iii) |
| TOTAL UNDP |  |  |  |  | 2,648,187 |  | 186,379 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| ALG/SEV/84/TAS/83 | Enabling activities for HFC phase-down | Jun-22 | 150,000 | 142,499 | 7,501 |  | 525 | 1 | 96 |  |
| BKF/PHA/84/PRP/41 | Preparation of a HCFC phase-out management plan (stage II) | Dec-23 | 20,000 | 19,207 | 793 |  | 55 | 1 | 96 |  |
| CMR/KIP/88/PRP/49 | Preparation of Kigali HFC implementation plan | Dec-23 | 190,000 | 188,245 | 1,755 |  | 123 | 1 | 96 |  |
| CPR/PHA/88/INV/607 | HCFC phase-out management plan (stage II, fourth tranche) (extruded polystyrene foam sector plan) | Dec-23 | 4,400,000 | 3,960,000 | 440,000 |  | 30,800 | 1 | 96 |  |
| GAB/PHA/79/INV/34 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 119,900 | 60,409 | 59,491 |  | 5,354 | 1 | 96 |  |
| GUA/PHA/91/TAS/61 | Verification report on the implementation of stage II of the HCFC phase-out management plan | Dec-23 | 30,000 | 29,899 | 101 |  | 9 | 1 | 96 |  |
| GUI/PHA/86/PRP/37 | Preparation of a HCFC phase-out management plan (stage II) | Dec-23 | 10,000 | 9,999 | 1 |  | 0 | n.a. | 96 |  |
| IRQ/PHA/58/INV/09 | National phase-out plan (first tranche) | Jun-21 | 4,353,530 | 2,398,765 | 1,954,765 |  | 146,607 | 1 | 96 | 71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c) |
| IRQ/PHA/74/INV/23 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Dec-21 | 230,000 | 66,856 | 163,144 |  | 12,236 | 1 | 96 |  |
| IVC/PHA/84/INV/45 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 460,000 | 449,046 | 10,954 |  | 767 | 1 | 96 | 90/32(a) |
| JOR/PHA/77/INV/101 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-23 | 227,686 | 227,444 | 242 |  | 17 | 1 | 96 |  |
| JOR/PHA/84/TAS/107 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector, project management and coordination) | Dec-23 | 294,122 | 280,486 | 13,636 |  | 954 | 1 | 96 |  |
| LEB/REF/88/PRP/99 | Project preparation for HFC-related project in the manufacturing sector at Lematic Industries to convert the production of residential air-conditioning from R-410A to R-290 | Dec-23 | 30,000 | 24,155 | 5,845 |  | 409 | 1 | 96 |  |
| LIB/PHA/75/INV/36 | HCFC phase-out management plan (stage I, first tranche) (foam sector) | Dec-23 | 943,094 | 713,112 | 229,982 |  | 16,099 | 1 | 96 | 93/23(c) |
| LIB/SEV/85/INS/44 | Renewal of the institutional strengthening project (phase VI: 7/2020-6/2022) | Jun-23 | 174,164 | 166,234 | 7,930 |  | 555 | 1 | 96 |  |
| MDN/SEV/88/INS/48 | Extension of the institutional strengthening project (phase VII: 12/2021-11/2023) | Dec-23 | 169,404 | 158,932 | 10,472 |  | 733 | 1 | 96 |  |
| MEX/PHA/73/INV/174 | HCFC phase-out management plan (stage II, first tranche) (cleaning agent phase-out in refrigeration servicing sector) | Jun-23 | 673,009 | 672,892 | 117 |  | 8 | 1 | 96 |  |
| MEX/PHA/81/INV/189 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | Dec-23 | 2,139,719 | 2,142,290 | -2,571 |  | -180 | n.a. | 96 |  |
| MOZ/PHA/66/INV/23 | HCFC phase-out management plan (stage I, first tranche) | Dec-22 | 75,000 | 72,133 | 2,867 |  | 258 | 1 | 96 |  |
| MOZ/PHA/83/INV/31 | HCFC phase-out management plan (stage I, third and fourth tranches) | Jun-23 | 85,000 | 75,322 | 9,678 |  | 871 | 1 | 96 |  |
| NER/PHA/84/INV/39 | HCFC phase-out management plan (stage I, second tranche) | Dec-22 | 90,000 | 76,492 | 13,508 |  | 946 | 1 | 96 |  |
| NER/PHA/88/INV/41 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 20,000 | 19,002 | 998 |  | 70 | 1 | 96 |  |
| NIC/PHA/86/INV/40 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 100,092 | 98,549 | 1,543 |  | 108 | 1 | 96 |  |
| PHI/PHA/83/INV/104 | HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector) | Dec-23 | 537,856 | 345,899 | 191,957 |  | 13,436 | 1 | 96 | 87/19(c) |
| PHI/PHA/83/TAS/105 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Dec-23 | 273,894 | 233,872 | 40,022 |  | 2,802 | 1 | 96 | 87/19(c) |
| PHI/PHA/88/PRP/108 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | Dec-23 | 70,000 | 69,762 | 238 |  | 17 | 1 | 96 |  |
| SEN/PHA/85/INV/41 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 50,000 | 18,910 | 31,090 |  | 2,332 | 1 | 96 |  |
| SEN/PHA/85/PRP/43 | Preparation of a HCFC phase-out management plan (stage II) | Jun-22 | 20,000 | 4,977 | 15,023 |  | 1,052 | 1 | 96 |  |
| SOA/PHA/91/INV/16 | HCFC phase-out management plan (stage I, fifth tranche) (refrigeration servicing, custom training and monitoring) | Dec-23 | 178,760 | 157,305 | 21,455 |  | 1,502 | 1 | 96 | 94/9(b) |
| SOM/PHA/88/INV/16 | HCFC phase-out management plan (stage I, third tranche) | Jun-23 | 40,000 | 34,494 | 5,506 |  | 385 | 1 | 96 | 88/40(a) |
| SYR/REF/62/INV/103 | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group | Dec-21 | 1,465,361 | 1,460,663 | 4,698 |  | 352 | 1 | 96 |  |
| TKM/PHA/86/INV/17 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 165,000 | 164,864 | 137 |  | 10 | 1 | 96 |  |
| ZAM/PHA/77/INV/33 | HCFC phase-out management plan (stage I, third tranche) | Jun-23 | 70,000 | 69,311 | 689 |  | 62 | 1 | 96 |  |
| TOTAL UNIDO |  |  |  |  | 3,243,565 |  | 239,274 |  |  |  |
| SPAIN |  |  |  |  |  |  |  |  |  |  |
| MEX/PHA/81/TAS/190 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | Dec-23 | 1,070,000 | 1,066,326 | 3,674 |  | 421 |  |  |  |
| TOTAL SPAIN |  |  |  |  | 3,674 |  | 421 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS

| CODE | Project title | Approved funding plus adjustments as of 31 December 2023 (US $) | Funds disbursed as of 95th meeting (US $) | Balances committed as per 95th meeting (US $) | Balances not- committed as per 95th meeting (US $) | Support cost on balances committed and not-committed as per 95th meeting (US $) | Why any balances could not be returned? | When they could be returned? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNIDO |  |  |  |  |  |  |  |  |
| ARG/REF/81/INV/01+ | Conversion project for replacement of HFC-134a with isobutane (R-600a)/propane (R-290)-based refrigerant in the manufacture of domestic and commercial refrigeration equipment at Briket, Bambi and Mabe-Kronen | 1,840,755 | 1,597,406 | 2,622 |  | 184 | 1 | 96 |
| ARG/SEV/81/TAS/02+ | Enabling activities for HFC phase-down | 250,000 | 164,539 | 85,461 |  | 5,982 | 1 | 96 |
| VEN/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 250,000 | 248,415 | 1,585 |  | 111 | 1 | 96 |
| TOTAL UNIDO |  |  |  | 89,668 |  | 6,277 |  |  |

Annex III

DETAILS ON COMPLETED, BY DECISIONS AND ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AND BILATERAL AGENCIES

| Code |  | Project title |  |  | Project costs returned (US $) | Agency support costs (US $) |  | Total (US $) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |
| ANG/PHA/84/TAS/22 |  | Verification report on the implementation of the HCFC phase-out management plan |  |  | 411 | 37 |  | 448 |
| BGD/SEV/81/TAS/52 |  | Enabling activities for HFC phase-down |  |  | 10,751 | 753 |  | 11,504 |
| CHI/SEV/87/INS/204 |  | Extension of the institutional strengthening project (phase XIV: 7/2021-6/2023) |  |  | 574 | 40 |  | 614 |
| CUB/PHA/82/PRP/61 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 2,087 | 146 |  | 2,233 |
| DOM/PHA/83/PRP/68 |  | Preparation of a HCFC phase-out management plan (stage III) |  |  | 3,290 | 230 |  | 3,520 |
| FIJ/PHA/86/INV/38 |  | HCFC phase-out management plan (stage I, fourth tranche) |  |  | 4,942 | 445 |  | 5,387 |
| IDS/PHA/76/INV/211 |  | HCFC phase-out management plan (stage II, first tranche) (firefighting sector) |  |  | 14,922 | 1,045 |  | 15,967 |
| IND/SEV/88/INS/491 |  | Extension of institutional strengthening project (phase XIII: 12/2021-11/2023) |  |  | 2,941 | 206 |  | 3,147 |
| JAM/PHA/81/PRP/38 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 6,499 | 455 |  | 6,954 |
| SRL/SEV/86/INS/57 |  | Extension of the institutional strengthening project (phase XIII: 1/2021-12/2022) |  |  | 3,221 | 225 |  | 3,446 |
| TRI/PHA/82/PRP/36 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 100 | 7 |  | 107 |
| Total completed projects |  |  |  |  | 49,738 | 3,589 |  | 53,327 |
| TOTAL UNDP |  |  |  |  | 49,738 | 3,589 |  | 53,327 |
| UNEP |  |  |  |  |  |  |  |  |
| AFG/PHA/85/TAS/27 |  | HCFC phase-out management plan (stage I, fourth tranche) |  |  | 28,453 | 3,699 |  | 32,151 |
| AFG/PHA/85/TAS/29 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 180,908 | 23,518 |  | 204,426 |
| AFG/SEV/87/INS/31 |  | Extension of institutional strengthening project (phase X: 1/2022-12/2023) |  |  | 192,000 | 0 |  | 192,000 |
| ALB/KIP/87/PRP/44 |  | Preparation of Kigali HFC implementation plan |  |  | 1,633 | 212 |  | 1,846 |
| ALB/PHA/85/TAS/42 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 1,346 | 175 |  | 1,521 |
| ASP/PHA/85/TAS/62 |  | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) |  |  | 9,702 | 1,261 |  | 10,964 |
| BAH/PHA/88/TAS/40 |  | HCFC phase-out management plan (stage II, first tranche) (servicing sector) |  |  | 73 | 9 |  | 82 |
| BAH/PHA/88/TAS/42 |  | HCFC phase-out management plan (stage II, first tranche) (PMU) |  |  | 49 | 6 |  | 55 |
| BDI/PHA/86/TAS/41 |  | Verification report on the implementation of stage I of the HCFC phase-out management plan |  |  | 205 | 27 |  | 232 |
| BHA/PHA/88/TAS/31 |  | HCFC phase-out management plan (stage I, fourth tranche) |  |  | -4,504 | -585 |  | -5,089 |
| BKF/SEV/87/INS/45 |  | Extension of the institutional strengthening project (phase XIV: 7/2021-6/2023) |  |  | 1 | 0 |  | 1 |
| BOT/PHA/82/TAS/22 |  | HCFC phase-out management plan (stage I, second tranche) |  |  | -181 | -23 |  | -204 |
| BOT/PHA/88/TAS/28 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 205 | 27 |  | 232 |
| CHI/KIP/88/PRP/208 |  | Preparation of Kigali HFC implementation plan |  |  | 12,675 | 1,648 |  | 14,323 |
| CHI/PHA/76/TAS/191 |  | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) |  |  | 15,183 | 1,974 |  | 17,157 |
| CHI/PHA/85/TAS/199 |  | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) |  |  | 567 | 74 |  | 641 |
| COI/PHA/84/PRP/30 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 26 | 3 |  | 29 |
| COL/PHA/84/TAS/107 |  | HCFC phase-out management plan (stage II, third tranche) (technical assistance in policies formulation and implementation) |  |  | 26,575 | 3,455 |  | 30,029 |
| COL/PHA/88/TAS/112 |  | HCFC phase-out management plan (stage II, fourth tranche) |  |  | 447 | 58 |  | 505 |
| GAB/PHA/84/PRP/39 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 485 | 63 |  | 548 |
| GAB/SEV/87/INS/40 |  | Extension of the institutional strengthening project (phase XI: 7/2021-6/2023) |  |  | 50 | 0 |  | 50 |
| GAM/PHA/88/TAS/43 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 205 | 27 |  | 232 |
| GBS/SEV/87/INS/28 |  | Extension of the institutional strengthening project (phase VII: 7/2021-6/2023) |  |  | 16 | 0 |  | 16 |
| GHA/KIP/87/PRP/53 |  | Preparation of Kigali HFC implementation plan |  |  | 410 | 53 |  | 463 |
| GHA/PHA/87/TAS/52 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 459 | 60 |  | 519 |
| GLO/SEV/91/TAS/361 |  | Compliance Assistance Programme: 2023 budget |  |  | 1,192,987 | 95,439 |  | 1,288,426 |
| GUI/PHA/85/TAS/33 |  | HCFC phase-out management plan (stage I, third tranche) |  |  | 205 | 27 |  | 232 |
| GUI/PHA/86/PRP/38 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 7,880 | 1,024 |  | 8,904 |
| GUY/PHA/86/TAS/34 |  | Verification report on the implementation of the HCFC phase-out management plan |  |  | 9,850 | 1,281 |  | 11,131 |
| HON/PHA/86/TAS/52 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 240 | 31 |  | 271 |
| IVC/PHA/84/PRP/46 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 463 | 60 |  | 523 |
| MEX/KIP/87/PRP/197 |  | Preparation of Kigali HFC implementation plan |  |  | 2,168 | 282 |  | 2,450 |
| MEX/PHA/90/TAS/201 |  | HCFC phase-out management plan (stage II, fourth tranche) |  |  | 3,377 | 439 |  | 3,816 |
| MLW/KIP/88/PRP/50 |  | Preparation of Kigali HFC implementation plan |  |  | 460 | 60 |  | 520 |
| MLW/PHA/91/TAS/53 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 205 | 27 |  | 232 |
| NIC/PHA/88/TAS/46 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 6,071 | 789 |  | 6,860 |
| NIR/KIP/87/PRP/157 |  | Preparation of Kigali HFC implementation plan |  |  | 430 | 56 |  | 486 |
| PAK/SEV/81/TAS/97 |  | Enabling activities for HFC phase-down |  |  | 2,580 | 181 |  | 2,761 |
| PER/PHA/85/TAS/58 |  | HCFC phase-out management plan (stage II, second tranche) |  |  | 3,823 | 497 |  | 4,320 |
| PHI/SEV/87/INS/107 |  | Extension of institutional strengthening project (phase XIII: 1/2022-12/2023) |  |  | 2,908 | 0 |  | 2,908 |
| STK/PHA/82/TAS/22 |  | Verification report on the implementation of the HCFC phase-out management plan |  |  | 982 | 128 |  | 1,110 |
| STP/PHA/81/PRP/28 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 8 | 1 |  | 9 |
| SUR/PHA/81/TAS/26 |  | HCFC phase-out management plan (stage I, third tranche) |  |  | 1,250 | 163 |  | 1,413 |
| SUR/PHA/83/PRP/29 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 4,950 | 644 |  | 5,594 |
| YEM/SEV/73/INS/43 |  | Extension of the institutional strengthening project (phase VIII: 1/2015-12/2016) |  |  | 14 | 0 |  | 14 |
| ZAM/PHA/91/TAS/45 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 205 | 27 |  | 232 |
| ZIM/PHA/88/TAS/64 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 205 | 27 |  | 232 |
| Total completed projects |  |  |  |  | 1,708,250 | 136,920 |  | 1,845,170 |
| ANG/SEV/80/TAS/01+ |  | Enabling activities for HFC phase-down |  |  | (1,750) | (123) |  | (1,873) |
| BRU/SEV/82/TAS/01+ |  | Enabling activities for HFC phase-down |  |  | 30,188 | 2,113 |  | 32,301 |
| DMI/SEV/80/TAS/01+ |  | Enabling activities for HFC phase-down |  |  | 10,000 | 700 |  | 10,700 |
| NAU/SEV/81/TAS/01+ |  | Enabling activities for HFC phase-down |  |  | (8,278) | (579) |  | (8,857) |
| STL/SEV/80/TAS/01+ |  | Enabling activities for HFC phase-down |  |  | 38,000 | 2,660 |  | 40,660 |
| SYR/SEV/83/TAS/01+ |  | Enabling activities for HFC phase-down |  |  | 19,000 | 1,330 |  | 20,330 |
| Total “additional voluntary contributions” projects |  |  |  |  | 87,160 | 6,101 |  | 93,261 |
| TOTAL UNEP |  |  |  |  | 1,795,410 | 143,021 |  | 1,938,431 |
| UNIDO |  |  |  |  |  |  |  |  |
| AFG/PHA/77/INV/20 |  | HCFC phase-out management plan (stage I, second tranche) |  |  | 512 | 46 |  | 558 |
| ALB/PHA/85/INV/41 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 108 | 9 |  | 117 |
| ARG/PHA/79/INV/180 |  | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) |  |  | 3,200 | 224 |  | 3,424 |
| ARG/PHA/80/TAS/185 |  | HCFC phase-out management plan (stage II, first tranche) (management and coordination) |  |  | 2,911 | 204 |  | 3,115 |
| BHE/PHA/86/TAS/38 |  | Verification report on implementation of stage I of the HCFC phase-out management plan |  |  | 9,094 | 818 |  | 9,912 |
| BOL/KIP/87/PRP/52 |  | Preparation of Kigali HFC implementation plan |  |  | 4,594 | 321 |  | 4,915 |
| BOT/PHA/75/INV/18 |  | HCFC phase-out management plan (stage I, first tranche) |  |  | 9,859 | 690 |  | 10,549 |
| BOT/PHA/82/INV/21 |  | HCFC phase-out management plan (stage I, second tranche) |  |  | 29,918 | 2,094 |  | 32,013 |
| CHI/PHA/76/TAS/189 |  | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) |  |  | 173 | 12 |  | 185 |
| CHI/PHA/81/TAS/196 |  | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) |  |  | 3,923 | 274 |  | 4,197 |
| CHI/PHA/85/TAS/200 |  | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) |  |  | 2,123 | 149 |  | 2,272 |
| ECU/KIP/87/PRP/76 |  | Preparation of Kigali HFC implementation plan |  |  | 5,810 | 407 |  | 6,217 |
| ECU/PHA/86/INV/75 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 8,363 | 586 |  | 8,949 |
| ECU/SEV/87/INS/77 |  | Extension of institutional strengthening project (phase VII: 7/2019-6/2021) |  |  | 974 | 68 |  | 1,042 |
| EGY/PHA/84/TAS/145 |  | HCFC phase-out management plan (stage II, second tranche) (air-conditioning sector) |  |  | 3,494 | 245 |  | 3,738 |
| GLO/REF/80/DEM/344 |  | Global chiller replacement project (Argentina) |  |  | 253,768 | 19,033 |  | 272,801 |
| HON/PHA/86/INV/50 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 879 | 61 |  | 941 |
| KUW/PHA/66/INV/21 |  | HCFC phase-out management plan (stage I, first tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company) |  |  | 10,247 | 769 |  | 11,016 |
| KUW/PHA/74/INV/24 |  | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector phase-out: Kuwait polyurethane Industry Co.; Kirby Building Systems, technical assistance to spray foam users and other small users) |  |  | 7,558 | 529 |  | 8,088 |
| KUW/PHA/74/INV/25 |  | HCFC phase-out management plan (stage I, second tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company) |  |  | 429 | 30 |  | 460 |
| KUW/PHA/88/INV/45 |  | HCFC phase-out management plan (stage I, fourth tranche) (extruded polystyrene foam sector phase-out) |  |  | 72,516 | 5,076 |  | 77,592 |
| LIB/FOA/82/PRP/41 |  | Preparation for HCFC phase-out investment activities (stage II) (foam sector) |  |  | 436 | 31 |  | 467 |
| LIB/PHA/75/INV/37 |  | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) |  |  | 12,538 | 878 |  | 13,416 |
| MAG/PHA/84/PRP/33 |  | Preparation of a HCFC phase-out management plan (stage II) |  |  | 1,023 | 72 |  | 1,094 |
| MEX/PHA/77/INV/183 |  | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) |  |  | 199 | 14 |  | 213 |
| MEX/PRO/86/INV/194 |  | Control and phase-out of HFC-23 emissions in production of HCFC-22 at Quimobasicos |  |  | 301 | 21 |  | 322 |
| MLW/KIP/88/PRP/51 |  | Preparation of Kigali HFC implementation plan |  |  | 1,878 | 131 |  | 2,009 |
| MLW/PHA/85/INV/48 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 4,748 | 427 |  | 5,175 |
| MOG/PHA/88/TAS/18 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 4,410 | 397 |  | 4,807 |
| NIC/KIP/87/PRP/45 |  | Preparation of Kigali HFC implementation plan |  |  | 1,615 | 113 |  | 1,728 |
| NIR/PHA/83/PRP/153 |  | Preparation of a HCFC phase-out management plan (stage III) |  |  | 762 | 53 |  | 815 |
| OMA/SEV/86/INS/42 |  | Renewal of institutional strengthening support (phase VIII: 12/2020-11/2022) |  |  | 8,339 | 584 |  | 8,923 |
| PAK/FOA/84/INV/103 |  | Phase-out of HCFC-142b/HCFC-22 from the manufacturing of extruded polystyrene at Symobl Industries, Lahore |  |  | 1,100 | 77 |  | 1,177 |
| RWA/PHA/86/INV/35 |  | HCFC phase-out management plan (stage II, first tranche) |  |  | 711 | 64 |  | 775 |
| SOA/FOA/67/INV/03 |  | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) |  |  | 8,098 | 567 |  | 8,665 |
| SOA/PHA/76/INV/10 |  | HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan) |  |  | 3,398 | 238 |  | 3,636 |
| SOA/PHA/83/TAS/13 |  | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring) |  |  | 1,455 | 102 |  | 1,557 |
| SOM/PHA/77/INV/12 |  | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) |  |  | 2,662 | 186 |  | 2,849 |
| SYR/KIP/88/PRP/109 |  | Preparation of Kigali HFC implementation plan |  |  | 3,210 | 225 |  | 3,435 |
| TKM/PHA/88/TAS/19 |  | Verification report on the implementation of stage II of the HCFC phase-out management plan |  |  | 81 | 7 |  | 89 |
| TUR/SEV/84/INS/110 |  | Extension of institutional strengthening project (phase IX: 12/2019-11/2021) |  |  | 24,482 | 1,713 |  | 26,195 |
| Total completed projects |  |  |  |  | 511,900 | 37,546 |  | 549,446 |
| MOR/SEV/81/TAS/01+ |  | Enabling activities for HFC phase-down |  |  | 55,275 | 3,869 |  | 59,144 |
| Total “additional voluntary contributions” projects |  |  |  |  | 55,275 | 3,869 |  | 59,144 |
| TOTAL UNIDO |  |  |  |  | 567,175 | 41,415 |  | 608,590 |
| WORLD BANK |  |  |  |  |  |  |  |  |
| GLO/SEV/91/TAS/362 |  | Core unit budget (2023) |  |  |  | 70,433 |  | 70,433 |
| IDS/PHA/88/INV/218 |  | HCFC phase-out management plan (stage II, third tranche) (foam sector) |  |  | 14,628 | 1,024 |  | 15,652 |
| VIE/EEF/93/PRP/89 |  | EE project at an AC enterprise will not go forward |  |  | 30,000 | 2,100 |  | 32,100 |
| VIE/PHA/91/INV/82 |  | Savings after closing the Stage II HPMP. Slightly adjusted after WB-Viet Nam project financial closure (with $269 more disbursed than reported in the 2023 PR). |  |  | 575,828 | 40,308 |  | 616,136 |
| Total completed projects |  |  |  |  | 620,456 | 113,865 |  | 734,321 |
| Total WORLD BANK |  |  |  |  | 620,456 | 113,865 |  | 734,321 |
| JAPAN |  |  |  |  |  |  |  |  |
| VIE/PHA/87/INV/79 |  | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) |  |  | 2,301 | 299 |  | 2,600 |
| TOTAL JAPAN |  |  |  |  | 2,301 | 299 |  | 2,600 |

UNEP/OzL.Pro/ExCom/95/1

Los datos presentados se basan en el formato de presentación de informes que se ha elaborado en respuesta a la decisión 31/2

UNEP/OzL.Pro/ExCom/95/3

Véase también el documento UNEP/OzL.Pro/ExCom/95/20 relativo a los informes sobre proyectos con requisitos específicos de presentación de informes sin cuestiones pendientes.

Carta de fecha 8 de julio de 2024 de la Agencia Nacional de Protección del Medio Ambiente de Afganistán y véase también el documento UNEP/OzL.Pro/ExCom/95/37 sobre las enmiendas al programa de trabajo de la ONUDI para 2024.

La cantidad no incluye los fondos devueltos por el PNUMA por valor de USD 401.361, más los gastos de apoyo al organismo por valor de USD 27.217, para tres proyectos que se transferirán a la ONUDI, como se indica en el cuadro 5.

Outstanding obligations to be paid, funds will be returned with next balance list.

Outstanding obligations to be paid, funds will be returned with next balance list.