| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/93/4 20 November 2023 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-third Meeting

Montreal, 15-19 December 2023

Item 4(b) of the provisional agenda

# report on balances and availability of resources

# Introduction

# This document presents a summary of financial adjustments indicated by the implementing agencies (IAs) and bilateral agencies (BAs) as agreed by the Secretariat. It includes statistical data from all projects with balances that have been held for over 12 months following completion of the project, as required by decisions 28/7 and 56/2(c). It addresses balances to be returned against projects as a follow-up to relevant decisions (referred to as “by-decision” projects in this document). It also indicates the level of resources available to the Executive Committee in cash as recorded in the status of contributions and disbursements document, as required by decision 41/92(b), and presents a recommendation. The amounts that are held by IAs for completed projects and for additional voluntary contributions projects are included in annex I and annex II. Annex III presents the funds returned by BAs and IAs from completed, by-decision and additional voluntary contributions projects.

Funds to be returned to the 93rd meeting

# The total funds to be returned amount to US $4,286,636 (i.e., US $50,850 by BAs and US $4,235,786 by IAs) from completed, by-decisions, and additional voluntary contributions projects.

Funds to be returned by IAs

# The total funds to be returned by IAs amount to US $4,235,786 as shown in table 1.

# Table 1. Funds to be returned by IAs to the 93rd meeting (US $)

| Agency | Project cost | Agency support cost | Total cost |
| --- | --- | --- | --- |
| UNDP | 562,920 | 39,505 | 602,425 |
| UNEP | 2,245,847 | 175,064 | 2,420,911 |
| UNIDO | 551,323 | 38,603 | 589,926 |
| World Bank | 320,000 | 302,524 | 622,524 |
| Total | 3,680,090 | 555,696 | 4,235,786 |

Funds withheld by IAs

# Table 2 presents information on balances of completed and additional voluntary contributions projects that are withheld by the IAs.

Table 2. Balances of completed and additional voluntary contributions projects withheld by IAs (including agency support costs)

| Year completed | UNDP |  | UNIDO |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Number | (US $) | Number | (US $) | Number | (US $) |
| Projects completed over two years ago |  |  |  |  |  |  |
| 2019 | 1 | 6,306 |  |  | 1 | 6,306 |
| 2020 | 1 | 40,434 |  |  | 1 | 40,434 |
| 1 Jan to 31 Oct 2021 | 5 | 63,190 | 2 | 1,828,437 | 7 | 1,891,627 |
| Sub-total | 7 | 109,930 | 2 | 1,828,437 | 9 | 1,938,367 |
| Projects completed in less than two years ago |  |  |  |  |  |  |
| 1 Nov to 31 Dec 2021 | 5 | 37,308 | 4 | 39,841 | 9 | 77,149 |
| 2022 | 20 | 277,877 | 25 | 558,563 | 45 | 836,440 |
| Sub-total | 25 | 315,185 | 29 | 598,404 | 54 | 913,589 |
| Total | 32 | 425,115 | 31 | 2,426,841 | 63 | 2,851,956 |
| Additional voluntary contributions projects |  |  |  |  |  |  |
|  | 2 | 7,953 | 5 | 122,134 | 7 | 130,087 |
| Grand total | 34 | 433,068 | 36 | 2,548,975 | 70 | 2,982,043 |

Funds to be returned to the 93rd meeting by BAs

5.	The total funds to be returned by a BA amount to US $50,850 from completed projects as shown in table 3.

| Agency | Project cost | Agency support cost | Total |
| --- | --- | --- | --- |
| France | 45,000 | 5,850 | 50,850 |

Table 3. Funds to be returned by a BA (US $)

Availability of resources

# The status of contributions and disbursements document indicates an available balance of US $523,322,098 as of 8 November 2023. The total balance returned by BAs and IAs, to the 93rd meeting amounts to US $4,286,636. Therefore, excluding the amount of US $246 million pertaining to the remaining funds from the 2018-2020 triennium and to be used after 2023, the total level of resources available for approvals at the 93rd meeting, is US $281,608,734.

# Secretariat’s comments

# The Secretariat reminded IAs that balances of by-decisions projects, projects completed one year ago and more, and additional voluntary contributions projects should be returned to the Multilateral Fund as soon as possible.

# Considering that the total level of funding for projects and activities as submitted to the 93rd meeting as of 22 October 2023 is US $122,704,590 there are sufficient resources available for approvals at the 
93rd meeting.

Recommendation

# The Executive Committee may wish:

  - To note:

- The report on balances and availability of resources contained in document UNEP/OzL.Pro/ExCom/93/4;

- That the net level of funds being returned by the implementing agencies at the 
93rd meeting is US $4,235,786 consisting of US $562,920, plus agency support costs of US $39,505 from UNDP; US $2,245,847, plus agency support costs of US $175,064 from UNEP; US $551,323, plus agency support costs of US $38,603 from UNIDO; and US $320,000, plus agency support costs of US $302,524 from the World Bank;

- That UNDP held balances of US $109,930, including agency support costs, for seven projects completed over two years previously, and US $7,953, including agency support costs, for two completed projects funded using the additional voluntary contributions made by a group of donor countries to finance fast-start activities for the implementation of HFC phase-down;

- That UNIDO held balances of US $1,828,437 including agency support costs for two projects funded completed over two years previously and US $122,134, including agency support cost for five completed projects using the additional voluntary contributions made by a group of donor countries to finance fast-start activities for the implementation of HFC phase-down; and

- That the level of funds being returned at the 93rd meeting by the Government of France is US $50,850, consisting of US $45,000 plus agency support costs of US $5,850.

## To request:

### UNDP and UNIDO:

To proceed with disbursement or to cancel committed and not-committed funds that were not needed for completed projects, and to return the associated balances at the 94th meeting;

To proceed with disbursement or to cancel commitments for the projects completed over two years previously, and to return balances at the 94th meeting; and

To proceed with disbursement or return at the 94th meeting the balances of completed projects funded using the additional voluntary contributions;

### The Treasurer to follow up with the Government of France, on the return, in cash, of the amount of US $50,850 referred to in sub-paragraph (a)(v) above.

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 Dec 2022 (US $) | Funds disbursed as of 93rd meeting (US $) | Balances committed as per 93rd meeting (US $) | Balances not-committed as per 93rd meeting (US $) | Support cost on balances committed and not committed as per 93rd meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| ANG/PHA/84/TAS/22 | Verification report on the implementation of the HCFC phase-out management plan | Dec-21 | 30,000 | 22,149 | 7,851 |  | 707 |  |  |  |
| ARG/SEV/82/INS/188 | Extension for institutional strengthening project (phase X: 1/2019-12/2020) | Dec-22 | 398,806 | 384,407 | 14,399 |  | 1,008 |  |  |  |
| BGD/SEV/81/TAS/52 | Enabling activities for HFC phase-down | Jun-22 | 14,000 | 3,249 | 10,751 |  | 753 |  |  |  |
| BRA/DES/72/DEM/305 | Pilot demonstration project on ODS waste management and disposal | Dec-22 | 1,490,600 | 1,488,205 | 2,395 |  | 168 |  |  |  |
| BRU/PHA/85/INV/26 | HCFC phase-out management plan (stage I, fourth tranche) | Dec-22 | 6,600 | 149 | 6,451 |  | 581 |  |  |  |
| BZE/SEV/85/TAS/37 | Enabling activities for HFC phase-down | Oct-22 | 55,000 | 49,576 | 5,424 |  | 380 |  |  |  |
| CHI/PHA/81/INV/197 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | Dec-22 | 1,290,468 | 1,203,966 | 86,502 |  | 6,055 |  |  |  |
| COL/PHA/84/TAS/108 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector, project management and monitoring) | Dec-22 | 635,749 | 623,148 | 12,601 |  | 882 |  |  |  |
| CUB/PHA/82/PRP/61 | Preparation of a HCFC phase-out management plan (stage II) | Oct-21 | 60,000 | 38,281 | 21,719 |  | 1,520 |  |  |  |
| CUB/SEV/83/INS/62 | Extension of institutional strengthening project (phase XI: 7/2019-6/2021) | Dec-22 | 190,804 | 190,442 | 362 |  | 25 |  |  |  |
| DOM/PHA/83/PRP/68 | Preparation of a HCFC phase-out management plan (stage III) | Jun-21 | 60,000 | 47,408 | 12,592 |  | 881 |  |  |  |
| DRC/PHA/79/PRP/42 | Preparation of a HCFC phase-out management plan (stage II) | Dec-21 | 17,143 | 16,296 | 847 |  | 59 |  |  |  |
| EGY/PHA/79/INV/135 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | Jul-22 | 967,352 | 933,070 | 34,282 |  | 2,400 |  |  |  |
| FIJ/PHA/77/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 59,850 | 54,065 | 5,785 |  | 521 |  |  |  |
| FIJ/PHA/82/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | Dec-21 | 30,000 | 26,442 | 3,558 |  | 249 |  |  |  |
| FIJ/PHA/86/INV/38 | HCFC phase-out management plan (stage I, fourth tranche) | Dec-22 | 19,950 | 0 | 19,950 |  | 1,795 |  |  |  |
| GEO/PHA/85/INV/42 | HCFC phase-out management plan (stage I, fourth tranche) | Dec-22 | 31,500 | 25,577 | 5,923 |  | 444 |  |  |  |
| GHA/SEV/86/INS/49 | Extension of the institutional strengthening project (phase XIV: 1/2021-12/2022) | Dec-22 | 178,048 | 177,873 | 175 |  | 12 |  |  |  |
| HAI/SEV/84/TAS/23 | Enabling activities for HFC phase-down | Dec-21 | 95,000 | 90,311 | 4,689 |  | 328 |  |  |  |
| JAM/PHA/81/PRP/38 | Preparation of a HCFC phase-out management plan (stage II) | Jul-21 | 40,000 | 33,501 | 6,499 |  | 455 |  |  |  |
| MOL/PHA/86/INV/43 | HCFC phase-out management plan (stage II, third tranche) | Dec-21 | 17,450 | 0 | 17,450 |  | 1,570 |  |  |  |
| MOL/PHA/86/TAS/42 | Verification report for implementation of stage II of the HCFC phase-out management plan | Dec-22 | 30,000 | 21,459 | 8,541 |  | 769 |  |  |  |
| MOL/SEV/85/TAS/41 | Enabling activities for HFC phase-down | Dec-22 | 50,000 | 38,716 | 11,284 |  | 790 |  |  |  |
| NEP/PHA/86/INV/44 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 8,400 | 0 | 8,400 |  | 756 |  |  |  |
| NIR/PHA/83/PRP/154 | Preparation of a HCFC phase-out management plan (stage III) | Dec-22 | 22,500 | 11,717 | 10,783 |  | 755 |  |  |  |
| PAN/PHA/83/PRP/49 | Preparation of a HCFC phase-out management plan (stage III) | Jun-21 | 60,000 | 42,695 | 17,305 |  | 1,211 |  |  |  |
| SRL/SEV/86/INS/57 | Extension of the institutional strengthening project (phase XIII: 1/2021-12/2022) | Dec-22 | 171,592 | 171,357 | 235 |  | 16 |  |  |  |
| SWA/PHA/83/PRP/27 | Preparation of a HCFC phase-out management plan (stage II) | Jun-21 | 10,000 | 9,059 | 941 |  | 66 |  |  |  |
| URU/PHA/77/INV/67 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Dec-20 | 100,000 | 62,211 | 37,789 |  | 2,645 |  |  |  |
| URU/PHA/85/INV/75 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector and implementation and monitoring) | Dec-22 | 111,268 | 104,570 | 6,698 |  | 469 |  |  |  |
| URU/SEV/84/INS/74 | Extension of institutional strengthening project (phase XIII: 1/2020-12/2021) | Apr-22 | 193,024 | 181,625 | 11,399 |  | 798 |  |  |  |
| VEN/SEV/82/INS/136 | Renewal of institutional strengthening project (phase XIV: 1/2019-12/2020) | Dec-22 | 365,414 | 363,110 | 2,305 |  | 162 |  |  |  |
| TOTAL UNDP |  |  |  |  | 395,885 |  | 29,230 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| AFG/PHA/77/INV/20 | HCFC phase-out management plan (stage I, second tranche) | Sep-21 | 131,938 | 131,427 | 511 |  | 46 | 2 | 94 |  |
| ALG/SEV/84/TAS/83 | Enabling activities for HFC phase-down | Jun-22 | 150,000 | 145,808 | 4,192 |  | 293 | 2 | 94 |  |
| ARG/PHA/79/INV/180 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Jun-22 | 645,746 | 642,391 | 3,355 |  | 235 | 2 | 94 |  |
| BDI/PHA/85/PRP/40 | Preparation of a HCFC phase-out management plan (stage II) | Dec-22 | 10,000 | 9,815 | 185 |  | 13 | 3 | 94 |  |
| BHE/PHA/72/INV/29 | HCFC phase-out management plan (stage I, second tranche) (activities in the refrigeration servicing sector including policy actions) | Dec-22 | 128,979 | 128,879 | 100 |  | 7 | 2 | 94 |  |
| BHE/PHA/76/INV/33 | HCFC phase-out management plan (stage I, third tranche) (activities in the refrigeration servicing sector including policy actions) | Dec-22 | 117,692 | 117,416 | 276 |  | 19 | 2 | 94 |  |
| BHE/PHA/82/INV/36 | HCFC phase-out management plan (stage I, fourth tranche) (activities in the refrigeration servicing sector including policy actions) | Dec-22 | 31,000 | 30,339 | 661 |  | 46 | 2 | 94 |  |
| BOT/PHA/75/INV/18 | HCFC phase-out management plan (stage I, first tranche) | Dec-22 | 140,000 | 132,272 | 7,728 |  | 541 | 3 | 94 |  |
| GAB/PHA/79/INV/34 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 119,900 | 108,729 | 11,171 |  | 1,005 | 2 | 94 |  |
| GLO/REF/80/DEM/344 | Global chiller replacement project (Argentina) | Dec-22 | 808,438 | 554,732 | 253,706 |  | 19,028 | 2 | 94 | 82/21(d), 86/17(h) and 88/15(b)(ii) |
| GUI/PHA/85/INV/34 | HCFC phase-out management plan (stage I, third tranche) | Jul-22 | 125,000 | 120,432 | 4,568 |  | 320 | 2 | 94 |  |
| IRQ/PHA/58/INV/09 | National phase-out plan (first tranche) | Jun-21 | 4,353,530 | 2,653,177 | 1,700,353 |  | 127,527 | 2 | 94 | 71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c) |
| IRQ/PHA/74/INV/23 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Dec-21 | 230,000 | 229,936 | 64 |  | 5 | 2 | 94 |  |
| IRQ/PHA/84/INV/29 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | Dec-21 | 210,000 | 177,225 | 32,775 |  | 2,458 | 2 | 94 |  |
| IVC/PHA/84/INV/45 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 460,000 | 451,891 | 8,109 |  | 568 | 2 | 94 | 90/32(a) |
| JOR/PHA/77/INV/100 | HCFC phase-out management plan (stage II, first tranche) (polyurethane spray foam sector) | Dec-22 | 164,485 | 164,374 | 111 |  | 8 | 3 | 94 |  |
| JOR/PHA/84/INV/106 | HCFC phase-out management plan (stage II, second tranche) (polyurethane spray foam sector) | Dec-22 | 246,727 | 239,272 | 7,455 |  | 522 | 3 | 94 |  |
| KUW/PHA/66/INV/21 | HCFC phase-out management plan (stage I, first tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company) | Jun-22 | 3,510,450 | 3,506,188 | 4,262 |  | 320 | 2 | 94 |  |
| KUW/PHA/74/INV/24 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector phase-out: Kuwait polyurethane Industry Co.; Kirby Building Systems, technical assistance to spray foam users and other small users) | Jun-22 | 643,382 | 637,195 | 6,187 |  | 433 | 2 | 94 |  |
| KUW/PHA/74/INV/25 | HCFC phase-out management plan (stage I, second tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company) | Jun-22 | 2,706,000 | 2,703,464 | 2,536 |  | 177 | 2 | 94 |  |
| KUW/PHA/83/TAS/37 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | Jun-22 | 218,000 | 28,335 | 189,665 |  | 13,277 | 2 | 94 |  |
| KUW/PHA/88/INV/45 | HCFC phase-out management plan (stage I, fourth tranche) (extruded polystyrene foam sector phase-out) | Jun-22 | 877,675 | 876,444 | 1,231 |  | 86 | 2 | 94 |  |
| KUW/PHA/88/INV/46 | HCFC phase-out management plan (stage I, fourth tranche) (polyurethane foam sector phase-out) | Jun-22 | 42,325 | 42,289 | 36 |  | 3 | 2 | 94 |  |
| MAG/PHA/84/PRP/33 | Preparation of a HCFC phase-out management plan (stage II) | Dec-22 | 20,000 | 19,232 | 768 |  | 54 | 3 | 94 |  |
| MOZ/PHA/66/INV/23 | HCFC phase-out management plan (stage I, first tranche) | Dec-22 | 75,000 | 74,225 | 775 |  | 70 | 3 | 94 |  |
| MYA/PHA/80/INV/19 | HCFC phase-out management plan (stage I, second tranche) | Dec-22 | 60,000 | 53,880 | 6,120 |  | 551 | 3 | 94 |  |
| NER/KIP/87/PRP/40 | Preparation of Kigali HFC implementation plan | Dec-22 | 170,000 | 169,632 | 368 |  | 26 | 3 | 94 |  |
| SEN/PHA/85/INV/41 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 50,000 | 48,582 | 1,418 |  | 106 | 2 | 94 |  |
| SEN/PHA/85/PRP/43 | Preparation of a HCFC phase-out management plan (stage II) | Jun-22 | 20,000 | 13,145 | 6,855 |  | 480 | 2 | 94 |  |
| SOM/PHA/77/INV/12 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Dec-22 | 141,500 | 141,442 | 58 |  | 4 | 3 | 94 | 88/40(a) |
| SYR/REF/62/INV/103 | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group | Dec-21 | 1,465,361 | 1,462,556 | 2,805 |  | 210 | 2 | 94 |  |
| TOTAL UNIDO |  |  |  |  | 2,258,404 |  | 168,437 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS

| CODE | Project title | Approved funding plus adjustments as of 31 December 2022 (US $) | Funds disbursed as of 93rd meeting (US $) | Balances committed as per 93rd meeting (US $) | Balances not- committed as per 93rd meeting (US $) | Support cost on balances committed and not-committed as per 93rd meeting (US $) | Why any balances could not be returned? | When they could be returned? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |
| CHI/SEV/80/TAS/03+ | Enabling activities for HFC phase-down | 33,000 | 27,058 | 5,942 |  | 416 |  |  |
| URU/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 100,000 | 98,509 | 1,491 |  | 104 |  |  |
| TOTAL UNDP |  |  |  | 7,433 |  | 520 |  |  |
| UNIDO |  |  |  |  |  |  |  |  |
| ARG/REF/81/INV/01+ | Conversion project for replacement of HFC-134a with isobutane (R-600a)/propane (R-290)-based refrigerant in the manufacture of domestic and commercial refrigeration equipment at Briket, Bambi and Mabe-Kronen | 1,840,755 | 1,835,494 | 5,261 |  | 368 | 1 | 94 |
| ARG/SEV/81/TAS/02+ | Enabling activities for HFC phase-down | 250,000 | 199,189 | 50,811 |  | 3,557 | 1 | 94 |
| EGY/SEV/81/TAS/02+ | Enabling activities for HFC phase-down | 105,000 | 101,318 | 3,682 |  | 258 | 1 | 94 |
| MOR/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 150,000 | 95,809 | 54,191 |  | 3,793 | 1 | 94 |
| VEN/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 250,000 | 249,800 | 200 |  | 14 | 1 | 94 |
| TOTAL UNIDO |  |  |  | 114,144 |  | 7,990 |  |  |

Annex III

DETAILS ON COMPLETED, BY DECISIONS AND ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES

| Code | Project title | Project costs returned (US $) | Agency support costs (US $) | Total (US $) |
| --- | --- | --- | --- | --- |
| BGD/SEV/83/INS/55 | Renewal of the institutional strengthening project (phase IX: 7/2019-6/2021) | 18 | 1 | 19 |
| BZE/PHA/50/PRP/17 | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | 1 | 0 | 1 |
| BZE/PHA/82/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | 1,250 | 87 | 1,338 |
| CHI/SEV/83/INS/198 | Extension of the institutional strengthening project (phase XIII: 7/2019-6/2021) | 169 | 12 | 181 |
| COL/PHA/81/INV/102 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | 542,962 | 38,007 | 580,969 |
| COL/SEV/79/INS/101 | Extension of institutional strengthening project (phase XI: 11/2017-10/2019) | 773 | 54 | 827 |
| COL/SEV/83/INS/106 | Extension of institutional strengthening project (phase XII: 11/2019-10/2021) | 2,624 | 184 | 2,808 |
| COS/SEV/84/INS/62 | Extension of institutional strengthening project (phase XIII: 1/2020-12/2021) | 362 | 25 | 387 |
| ELS/PHA/79/TAS/36 | Verification report for stage I of HCFC phase-out management plan | 835 | 75 | 910 |
| GUY/PHA/75/INV/28 | HCFC phase-out management plan (stage II, first tranche) | 1,893 | 133 | 2,026 |
| IDS/SEV/84/INS/215 | Extension of institutional strengthening project (phase XII: 1/2020-12/2021) | 2,244 | 157 | 2,401 |
| IND/SEV/84/INS/478 | Extension of institutional strengthening project (phase XII: 12/2019-11/2021) | 1,547 | 108 | 1,655 |
| IRA/SEV/82/INS/231 | Extension of the institutional strengthening project (phase XII: 4/2019-3/2021) | 474 | 33 | 507 |
| JAM/PHA/84/TAS/39 | Verification report on the implementation of the HCFC phase-out management plan | 3,421 | 308 | 3,729 |
| JAM/PHA/85/INV/41 | HCFC phase-out management plan (stage I, fourth tranche) | 3,102 | 233 | 3,335 |
| MAL/SEV/84/INS/188 | Extension of institutional strengthening project (phase XIII: 1/2020-12/2021) | 438 | 31 | 469 |
| PAN/SEV/80/INS/45 | Extension of institutional strengthening project (phase VIII: 12/2017-11/2019) | 1 | 0 | 1 |
| TOG/PHA/48/PRP/13 | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | 1 | 0 | 1 |
| TRI/PHA/82/PRP/36 | Preparation of a HCFC phase-out management plan (stage II) | 806 | 56 | 862 |
| Total completed projects |  | 562,920 | 39,505 | 602,425 |
| TOTAL UNDP |  | 562,920 | 39,505 | 602,425 |
| AFG/SEV/83/INS/26 | Extension of institutional strengthening project (phase IX: 1/2020-12/2021) | 38,119 | 0 | 38,119 |
| ALB/SEV/84/INS/38 | Renewal of institutional strengthening project (phase IX: 7/2020-6/2022) | 1,109 | 0 | 1,109 |
| BDI/SEV/85/TAS/39 | Enabling activities for HFC phase-down | 50,000 | 3,500 | 53,500 |
| BEN/PHA/84/PRP/37 | Preparation of a HCFC phase-out management plan (stage II) | 9,800 | 1,274 | 11,074 |
| BGD/SEV/81/TAS/54 | Enabling activities for HFC phase-down | 3,582 | 251 | 3,833 |
| BHA/PHA/84/PRP/30 | Preparation of a HCFC phase-out management plan (stage II) | 4,850 | 631 | 5,481 |
| BHU/PHA/76/TAS/25 | HCFC phase-out management plan (third tranche) | 10 | 1 | 11 |
| BHU/SEV/83/INS/28 | Extension of institutional strengthening project (phase VIII: 12/2019-11/2021) | 2,407 | 0 | 2,407 |
| BOT/PHA/82/TAS/22 | HCFC phase-out management plan (stage I, second tranche) | 9,481 | 1,232 | 10,713 |
| BOT/PHA/83/PRP/23 | Preparation of a HCFC phase-out management plan (stage II) | 3,255 | 423 | 3,678 |
| BOT/PHA/86/TAS/25 | HCFC phase-out management plan (stage I, third tranche) | 47,627 | 6,192 | 53,819 |
| BOT/SEV/76/INS/19 | Extension of institutional strengthening project (phase V: 6/2016-7/2018) | 65,956 | 0 | 65,956 |
| BRU/PHA/82/TAS/24 | HCFC phase-out management plan (stage I, third tranche) | 5,977 | 777 | 6,754 |
| CKI/PHA/74/TAS/11 | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Cook Islands) | 3,169 | 412 | 3,581 |
| CKI/PHA/85/TAS/16 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | 2,500 | 325 | 2,825 |
| CKI/SEV/84/INS/15 | Extension of the institutional strengthening project (phase VII: 7/2020-6/2022) | 5,000 | 0 | 5,000 |
| DJI/PHA/88/TAS/28 | HCFC phase-out management plan (stage I, fourth tranche) | 95 | 12 | 107 |
| DRC/SEV/87/INS/47 | Extension of the institutional strengthening project (phase X: 7/2021-6/2023) | 200 | 0 | 200 |
| ELS/PHA/86/TAS/40 | HCFC phase-out management plan (stage I, fourth tranche) | 32 | 1 | 33 |
| EQG/PHA/86/TAS/17 | Verification report on the implementation of the HCFC phase-out management plan | 240 | 31 | 271 |
| FSM/PHA/85/TAS/15 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | 142 | 18 | 161 |
| FSM/SEV/84/INS/13 | Renewal of institutional strengthening project (phase VII: 7/2020-6/2022) | 1,987 | 0 | 1,987 |
| GAB/PHA/87/TAS/41 | HCFC phase-out management plan (stage I, fifth tranche) | 200 | 26 | 226 |
| GLO/SEV/84/TAS/350 | Compliance Assistance Programme: 2020 budget | 79,692 | 6,375 | 86,067 |
| GLO/SEV/86/TAS/356 | Compliance Assistance Programme: 2021 budget | 212,006 | 16,960 | 228,967 |
| GLO/SEV/88/TAS/357 | Compliance Assistance Programme: 2022 budget | 599,922 | 47,994 | 647,915 |
| GRN/PHA/82/PRP/25 | Preparation of a HCFC phase-out management plan (stage II) | 9,800 | 1,274 | 11,074 |
| GRN/PHA/82/TAS/26 | Verification report on the implementation of the HCFC phase-out management plan | 18,890 | 2,456 | 21,346 |
| GUI/SEV/85/TAS/36 | Enabling activities for HFC phase-down | 50,000 | 3,500 | 53,500 |
| HAI/SEV/75/INS/20 | Extension of the institutional strengthening project (phase IV: 11/2015-10/2017) | 73,671 | 0 | 73,671 |
| HON/PHA/86/TAS/51 | HCFC phase-out management plan (stage I, fifth tranche) | 255 | 33 | 288 |
| IND/PHA/77/TAS/470 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector plan) | 144 | 17 | 161 |
| IND/PHA/87/PRP/490 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | 2,000 | 260 | 2,260 |
| IRA/SEV/82/TAS/233 | Enabling activities for HFC phase-down | 30,333 | 2,123 | 32,457 |
| IVC/PHA/90/TAS/48 | HCFC phase-out management plan (stage I, fifth tranche) | 380 | 46 | 426 |
| KAM/PHA/84/TAS/38 | Verification report on the implementation of the HCFC phase-out management plan | 4,900 | 637 | 5,537 |
| KUW/PHA/66/TAS/19 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector and monitoring and verification) | 50,071 | 5,988 | 56,059 |
| KUW/PHA/74/TAS/23 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector and monitoring and verification) | 113,335 | 13,553 | 126,888 |
| KUW/PHA/88/TAS/44 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing sector) | 24,000 | 2,870 | 26,870 |
| LAO/PHA/85/TAS/34 | HCFC phase-out management plan (stage I, third tranche) | 5,055 | 657 | 5,712 |
| MAG/PHA/84/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | 14,900 | 1,937 | 16,837 |
| MAS/PHA/74/TAS/11 | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Marshall Islands) | 3,370 | 438 | 3,809 |
| MAS/PHA/85/TAS/16 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | 2,900 | 377 | 3,277 |
| MAU/PHA/80/TAS/24 | HCFC phase-out management plan (stage I, first tranche) | 155 | 20 | 175 |
| MLI/PHA/83/TAS/40 | HCFC phase-out management plan (stage I, fourth tranche) | 200 | 26 | 226 |
| MLI/PHA/86/TAS/43 | Verification report on the implementation of the HCFC phase-out management plan | 205 | 27 | 232 |
| MLW/PHA/85/TAS/47 | HCFC phase-out management plan (stage II, first tranche) | 510 | 66 | 576 |
| MOZ/PHA/86/TAS/35 | Verification report on the implementation of the HCFC phase-out management plan | 26 | 3 | 30 |
| NAU/PHA/74/TAS/10 | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Nauru) | 5,776 | 751 | 6,527 |
| NAU/PHA/85/TAS/13 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | 4,370 | 568 | 4,938 |
| NEP/PHA/75/TAS/34 | HCFC phase-out management plan (stage I, second tranche) | 10,575 | 1,375 | 11,950 |
| NEP/PHA/86/TAS/42 | HCFC phase-out management plan (stage I, third tranche) | 6,487 | 843 | 7,330 |
| NIU/PHA/85/TAS/15 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | 3,051 | 397 | 3,448 |
| PAK/PHA/76/TAS/93 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 2,525 | 328 | 2,853 |
| PAK/PHA/85/PRP/104 | Preparation of a HCFC phase-out management plan (stage III) | 4,583 | 596 | 5,179 |
| PAR/PHA/86/TAS/40 | HCFC phase-out management plan (stage I, third tranche) | 44 | 6 | 50 |
| PAR/SEV/82/INS/38 | Extension of institutional strengthening project (phase IX: 1/2019-12/2020) | 3,805 | 0 | 3,805 |
| PER/PHA/80/TAS/54 | HCFC phase-out management plan (stage II, first tranche) | 48 | 6 | 54 |
| SAU/PHA/68/TAS/16 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | 3,375 | 418 | 3,793 |
| SAU/PHA/77/TAS/32 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring) | 4,125 | 511 | 4,636 |
| SEN/PHA/85/PRP/42 | Preparation of a HCFC phase-out management plan (stage II) | 42 | 5 | 47 |
| SIL/PHA/84/PRP/35 | Preparation of a HCFC phase-out management plan (stage II) | 4,658 | 606 | 5,264 |
| SOI/PHA/74/TAS/11 | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Solomon Islands) | 3,234 | 420 | 3,654 |
| SOI/PHA/85/TAS/17 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | 13 | 2 | 14 |
| SSD/PHA/84/TAS/05 | Verification report on the implementation of the HCFC phase-out management plan | 42 | 6 | 48 |
| SUD/SEV/81/INS/43 | Extension of institutional strengthening (phase IX: 7/2018-6/2020) | 18 | 0 | 18 |
| SUR/PHA/86/TAS/31 | Verification report on the implementation of the HCFC phase-out management plan | 4,750 | 618 | 5,368 |
| SWA/PHA/86/TAS/30 | Verification report on the implementation of the HCFC phase-out management plan | 42 | 6 | 48 |
| TLS/SEV/82/TAS/19 | Enabling activities for HFC phase-down | 3,331 | 233 | 3,565 |
| TLS/SEV/84/INS/20 | Extension of institutional strengthening (phase V: 7/2020-6/2022) | 2,746 | 0 | 2,746 |
| TOG/PHA/83/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | 9,800 | 1,274 | 11,074 |
| TOG/PHA/87/TAS/36 | HCFC phase-out management plan (stage I, fifth tranche) | 120 | 16 | 136 |
| TON/PHA/74/TAS/10 | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Tonga) | 1,891 | 246 | 2,137 |
| TUV/PHA/74/TAS/11 | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Tuvalu) | 1,981 | 257 | 2,238 |
| TUV/PHA/85/TAS/16 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | 2,000 | 260 | 2,260 |
| VAN/PHA/85/TAS/17 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | 3,750 | 487 | 4,237 |
| VAN/SEV/84/INS/15 | Extension of institutional strengthening project (phase VII: 7/2020-6/2022) | 5,000 | 0 | 5,000 |
| Total completed projects |  | 1,644,641 | 132,980 | 1,777,621 |
| AFG/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 13,112 | 918 | 14,030 |
| BEN/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 21,115 | 1,478 | 22,593 |
| BOT/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 53,352 | 3,735 | 57,087 |
| CBI/SEV/82/TAS/01+ | Enabling activities for HFC phase-down | 15,962 | 1,117 | 17,079 |
| CHD/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 19,800 | 1,386 | 21,186 |
| CKI/SEV/82/TAS/01+ | Enabling activities for HFC phase-down | 2,290 | 160 | 2,450 |
| COI/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 4,758 | 333 | 5,091 |
| DJI/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 27,578 | 1,930 | 29,508 |
| DRC/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 17,766 | 1,244 | 19,010 |
| EQG/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 36,846 | 2,579 | 39,425 |
| GAB/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 15,798 | 1,106 | 16,904 |
| GBS/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 24,197 | 1,694 | 25,891 |
| GUY/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 40,000 | 2,800 | 42,800 |
| IVC/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 14,395 | 1,008 | 15,403 |
| KEN/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 652 | 46 | 698 |
| KIR/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 17,102 | 1,197 | 18,299 |
| LAO/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 40,918 | 2,864 | 43,782 |
| MAG/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 34,446 | 2,411 | 36,857 |
| MAS/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 12,418 | 869 | 13,287 |
| MAU/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 47,662 | 3,336 | 50,998 |
| MDV/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 199 | 14 | 213 |
| MLI/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 1,931 | 135 | 2,066 |
| MYA/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 41,377 | 2,896 | 44,273 |
| NEP/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 7,835 | 548 | 8,383 |
| PAR/SEV/81/TAS/02+ | Enabling activities for HFC phase-down | 4,343 | 304 | 4,647 |
| SOI/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 6,345 | 444 | 6,789 |
| SRL/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 977 | 68 | 1,045 |
| STP/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 11,085 | 776 | 11,861 |
| SUD/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 5,833 | 408 | 6,241 |
| SUR/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 29,350 | 2,055 | 31,405 |
| SYR/SEV/83/TAS/01+ | Enabling activities for HFC phase-down | 31,765 | 2,224 | 33,989 |
| Total “additional voluntary contributions” projects |  | 601,206 | 42,084 | 643,290 |
| TOTAL UNEP |  | 2,245,847 | 175,064 | 2,420,911 |
| BAH/FOA/84/PRP/35 | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | 687 | 48 | 735 |
| BHE/PHA/87/INV/40 | HCFC phase-out management plan (stage I, fifth tranche) | 6,105 | 427 | 6,532 |
| BHE/SEV/80/INS/34 | Extension of the institutional strengthening project (phase VI: 3/2018-2/2020) | 32 | 3 | 35 |
| CHD/PHA/82/PRP/33 | Preparation of a HCFC phase-out management plan (stage II) | 857 | 60 | 917 |
| CPR/PHA/75/INV/564 | HCFC phase-out management plan (stage I, fifth tranche) (room air conditioner manufacturing sector plan) | 22,180 | 1,553 | 23,733 |
| EQG/PHA/84/PRP/15 | Preparation of a HCFC phase-out management plan (stage II) | 1,602 | 112 | 1,715 |
| GAM/PHA/82/PRP/37 | Preparation of a HCFC phase-out management plan (stage II) | 770 | 54 | 824 |
| GBS/PHA/81/PRP/23 | Preparation of a HCFC phase-out management plan (stage II) | 89 | 6 | 95 |
| KUW/PHA/83/INV/36 | HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector phase-out) | 17,780 | 1,245 | 19,024 |
| MOR/FOA/73/PRP/71 | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | 11,672 | 817 | 12,489 |
| MOR/PHA/73/PRP/70 | Preparation of a HCFC phase-out management plan (stage II) | 23,633 | 1,654 | 25,287 |
| NIR/PHA/81/INV/146 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector and project management unit) | 90 | 8 | 98 |
| PAK/PHA/85/PRP/105 | Preparation of a HCFC phase-out management plan (stage III) (foam sector) | 7,363 | 515 | 7,878 |
| PRC/PHA/81/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | 481 | 34 | 514 |
| SAU/PHA/72/INV/20 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring) | 25,449 | 1,782 | 27,231 |
| SAU/PHA/75/INV/24 | HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan) | 200,387 | 14,027 | 214,414 |
| SUD/PHA/82/INV/44 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 2,170 | 152 | 2,322 |
| TOG/PHA/79/INV/30 | HCFC phase-out management plan (stage I, third tranche) | 1,951 | 146 | 2,097 |
| VEN/PHA/76/TAS/132 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 166 | 12 | 177 |
| Total completed projects |  | 323,465 | 22,654 | 346,119 |
| SAU/REF/76/DEM/28 | Demonstration project on promoting HFO-based low-global warming potential refrigerants for air-conditioning sector in high ambient temperatures. | 114,237 | 7,997 | 122,234 |
| Total “by-decision” projects |  | 114,237 | 7,997 | 122,234 |
| LIB/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 2,492 | 174 | 2,667 |
| MEX/REF/81/INV/04+ | Conversion of commercial refrigeration manufacturing in two facilities from the use of HFC-134a and R-404A as the refrigerants to propane (R-290) and isobutane (R-600a) at Imbera | 92,426 | 6,469 | 98,895 |
| PHI/SEV/83/TAS/02+ | Enabling activities for HFC phase-down | 18,703 | 1,309 | 20,012 |
| Total “additional voluntary contributions” projects |  | 113,621 | 7,952 | 121,573 |
| TOTAL UNIDO |  | 551,323 | 38,603 | 589,926 |
| GLO/SEV/88/TAS/358 | Core unit budget (2022) | 0 | 280,124 | 280,124 |
| JOR/PHA/88/PRP/112 | Preparation of HCFC phase-out management plan (stage III) (commercial refrigeration manufacturing) | 30,000 | 2,100 | 32,100 |
| MAL/KIP/91/PRP/194 | Preparation of HFC investment projects in fire fighting sector | 150,000 | 10,500 | 160,500 |
| VIE/KIP/92/PRP/85 | Preparation of a KIP investment project in the commercial refrigeration sector for Sanaky | 30,000 | 2,100 | 32,100 |
| VIE/KIP/92/PRP/86 | Preparation of a KIP investment project in the domestic refrigeration sector for Aqua Electrical Appliances, Darling Electronics, and Hoa Phat Refrigeration Engineering | 80,000 | 5,600 | 85,600 |
| VIE/KIP/92/PRP/88 | Conversion of refrigerator manufacture from CFC-11 to cyclopentane foam blowing agent and CFC-12 to R-134a refrigerant at Domestic Appliances Ltd. (DAL) | 30,000 | 2,100 | 32,100 |
| Total completed projects |  | 320,000 | 302,524 | 622,524 |
| TOTAL WORLD BANK |  | 320,000 | 302,524 | 622,524 |
| LAO/PHA/74/INV/28 | HCFC phase-out management plan (stage I, second tranche) | 40,500 | 5,265 | 45,765 |
| LAO/PHA/85/TAS/35 | HCFC phase-out management plan (stage I, third tranche) | 4,500 | 585 | 5,085 |
| TOTAL FRANCE |  | 45,000 | 5,850 | 50,850 |

UNEP/OzL.Pro/ExCom/93/1

The data presented are based on the reporting format that has been developed pursuant to decision 31/2.

UNEP/OzL.Pro/ExCom/93/3

1: Funds returned in previous meetings; no action needed. 2: Financial closure-initiated funds not returned due to ongoing unpaid obligations. 3: Since funds can be returned up to one year after operational completion, funds will be returned in 94th meeting.

1: Financial closure-initiated fund not returned due to ongoing unpaid obligations.