UNEP/OzL.Pro/ExCom/84/19
 19 November 2019

PROGRESS REPORT OF UNEP AS AT 31 DECEMBER 2018

# This document presents the progress report of UNEP as at 31 December 2018.

Scope of the document

# This document consists of the following parts:

## Part I:	Projects approved under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2018 and cumulative since 1991 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs); it contains a review on the status of implementation of each ongoing project at the country level; and it identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## Part II:	Projects approved under the additional voluntary contributions for fast start support for HFC phase-down. It provides a status of implementation of HFC phase-down projects funded under the voluntary contributions.

Recommendation.

# This document also contains the following annexes:

Annex I: 	A summary status and a recommendation for each ongoing project with outstanding issues for consideration by the Executive Committee.

Annex II: 	An analysis of the progress report.

Measurements used in the progress reports

# Prior to agreement on the Kigali Amendment, all controlled substances under the Montreal Protocol were ozone-depleting substances, measured in ODP tonnes. Controlled substances under the Kigali Amendment are not ozone-depleting substances, and their control targets are measured in mt CO2-eq. (i.e., consumption in metric tonnes (mt) multiplied by the global warming-potential (GWP) of the substance). Notwithstanding the two different measurements for reporting controlled substances, the progress report of UNEP submitted to the 84th meeting is based on ODP tonnes for all controlled substances.

An overview of HFC phase-down activities

# As of 31 December 2018, the Executive Committee has approved 89 enabling activities amounting to US $9.81 million. Regarding enabling activities, extension of the completion dates of 26 of these projects was approved at the 83rd meeting and requests for extension for 48 others have been submitted to the 84th meeting.

Progress review process by the Secretariat

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2018, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The Secretariat had several discussions with UNEP, where a number of issues on ongoing projects were raised and subsequently satisfactorily resolved.

Part I: 	Projects approved under the regular contributions to the Multilateral Fund

Summary of progress in implementation of projects for 2018 and cumulative

# Implementation of projects and activities by UNEP for 2018 and cumulative since 1991 up to 31 December 2018 is summarized as follows:

## Phase-out: In 2018, 35.2 ODP tonnes of consumption of controlled substances were phased out and 123.9 ODP tonnes of consumption of controlled substances were approved for phase-out. Since 1991, 1,586 ODP tonnes of consumption of controlled substances had been phased out, of an expected total of 2,183 ODP tonnes from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2018, US $17.83 million was disbursed and US $22.57 million was planned for disbursement based on the 2017 progress report, representing a rate of disbursement of 79 per cent of that planned. Cumulatively, US $268.32 million had been disbursed out of the total US $315.35 million approved for disbursement (excluding agency support costs). This represents a rate of disbursement of 85 per cent. In 2018, US $21.95 million was approved for implementation;

## Number of projects completed: In 2018, 108 projects were completed. Since 1991, 1,929 projects of the 2,253 projects approved (excluding closed or transferred projects) were completed. This represents a completion rate of 86 per cent;

## Speed of delivery – non-investment projects: Projects that were completed in 2018 were completed on average 48 months after their approval. Since 1991, the average time for completion of non-investment projects has been 36 months after their approval. First disbursements under these projects occurred, on average, 11 months after they had been approved;

## Project preparation: Of the 218 project preparation activities approved by the end of 2018, 189 have been completed, leaving 29 ongoing. In 2018, two projects have been completed;

## Implementation delays: There were a total of 295 non-investment projects under implementation at the end of 2018. These projects, on average, are experiencing a delay of 11 months. However, there is one project classified as “projects with implementation delays” that is subject to the procedures of project cancellation (as project preparation, multi-year agreements (MYAs) and institutional strengthening (IS) are not subject to those procedures); and

## MYAs: In 2018, UNEP was implementing 102 MYAs for HCFC phase-out management plans (HPMPs). Since 1991, 189 MYAs have been approved and 87 MYAs have been completed.

Project implementation progress in 2018

# Further to the review process, a number of issues were resolved, except for a number of projects or tranches of MYAs for the phase-out of HCFCs, project preparation, renewal of IS projects and enabling activities for HFC phase-down, as shown in Annex I to the present document. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Of the 172 ongoing projects, excluding IS and project preparation, 47 projects have revised planned dates of completion since the 2017 progress report.

# Details of progress in implementation of projects associated with the HPMPs for Bahrain, China (stage II, servicing sector), Colombia, Congo (the), Côte d’Ivoire, Dominica, Egypt, Iran (Islamic Republic of), Iraq, Niger (the), Republic of Moldova, and Tunisia, and reports on projects with specific reporting requirements for the Bahamas (HPMP), Equatorial Guinea (HPMP), Honduras (HPMP), Maldives (HPMP) and Qatar (HPMP) have been submitted to the 84th meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of these documents. Issues relating to Saudi Arabia (HPMP) are addressed in the document on tranche submission delays. Outstanding issues for the remaining ongoing projects not included in Annex I to the present document, and requests for extension of date of completion, are addressed below.

# In line with decision 82/11(c)(ii), the Secretariat noted that renewal of IS projects for the Article 5 countries listed in Table 1 have not been submitted for the last two years. UNEP informed that it is planning to submit those renewal requests by the year indicated in the last column of Table 1. The main reasons for delays are large balances mainly on account of slow progress in implementation.

# Table 1: List of IS projects with no renewal requests submitted for the last two years

| Country | Plan for next renewal request |
| --- | --- |
| Algeria | 2020 |
| Antigua and Barbuda | 2020 |
| Botswana | 2020 |
| Central African Republic (the) | 2021 |
| Democratic People's Republic of Korea (the) | * |
| Ethiopia | 2020 |
| Guinea | 2020 |
| Haiti | 2020 |
| Kenya | 2020 |
| Morocco | 2020 |
| Nauru | 2020 |
| Peru | 2020 |
| Saint Lucia | 2020 |
| Saint Vincent and the Grenadines | 2020 |
| Saudi Arabia | 2020 |
| South Sudan | 2020 |
| Suriname | 2020 |
| Yemen | 2021 |

- *Removed from the 2019–2021 business plan.

# In addition, the Secretariat noted that for the renewal of four IS projects in Guinea-Bissau, Mauritius, South Sudan, and Zambia, the current phase was approved two years ago and the previous phase is still ongoing. UNEP has informed that all funds relating to these IS projects were disbursed by November 2019.

# In line with decision 82/11(b), UNEP has requested the extension of the duration of the third tranche of the HPMP for the Democratic Republic of the Congo (DRC/PHA/80/TAS/44), from December 2018 to June 2020, as the implementation of phase-out activities has been delayed due to the Ebola outbreak. The Executive Committee may wish to approve the extension, to 30 June 2020, of the HPMP for the Democratic Republic of the Congo.

# Part II:	Projects approved under the additional voluntary contributions for fast start support for HFC phase-down

# As of 31 December 2018, the Executive Committee had approved 78 HFC-related projects under the additional voluntary contributions amounting to US $8,101,000 (excluding agency support costs). A summary of the status of these projects is presented in Table 2.

# Table 2. HFC-related projects approved in 2018

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Technical assistance - Enabling activities | 78 | 0 | 0 | 8,101,000 | 627,073 | 7,473,927 | 8 |
| Total | 78 | 0 | 0 | 8,101,000 | 627,073 | 7,473,927 | 8 |

*Excludes agency support costs.

# The 78 ongoing enabling activities, including five approved at the 82nd meeting, are at various stages of implementation. Cumulatively, US $627,073 had been disbursed out of the total US $8,101,000 approved for disbursement (excluding support costs), representing a disbursement rate of 8 per cent. Issues related to enabling activities for HFC phase-down in three countries that could not be resolved are contained in Annex I to the present document.

Recommendation

# The Executive Committee may wish:

## To note the progress report of UNEP as at 31 December 2018 contained in document UNEP/OzL.Pro/ExCom/84/19;

## To approve the recommendations related to ongoing projects with specific issues contained in Annex I to the present document; and

## To approve the extension, to 30 June 2020, of the HCFC phase-out management plan for the Democratic Republic of the Congo (stage I, third tranche) (DRC/PHA/80/TAS/44), to allow UNEP to complete remaining servicing sector activities, noting the difficult situation in the country.

Annex I

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNEP

| Country/project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Algeria ALG/SEV/73/INS/81 | Extension of the institutional strengthening project (phase VI: 12/2014-11/2016) | 0 | No disbursement; slow progress in implementation of activities | To request a status report to the 85th meeting on the level of funds disbursement and on progress in implementation |
| Antigua and Barbuda ANT/SEV/73/INS/16 | Extension of institutional strengthening project (phase V: 1/2015-12/2016) | 0 | No disbursement; delay in signing of the small-scale funding agreement (SSFA) | To request a status report to the 85th meeting on the level of funds disbursement and signing of the SSFA |
| Antigua and Barbuda ANT/PHA/73/PRP/17 | Preparation of a HCFC phase-out management plan (stage II) | 99 | Submission of stage II delayed due to data verification challenges and additional consultations needed with the Government | To request a status report to the 85th meeting on submission of stage II |
| Botswana BOT/SEV/76/INS/19 | Extension of institutional strengthening project (phase V: 6/2016-7/2018) | 0 | No disbursement; delay in signing of the SSFA | To request a status report to the 85th meeting on the level of funds disbursement and signing of the SSFA |
| Central African Republic (the) CAF/SEV/68/INS/23 | Extension of the institutional strengthening project (phase VI: 1/2013-12/2014) | 0 | Delayed due to security situation in the country; difficulty in continuing implementation | To request a status report to the 85th meeting on the level of funds disbursement and on progress in implementation |
| Chile CHI/PHA/76/TAS/191 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 17 | Progress on disbursements delayed due to administrative approval delays | To request a status report to the 85th meeting on levels of funds disbursements |
| Dominica DMI/SEV/80/INS/23 | Additional emergency assistance for institutional strengthening | 0 | No disbursement; delay in signing of the SSFA | To request a status report to the 85th meeting on the level of funds disbursement and signing of the SSFA |
| Dominica DMI/SEV/81/INS/24 | Extension of the institutional strengthening project (phase VII: 6/2018-5/2020 ) | 0 | No disbursement; delay in signing of the SSFA | To request a status report to the 85th meeting on the level of funds disbursement and signing of the SSFA |
| Democratic Republic of the Congo (the) DRC/PHA/79/PRP/43 | Preparation of a HCFC phase-out management plan (stage II) | 0 | No disbursement; submission of stage II delayed due to challenges in completing national level stage II project preparation activities | To request a status report to the 85th meeting on the level of funds disbursement and on the submission of stage II |
| Democratic Republic of the Congo (the) DRC/SEV/77/INS/41 | Extension of institutional strengthening project (phase VIII: 1/2017-12/2018) | 0 | No disbursement; implementation affected by Ebola outbreak | To request a status report to the 85th meeting on the level of funds disbursement and progress in implementation noting the difficult situation in the country |
| Grenada GRN/PHA/62/TAS/18 | HCFC phase-out management plan (stage I, first tranche) | 50 | Delays in submission of progress and financial reports, resulting in delays in not disbursing the last two payments under SSFA | To request a status report to the 85th meeting on the submission of progress and financial reports and the release of remaining payments under SSFA |
| Grenada GRN/PHA/77/TAS/22 | HCFC phase-out management plan (stage I, second tranche) | 0 | No disbursement; delay in signing of the SSFA | To request a status report to the 85th meeting on the level of funds disbursement and signing of the SSFA |
| Guatemala GUA/PHA/75/TAS/50 | HCFC phase-out management plan (stage I, third tranche) | 10 | Slow progress in activities due to delays in development of regulatory framework for the servicing sector | To request a status report to the 85th meeting on progress in implementation |
| Guatemala GUA/PHA/81/TAS/52 | HCFC phase-out management plan (stage I, fourth tranche) | 0 | No disbursement; slow progress in activities due to delays in finalisation of the work plan | To request a status report to the 85th meeting on the level of funds disbursement and on progress in implementation |
| Guyana GUY/PHA/77/TAS/29 | Verification report on the implementation of the HCFC phase-out management plan | 0 | No disbursement despite the fact that the verification report was submitted with the second tranche approved at the 83rd meeting | To request a report to the 85th meeting on the level of funds disbursement |
| Haiti HAI/PHA/68/TAS/18 | HCFC phase-out management plan (stage I, first tranche) | 49 | Slow progress in activities due to changes in NOU administration and delays in initiation of activities | To request a status report to the 85th meeting on progress in implementation |
| Haiti HAI/PHA/76/TAS/21 | HCFC phase-out management plan (stage I, second tranche) | 0 | No disbursement; slow progress in activities due to changes in NOU administration and delays in initiation of activities | To request a status report to the 85th meeting on the level of funds disbursement and on progress in implementation |
| Haiti HAI/SEV/75/INS/20 | Extension of the institutional strengthening project (phase IV: 11/2015-10/2017) | 20 | Slow progress in project due to changes in NOU administration and delays in initiation of activities | To request a status report to the 85th meeting on progress in implementation |
| Nauru NAU/PHA/74/TAS/10 | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Nauru) | 14 | Slow progress in activities due to absence of national ozone officer (NOO) | To request a status report to the 85th meeting on progress in implementation |
| Nauru NAU/SEV/72/INS/09 | Extension of the institutional strengthening project (phase V: 8/2014-7/2016) | 0 | No disbursement; slow progress in activities due to absence of NOO | To request a status report to the 85th meeting on the level of funds disbursement and on progress in implementation |
| Peru PER/PHA/80/TAS/54 | HCFC phase-out management plan (stage II, first tranche) | 0 | No disbursement; slow progress in activities due to changes in NOU administration and delay in hiring experts for project implementation | To request a status report to the 85th meeting on the level of funds disbursement and on progress in implementation |
| Peru PER/SEV/80/INS/56 | Renewal of institutional strengthening project (phase V: 1/2018-12/2019) | 0 |  |  |
| Qatar QAT/PHA/65/TAS/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 4 | Slow progress in activities; balances to be returned as per decision 82/34(f) | To request balances be returned to the 84th meeting |
| Qatar QAT/PHA/73/PRP/20 | Preparation of a HCFC phase-out management plan (stage II) | 0 | No disbursement; slow progress in preparation of stage II | To request a status report to the 85th meeting on the level of funds disbursement and on the submission of stage II |
| Saudi Arabia SAU/SEV/67/INS/15 | Extension of the institutional strengthening project (phase II: 7/2012-6/2014) | 0 | No disbursement; delay in signing of the SSFA | To request a status report to the 85th meeting on the level of funds disbursement and the signing of the SSFA |
| South Sudan SSD/PHA/77/TAS/04 | HCFC phase-out management plan (stage I, first tranche) | 0 | No disbursement; delay in signing of the SSFA | To request a status report to the 85th meeting on the level of funds disbursement and the signing of the SSFA |
| South Sudan SSD/SEV/68/INS/01 | Institutional strengthening project (start-up cost) | 63 | Return balances in line with decision 82/11(c)(i), given that the current IS phase V was approved at the 76th meeting | To return the balances to the 84th meeting in line with decision 82/11(c)(i) |
| South Sudan SSD/SEV/76/INS/03 | Institutional strengthening project (phase I: 5/2016-4/2018) | 0 | No disbursement; delay in signing of the SSFA | To request a status report to the 85th meeting on the level of funds disbursement and the signing of the SSFA |
| Saint Kitts and Nevis STK/PHA/74/TAS/20 | HCFC phase-out management plan (stage I, second tranche) | 0 | No disbursement; slow progress in activities due to delays at the national level on implementation and coordination of activities with agency | To request a status report to the 85th meeting on the level of funds disbursement and on progress in implementation |
| Saint Kitts and Nevis STK/SEV/81/INS/21 | Extension of institutional strengthening project (phase VII: 6/2018-5/2020) | 0 |  |  |
| Saint Vincent and the Grenadines STV/PHA/77/TAS/24 | Verification report on the implementation of the HCFC phase-out management plan | 0 | 12 and 18 months delays | To request UNEP to report to the 85th meeting on this project with implementation delays |
| Suriname SUR/PHA/81/TAS/26 | HCFC phase-out management plan (stage I, third tranche) | 0 | No disbursement; delay in signing of the SSFA | To request a status report to the 85th meeting on the level of funds disbursement and the signing of the SSFA |
| Yemen YEM/SEV/73/INS/43 | Extension of the institutional strengthening project (phase VIII: 1/2015-12/2016) | 0 | Delayed due to security situation in the country; difficulty in continuing implementation | To request a status report to the 85th meeting on progress in implementation |
| HFC projects |  |  |  |  |
| Dominica DMI/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 0 | No disbursement; slow progress in activities as the national ozone unit is still re-establishing office after the hurricane | To request a status report to the 85th meeting on the level of funds disbursement and on progress in implementation |
| Myanmar MYA/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 0 | No disbursement; delay in signing of the SSFA | To request a status report to the 85th meeting on the level of funds disbursement and the signing of the SSFA |
| Nauru NAU/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 0 | No disbursement; delay in signing of the SSFA | To request a status report to the 85th meeting on the level of funds disbursement and the signing of the SSFA |

Annex II

ANALYSIS OF THE PROGRESS REPORT OF UNEP AS AT 31 DECEMBER 2018

# This Annex consists of the following two parts:

## Part I:	Projects approved under the regular contributions to the Multilateral Fund.

## Part II:	Projects approved under the additional voluntary contributions for fast start support for HFC phase-down.

Part I: 	Projects approved under the regular contributions to the Multilateral Fund

# As of 31 December 2018, the Executive Committee had approved US $341.67 million consisting of US $315.35 million for the implementation of investment and non-investment projects and US $26.32 million for agency support costs, as shown in Table 1. In 2018, 126 new projects and activities were approved. This level of funding is expected to result in the phase-out of 2,183 ODP tonnes of consumption of controlled substances.

# Table 1: Approved funding by sector for UNEP as at 31 December 2018

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 882,689 |
| Destruction | 190,040 |
| Halon | 767,640 |
| Fumigants | 2,614,366 |
| Phase-out plan | 54,152,307 |
| Refrigeration | 13,872,913 |
| Several | 242,675,275 |
| Solvents | 198,860 |
| Sub-total | 315,354,091 |
| Agency support costs | 26,318,076 |
| Total | 341,672,167 |

# A summary of the status of projects implemented by category is presented in Table 2.

Table 2: Status of project implementation by category

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 94 | 94 | 100 | 2,946,574 | 2,946,574 | 0 | 100 |
| Demonstration | 3 | 2 | 67 | 559,198 | 221,321 | 337,877 | 40 |
| Institutional strengthening (IS) | 818 | 695 | 85 | 64,468,096 | 53,006,488 | 11,461,609 | 82 |
| Investment | 1 | 1 | 100 | 135,000 | 135,000 | 0 | 100 |
| Project preparation | 218 | 189 | 87 | 9,519,600 | 8,337,322 | 1,182,278 | 88 |
| Technical assistance | 923 | 752 | 81 | 223,433,065 | 189,384,297 | 34,048,768 | 85 |
| Training | 196 | 196 | 100 | 14,292,557 | 14,292,557 | 0 | 100 |
| Total | 2,253 | 1,929 | 86 | 315,354,091 | 268,323,558 | 47,030,533 | 85 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

# Table 3 presents an overview of the status of project implementation by year. All projects and activities approved between 1991 and 2009, have now been completed.

Table 3: Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 11 | 11 | 100 | 1,372,335 | 1,372,335 | 0 | 100 |
| 1992 | 15 | 15 | 100 | 1,711,000 | 1,711,000 | 0 | 100 |
| 1993 | 49 | 49 | 100 | 4,194,343 | 4,194,343 | 0 | 100 |
| 1994 | 58 | 58 | 100 | 4,231,169 | 4,231,169 | 0 | 100 |
| 1995 | 50 | 50 | 100 | 4,047,683 | 4,047,683 | 0 | 100 |
| 1996 | 47 | 47 | 100 | 3,366,039 | 3,366,039 | 0 | 100 |
| 1997 | 87 | 87 | 100 | 7,962,291 | 7,962,291 | 0 | 100 |
| 1998 | 64 | 64 | 100 | 4,669,124 | 4,669,124 | 0 | 100 |
| 1999 | 87 | 87 | 100 | 6,368,983 | 6,368,983 | 0 | 100 |
| 2000 | 85 | 85 | 100 | 6,300,398 | 6,300,398 | 0 | 100 |
| 2001 | 59 | 59 | 100 | 7,411,159 | 7,411,159 | 0 | 100 |
| 2002 | 72 | 72 | 100 | 9,469,401 | 9,469,401 | 0 | 100 |
| 2003 | 78 | 78 | 100 | 11,165,394 | 11,165,394 | 0 | 100 |
| 2004 | 99 | 99 | 100 | 12,362,652 | 12,362,652 | 0 | 100 |
| 2005 | 72 | 72 | 100 | 12,339,483 | 12,339,483 | 0 | 100 |
| 2006 | 108 | 108 | 100 | 12,731,484 | 12,731,484 | 0 | 100 |
| 2007 | 79 | 79 | 100 | 14,697,515 | 14,566,111 | 131,404 | 99 |
| 2008 | 132 | 132 | 100 | 17,863,078 | 17,875,070 | (11,993) | 100 |
| 2009 | 115 | 115 | 100 | 17,263,209 | 17,240,376 | 22,833 | 100 |
| 2010 | 79 | 76 | 96 | 14,361,829 | 14,224,676 | 137,154 | 99 |
| 2011 | 100 | 97 | 97 | 16,847,287 | 16,433,772 | 413,515 | 98 |
| 2012 | 81 | 72 | 89 | 16,566,273 | 14,969,487 | 1,596,786 | 90 |
| 2013 | 91 | 86 | 95 | 14,212,034 | 13,916,359 | 295,675 | 98 |
| 2014 | 76 | 63 | 83 | 14,789,425 | 11,400,573 | 3,388,853 | 77 |
| 2015 | 180 | 142 | 79 | 22,118,610 | 17,948,871 | 4,169,738 | 81 |
| 2016 | 96 | 24 | 25 | 20,096,791 | 11,978,950 | 8,117,841 | 60 |
| 2017 | 57 | 2 | 4 | 14,884,529 | 8,066,376 | 6,818,153 | 54 |
| 2018 | 126 | 0 | 0 | 21,950,573 | 0 | 21,950,573 | 0 |
| Total | 2,253 | 1,929 | 86 | 315,354,091 | 268,323,558 | 47,030,533 | 85 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

# Table 4 presents project implementation by country for 2018.

Table 4. Summary of project implementation by UNEP for 2018

| Country | Estimated funds disbursed in 2018 (US$) | Funds disbursed in 2018 (US$) | Percentage of funds disbursed over estimation in 2018 | Percentage of planned projects completed in 2018 |
| --- | --- | --- | --- | --- |
| Afghanistan | 213,849 | 153,737 | 72 | 100 |
| Albania | 75,839 | 36,303 | 48 | 100 |
| Algeria | 152,960 | 25,740 | 17 | 0 |
| Angola | 71,026 | 64,720 | 91 | 100 |
| Antigua and Barbuda | 50,141 | 17,500 | 35 | 100 |
| Armenia | 10,469 | 0 | 0 | 0 |
| Bahamas (the) | 69,565 | 25,702 | 37 | 0 |
| Bahrain | 137,739 | 257,392 | 187 | 67 |
| Bangladesh | 25,256 | 59,010 | 234 | 100 |
| Barbados | 78,529 | 95,877 | 122 | 100 |
| Belize | 45,900 | 39,270 | 86 | 100 |
| Benin | 80,496 | 117,823 | 146 | 100 |
| Bhutan | 50,963 | 44,960 | 88 |  |
| Bolivia (Plurinational State of) | 37,710 | 29,707 | 79 |  |
| Botswana | 90,812 | 201,560 | 222 | 67 |
| Brunei Darussalam | 118,434 | 113,079 | 95 | 67 |
| Burkina Faso | 53,905 | 87,127 | 162 | 100 |
| Burundi | 21,750 | 72,500 | 333 | 100 |
| Cambodia | 69,564 | 113,500 | 163 |  |
| Cameroon | 53,580 | 0 | 0 |  |
| Cabo Verde | 75,762 | 144,582 | 191 | 100 |
| Central African Republic (the) | 36,000 | 0 | 0 | 67 |
| Chad | 38,104 | 35,040 | 92 | 100 |
| Chile | 110,859 | 65,742 | 59 |  |
| China | 1,545,759 | 718,369 | 46 | 100 |
| Colombia | 11,891 | 35,536 | 299 |  |
| Comoros (the) | 45,002 | 45,355 | 101 | 0 |
| Congo (the) | 39,666 | 57,569 | 145 | 50 |
| Cook Islands | 78,520 | 47,437 | 60 |  |
| Cote d'Ivoire | 176,160 | 45,417 | 26 | 0 |
| Democratic People's Republic of Korea (the) | 41,317 | 0 | 0 | 100 |
| Democratic Republic of the Congo (the) | 58,378 | 32,478 | 56 | 0 |
| Djibouti | 80,571 | 87,376 | 108 | 67 |
| Dominica | 44,880 | 0 | 0 | 0 |
| Dominican Republic (the) | 92,766 | 142,625 | 154 | 50 |
| Ecuador | 69,077 | 170,919 | 247 | 50 |
| Egypt | 77,167 | 117,223 | 152 | 100 |
| El Salvador | 82,215 | 46,501 | 57 | 0 |
| Equatorial Guinea | 10,000 | 0 | 0 | 100 |
| Eritrea | 63,339 | 135,000 | 213 | 67 |
| Eswatini | 84,133 | 123,824 | 147 | 67 |
| Ethiopia | 96,000 | 87,000 | 91 | 100 |
| Fiji | 41,715 | 80,748 | 194 | 100 |
| Gabon | 54,105 | 105,615 | 195 | 67 |
| Gambia (the) | 86,822 | 70,000 | 81 | 50 |
| Grenada | 64,078 | 105,000 | 164 | 50 |
| Guatemala | 28,331 | 70,447 | 249 | 33 |
| Guinea | 72,002 | 117,167 | 163 | 100 |
| Guinea-Bissau | 101,750 | 82,500 | 81 | 0 |
| Guyana | 82,413 | 30,000 | 36 | 0 |
| Haiti | 67,230 | 45,376 | 67 | 33 |
| Honduras | 61,804 | 73,024 | 118 | 0 |
| India | 561,571 | 559,197 | 100 | 67 |
| Iran (Islamic Republic of) | 63,544 | 43,403 | 68 |  |
| Iraq | 287,568 | 178,558 | 62 | 50 |
| Jamaica | 107,563 | 47,027 | 44 | 0 |
| Kenya | 93,420 | 74,767 | 80 | 100 |
| Kiribati | 35,432 | 44,225 | 125 |  |
| Kuwait | 510,808 | 313,839 | 61 | 67 |
| Kyrgyzstan | 51,778 | 135,400 | 262 | 50 |
| Lao People's Democratic Republic (the) | 36,567 | 73,485 | 201 | 100 |
| Lesotho | 96,078 | 115,106 | 120 | 100 |
| Liberia | 57,263 | 81,804 | 143 | 100 |
| Madagascar | 43,500 | 102,383 | 235 | 67 |
| Malawi | 37,626 | 125,413 | 333 | 100 |
| Maldives | 70,698 | 109,100 | 154 | 0 |
| Mali | 47,574 | 99,177 | 208 | 67 |
| Marshall Islands (the) | 48,297 | 0 | 0 |  |
| Mauritania | 75,000 | 30,000 | 40 |  |
| Mauritius | 56,996 | 25,000 | 44 | 0 |
| Mexico | 1,212 |  | 0 | 0 |
| Micronesia (Federated States of) | 90,334 | 57,039 | 63 |  |
| Mongolia | 39,000 | 60,506 | 155 |  |
| Mozambique | 130,637 | 75,008 | 57 | 67 |
| Myanmar | 62,304 | 17,414 | 28 | 0 |
| Namibia | 39,000 | 45,000 | 115 | 100 |
| Nauru | 41,109 | 0 | 0 |  |
| Nepal | 60,620 | 131,025 | 216 | 100 |
| Nicaragua | 21,217 | 42,222 | 199 | 0 |
| Niger (the) | 25,500 | 0 | 0 |  |
| Niue | 29,658 | 0 | 0 |  |
| Oman | 28,777 | 42,461 | 148 | 100 |
| Pakistan | 60,000 | 24,593 | 41 |  |
| Palau | 33,038 | 33,900 | 103 |  |
| Panama | 5,086 | 13,074 | 257 | 100 |
| Paraguay | 66,431 | 39,780 | 60 |  |
| Peru | 149,532 | 27,099 | 18 | 100 |
| Philippines (the) | 127,669 | 157,785 | 124 |  |
| Qatar | 36,314 | 0 | 0 | 0 |
| Republic of Moldova (the) | 44,504 | 104,194 | 234 | 0 |
| Rwanda | 68,625 | 115,630 | 168 | 100 |
| Saint Kitts and Nevis | 68,760 | 0 | 0 | 0 |
| Saint Lucia | 100,755 | 31,155 | 31 | 0 |
| Saint Vincent and the Grenadines | 85,500 | 30,000 | 35 | 33 |
| Samoa | 35,421 | 67,500 | 191 |  |
| Sao Tome and Principe | 41,626 | 62,671 | 151 | 0 |
| Saudi Arabia | 408,143 | 24,988 | 6 | 0 |
| Senegal | 171,208 | 173,739 | 101 | 50 |
| Serbia | 12,574 | 0 | 0 | 100 |
| Seychelles | 19,125 | 63,750 | 333 | 100 |
| Sierra Leone | 58,898 | 114,318 | 194 | 67 |
| Solomon Islands | 53,955 | 72,300 | 134 | 100 |
| Somalia | 25,500 | 45,000 | 176 | 0 |
| South Sudan | 45,991 | 20,090 | 44 | 0 |
| Sri Lanka | 13,625 | 9,894 | 73 |  |
| Sudan (the) | 88,381 | 86,598 | 98 | 100 |
| Suriname | 86,025 | 17,372 | 20 | 50 |
| Timor-Leste | 87,836 | 78,972 | 90 | 100 |
| Togo | 59,835 | 92,176 | 154 | 33 |
| Tonga | 46,328 | 67,415 | 146 | 100 |
| Trinidad and Tobago | 85,659 | 20,000 | 23 |  |
| Tunisia | 16,454 | 0 | 0 | 0 |
| Turkey | 7,693 | 18,226 | 237 | 100 |
| Turkmenistan | 35,039 | 33,636 | 96 |  |
| Tuvalu | 23,181 | 13,703 | 59 |  |
| Uganda | 43,718 | 37,226 | 85 | 100 |
| United Republic of Tanzania (the) | 59,400 | 41,990 | 71 | 33 |
| Vanuatu | 53,465 | 40,986 | 77 | 50 |
| Viet Nam | 28,012 | 53,890 | 192 |  |
| Yemen | 190,248 | 0 | 0 | 75 |
| Zambia | 64,982 | 60,000 | 92 | 33 |
| Zimbabwe | 56,925 | 97,779 | 172 |  |
| Global | 11,727,382 | 8,737,022 | 75 | 50 |
| Region: ASP | 101,302 | 0 | 0 | 0 |
| Total | 22,571,098 | 17,830,385 | 79 | 56 |

# Table 5 presents a summary of HFC-related projects approved under regular contributions.

Table 5. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Technical assistance - Enabling activities | 11 | 0 | 0 | 1,706,000 | 0 | 1,706,000 | 0 |
| Total | 11 | 0 | 0 | 1,706,000 | 0 | 1,706,000 | 0 |

*Excludes agency support costs.

# There are currently 11 enabling activities approved under regular contributions at a total value of US $1,706,000. Funds have not been disbursed for these projects. These projects are progressing at various stages of implementation and are expected to be completed on time in 2020.

# Part II:	Projects approved under the additional voluntary contributions for fast start support for HFC phase-down

# As of 31 December 2018, the Executive Committee had approved 78 HFC-related projects under the additional voluntary contributions amounting to US $8,101,000 (excluding agency support costs). A summary of the status of these projects is presented in Table 6.

# Table 6. HFC-related projects approved in 2018

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Technical assistance - Enabling activities | 78 | 0 | 0 | 8,101,000 | 627,073 | 7,473,927 | 8 |
| Total | 78 | 0 | 0 | 8,101,000 | 627,073 | 7,473,927 | 8 |

*Excludes agency support costs.

# The 78 ongoing enabling activities, including five approved at the 82nd meeting, are at various stages of implementation. Cumulatively, US $627,073 had been disbursed out of the total US $8,101,000 approved for disbursement (excluding support costs), representing a disbursement rate of 8 per cent.

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database that is available upon request.

Ongoing projects are all projects that were under implementation as at 31 December 2018. Key indicators of progress include: percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

The issue of the two different measurements of controlled substances is discussed in the consolidated progress report (UNEP/OzL.Pro/ExCom/84/16).

All the controlled substances under these projects were ozone-depleting substances. No phase-out approved under enabling activities.

UNEP/OzL.Pro/ExCom/84/40

UNEP/OzL.Pro/ExCom/84/42

UNEP/OzL.Pro/ExCom/84/43

UNEP/OzL.Pro/ExCom/84/44

UNEP/OzL.Pro/ExCom/84/46

UNEP/OzL.Pro/ExCom/84/48

UNEP/OzL.Pro/ExCom/84/49

UNEP/OzL.Pro/ExCom/84/51

UNEP/OzL.Pro/ExCom/84/52

UNEP/OzL.Pro/ExCom/84/55

UNEP/OzL.Pro/ExCom/84/58

UNEP/OzL.Pro/ExCom/84/60

UNEP/OzL.Pro/ExCom/84/22 and Add.1

UNEP/OzL.Pro/ExCom/84/25

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively-financed projects.