| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | Programme des Nations Unies pour l’environnement | Distr. GÉNÉRALE UNEP/OzL.Pro/ExCom/92/4 9 mai 2023 FRANÇAIS ORIGINAL: ANGLAIS |

COMITÉ EXÉCUTIF 
  DU FONDS MULTILATÉRAL AUX FINS 
  D’APPLICATION DU PROTOCOLE DE MONTRÉAL
Quatre-vingt-douzième réunion

Montréal, 29 mai – 2 juin 2023

Point 4(b) de l’ordre du jour provisoire

# RAPPORT SUR LES SOLDES ET DISPONIBILITE DES RESSOURCES

# Introduction

- Ce document présente un résumé des ajustements financiers communiqués par les agences d’exécution, et approuvés par le Secrétariat. Il comprend les données statistiques de tous les projets dont les soldes ont été détenus pendant plus de 12 mois après l’achèvement du projet, conformément aux décisions 28/7 et 56/2(c). Il examine les soldes à restituer provenant de certains projets au titre du suivi donné aux décisions les concernant (appelés projets « soumis à décision » dans le présent document) et aux transferts de projets. Il indique également au Comité exécutif le niveau des ressources disponibles en liquidités enregistrées dans le document État des contributions et décaissements, conformément à la décision 41/92(b), et présente une recommandation. Les sommes détenues par les agences d’exécution dans le cadre de projets achevés, de projets soumis à décision et de projets financés à l’aide de contributions volontaires supplémentaires sont incluses respectivement dans les Annexes I, II et III. L’Annexe IV présente les fonds restitués par les agences d’exécution et provenant de projets achevés et de projets financés par des contributions volontaires supplémentaires.

Fonds devant être restitués à la 92e réunion par les agences d’exécution

# Le montant total des fonds à restituer, associés à des projets achevés, des projets soumis à décision et des projets financés par des contributions volontaires supplémentaires, s’élève à 2 508 725 $ US (voir tableau 1).

# Tableau 1. Fonds devant être restitués par les agences d’exécution à la 92e réunion ($ US)

| Agence | Coût du projet | Coûts d’appui d’agence | Coût total |
| --- | --- | --- | --- |
| PNUD | 334 630 | 23 485 | 358 115 |
| PNUE | 277 372 | 17 732 | 295 104 |
| ONUDI | 1 728 863 | 123 876 | 1 852 740 |
| Banque mondiale | 2 586 | 181 | 2 767 |
| Total | 2 343 451 | 165 274 | 2 508 725 |

Soldes encore détenus par les agences d’exécution

# Le tableau 2 présente les soldes encore détenus par les agences d’exécution pour des projets achevés, des projets soumis à décision et des projets financés par des contributions volontaires supplémentaires.

Tableau 2. Soldes encore détenus par les agences d’exécution (coûts d’appui d’agence inclus) pour des projets achevés, des projets soumis à décision et des projets financés par des contributions volontaires supplémentaires

| Année d’achèvement | PNUD |  | ONUDI |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Nombre | ($ US) | Nombre | ($ US) | Nombre | ($ US) |
| Projets achevés depuis plus de deux ans |  |  |  |  |  |  |
| 2019 | 2 | 8 332 | 0 | 0 | 2 | 8 332 |
| 2020 | 1 | 40 434 | 0 | 0 | 1 | 40 434 |
| Du 1er janvier au 30 avril 2021 | 2 | 1 477 | 0 | 0 | 2 | 1 477 |
| Total partiel | 5 | 50 243 | 0 | 0 | 5 | 50 243 |
| Projets achevés depuis moins de deux ans |  |  |  |  |  |  |
| Du 1er mai au 31 décembre 2021 | 24 | 727 722 | 9 | 84 953 | 33 | 812 675 |
| En cours |  |  | 1 | 120 612 | 1 | 120 612 |
| Total partiel | 24 | 727 722 | 10 | 205 565 | 34 | 933 287 |
| Total | 29 | 777 965 | 10 | 205 565 | 39 | 983 530 |
| Projets soumis à décision |  |  |  |  |  |  |
|  | 1 | 20 012 | 11 | 845 599 | 12 | 865 611 |
| Projets financés par des contributions volontaires supplémentaires |  |  |  |  |  |  |
|  | 1 | 23 411 | 2 | 119 069 | 3 | 142 480 |
| Total général | 31 | 821 388 | 23 | 1 170 233 | 54 | 1 991 621 |

Transferts de projets

# Le gouvernement de la République islamique d’Iran a demandé au Secrétariat du Fonds de transférer au PNUD le solde restant des projets associés à la phase II du plan de gestion de l’élimination des HCFC (PGEH) et à la préparation de la phase III du PGEH, actuellement mis en œuvre par le gouvernement de l’Allemagne. Le montant total que le gouvernement de l’Allemagne doit restituer au Fonds s’élève à 866 272 $ US, plus des coûts d’appui d’agence de 99 019 $ US. Le transfert au PNUD de 866 272 $ US impliquerait une baisse des coûts d’appui d’agence, s’élevant à 60 639 $ US.

# Le gouvernement du Turkménistan a demandé au Secrétariat du Fonds de transférer, du PNUE à l’ONUDI, le solde restant de la préparation de projet du plan de mise en œuvre de l’Amendement de Kigali pour les HFC (KIP) d’un montant de 10 000 $ US, plus des coûts d’appui d’agence de 1 300 $ US. Le transfert à l’ONUDI de 10 000 $ US impliquerait une baisse des coûts d’appui d’agence, s’élevant à 700 $ US.

# Le gouvernement de la Jordanie a demandé au Secrétariat du Fonds de transférer, de la Banque mondiale à l’ONUDI, le solde restant de la préparation de projet de la phase III du PGEH (global) d’un montant de 35 000 $ US, plus des coûts d’appui d’agence de 2 450 $ US.

# Le tableau 3 présente le détail des soldes devant être transférés. Le Comité exécutif pourrait souhaiter approuver ces demandes.

Tableau 3. Soldes des projets devant être transférés

| Titre du projet | N° du projet | Restitution |  |  | Transfert |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Au Fonds multilatéral |  |  | À l’agence |  |  |
|  |  | De | Solde | PSC | Vers | Solde | PSC |
| PGEH pour la République islamique d’Iran (phase II) | IRA/PHA/84/INV/236 | Allemagne | 93 017 | 10 580 | PNUD | 93 017 | 6 511 |
|  | IRA/PHA/86/INV/250 | Allemagne | 145 255 | 16 521 | PNUD | 145 255 | 10 168 |
|  | IRA/PHA/90/INV/259 | Allemagne | 502 500 | 57 156 | PNUD | 502 500 | 35 175 |
|  | IRA/PHA/90/INV/260 | Allemagne | 95 500 | 10 862 | PNUD | 95 500 | 6 685 |
| Préparation du PGEH pour la République islamique d’Iran (phase III) | IRA/PHA/87/PRP/251 | Allemagne | 5 000 | 650 | PNUD | 5 000 | 350 |
|  | IRA/PHA/87/PRP/252 | Allemagne | 25 000 | 3 250 | PNUD | 25 000 | 1 750 |
| Préparation du KIP pour le Turkménistan | TKM/KIP/87/PRP/87 | PNUE | 10 000 | 1 300 | ONUDI | 10 000 | 700 |
| Préparation du PGEH pour la Jordanie (phase III) (global) | JOR/PHA/88/PRP/110 | Banque mondiale | 35 000 | 2 450 | ONUDI | 35 000 | 2 450 |
| Total |  |  | 911 272 | 102 769 |  | 911 272 | 63 789 |

Disponibilité des ressources

# Le document détaillant l’état des contributions et des décaissements indique un solde disponible de 485 059 124 $ US au 9 mai 2023. Le solde total restitué par les agences d’exécution à la 92e réunion s’élève à 2 508 725 $ US. Ainsi, en excluant le montant de 246 millions de $ US se rapportant aux fonds restant de la période triennale 2018-2020 et devant être utilisés après 2023, le niveau total des ressources disponibles aux fins d’approbation à la 92e réunion est de 241 567 849 $ US.

# Observations du Secrétariat

# Le Secrétariat a rappelé aux agences d’exécution que les soldes des projets soumis à décision, des projets achevés depuis au moins un an et des projets financés par des contributions volontaires supplémentaires doivent être restitués au Fonds multilatéral dès que possible.

# Compte tenu du fait qu’au au 9 mai 2023, le montant total du financement des projets et activités soumis à la 92e réunion s’élève à 31 154 966 $ US, les ressources disponibles sont suffisantes pour les approbations lors de cette réunion.

Recommandation

# Le Comité exécutif pourrait souhaiter :

  - Prendre note :

- Du rapport sur les soldes et la disponibilité des ressources présenté dans le document UNEP/OzL.Pro/ExCom/92/4 ;

- Du fait que le montant net des fonds restitués par les agences d’exécution à la 92e réunion est de 2 508 725 $ US, soit 334 630 $ US, plus des coûts d’appui d’agence de 23 485 $ US, pour le PNUD ; 277 372 $ US, plus des coûts d’appui d’agence de 17 732 $ US, pour le PNUE ; 1 728 863 $ US, plus des coûts d’appui d’agence de 123 876 $ US, pour l’ONUDI ; et 2 586 $ US, plus des coûts d’appui d’agence de 181 $ US, pour la Banque mondiale ;

- Du fait que le PNUD détient un solde de 50 243 $ US, coûts d’appui d’agence compris, pour cinq projets achevés depuis plus de deux ans, de 20 012 $ US, coûts d’appui d’agence compris, pour un projet achevé « soumis à décision du Comité exécutif », et de 23 411 $ US, coûts d’appui d’agence compris, pour un projet achevé financé par des contributions volontaires supplémentaires de la part d’un groupe de pays donateurs destinées à financer des activités à démarrage rapide pour la mise en œuvre de la réduction progressive des HFC ;

- Du fait que l’ONUDI détient un solde de 119 069 $ US, coûts d’appui d’agence compris, pour deux projets financés par des contributions volontaires supplémentaires de la part d’un groupe de pays donateurs destinées à financer des activités à démarrage rapide pour la mise en œuvre de la réduction progressive des HFC ;

## Demander :

### Aux agences d’exécution de procéder au décaissement ou d’annuler les sommes engagées et non engagées qui ne sont pas nécessaires pour les projets achevés et les projets achevés « soumis à décision du Comité exécutif », et de restituer les soldes associés à la 93e réunion ;

### Au PNUD de procéder au décaissement ou d’annuler ses engagements pour les projets achevés depuis plus de deux ans, et de restituer les soldes à la 93e réunion ;

### Au PNUD et à l’ONUDI de procéder au décaissement ou de restituer à la 93e réunion les soldes des projets achevés qui ont été financés au moyen des contributions volontaires supplémentaires ;

### Au gouvernement de l’Allemagne de restituer, à la 92e réunion, le solde de la phase II du plan de gestion de l’élimination des HCFC (PGEH) pour la République islamique d’Iran d’un montant 836 272 $ US, plus des coûts d’appui d’agence de 95 119 $ US, comprenant :

- 93 017 $ US, plus des coûts d’appui d’agence de 10 580 $ US, issus de la deuxième tranche (IRA/PHA/84/INV/236) ;

- 145 255 $ US, plus des coûts d’appui d’agence de 16 521 $ US, issus de la troisième tranche (IRA/PHA/86/INV/250) ;

- 502 500 $ US, plus des coûts d’appui d’agence de 57 156 $ US, et 95 500 $ US, plus des coûts d’appui d’agence de 10 862 $ US, issus de la quatrième tranche (IRA/PHA/90/INV/259 et IRA/PHA/90/INV/260, respectivement) ;

### Au Trésorier de transférer au PNUD, à la 92e réunion et aux fins de mise en œuvre, les fonds restitués pour les projets mentionnés à l’alinéa (b)(iv) ci-dessus, d’un montant de 836 272 $ US, plus des coûts d’appui d’agence de 58 539 $ US, comprenant :

- 93 017 $ US, plus des coûts d’appui d’agence de 6 511 $ US, pour la deuxième tranche (IRA/PHA/84/INV/236) ;

- 145 255 $ US, plus des coûts d’appui d’agence de 10 168 $ US, pour la troisième tranche (IRA/PHA/86/INV/250) ;

- 502 500 $ US, plus des coûts d’appui d’agence de 35 175 $ US, et 95 500 $ US, plus des coûts d’appui d’agence de 6 685 $ US, pour la quatrième tranche (IRA/PHA/90/INV/259 et IRA/PHA/90/INV/260, respectivement) ;

### Au gouvernement de l’Allemagne de restituer, à la 92e réunion, le solde de la préparation de la phase III du PGEH pour la République islamique d’Iran d’un montant de 30 000 $ US, plus des coûts d’appui d’agence de 3 900 $ US, comprenant :

- 5 000 $ US, plus des coûts d’appui d’agence de 650 $ US, issus de la préparation de la stratégie globale (IRA/PHA/87/PRP/251) ;

- 25 000 $ US, plus des coûts d’appui d’agence de 3 250 $ US, issus de la préparation des activités d’investissement dans le secteur de la réfrigération et de la climatisation industrielles (IRA/PHA/87/PRP/252) ;

### Au Trésorier de transférer au PNUD, à la 92e réunion et aux fins de mise en œuvre, les fonds restitués pour les projets mentionnés à l’alinéa (b)(vi) ci-dessus, d’un montant de 30 000 $ US, plus des coûts d’appui d’agence de 2 100 $ US, comprenant :

- 5 000 $ US, plus des coûts d’appui d’agence de 350 $ US, pour la préparation de la stratégie globale (IRA/PHA/87/PRP/251) ;

- 25 000 $ US, plus des coûts d’appui d’agence de 1 750 $ US, pour la préparation des activités d’investissement dans le secteur de la réfrigération et de la climatisation industrielles (IRA/PHA/87/PRP/252) ;

### Au PNUE de restituer, à la 92e réunion, le solde de la préparation du plan de mise en œuvre de l’Amendement de Kigali pour les HFC pour le Turkménistan (TKM/KIP/87/PRP/18) d’un montant 10 000 $ US, plus des coûts d’appui d’agence de 1 300 $ US ;

### Au Trésorier de transférer à l’ONUDI, à la 92e réunion et aux fins de mise en œuvre, les fonds restitués pour le projet mentionné à l’alinéa (b)(viii) ci-dessus, d’un montant de 10 000 $ US, plus des coûts d’appui d’agence de 700 $ US ;

### À la Banque mondiale de restituer, à la 92e réunion, le solde de la préparation de la phase III du PGEH pour la Jordanie (global) (JOR/PHA/88/PRP/110) d’un montant de 35 000 $ US, plus des coûts d’appui d’agence de 2 450 $ US ;

### Au Trésorier de transférer à l’ONUDI, à la 92e réunion et aux fins de mise en œuvre, les fonds restitués pour le projet mentionné à l’alinéa (b)(x) ci-dessus, d’un montant de 35 000 $ US, plus des coûts d’appui d’agence de 2 450 $ US.

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 Dec 2021 (US $) | Funds disbursed as of 92nd meeting (US $) | Balances committed as per 92nd meeting (US $) | Balances not-committed as per 92nd meeting (US $) | Support cost on balances committed and not committed as per 92nd meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| ANG/PHA/84/TAS/22 | Verification report on the implementation of the HCFC phase-out management plan | Dec-21 | 30,000 | 7,391 | 22,609 |  | 2,035 |  |  |  |
| BZE/PHA/82/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | Jun-21 | 10,000 | 8,750 | 1,250 |  | 87 |  |  |  |
| CHI/SEV/83/INS/198 | Extension of the institutional strengthening project (phase XIII: 7/2019-6/2021) | Dec-21 | 238,784 | 238,615 | 169 |  | 12 |  |  |  |
| COL/PHA/81/INV/102 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | Dec-21 | 1,137,247 | 594,285 | 542,962 |  | 38,007 |  |  |  |
| COL/SEV/79/INS/101 | Extension of institutional strengthening project (phase XI: 11/2017-10/2019) | Jul-21 | 352,768 | 351,995 | 773 |  | 54 |  |  |  |
| COS/SEV/84/INS/62 | Extension of institutional strengthening project (phase XIII: 1/2020-12/2021) | Dec-21 | 179,857 | 179,495 | 362 |  | 25 |  |  |  |
| CUB/PHA/82/PRP/61 | Preparation of a HCFC phase-out management plan (stage II) | Oct-21 | 60,000 | 38,281 | 21,719 |  | 1,520 |  |  |  |
| CUB/SEV/81/TAS/57 | Enabling activities for HFC phase-down | Dec-21 | 75,000 | 71,408 | 3,592 |  | 251 |  |  |  |
| DOM/PHA/83/PRP/68 | Preparation of a HCFC phase-out management plan (stage III) | Jun-21 | 60,000 | 47,408 | 12,592 |  | 881 |  |  |  |
| DRC/PHA/79/PRP/42 | Preparation of a HCFC phase-out management plan (stage II) | Dec-21 | 17,143 | 12,931 | 4,212 |  | 295 |  |  |  |
| ELS/PHA/79/TAS/36 | Verification report for stage I of HCFC phase-out management plan | Jun-21 | 30,000 | 29,165 | 835 |  | 75 |  |  |  |
| ELS/SEV/81/TAS/37 | Enabling activities for HFC phase-down | Sep-21 | 100,000 | 99,478 | 523 |  | 37 |  |  |  |
| FIJ/PHA/77/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 59,850 | 54,065 | 5,785 |  | 521 |  |  |  |
| FIJ/PHA/82/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | Dec-21 | 30,000 | 26,442 | 3,558 |  | 249 |  |  |  |
| GHA/PHA/84/INV/48 | HCFC phase-out management plan (stage I, sixth tranche) | Dec-21 | 121,311 | 116,236 | 5,075 |  | 381 |  |  |  |
| GUY/PHA/75/INV/28 | HCFC phase-out management plan (stage II, first tranche) | Dec-19 | 159,750 | 157,857 | 1,893 |  | 133 |  |  |  |
| HAI/SEV/84/TAS/23 | Enabling activities for HFC phase-down | Dec-21 | 95,000 | 90,311 | 4,689 |  | 328 |  |  |  |
| IND/SEV/84/INS/478 | Extension of institutional strengthening project (phase XII: 12/2019-11/2021) | Nov-21 | 477,734 | 476,187 | 1,547 |  | 108 |  |  |  |
| IRA/SEV/82/INS/231 | Extension of the institutional strengthening project (phase XII: 4/2019-3/2021) | Mar-21 | 222,094 | 221,620 | 474 |  | 33 |  |  |  |
| JAM/PHA/81/PRP/38 | Preparation of a HCFC phase-out management plan (stage II) | Jul-21 | 40,000 | 33,501 | 6,499 |  | 455 |  |  |  |
| JAM/PHA/84/TAS/39 | Verification report on the implementation of the HCFC phase-out management plan | Dec-21 | 30,000 | 26,579 | 3,421 |  | 308 |  |  |  |
| JAM/PHA/85/INV/41 | HCFC phase-out management plan (stage I, fourth tranche) | Dec-21 | 58,000 | 54,898 | 3,102 |  | 233 |  |  |  |
| MAL/SEV/84/INS/188 | Extension of institutional strengthening project (phase XIII: 1/2020-12/2021) | Dec-21 | 357,760 | 357,322 | 438 |  | 31 |  |  |  |
| MOL/PHA/86/INV/43 | HCFC phase-out management plan (stage II, third tranche) | Dec-21 | 17,450 | 0 | 17,450 |  | 1,570 |  |  |  |
| PAN/PHA/83/PRP/49 | Preparation of a HCFC phase-out management plan (stage III) | Jun-21 | 60,000 | 42,695 | 17,305 |  | 1,211 |  |  |  |
| PAN/SEV/81/TAS/46 | Enabling activities for HFC phase-down | Dec-21 | 100,000 | 99,825 | 175 |  | 12 |  |  |  |
| SWA/PHA/83/PRP/27 | Preparation of a HCFC phase-out management plan (stage II) | Jun-21 | 10,000 | 5,609 | 4,391 |  | 307 |  |  |  |
| TRI/PHA/82/PRP/36 | Preparation of a HCFC phase-out management plan (stage II) | Jan-21 | 60,000 | 59,094 | 906 |  | 63 |  |  |  |
| URU/PHA/77/INV/67 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Dec-20 | 100,000 | 62,211 | 37,789 |  | 2,645 |  |  |  |
| TOTAL UNDP |  |  |  |  | 726,096 |  | 51,869 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| AFG/PHA/77/INV/20 | HCFC phase-out management plan (stage I, second tranche) | Sep-21 | 131,938 | 131,427 | 511 |  | 46 | 1 | 93 |  |
| CPR/PHA/71/INV/536 | HCFC phase-out management plan (stage I, third tranche) (room air-conditioner manufacturing sector plan) | Dec-21 | 8,495,000 | 8,494,893 | 107 |  | 8 | 1 | 93 | 84/68(d)(i) and 86/33(d) |
| GAM/PHA/82/PRP/37 | Preparation of a HCFC phase-out management plan (stage II) | Jun-21 | 10,000 | 9,238 | 762 |  | 53 | 1 | 93 |  |
| IRA/PHA/86/INV/246 | HCFC phase-out management plan (stage II, third tranche) (foam sector) |  | 524,000 | 35,578 | 112,721 |  | 7,891 | N.A. | N.A. |  |
| IRQ/PHA/58/INV/09 | National phase-out plan (first tranche) | Jun-21 | 4,353,530 | 4,317,013 | 36,517 |  | 2,739 | 1 | 93 | 71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c) |
| IRQ/PHA/84/INV/29 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | Dec-21 | 210,000 | 177,161 | 32,839 |  | 2,463 | 1 | 93 |  |
| NIR/PHA/81/INV/146 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector and project management unit) | Dec-21 | 176,837 | 176,826 | 11 |  | 1 | 1 | 93 |  |
| SEN/PHA/85/INV/41 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 50,000 | 46,281 | 3,719 |  | 279 | 1 | 93 |  |
| SYR/REF/62/INV/103 | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group | Dec-21 | 1,465,361 | 1,462,556 | 2,805 |  | 210 | 1 | 93 |  |
| TOG/PHA/79/INV/30 | HCFC phase-out management plan (stage I, third tranche) | Jun-21 | 150,000 | 148,249 | 1,751 |  | 131 | 1 | 93 |  |
| TOTAL UNIDO |  |  |  |  | 191,744 |  | 13,821 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS

| Code | Project title | Financial date of completion per decision | Approved funding plus adjustments as of 31 December 2021 (US $) | Funds disbursed as of 92nd meeting (US $) | Balances committed as per 92nd meeting (US $) | Balances not- committed as per 92nd meeting (US $) | Support cost on balances committed and not-committed as per 92nd meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BRA/DES/72/DEM/305 | Pilot demonstration project on ODS waste management and disposal | Dec-23 | 1,490,600 | 1,471,897 | 18,703 |  | 1,309 |  |  | 79/18(c)(i) and 81/24(e)(ii) |
| TOTAL UNDP |  |  |  |  | 18,703 |  | 1,309 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| BRA/PHA/75/INV/311 | HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector) | ONG | 1,674,275 | 1,456,105 | 16,070 |  | 1,125 | 2 | 93 |  |
| GLO/REF/80/DEM/344 | Global chiller replacement project (Argentina) | ONG | 808,438 | 770,732 | 37,706 |  | 2,828 | 2 | 93 |  |
| IVC/PHA/66/INV/36 | HCFC phase-out management plan (stage I, first tranche) | ONG | 460,000 | 459,623 | 377 |  | 28 | 2 | 93 |  |
| IVC/PHA/84/INV/45 | HCFC phase-out management plan (stage I, third tranche) | ONG | 460,000 | 449,228 | 10,772 |  | 754 | 2 | 93 |  |
| PHI/PHA/83/INV/104 | HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector) | ONG | 736,129 | 236,717 | 301,139 |  | 21,079 | 2 | 93 |  |
| PHI/PHA/83/TAS/105 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | ONG | 273,894 | 180,332 | 93,562 |  | 6,549 | 2 | 93 |  |
| SAU/PHA/72/INV/20 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring) | ONG | 270,000 | 248,066 | 21,934 |  | 1,535 | 2 | 93 |  |
| SAU/PHA/75/INV/24 | HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan) | ONG | 1,100,000 | 908,061 | 191,939 |  | 13,436 | 2 | 93 |  |
| SAU/REF/76/DEM/28 | Demonstration project on promoting HFO-based low-global warming potential refrigerants for air-conditioning sector in high ambient temperatures | ONG | 1,300,000 | 1,188,813 | 111,187 |  | 7,783 | 1 | 93 |  |
| SOM/PHA/77/INV/12 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | ONG | 141,500 | 141,442 | 58 |  | 4 | 2 | 93 |  |
| SOM/PHA/88/INV/16 | HCFC phase-out management plan (stage I, third tranche) | ONG | 40,000 | 34,641 | 5,359 |  | 375 | 2 | 93 |  |
| TOTAL UNIDO |  |  |  |  | 790,103 |  | 55,496 |  |  |  |

Annex III

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS

| CODE | Project title | Approved funding plus adjustments as of 31 December 2021 (US $) | Funds disbursed as of 92nd meeting (US $) | Balances committed as per 92nd meeting (US $) | Balances not- committed as per 92nd meeting (US $) | Support cost on balances committed and not-committed as per 92nd meeting (US $) | Why any balances could not be returned? | When they could be returned? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |
| URU/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 100,000 | 78,121 | 21,879 |  | 1,532 |  |  |
| TOTAL UNDP |  |  |  | 21,879 |  | 1,532 |  |  |
| UNIDO |  |  |  |  |  |  |  |  |
| MEX/REF/81/INV/04+ | Conversion of commercial refrigeration manufacturing in two facilities from the use of HFC-134a and R-404A as the refrigerants to propane (R-290) and isobutane (R-600a) at Imbera | 1,018,123 | 925,466 | 92,657 |  | 6,486 | 1 | 93 |
| PHI/SEV/83/TAS/02+ | Enabling activities for HFC phase-down | 225,992 | 207,370 | 18,622 |  | 1,304 | 1 | 93 |
| TOTAL UNIDO |  |  |  | 111,279 |  | 7,790 |  |  |

Annex IV

DETAILS ON COMPLETED, BY DECISIONS AND ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES

| Code | Project title | Project costs returned (US $) | Agency support costs (US $) | Total (US $) |
| --- | --- | --- | --- | --- |
| ARM/PHA/86/INV/26 | HCFC phase-out management plan (stage II, third tranche) | 1,239 | 112 | 1,351 |
| COS/PHA/83/INV/59 | HCFC phase-out management plan (stage I, fifth tranche) | 45 | 3 | 48 |
| CUB/PHA/85/TAS/63 | HCFC phase-out management plan (stage I, fifth tranche) | 207 | 16 | 223 |
| ELS/PHA/86/INV/41 | HCFC phase-out management plan (stage I, fourth tranche) | 7,059 | 529 | 7,588 |
| KYR/PHA/85/INV/42 | HCFC phase-out management plan (stage II, third tranche) | 434 | 30 | 464 |
| PAN/PHA/85/TAS/51 | HCFC phase-out management plan (stage II, third tranche) | 33 | 2 | 36 |
| TRI/SEV/83/INS/37 | Extension of the institutional strengthening project (phase X: 1/2020-12/2021) | 491 | 34 | 525 |
| Total completed projects |  | 9,508 | 727 | 10,235 |
| IND/PHA/86/INV/479 | HCFC phase-out management plan (stage II, third tranche) (air-conditioning manufacturing sector plan) | 316,592 | 22,161 | 338,753 |
| Total “by-decisions” projects |  | 316,592 | 22,161 | 338,753 |
| COL/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 3,656 | 256 | 3,912 |
| FIJ/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 2,301 | 161 | 2,462 |
| PAR/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 2,573 | 180 | 2,753 |
| Total “additional voluntary contributions” projects |  | 8,530 | 597 | 9,127 |
| TOTAL UNDP |  | 334,630 | 23,485 | 358,115 |
| AFG/PHA/79/TAS/21 | HCFC phase-out management plan (stage I, third tranche) | 11,374 | 1,479 | 12,853 |
| ELS/PHA/77/TAS/35 | HCFC phase-out management plan (stage I, third tranche) | 8,550 | 234 | 8,784 |
| GUA/SEV/81/INS/53 | Renewal of the institutional strengthening project (phase VIIl: 7/2018-6-2020) | 9,853 | 0 | 9,853 |
| KUW/PHA/84/PRP/39 | Preparation of a HCFC phase-out management plan (stage II) | 8,335 | 1,084 | 9,419 |
| KUW/SEV/81/TAS/33 | Enabling activities for HFC phase-down | 112,000 | 7,840 | 119,840 |
| MOL/SEV/82/INS/37 | Extension of the institutional strengthening project (phase X: 1/2019-12/2020) | 2,917 | 0 | 2,917 |
| NIC/PHA/81/TAS/36 | HCFC phase-out management plan (stage I, third tranche) | 532 | 69 | 601 |
| PAR/SEV/82/INS/38 | Extension of institutional strengthening project (phase IX: 1/2019-12/2020) | 6,740 | 0 | 6,740 |
| PHI/SEV/83/INS/106 | Extension of institutional strengthening project (phase XII: 1/2020-12/2021) | 34,093 | 0 | 34,093 |
| QAT/PHA/73/PRP/20 | Preparation of a HCFC phase-out management plan (stage II) | 9,900 | 1,287 | 11,187 |
| SAU/SEV/81/TAS/33 | Enabling activities for HFC phase-down | 56,830 | 3,978 | 60,808 |
| SEN/PHA/85/TAS/40 | HCFC phase-out management plan (stage I, third tranche) | 851 | 111 | 962 |
| Total completed projects |  | 261,975 | 16,081 | 278,056 |
| HAI/PHA/76/TAS/21 | HCFC phase-out management plan (stage I, second tranche) | 9,556 | 1,242 | 10,798 |
| Total “by-decisions” projects |  | 9,556 | 1,242 | 10,798 |
| CHI/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 5,771 | 404 | 6,175 |
| HON/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 70 | 5 | 75 |
| Total “additional voluntary contributions” projects |  | 5,841 | 409 | 6,250 |
| TOTAL UNEP |  | 277,372 | 17,732 | 295,104 |
| BDI/PHA/81/INV/37 | HCFC phase-out management plan (stage I, third tranche) | 313 | 28 | 341 |
| CPR/PHA/64/INV/513 | HCFC phase-out management plan (room air-conditioner manufacturing sector plan) (stage I, first tranche) | 83 | 6 | 89 |
| EGY/SEV/86/INS/148 | Extension of the institutional strengthening project (phase XIII: 1/2021-12/2022) | 253 | 18 | 271 |
| GAM/PHA/77/INV/33 | HCFC phase-out management plan (stage I, third tranche) | 2,899 | 261 | 3,160 |
| GUA/PHA/85/TAS/59 | HCFC phase-out management plan (stage I, fifth tranche) | 21 | 2 | 23 |
| IRQ/PHA/73/PRP/19 | Preparation of a HCFC phase-out management plan (stage II) | 11,555 | 809 | 12,364 |
| JOR/SEV/82/TAS/104 | Enabling activities for HFC phase-down | 22,292 | 1,561 | 23,853 |
| LIB/SEV/81/INS/40 | Renewal of institutional strengthening project (Phase V: 7/2018-6/2020) | 1,632 | 114 | 1,746 |
| LIR/PHA/84/PRP/27 | Preparation of a HCFC phase-out management plan (stage II) | 143 | 10 | 153 |
| MAG/PHA/76/INV/28 | HCFC phase-out management plan (stage I, third tranche) | 231 | 17 | 248 |
| MOG/PHA/83/INV/13 | HCFC phase-out management plan (stage I, fourth tranche) | 2,771 | 208 | 2,979 |
| MOG/PHA/84/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | 2,475 | 223 | 2,698 |
| MOG/PHA/85/INV/15 | HCFC phase-out management plan (stage I, fifth tranche) | 296 | 22 | 318 |
| OMA/PHA/86/PRP/40 | Preparation of a HCFC phase-out management plan (stage III) | 660 | 46 | 706 |
| PRC/PHA/76/INV/31 | HCFC phase-out management plan (stage I, third tranche) | 6,596 | 594 | 7,190 |
| SAU/FOA/62/INV/13 | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Al-Watania Plastics | 518,307 | 38,873 | 557,180 |
| SAU/PHA/72/INV/21 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | 613,276 | 42,929 | 656,205 |
| SAU/PHA/77/INV/31 | HCFC phase-out management plan (stage I, fourth tranche) (polyurethane foam sector plan) | 412,484 | 28,874 | 441,358 |
| SOA/PHA/71/INV/05 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | 6,834 | 478 | 7,312 |
| SOA/PHA/82/PRP/12 | Preparation of a HCFC phase-out management plan (stage II) | 2 | 0 | 2 |
| SUD/PHA/86/INV/46 | HCFC phase-out management plan (stage II, third tranche) | 29 | 4 | 33 |
| SUD/PHA/86/PRP/45 | Preparation of a HCFC phase-out management plan (stage III) | 259 | 18 | 277 |
| TKM/PHA/85/INV/15 | HCFC phase-out management plan (stage I, fourth tranche) | 94 | 7 | 101 |
| TOG/PHA/83/PRP/33 | Preparation of a HCFC phase-out management plan (stage II) | 245 | 17 | 262 |
| VEN/PHA/76/INV/134 | HCFC phase-out management plan (stage II, first tranche) (technical assistance in refrigeration and air-conditioning manufacturing sector) | 5,948 | 416 | 6,364 |
| Total completed projects |  | 1,609,698 | 115,535 | 1,725,233 |
| BKF/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 4,557 | 319 | 4,876 |
| CHI/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 6,950 | 3,264 | 49,897 |
| SOA/SEV/82/TAS/01+ | Enabling activities for HFC phase-down | 46,633 | 398 | 6,085 |
| SOM/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 5,687 | 3,873 | 59,198 |
| TUR/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 55,325 | 1 | 14 |
| URU/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 13 | 487 | 7,437 |
| Total “additional voluntary contributions” projects |  | 119,165 | 8,341 | 127,507 |
| TOTAL UNIDO |  | 1,728,863 | 123,876 | 1,852,740 |
| THA/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 2,586 | 181 | 2,767 |
| Total “additional voluntary contributions” projects |  | 2,586 | 181 | 2,767 |
| TOTAL WORLD BANK |  | 2,586 | 181 | 2,767 |

UNEP/OzL.Pro/ExCom/92/1

Les données sont présentées selon le format de déclaration élaboré conformément à la décision 31/2.

UNEP/OzL.Pro/ExCom/92/3

Ce transfert est également examiné dans les rapports de situation et les rapports sur les projets comportant des exigences particulières (UNEP/OzL.Pro/ExCom/92/9).

1:  Financial closure-initiated fund not returned due to ongoing unpaid obligations. 2: Ongoing grants, balances are not due for this meeting and therefore, funds will be returned after one year after the agreement end date

1:  Financial closure-initiated fund not returned due to ongoing unpaid obligations. 2: Ongoing grants, balances are not due for this meeting and therefore, funds will be returned after one year after the agreement end date

1:  Financial closure-initiated fund not returned due to ongoing unpaid obligations.