| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/92/11 9 May 2023 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-second Meeting

Montreal, 29 May to 2 June 2023

Item 8(a) of the provisional agenda

UPDATE ON THE STATUS OF IMPLEMENTATION OF THE 2023–2025 CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND

- Introduction

# The present document consists of the following sections:

## I.	An update on the status of the implementation of the 2023–2025 business plan

## II.	Resource allocation for the 2021–2023 triennium

III.	Recommendation

## I.	Update on the status of the implementation of the 2023–2025 business plan

# At its 91st meeting, the Executive Committee endorsed the 2023–2025 consolidated business plan of the Multilateral Fund. In response to decision 91/31, the Secretariat adjusted the consolidated 2023–2025 business plan, as shown in table 1.

Table 1. Resource allocation of the adjusted 2023–2025 consolidated business plan of the Multilateral Fund (US $)*

| Description | 2023 | 2024 | 2025 | Total |
| --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 60,280,861 | 56,111,450 | 43,084,350 | 159,476,661 |
| HPMP project preparation (PRP) – stage II | 200,480 | 77,600 | 0 | 278,080 |
| HPMP stage II | 2,937,082 | 5,199,804 | 3,462,199 | 11,599,085 |
| HPMP stage II – investment | 0 | 248,532 | 0 | 248,532 |
| HPMP PRP – stage III | 290,100 | 92,750 | 0 | 382,850 |
| HPMP stage III | 14,794,713 | 10,344,520 | 20,526,731 | 45,665,964 |
| HPMP PRP – stage IV | 90,000 | 0 | 0 | 90,000 |
| HPMP stage IV | 0 | 0 | 2,093,000 | 2,093,000 |
| HPMP – energy efficiency | 3,258,494 | 2,672,980 | 3,379,420 | 9,310,894 |
| HPMP verification** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| HCFC activities subtotal | 82,440,330 | 75,336,236 | 73,134,299 | 230,910,865 |
| HFC activities |  |  |  |  |
| Enabling activities for HFC phase-down | 53,500 | 160,500 | 0 | 214,000 |
| Kigali HFC implementation plans (KIPs) – PRP | 3,945,431 | 2,567,011 | 144,560 | 6,657,002 |
| KIPs | 27,299,967 | 21,437,607 | 245,413 | 48,982,987 |
| KIPs PRP – investment | 129,000 | 0 | 0 | 129,000 |
| KIPs – investment | 321,000 | 8,963,616 | 0 | 9,284,616 |
| HFC-23 emissions control PRP | 43,000 | 0 | 0 | 43,000 |
| HFC-23 emissions control | 0 | 8,000,000 | 0 | 8,000,000 |
| HFC – technical assistance | 0 | 678,000 | 0 | 678,000 |
| HFC activities subtotal | 31,791,898 | 41,806,734 | 389,973 | 73,988,605 |
| Pilot project for energy efficiency |  |  |  |  |
| Pilot project for energy efficiency | 20,000,000 | 0 | 0 | 20,000,000 |
| Pilot project for energy efficiency subtotal | 20,000,000 | 0 | 0 | 20,000,000 |
| Standard activities |  |  |  |  |
| Institutional strengthening (IS) | 27,860,444 | 16,639,896 | 0 | 44,500,341 |
| Compliance Assistance Programme (CAP) | 11,445,002 | 11,788,350 | 12,142,003 | 35,375,355 |
| Core unit | 5,969,740 | 6,011,529 | 6,053,610 | 18,034,878 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 7,237,326 | 7,202,023 | 6,816,624 | 21,255,973 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |
| Standard activities subtotal | 53,012,512 | 42,141,798 | 25,512,237 | 120,666,547 |
| Grand total | 187,244,740 | 159,284,767 | 99,036,509 | 445,566,017 |
| Australia | 0 | 0 | 152,497 | 152,497 |
| Austria | 783,667 | 0 | 0 | 783,667 |
| France | 671,075 | 0 | 0 | 671,075 |
| Germany | 1,349,869 | 3,705,721 | 1,028,250 | 6,083,840 |
| Japan | 67,800 | 0 | 0 | 67,800 |
| UNDP | 62,425,117 | 54,216,500 | 29,064,016 | 145,705,634 |
| UNEP | 40,325,066 | 36,674,895 | 22,071,085 | 99,071,046 |
| UNIDO | 38,767,526 | 29,078,890 | 29,553,746 | 97,400,162 |
| World Bank | 14,528,694 | 27,318,138 | 9,261,691 | 51,108,523 |
| HPMP verification** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| Pilot project for energy efficiency | 20,000,000 | 0 | 0 | 20,000,000 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 7,237,326 | 7,202,023 | 6,816,624 | 21,255,973 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |

* Including agency support costs where applicable.

** Funding for the preparation of HPMP verification reports for low-volume-consuming countries is approved by the Executive Committee on an annual basis.

I.1	Status of implementation of the 2023 business plan

# Table 2 sets out the submissions by agency to the 92nd meeting (as at 9 May 2023), and the balance of funds from projects in the 2023 business plans.

Table 2. 2023 consolidated business plan, projects recommended to the 92nd meeting, and balance (US $)*

| Budget items | Total value in business plan | Activities recommended to the 92nd meeting | Balance (above)/below |
| --- | --- | --- | --- |
| Bilateral agencies | 2,872,411 | 687,988 | 2,184,423 |
| UNDP | 62,425,117 | 11,901,104 | 50,524,013 |
| UNEP | 40,325,066 | 6,702,361 | 33,622,705 |
| UNIDO | 38,767,526 | 8,573,725 | 30,193,802 |
| World Bank | 14,528,694 | 2,681,988 | 11,846,706 |
| HPMP verification | 588,600 | 573,900 | 14,700 |
| Pilot project for energy efficiency | 20,000,000 | 33,900 | 19,966,100 |
| Subtotal (agencies) | 179,507,414 | 31,154,966 | 148,352,448 |
| Secretariat/Executive Committee/Monitoring and Evaluation (excluding Canadian counterpart) | 7,237,326 | 0 | 7,237,326 |
| Treasurer | 500,000 | 0 | 500,000 |
| Subtotal (standard costs) | 7,737,326 | 0 | 7,737,326 |
| Total | 187,244,740 | 31,154,966 | 156,089,774 |

* Including core unit costs.

# The value of project proposals recommended to the 92nd meeting of US $31,154,966 is US $1,508,497 above its value in the 2023 business plan and includes US $1,544,028 associated with project proposals not included in the 2023 business plan.

# The value of HFC-related activities submitted to the 92nd meeting is US $3,822,128 of which US $751,182 is associated with project proposals not included in the 2023 business plan. Annex I to the present document lists HFC-related projects submitted by the bilateral and implementing agencies to the 92nd meeting.

# I.2	Forward commitments

# The total amount for existing forward commitments for multi-year agreements (MYAs) for the period 2023 to 2031 is US $247.81 million, assuming that the funding requests of MYAs submitted to the 92nd meeting will be approved in principle, as shown in table 3.

Table 3. Forward commitments (2023–2031) (US $000)

| Description | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approved in principle | 60,788 | 56,111 | 43,084 | 42,503 | 10,189 | 1,429 | 4,733 | 6,410 | 57 | 225,305 |
| Submitted to the 92nd meeting | 6,871 | 0 | 6,257 | 2,346 | 0 | 4,741 | 0 | 2,291 | 0 | 22,506 |
| Total | 67,659 | 56,111 | 49,342 | 44,850 | 10,189 | 6,170 | 4,733 | 8,701 | 57 | 247,811 |

# II.	Resource allocation for the 2021–2023 triennium

# The resources approved by the Parties to the Montreal Protocol for the 2021–2023 triennium amount to US $540,000,000. Taking into account the approvals in 2021 and 2022 and the 2023 business plans of US $187,244,740, the resources available at the end of 2023 is US $141,594,808. In addition, the Fifth Extraordinary Meeting of the Parties also noted that US $246 million in remaining funds that were due to the Multilateral Fund during the triennium 2018–2020 will be used after 2023 to support the implementation of the Montreal Protocol (decision Ex.V/1). Therefore, the total resources available for the 2024–2026 triennium is US $387,594,808.

Table 4. Resource allocation for the 2021-2023 triennium (US $)

| Description | Amount (US $) |
| --- | --- |
| Total budget for the 2021–2023 triennium | 540,000,000 |
| 2021 approvals including Secretariat/Executive Committee/Monitoring and Evaluation/Treasurer | (104,132,796) |
| 2022 approvals including Secretariat/Executive Committee/Monitoring and Evaluation/Treasurer | (107,027,656) |
| 2023 business plans | (179,507,414) |
| 2023 Secretariat/Executive Committee/Monitoring and Evaluation/Treasurer | (7,737,326) |
| Resources available at the end of 2023 | 141,594,808 |
| Carry-over from the 2018–2020 triennium to be used after 2023 | 246,000,000 |
| Total resources available for the 2024–2026 triennium | 387,594,808 |

# III.	Recommendation

# The Executive Committee may wish to note:

## The update on the status of implementation of the 2023–2025 consolidated business plan of the Multilateral Fund as contained in document UNEP/OzL.Pro/ExCom/92/11; and

## That the total value of activities as requested to the 92nd meeting amounts to US $31,154,966 (including US $3,822,128 for HFC-related activities), of which US $1,544,028 is associated with project proposals not included in the 2023 business plan.

Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 92ND MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Burundi | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan | 119,000 | 15,470 |
| Burundi | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan | 51,000 | 3,570 |
| Cameroon | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 355,500 | 24,885 |
| Costa Rica | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 1,571,267 | 109,989 |
| Guatemala | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan | 51,000 | 6,630 |
| Guatemala | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan | 119,000 | 8,330 |
| India | Germany | PRP | KIP | Preparation for a pilot project to maintain and/or enhance energy efficiency | 30,000 | 3,900 |
| India | UNDP | PRP | KIP | Preparation of a KIP investment project in the air conditioner (AC) manufacturing sector for Voltas Limited | 30,000 | 2,100 |
| India | UNDP | PRP | KIP | Preparation of a KIP investment project in the refrigeration manufacturing sector for Mech Air Industries | 30,000 | 2,100 |
| India | UNDP | PRP | KIP | Preparation of a KIP investment project in the refrigeration manufacturing sector for Rockwell Industries | 30,000 | 2,100 |
| Indonesia | IBRD | PRP | KIP | Preparation of a Kigali HFC implementation plan | 220,000 | 15,400 |
| Mexico | UNDP | INV | REF | Conversion of the manufacturing of commercial refrigerators from HFC-134a to propane (R-290) at the enterprise Friocima | 143,850 | 12,947 |
| Mexico | UNIDO | INV | PHA | Destruction of emissions of HFC-23 generated in the production of HCFC-22 in Quimobasicos (second tranche) | 387,561 | 27,129 |
| Morocco | UNIDO | PRP | KIP | Preparation of a KIP investment project in the refrigeration manufacturing sector for MANAR | 30,000 | 2,100 |
| Venezuela (Bolivarian Republic of) | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan | 220,000 | 15,400 |
| Viet Nam | IBRD | PRP | KIP | Preparation of a KIP investment project in the commercial refrigeration sector for Sanaky | 30,000 | 2,100 |
| Viet Nam | IBRD | PRP | KIP | Preparation of a KIP investment project in the domestic refrigeration sector for Aqua Electrical Appliances, Darling Electronics, and Hoa Phat Refrigeration Engineering | 80,000 | 5,600 |
| Viet Nam | IBRD | PRP | KIP | Preparation of a KIP investment project in the industrial refrigeration sector for Quang Thang Refrigeration | 30,000 | 2,100 |
| Viet Nam | IBRD | PRP | KIP | Preparation of a KIP investment project in the mobile air-conditioning sector for Thaco Auto | 30,000 | 2,100 |

UNEP/OzL.Pro/ExCom/92/1

Stage III of the HPMPs for Indonesia (Australia) and Uruguay (UNIDO); five KIP preparation for investment projects for Morocco (UNIDO) and Viet Nam (four projects) (World Bank); one HFC investment project for Mexico (UNDP); one energy efficiency project under decision 89/6 for Burkina Faso (Germany); and stage I of KIP for Cameroon (UNIDO).