| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/91/15 9 November 2022 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-first Meeting

Montreal, 5-9 December 2022

Item 7(a)(iv) of the provisional agenda

PROGRESS REPORT OF UNEP AS AT 31 DECEMBER 2021

Introduction

# This document presents the progress report of UNEP as at 31 December 2021.

# The progress report of UNEP includes the status of implementation of projects, including 79 HFC-related projects that have been funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2021, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs which are measured in CO2-eq tonnes.

# This document consists of the following sections:

## I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2021 and cumulative since 1991 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs). It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## II.	Projects approved for Annex F substances (HFCs) under the additional voluntary contributions for fast-start support for HFC phase-down.

III.	Recommendation.

I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund

I.1	Progress in implementation of projects for 2021 and cumulative since 1991

# As of 31 December 2021, the Executive Committee had approved US $394.44 million in projects for UNEP, consisting of US $364.34 million for the implementation of investment and non-investment projects, and US $30.1 million for agency support costs, as shown in table 1.

# Table 1. Approved funding by sector for UNEP as at 31 December 2021

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 882,689 |
| Destruction | 190,040 |
| Halon | 767,640 |
| HFC phase-down plan | 2,218,000 |
| Fumigants | 2,614,366 |
| Phase-out plan | 70,596,786 |
| Refrigeration | 13,868,100 |
| Several | 273,001,282 |
| Solvents | 198,860 |
| Sub-total | 364,337,763 |
| Agency support costs | 30,104,814 |
| Total | 394,442,577 |

# In 2021, 127 new projects and activities were approved. This level of funding is expected to result in the phase-out of 2,299 ODP tonnes of consumption of controlled substances. Annex I shows the status of project implementation per country in 2021.

# Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2021. Annex II presents analytical information per year since 1991.

Table 2. Status of project implementation by type as at 31 December 2021

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 94 | 94 | 100 | 2,946,574 | 2,946,574 | 0 | 100 |
| Demonstration | 3 | 3 | 100 | 554,385 | 542,845 | 11,540 | 98 |
| Institutional strengthening (IS) | 937 | 832 | 89 | 76,577,781 | 66,625,040 | 9,952,740 | 87 |
| Investment | 3 | 2 | 67 | 490,500 | 379,450 | 111,050 | 77 |
| Project preparation | 279 | 222 | 80 | 12,601,312 | 9,503,281 | 3,098,032 | 75 |
| Technical assistance | 1,108 | 925 | 83 | 256,874,653 | 225,532,455 | 31,342,198 | 88 |
| Training | 196 | 196 | 100 | 14,292,557 | 14,292,557 | 0 | 100 |
| Total | 2,620 | 2,274 | 87 | 364,337,763 | 319,822,202 | 44,515,561 | 88 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

# Implementation of projects and activities by UNEP for 2021 and cumulative since 1991 up to 31 December 2021, is summarized as follows:

## Phase-out: In 2021, zero ODP tonnes of consumption of controlled substances were phased out and 76 ODP tonnes of consumption of controlled substances were approved for phase-out. Since 1991, 1,575 ODP tonnes of consumption of controlled substances had been phased out, of an expected total of 2,299 ODP tonnes from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2021, US $18.57 million was disbursed and US $21.57 million was planned for disbursement based on the 2020 progress report, representing a rate of disbursement of 86 per cent of that planned. Cumulatively, US $319.82 million had been disbursed out of the total US $364.34 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 88 per cent. In 2021, US $23.92 million was approved for implementation;

## Number of projects completed: In 2021, 150 projects were completed. Since 1991, 2,274 projects of the 2,620 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 87 per cent;

## Speed of delivery – non-investment projects: Projects that were completed in 2021 were completed on average 32 months after their approval. Since 1991, the average time for completion of non-investment projects has been 36 months after their approval. First disbursements under these projects occurred, on average, 11 months after they had been approved;

## Project preparation: Of the 279 project preparation activities approved by the end of 2021, 222 have been completed, leaving 57 ongoing activities. In 2021, 17 project preparation activities have been completed;

## Implementation delays: A total of 346 projects were under implementation at the end of 2021, experiencing, on average, a delay of 10 months. Twenty-five of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2021, 123 MYAs for HCFC phase-out management plans (HPMPs) were under implementation. Since 1991, 242 MYAs have been approved and 119 MYAs have been completed, representing a completion rate of 49 per cent.

# Table 3 summarized progress made by UNEP since 1991.

## Table 3. Progress made by UNEP since 1991

| Phase out achieved |  | Disbursement (US $) | Number of projects |  | Speed of delivery for completion for non-investment projects (months) | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes | CO2-eq tonnes |  | Approved | Completed |  |  | Approved | Completed |
| 1,575 | 0 | 319,822,202 | 2,620 | 2,274 | 36 | 10 | 242 | 119 |

HFC-related projects

# As of 31 December 2021, the Executive Committee had approved 40 HFC-related projects (including 26 preparation projects and 14 enabling activities) under regular contributions amounting to US $4,474,000 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9.

Table 4. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Project preparation | 26 | 0 | 0 | 2,218,000 | 0 | 2,218,000 | 0 |
| Technical assistance - Enabling activities | 14 | 7 | 50 | 2,256,000 | 1,027,822 | 1,228,178 | 46 |
| Total | 40 | 7 | 18 | 4,474,000 | 1,027,822 | 3,446,178 | 23 |

* Excludes agency support costs.

# As of the end of 2021, of the 40 projects, seven enabling activities have been completed, leaving 33 ongoing. Of the seven ongoing enabling activities, extension of the completion dates of six was approved. These ongoing activities are at various stages of implementation.

# Of the total cumulative funding approved of US $4,474,000 (excluding agency support costs), US $1,027,822 had been disbursed, representing a disbursement rate of 23 per cent.

I.2	Issues identified in project implementation in 2021

# Further to the review process, several issues were discussed and satisfactorily addressed, except for issues on 25 projects classified as projects with implementation delays (including 23 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); and two technical assistance projects). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 92nd meeting.

# In addition, several issues have been identified regarding projects or tranches of MYAs for the phase-out of HCFCs; renewal of IS projects; and enabling activities for HFC phase-down. These issues are also presented in Annex III. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Details of progress in implementation of projects associated with the HPMPs for Albania, Barbados, China (refrigeration servicing sector plan and enabling components), the Congo, Eritrea,  Mauritania, Serbia, South Sudan, Syrian Arab Republic, and Togo and a report on projects with specific reporting requirements associated with Senegal (HPMP) has been submitted to the 91st meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. The issues relating to the HPMPs for Burundi, Guyana, Mali, Saint Kitts and Nevis, Suriname and Tunisia, tranches of which were due at the 91st meeting but were not submitted, and for Iraq, the tranche of which was submitted to the 91st meeting but subsequently withdrawn during the project review process, are addressed in the document on tranche submission delays. Outstanding issues for the remaining ongoing projects not included in Annex III to the present document are addressed below.

# Of the 184 ongoing projects, excluding IS and project preparation, 53 projects have revised planned dates of completion since the 2020 progress report.

# In line with decision 82/11(c)(ii), the Secretariat noted that renewal of IS projects had not been submitted for the last two years for five Article 5 countries namely, Angola, Bolivia (Plurinational State of), Guyana, Myanmar and Nepal. These projects have large remaining balances due to slow progress in implementation for various reasons including those related to the COVID-19 pandemic. UNEP informed that it has been providing assistance to those countries and is planning to submit those renewal requests by 2023, except for the case of Myanmar, which will be subject to the political situation and the resumption of activities in the country.

# Pursuant to decision 90/6(a)(ii), the Secretariat sent letters to the relevant Governments regarding possible cancellation of the HPMPs for the Congo (stage I, third tranche) (PRC/PHA/76/TAS/30) and Saint Kitts and Nevis (stage I, second tranche) (STK/PHA/74/TAS/20). As mentioned in paragraph 15, the project associated with the HPMP for the Congo has been submitted to the 91st meeting. Based on the information presented in the progress report, the Secretariat also noted that some progress was made in implementation of the HPMP for Saint Kitts and Nevis, and therefore recommends continue monitoring of the project, as reflected in Annex III to the document.

# At its 90th meeting, the Executive Committee, noting the continuing challenges in implementation of stage I of the HPMPs for Haiti and Mali, inter alia decided to allow, on an exceptional basis, UNEP to continue implementation of the outstanding activities, and to request UNEP to submit at the 91st meeting a report on the status of their implementation as part of the UNEP’s progress report in line with decision 88/29(b)(ii) (decision 90/23(e)).

# In the case of Haiti, UNEP reported that the implementation challenges have not yet been resolved and, with the agreement of the Government through its letter to the Secretariat dated 3 November 2022, requested cancellation of the HPMP (stage I, second tranche) (HAI/PHA/76/TAS/21). Accordingly, the Executive Committee way wish to cancel the project at the 91st meeting and request UNEP to return the remaining balances in line with decision 28/7.

# In line with decision 90/23(e), the activities under stage I of the HPMP for Mali that is delayed due to the national political situation, would continue to be implemented by UNEP. The Executive Committee may wish to request UNEP to provide a status report on the implementation of the project to the 92nd meeting.

# The Secretariat further noted that no progress was made for the HPMP for Suriname (stage I, third tranche) (SUR/PHA/81/TAS/26) for two consecutive meetings. The Executive Committee may wish to request the Secretariat to send a letter to the Government and UNEP regarding possible cancellation of this project.

II.	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2021, the Executive Committee had approved 79 HFC-related projects under the additional voluntary contributions amounting to US $8,310,037 (excluding agency support costs). A summary of the status of these projects is presented in table 6.

# Table 6. Status of approved HFC-related projects as of the end of 2021

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Technical assistance - Enabling activities | 79 | 43 | 54 | 8,310,037 | 6,068,367 | 2,241,670 | 73 |

* Excludes agency support costs.

# As of the end of 2021, of the 79 enabling activities approved, 43 had been completed. Extension of the completion dates of the remaining 36 ongoing enabling activities was approved; these activities are at various stages of implementation.

# Of the total cumulative funding approved of US $8,310,037, US $6,068,367 had been disbursed, representing a disbursement rate of 73 per cent.

# Further to the review process, five projects for enabling activities are classified as projects with implementation delays and are included in Annex III to the present document containing the Secretariat’s recommendation requesting the submission of a report to the 92nd meeting.

III.	Recommendation

# The Executive Committee may wish:

## To note the progress report of UNEP as at 31 December 2021 contained in document UNEP/OzL.Pro/ExCom/91/15;

## To approve the recommendations related to ongoing projects with specific issues contained in Annex III to the present document;

## To cancel the HCFC phase-out management plan (HPMP) for Haiti (stage I, second tranche) (HAI/PHA/76/TAS/21) at the 91st meeting and to request UNEP to return the remaining balances in line with decision 28/7;

## To allow, on an exceptional basis, UNEP to continue implementation of the outstanding activities related to stage I of the HPMP for Mali, and to request UNEP to submit at the 92nd meeting a report on the status of its implementation; and

## To request the Secretariat to send a letter to the Government of Suriname and UNEP regarding possible cancellation of its HPMP (stage I, third tranche) (SUR/PHA/81/TAS/26).

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNEP

PER COUNTRY FOR 2021

# Table 1 of Annex I presents the status of project implementation by country for 2021 in achieved phased out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation by UNEP for 2021

| Country | Estimated funds disbursed in 2021 (US$) | Funds disbursed in 2021 (US$) | Percentage of funds disbursed over estimation in 2021 | Percentage of planned projects completed in 2021* |
| --- | --- | --- | --- | --- |
| Afghanistan | 112,392 | 0 | 0 | 100 |
| Albania | 53,661 | 81,459 | 152 | 100 |
| Algeria | 257,400 | 257,400 | 100 | 100 |
| Angola | 84,610 | 0 | 0 | 0 |
| Antigua and Barbuda | 60,000 | 0 | 0 | 0 |
| Armenia | 14,970 | 48,017 | 321 | 100 |
| Bahamas (the) | 73,675 | 68,525 | 93 | 50 |
| Bahrain | 113,278 | 239,065 | 211 | 100 |
| Bangladesh | 124,268 | 27,070 | 22 | 0 |
| Barbados | 82,280 | 115,608 | 141 | 0 |
| Belize | 65,098 | 80,708 | 124 | 100 |
| Benin | 40,163 | 90,200 | 225 | 50 |
| Bhutan | 57,078 | 77,603 | 136 |  |
| Bolivia (Plurinational State of) | 50,568 | 20,283 | 40 |  |
| Botswana | 170,811 | 0 | 0 | 0 |
| Brunei Darussalam | 72,528 | 19,758 | 27 | 50 |
| Burkina Faso | 42,056 | 115,685 | 275 | 67 |
| Burundi | 63,471 | 144,834 | 228 | 100 |
| Cambodia | 52,094 | 103,548 | 199 | 100 |
| Cameroon | 53,580 | 88,932 | 166 | 100 |
| Cabo Verde | 34,250 | 115,972 | 339 | 100 |
| Central African Republic (the) | 60,000 | 0 | 0 | 0 |
| Chad | 42,520 | 129,981 | 306 | 100 |
| Chile | 81,961 | 19,029 | 23 | 0 |
| China | 2,221,810 | 1,912,411 | 86 | 0 |
| Colombia | 28,094 | 35,823 | 128 | 100 |
| Comoros (the) | 27,368 | 86,103 | 315 | 67 |
| Congo (the) | 60,400 | 62,800 | 104 | 50 |
| Cook Islands | 90,923 | 44,165 | 49 | 50 |
| Cote d’Ivoire | 136,835 | 416,000 | 304 | 67 |
| Democratic Republic of the Congo (the) | 56,447 | 85,300 | 151 | 100 |
| Djibouti | 47,689 | 152,069 | 319 | 67 |
| Dominica | 136,418 | 5,454 | 4 | 0 |
| Dominican Republic (the) | 129,205 | 151,833 | 118 | 100 |
| Ecuador | 38,609 | 12,884 | 33 |  |
| Egypt | 118,712 | 203,240 | 171 | 100 |
| El Salvador | 156,554 | 12,641 | 8 | 50 |
| Equatorial Guinea | 29,209 | 78,576 | 269 | 50 |
| Eritrea | 36,750 | 106,000 | 288 | 67 |
| Eswatini | 52,000 | 94,958 | 183 | 100 |
| Ethiopia | 124,500 | 90,000 | 72 | 100 |
| Fiji | 28,638 | 0 | 0 | 50 |
| Gabon | 19,500 | 50,000 | 256 | 50 |
| Gambia (the) | 70,750 | 100,000 | 141 | 100 |
| Grenada | 52,500 | 95,180 | 181 | 33 |
| Guatemala | 65,128 | 110,604 | 170 | 100 |
| Guinea | 76,250 | 212,070 | 278 |  |
| Guinea-Bissau | 26,500 | 73,000 | 275 | 67 |
| Guyana | 103,150 | 77,420 | 75 | 0 |
| Haiti | 135,110 | 148 | 0 | 0 |
| Honduras | 63,211 | 65,462 | 104 | 50 |
| India | 396,444 | 160,570 | 41 |  |
| Iran (Islamic Republic of) | 203,571 | 71,490 | 35 |  |
| Iraq | 361,229 | 657,387 | 182 | 100 |
| Jamaica | 27,500 | 0 | 0 | 0 |
| Kenya | 79,908 | 104,580 | 131 | 100 |
| Kiribati | 97,634 | 35,741 | 37 | 67 |
| Kuwait | 731,213 | 164,675 | 23 | 60 |
| Kyrgyzstan | 104,378 | 192,617 | 185 | 100 |
| Lao People's Democratic Republic (the) | 76,813 | 26,102 | 34 |  |
| Lesotho | 21,250 | 85,000 | 400 |  |
| Liberia | 18,838 | 57,793 | 307 | 50 |
| Madagascar | 46,000 | 91,100 | 198 | 50 |
| Malawi | 120,650 | 239,655 | 199 | 100 |
| Maldives | 78,032 | 100,384 | 129 | 100 |
| Mali | 44,940 | 67,800 | 151 | 33 |
| Marshall Islands (the) | 71,030 | 49,578 | 70 | 50 |
| Mauritania | 30,000 | 105,000 | 350 | 0 |
| Mauritius | 28,613 | 85,000 | 297 | 100 |
| Micronesia (Federated States of) | 100,621 | 58,572 | 58 | 50 |
| Mongolia | 70,991 | 71,713 | 101 | 100 |
| Mozambique | 72,465 | 161,247 | 223 | 33 |
| Myanmar | 104,759 | 26,873 | 26 | 0 |
| Namibia | 65,500 | 52,504 | 80 | 0 |
| Nauru | 90,016 | 18,627 | 21 | 67 |
| Nepal | 95,818 | 19,999 | 21 | 0 |
| Nicaragua | 66,560 | 31,799 | 48 | 100 |
| Niger (the) | 69,000 | 220,000 | 319 | 33 |
| Niue | 45,789 | 16,960 | 37 | 100 |
| Oman | 62,870 | 114,510 | 182 | 100 |
| Pakistan | 163,620 | 53,815 | 33 | 50 |
| Palau | 84,873 | 43,766 | 52 | 100 |
| Paraguay | 84,847 | 97,618 | 115 | 50 |
| Peru | 74,631 | 74,024 | 99 | 0 |
| Philippines (the) | 0 | 197,757 | Over |  |
| Qatar | 89,425 | 40,000 | 45 | 100 |
| Republic of Moldova (the) | 47,757 | 74,860 | 157 | 100 |
| Rwanda | 79,000 | 158,000 | 200 | 100 |
| Saint Kitts and Nevis | 83,700 | 58,813 | 70 | 0 |
| Saint Lucia | 72,335 | 81,397 | 113 | 67 |
| Saint Vincent and the Grenadines | 119,974 | 0 | 0 | 0 |
| Samoa | 67,220 | 51,000 | 76 | 100 |
| Sao Tome and Principe | 31,257 | 46,860 | 150 | 75 |
| Saudi Arabia | 488,009 | 157,450 | 32 | 25 |
| Senegal | 69,307 | 217,647 | 314 | 100 |
| Serbia | 15,573 | 15,358 | 99 | 100 |
| Seychelles | 34,754 | 85,014 | 245 | 100 |
| Sierra Leone | 53,233 | 124,724 | 234 | 75 |
| Solomon Islands | 127,007 | 65,977 | 52 | 0 |
| Somalia | 13,605 | 45,350 | 333 | 100 |
| South Sudan | 114,000 | 29,958 | 26 | 0 |
| Sri Lanka | 55,338 | 10,157 | 18 | 100 |
| Sudan (the) | 41,981 | 46,719 | 111 | 0 |
| Suriname | 94,400 | 2,020 | 2 | 0 |
| Syrian Arab Republic | 76,982 | 0 | 0 |  |
| Timor-Leste | 56,106 | 68,542 | 122 | 0 |
| Togo | 18,000 | 25,000 | 139 | 50 |
| Tonga | 101,337 | 21,620 | 21 | 50 |
| Tunisia | 27,300 | 91,000 | 333 | 100 |
| Tuvalu | 70,650 | 100,682 | 143 | 67 |
| Uganda | 78,318 | 155,300 | 198 | 100 |
| United Republic of Tanzania (the) | 55,500 | 50,000 | 90 | 50 |
| Vanuatu | 88,870 | 42,305 | 48 | 50 |
| Viet Nam | 50,518 | 41,488 | 82 | 100 |
| Yemen | 169,999 | 0 | 0 | 0 |
| Zambia | 71,000 | 100,000 | 141 | 100 |
| Zimbabwe | 100,100 | 127,000 | 127 | 100 |
| Region: ASP | 290,229 | 46,137 | 16 |  |
| Global | 8,828,205 | 6,653,635 | 75 | 100 |
| Grand total | 21,566,364 | 18,566,084 | 86 | 59 |

* For projects that were planned to be completed in 2021.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNEP

PER YEAR AS AT 31 DECEMBER 2021

# Table 1 of Annex II presents an overview of the status of project implementation by year.  All projects and activities approved between 1991 and 2009, and in 2011 and 2013 have now been completed.

Table 1. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 11 | 11 | 100 | 1,372,335 | 1,372,335 | 0 | 100 |
| 1992 | 15 | 15 | 100 | 1,711,000 | 1,711,000 | 0 | 100 |
| 1993 | 49 | 49 | 100 | 4,194,343 | 4,194,343 | 0 | 100 |
| 1994 | 58 | 58 | 100 | 4,231,169 | 4,231,169 | 0 | 100 |
| 1995 | 50 | 50 | 100 | 4,047,683 | 4,047,683 | 0 | 100 |
| 1996 | 47 | 47 | 100 | 3,366,039 | 3,366,039 | 0 | 100 |
| 1997 | 87 | 87 | 100 | 7,962,291 | 7,962,291 | 0 | 100 |
| 1998 | 64 | 64 | 100 | 4,669,124 | 4,669,124 | 0 | 100 |
| 1999 | 87 | 87 | 100 | 6,368,983 | 6,368,983 | 0 | 100 |
| 2000 | 85 | 85 | 100 | 6,300,398 | 6,300,398 | 0 | 100 |
| 2001 | 59 | 59 | 100 | 7,411,159 | 7,411,159 | 0 | 100 |
| 2002 | 72 | 72 | 100 | 9,469,401 | 9,469,401 | 0 | 100 |
| 2003 | 78 | 78 | 100 | 11,165,394 | 11,165,394 | 0 | 100 |
| 2004 | 99 | 99 | 100 | 12,362,652 | 12,362,652 | 0 | 100 |
| 2005 | 72 | 72 | 100 | 12,339,483 | 12,339,483 | 0 | 100 |
| 2006 | 108 | 108 | 100 | 12,731,484 | 12,731,484 | 0 | 100 |
| 2007 | 79 | 79 | 100 | 14,671,931 | 14,611,111 | 60,820 | 100 |
| 2008 | 132 | 132 | 100 | 17,875,070 | 17,875,070 | 0 | 100 |
| 2009 | 115 | 115 | 100 | 17,250,876 | 17,250,876 | 0 | 100 |
| 2010 | 79 | 78 | 99 | 14,361,124 | 14,288,901 | 72,224 | 99 |
| 2011 | 100 | 100 | 100 | 16,796,736 | 16,782,435 | 14,301 | 100 |
| 2012 | 80 | 75 | 94 | 16,211,080 | 15,648,751 | 562,329 | 97 |
| 2013 | 90 | 90 | 100 | 14,152,112 | 14,152,112 | 0 | 100 |
| 2014 | 74 | 71 | 96 | 12,368,311 | 12,109,041 | 259,270 | 98 |
| 2015 | 180 | 165 | 92 | 21,419,984 | 20,770,423 | 649,561 | 97 |
| 2016 | 96 | 85 | 89 | 19,751,863 | 18,328,917 | 1,422,946 | 93 |
| 2017 | 57 | 49 | 86 | 12,601,275 | 12,137,976 | 463,299 | 96 |
| 2018 | 126 | 103 | 82 | 20,241,323 | 16,677,336 | 3,563,988 | 82 |
| 2019 | 110 | 61 | 55 | 15,096,282 | 11,405,548 | 3,690,734 | 76 |
| 2020 | 134 | 30 | 22 | 17,920,690 | 8,080,769 | 9,839,921 | 45 |
| 2021 | 127 | 0 | 0 | 23,916,170 | 0 | 23,916,170 | 0 |
| Total | 2,620 | 2,274 | 87 | 364,337,763 | 319,822,202 | 44,515,561 | 88 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNEP

| Country/project code* | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Afghanistan AFG/PHA/85/TAS/27 | HCFC phase-out management plan (stage I, fourth tranche) | 0 | Challenging political situation | To request UNEP to submit a status report to the 92nd meeting on implementation progress including updates on the resumption of activities |
| Afghanistan AFG/PHA/85/TAS/29 | HCFC phase-out management plan (stage II, first tranche) | 0 |  |  |
| Afghanistan AFG/SEV/87/INS/31 | Extension of institutional strengthening project (phase X: 1/2022-12/2023) | 0 |  |  |
| Antigua and Barbuda ANT/SEV/73/INS/16 | Extension of institutional strengthening project (phase V: 1/2015-12/2016) | 0 | Project delayed due to delays in the submission of progress and financial reports | To request UNEP to submit a status report to the 92nd meeting on the status of submission of progress and financial reports |
| Antigua and Barbuda ANT/PHA/73/PRP/17 | Preparation of a HCFC phase-out management plan (stage II) | 100 | Stage II of the HPMP preparation delayed due to delays in the submission of survey results and other reports | To request UNEP to submit a status report to the 92nd meeting on the status of preparation of stage II of the HPMP |
| Bangladesh BGD/PHA/81/TAS/50 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 0 | 18 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Botswana BOT/PHA/82/TAS/22 | HCFC phase-out management plan (stage I, second tranche) | 50 | 12 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Brunei Darussalam BRU/PHA/82/TAS/24 | HCFC phase-out management plan (stage I, third tranche) | 15 | 12 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Cambodia KAM/PHA/84/TAS/38 | Verification report on the implementation of the HCFC phase-out management plan | 0 | 18 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Central African Republic (the) CAF/SEV/68/INS/23 | Extension of the institutional strengthening project (phase VI: 1/2013-12/2014) |  | Project completion delayed due to delays in the submission of progress and financial reports | To request UNEP to submit a status report to the 92nd meeting on the status of submission of progress and financial reports and completion of the project |
| Chile CHI/PHA/76/TAS/191 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 58 | 12 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Chile CHI/PHA/81/TAS/195 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 7 | 12 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Colombia COL/PHA/84/TAS/107 | HCFC phase-out management plan (stage II, third tranche) (technical assistance in policies formulation and implementation) | 0 | 18 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Dominica DMI/PHA/62/TAS/19 | HCFC phase-out management plan (stage I, first tranche) | 12 | (i) 12 months delays (ii) Project implementation delayed due to change in management of national ozone unit (NOU) resulting in delays in submitting progress and financial reports | (i) To request UNEP to report to the 92nd meeting on this project with implementation delays (ii) To request UNEP to submit a status report to the 92nd meeting on the status of submission of progress and financial reports |
| Dominica DMI/SEV/80/INS/23 | Additional emergency assistance for institutional strengthening | 0 | Delay in submitting final progress and financial reports | To request UNEP to submit a status report to the 92nd meeting on status of submission of final progress and financial reports |
| Dominica DMI/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 0 | (i) 18 months delays (ii) Delay in submitting final progress and financial reports | (i) To request UNEP to report to the 92nd meeting on this project with implementation delays (ii) To request UNEP to submit a status report to the 92nd meeting on the status of submission of final progress and financial reports |
| Dominica DMI/SEV/81/INS/24 | Extension of the institutional strengthening project (phase VII: 6/2018-5/2020) | 0 | Delay in project implementation and financial reports due to changes in project administrative rules | To request UNEP to submit a status report to the 92nd meeting on the status of submission of progress and financial reports |
| Dominica DMI/PHA/84/TAS/25 | HCFC phase-out management plan (stage I, second tranche) | 0 | (i) 18 months delays (ii) Project implementation delayed due to change in management of NOU resulting in delays in submitting progress and financial reports | (i) To request UNEP to report to the 92nd meeting on this project with implementation delays (ii) To request UNEP to submit a status report to the 92nd meeting on the status of submission of progress and financial reports |
| Dominica DMI/PHA/86/TAS/26 | Verification report on the implementation of stage I of the HCFC phase-out management plan | 0 | Delay in the preparation of the verification report due to delays in implementation of the HPMP | To request UNEP to submit a status report to the 92nd meeting on the status of preparation of verification reports |
| Grenada GRN/SEV/87/INS/27 | Extension of the institutional strengthening project (phase VII: 7/2021-6/2023) | 0 | Delay in the signing of the small-scale funding agreement (SSFA) for implementation of the project | To request UNEP to submit a status report to the 92nd meeting on the status of the signing of the SSFA and first disbursement |
| Iran (Islamic Republic of) IRA/PHA/84/TAS/234 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 0 | 18 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Kuwait KUW/PHA/66/TAS/19 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector and monitoring and verification) | 11 | 12 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Kuwait KUW/PHA/74/TAS/23 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector and monitoring and verification) | 22 | 12 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Mali MLI/PHA/83/TAS/40 | HCFC phase-out management plan (stage I, fourth tranche) | 48 | (i) 12 months delays (ii) Delay in project implementation due to security situation in the country | (i) To request UNEP to report to the 92nd meeting on this project with implementation delays (ii) To request UNEP to submit a status report to the 92nd meeting on implementation progress including updates on the resumption of activities |
| Mali MLI/PHA/84/PRP/42 | Preparation of a HCFC phase-out management plan (stage II) | 0 | Stage II of the HPMP preparation delayed due to security situation in the country | To request UNEP to submit a status report to the 92nd meeting on the status of preparation of stage II of the HPMP |
| Myanmar MYA/PHA/68/TAS/14 | HCFC phase-out management plan (stage I, first tranche) | 68 | (i) 12 months delays (ii) Challenging political situation | (i) To request UNEP to report to the 92nd meeting on this project with implementation delays (ii) To request UNEP to submit a status report to the 92nd meeting on implementation progress including updates on the resumption of activities |
| Myanmar MYA/PHA/80/TAS/18 | HCFC phase-out management plan (stage I, second tranche) | 10 |  |  |
| Myanmar MYA/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 38 | Challenging political situation | To request UNEP to submit a status report to the 92nd meeting on implementation progress including updates on the resumption of activities |
| Myanmar MYA/PHA/83/PRP/21 | Preparation of a HCFC phase-out management plan (stage II) | 51 |  |  |
| Myanmar MYA/SEV/84/INS/22 | Extension of institutional strengthening project (phase V: 7/2020-6/2022) | 26 |  |  |
| Myanmar MYA/PHA/86/TAS/23 | HCFC phase-out management plan (stage I, third tranche) | 0 |  |  |
| Myanmar MYA/PHA/86/TAS/24 | Verification report on the implementation of the HCFC phase-out management plan | 0 |  |  |
| Nauru NAU/PHA/74/TAS/10 | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Nauru) | 20 | 12 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Nepal NEP/PHA/75/TAS/34 | HCFC phase-out management plan (stage I, second tranche) | 71 | 12 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Pakistan PAK/PHA/83/TAS/101 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 10 | 12 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Peru PER/PHA/80/TAS/54 | HCFC phase-out management plan (stage II, first tranche) | 85 | 12 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Saint Kitts and Nevis STK/PHA/74/TAS/20 | HCFC phase-out management plan (stage I, second tranche) | 0 | (i) 12 and 18 months delays (ii) Delay in the submission of progress and financial reports | (i) To request UNEP to report to the 92nd meeting on this project with implementation delays (ii) To request UNEP to submit a status report to the 92nd meeting on the implementation progress and first disbursement |
| Saint Kitts and Nevis STK/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 0 | 18 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Saint Kitts and Nevis STK/PHA/82/TAS/22 | Verification report on the implementation of the HCFC phase-out management plan | 67 | (i) 12 months delays (ii) Delay in the preparation of the verification report due to delay in implementation of the HPMP | (i) To request UNEP to report to the 92nd meeting on this project with implementation delays (ii) To request UNEP to submit a status report to the 92nd meeting on the status of preparation of the verification report |
| Saint Lucia STL/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 0 | 18 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Saint Vincent and the Grenadines STV/PHA/75/TAS/23 | HCFC phase-out management plan (stage I, second tranche) | 52 | 12 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Saint Vincent and the Grenadines STV/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 0 | 18 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Saudi Arabia SAU/PHA/68/TAS/16 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | 77 | 12 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Saudi Arabia SAU/PHA/77/TAS/32 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring) | 42 | 12 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| South Sudan SSD/SEV/76/INS/03 | Institutional strengthening project (phase I: 5/2016-4/2018) | 0 | Delay in the signing of the SSFA due to administrative issues | To request UNEP to submit a status report to the 92nd meeting on the status of the signing of the SSFA and first disbursement |
| Suriname SUR/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 0 | 18 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |
| Suriname SUR/PHA/81/TAS/26 | HCFC phase-out management plan (stage I, third tranche) | 0 | 12 and 18 months delays | To request UNEP to report to the 92nd meeting on this project with implementation delays |

*Codes ending with “+” are from the additional contributions.

UNEP/OzL.Pro/ExCom/91/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database that is available upon request.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 91st meeting.

Ongoing projects are all projects that were under implementation as at 31 December 2021. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

In line with decision 84/12(b), a detailed progress report providing an overview of the objectives, status of implementation, key findings and lessons learned, the amounts of HFC phased out where applicable, the level of funds approved and disbursed and potential challenges in completing the projects and activities, is presented in the consolidated progress report (UNEP/OzL.Pro/ExCom/91/12).

All the controlled substances under these projects were ozone-depleting substances.

All the controlled substances under these projects were ozone-depleting substances.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/91/36

UNEP/OzL.Pro/ExCom/91/37

UNEP/OzL.Pro/ExCom/91/38

UNEP/OzL.Pro/ExCom/91/39

UNEP/OzL.Pro/ExCom/91/41

UNEP/OzL.Pro/ExCom/91/45

UNEP/OzL.Pro/ExCom/91/50

UNEP/OzL.Pro/ExCom/91/52

UNEP/OzL.Pro/ExCom/91/53

UNEP/OzL.Pro/ExCom/91/54

UNEP/OzL.Pro/ExCom/91/18

UNEP/OzL.Pro/ExCom/91/21

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.