| NACIONES UNIDAS |  | EP |
| --- | --- | --- |
|  | Programa de las Naciones Unidas para el Medio Ambiente | Distr. GENERAL UNEP/OzL.Pro/ExCom/95/23 25 de noviembre de 2024 ESPAÑOL ORIGINAL: INGLÉS |

COMITÉ EJECUTIVO DEL FONDO MULTILATERAL
 PARA LA APLICACIÓN DEL
 PROTOCOLO DE MONTREAL
Nonagésima quinta reunión

Montreal, 4 - 8 de diciembre de 2024

Punto 8 a) del orden del día provisional

INFORMACIÓN ACTUALIZADA SOBRE EL ESTADO DE EJECUCIÓN DEL PLAN ADMINISTRATIVO CONSOLIDADO DEL FONDO MULTILATERAL PARA 2024-2026

- Introducción

# En su 93a reunión, el Comité Ejecutivo avaló el plan administrativo consolidado del Fondo Multilateral para el período 2024–2026. En respuesta a la decisión 93/28, la Secretaría ajustó el plan administrativo consolidado correspondiente a 2024–2026 de la forma que se indica en el cuadro 1.

Cuadro 1. Asignación de recursos en el plan administrativo consolidado ajustado del Fondo Multilateral para el período 2024–2026 (USD)*

| Descripción | 2024 | 2025 | 2026 | Total |
| --- | --- | --- | --- | --- |
| Actividades relacionadas con los HCFC |  |  |  |  |
| Planes de gestión para la eliminación de HCFC (PGEH) aprobados | 48.499.466 | 50.384.491 | 50.158.180 | 149.042.137 |
| Planes de gestión para la eliminación de la producción de HCFC (PGEPH) aprobados | 23.232.000 | 0 | 0 | 23.232.000 |
| Etapa II del PGEH, preparación | 134.400 | 44.300 | 0 | 178.700 |
| Etapa II del PGEH | 4.970.041 | 6.870.087 | 10.870.876 | 22.711.004 |
| Etapa III del PGEH, preparación | 522.900 | 65.400 | 0 | 588.300 |
| Etapa III del PGEH | 15.849.471 | 10.765.760 | 23.015.282 | 49.630.513 |
| Etapa IV del PGEH, preparación | 70.000 | 0 | 0 | 70.000 |
| Etapa IV del PGEH | 0 | 0 | 3.691.000 | 3.691.000 |
| Verificación de los PGEH** | 588.600 | 588.600 | 588.600 | 1.765.800 |
| PGEH, eficiencia energética | 3.726.111 | 3.305.040 | 111.200 | 7.142.351 |
| Subtotal de actividades relacionadas con los HCFC | 97.592.989 | 72.023.678 | 88.435.138 | 258.051.805 |
| Actividades relacionadas con los HFC |  |  |  |  |
| Planes de aplicación de la Enmienda de Kigali relativa a los HFC (PAK) aprobados | 0 | 10.127.716 | 6.590.654 | 16.718.370 |
| Control de emisiones de HFC-23 aprobados | 414.238 | 626.900 | 572.433 | 1.613.571 |
| HFC, actividades de apoyo | 53.500 | 160.500 | 0 | 214.000 |
| HFC, asistencia técnica | 678.000 | 0 | 0 | 678.000 |
| HFC-23 | 8.000.000 | 0 | 0 | 8.000.000 |
| Etapa I del PAK | 11.458.349 | 27.565.521 | 6.378.667 | 45.402.537 |
| Etapa I del PAK, preparación de inversión | 32.100 | 0 | 0 | 32.100 |
| Etapa I del PAK, inversión | 3.712.616 | 0 | 0 | 3.712.616 |
| Etapa I del PAK, preparación | 2.891.415 | 1.167.771 | 211.280 | 4.270.466 |
| Subtotal de las actividades relacionadas con los HFC | 27.240.219 | 39.648.408 | 13.753.034 | 80.641.660 |
| Otras actividades |  |  |  |  |
| Proyectos piloto de eficiencia energética, demostración | 1.870.000 | 1.000.000 | 0 | 2.870.000 |
| Proyectos piloto de eficiencia energética, inversión | 4.789.988 | 248.600 | 0 | 5.038.588 |
| Proyectos piloto de eficiencia energética, preparación | 85.600 | 0 | 0 | 85.600 |
| Preparación bancos de SAO | 1.232.150 | 310.300 | 0 | 1.542.450 |
| Subtotal de las actividades relacionadas con los HFC | 7.977.738 | 1.558.900 | 0 | 9.536.638 |
| Actividades ordinarias |  |  |  |  |
| Fortalecimiento institucional | 22.071.008 | 1.830.362 | 21.294.756 | 45.196.125 |
| Programa de asistencia al cumplimiento | 11.765.667 | 12.113.777 | 12.310.330 | 36.189.774 |
| Unidad central | 6.611.529 | 6.653.609 | 6.095.985 | 19.361.122 |
| Costos de la Secretaría, del Comité Ejecutivo y de supervisión y evaluación menos la contraparte canadiense | 7.202.023 | 6.816.624 | 6.964.604 | 20.983.251 |
| Tesorería | 500.000 | 500.000 | 500.000 | 1.500.000 |
| Subtotal de las actividades ordinarias | 48.150.226 | 27.914.372 | 47.165.675 | 123.230.273 |
| Total general | 180.961.172 | 141.145.358 | 149.353.846 | 471.460.376 |
| Por organismos |  |  |  |  |
| Australia | 0 | 615.610 | 0 | 615.610 |
| Austria | 783.667 | 0 | 0 | 783.667 |
| Francia | 671.075 | 0 | 0 | 671.075 |
| Alemania | 7.500.449 | 2.148.339 | 5.834.901 | 15.483.689 |
| PNUD | 44.305.827 | 38.729.891 | 40.741.817 | 123.777.535 |
| PNUMA | 47.977.295 | 27.975.506 | 35.097.810 | 111.050.611 |
| ONUDI | 40.363.268 | 49.551.567 | 30.746.018 | 120.660.853 |
| Banco Mundial | 31.068.968 | 14.219.221 | 28.880.096 | 74.168.285 |
| Verificación de los PGEH** | 588.600 | 588.600 | 588.600 | 1.765.800 |
| Costos de la Secretaría, del Comité Ejecutivo y de supervisión y evaluación menos la contraparte canadiense | 7.202.023 | 6.816.624 | 6.964.604 | 20.983.251 |
| Tesorería | 500.000 | 500.000 | 500.000 | 1.500.000 |

* Incluidos los gastos de apoyo cuando corresponda

** El financiamiento para la preparación de informes de verificación de los PGEH de los países de bajo consumo se aprueba anualmente por el Comité Ejecutivo.

Estado de ejecución del plan administrativo de 2024

# La cuantía total del plan administrativo de 2024 asciende a USD 180.961.172. De esta cantidad, USD 61.332.446 fueron aprobados en la 94a reunión. Además, en la 95a reunión está previsto examinar actividades que ascienden a USD 124.178.563; si se aprobara el financiamiento de todas las propuestas de proyectos presentadas tal como se han comunicado, se excedería en USD 4.549.837 el presupuesto del plan administrativo de 2024, como se muestra en el cuadro 2.

Cuadro 2. Plan administrativo consolidado de 2024, aprobaciones de la 94a reunión, proyectos recomendados a la 95a reunión y saldo (USD)*

| Partidas presupuestarias | Monto total en el plan admin. | Aprobaciones de la 94a reunión | Actividades recomend. a la 95a reunión | Saldo (por encima)/por debajo |
| --- | --- | --- | --- | --- |
| Organismos bilaterales | 8.955.191 | 7.722.115 | 4.501.291 | (3.268.215) |
| PNUD | 44.305.827 | 16.932.440 | 22.592.547 | 4.780.840 |
| PNUMA | 47.977.295 | 12.910.251 | 34.033.332 | 1.033.712 |
| ONUDI | 40.363.268 | 23.196.140 | 27.767.338 | (10.600.210) |
| Banco Mundial | 31.068.968 | 0 | 27.582.032 | 3.486.936 |
| Verificación de los PGEH | 588.600 | 571.500 | 0 | 17.100 |
| Subtotal (organismos) | 173.259.149 | 61.332.446 | 116.476.540 | (4.549.837) |
| Secretaría/Comité Ejecutivo/Supervisión y evaluación (excluyendo la contraparte canadiense) | 7.202.023 | 0 | 7.202.023 | 0 |
| Tesorería | 500.000 | 0 | 500.000 | 0 |
| Subtotal (costos corrientes) | 7.702.023 | 0 | 7.702.023 | 0 |
| Total | 180.961.172 | 61.332.446 | 124.178.563 | (4.549.837) |

* Incluidos los costos de las unidades centrales

# El monto de las propuestas de proyectos recomendadas a la 95a reunión (USD 116.476.540) excede en USD 25.156.871 el contemplado en el plan administrativo de 2024 e incluye USD 15.899.209 asociados con propuestas de proyectos que no figuran en el plan administrativo de 2024.

# El monto de las actividades relacionadas con los HFC recomendadas a la 95a reunión asciende a USD 19.833.551, de los que USD 8.720.978 están asociados con propuestas de proyectos no incluidos en el plan administrativo de 2024. En el anexo I del presente documento figura una lista de los proyectos relacionados con los HFC presentados a la 95a reunión por los organismos bilaterales y de ejecución.

# El monto de los proyectos recomendados para la ventana de financiamiento para proyectos piloto de eficiencia energética de acuerdo con la decisión 91/65 es de USD 4.642.176. Teniendo en cuenta las aprobaciones de las reuniones 92a, 93a y 94a por un monto de USD 5.976.489 y las cuantías recomendadas a la 95a reunión, el remanente disponible de esta ventana de financiamiento es USD 9.381.335. En el anexo II del presente documento figura una lista de los proyectos piloto comunicados por los organismos bilaterales y de ejecución a la 95a reunión de acuerdo con la decisión 91/65.

# El monto de los proyectos recomendados para la ventana de financiamiento para eficiencia energética de conformidad con la decisión 94/60 es de USD 1.170.247 y el remanente disponible de esta ventana de financiamiento es de USD 98.829.753. En el anexo III del presente documento figura una lista de los proyectos comunicados por los organismos bilaterales y de ejecución a la 95a reunión de acuerdo con la decisión 94/60.

# El monto de los proyectos recomendados en el marco de la ventana de financiamiento para preparar inventarios nacionales de bancos de sustancias controladas de desecho de conformidad con la decisión 91/66 es USD 2.638.600, una cifra que incluye USD 2.446.500 que no figuran en el plan administrativo de 2024. En el anexo IV del presente documento figura una lista de las actividades de preparación de proyectos presentadas por los organismos bilaterales y de ejecución a la 95a reunión de acuerdo con la decisión 91/66.

# Compromisos futuros

# El monto total de los compromisos futuros para el periodo de 2024 a 2031 correspondientes a acuerdos plurianuales ya existentes es de USD 336.66 millones, asumiendo que las solicitudes de financiamiento de los acuerdos plurianuales presentadas a la 95a reunión se aprobarán en principio, tal como se indica en el cuadro 3.

Cuadro 3. Compromisos futuros (2024–2031) (en miles de USD)

| Descripción | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Aprobados en principio | 99.643 | 50.780 | 67.400 | 22.538 | 20.214 | 8.176 | 15.120 | 57 | 283.929 |
| Presentados a la 95a reunión | 22.866 | 0 | 0 | 24.773 | 139 | 2.367 | 2.583 | 0 | 52.729 |
| Total | 122.510 | 50.780 | 67.400 | 47.312 | 20.353 | 10.543 | 17.703 | 57 | 336.657 |

# Recomendación

# El Comité Ejecutivo podría desear tomar nota de:

## La información actualizada sobre la situación de ejecución del plan administrativo consolidado del Fondo Multilateral para el período 2024-2026 que figura en el documento UNEP/OzL.Pro/ExCom/95/23; y

## Que el monto total de las actividades recomendadas a la 95a reunión asciende a USD 116.476.540 (incluidos USD 19.833.551 destinados a actividades relacionadas con los HFC, USD 4.642.176 para proyectos piloto de eficiencia energética de acuerdo con la decisión 91/65, USD 1.170.247 para proyectos de eficiencia energética de acuerdo con la decisión 94/60 y USD 2.638.600 para la preparación de inventarios nacionales de bancos de sustancias controladas de desecho de acuerdo con la decisión 91/66), de los que USD 15.899.209 están asociados con propuestas de proyectos no incluidas en el plan administrativo de 2024.

Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 95TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Argentina | UNIDO | INV | KIP | Investment project to phase out R-410A in domestic air conditioner manufacturing sector in Argentina | 5,697,593 | 398,832 |
| Bahamas (the) | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 91,000 | 11,830 |
| Bahamas (the) | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 39,000 | 2,730 |
| Barbados | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 130,000 | 16,900 |
| Benin | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 117,500 | 15,275 |
| Benin | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 60,000 | 7,800 |
| Chad | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 141,000 | 18,330 |
| Chad | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 75,000 | 9,750 |
| China | UNDP | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 250,000 | 17,500 |
| Colombia | Germany | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 258,825 | 33,647 |
| Colombia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 1,066,225 | 74,636 |
| Colombia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (local installation and assembly subsector) | 341,100 | 23,877 |
| Colombia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (manufacturing sector) | 1,023,513 | 71,646 |
| Colombia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 124,148 | 8,690 |
| Cook Islands (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 23,250 | 3,023 |
| Costa Rica | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first trance) | 356,880 | 45,029 |
| Costa Rica | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first trance) (PMU) | 14,088 | 1,778 |
| Guatemala | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 10,000 | 1,300 |
| Guatemala | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 251,019 | 17,571 |
| Indonesia | IBRD | PRP | KIP | Preparation of a KIP investment project in the domestic and stand-alone commercial refrigerator manufacturing sector | 80,000 | 5,600 |
| Kiribati | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 15,000 | 1,950 |
| Lesotho | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 64,000 | 8,320 |
| Lesotho | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 18,000 | 2,340 |
| Marshall Islands (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 11,750 | 1,527 |
| Mauritius | Germany | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 103,000 | 13,390 |
| Micronesia (Federated States of) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 63,500 | 8,255 |
| Morocco | UNIDO | INV | KIP | Conversion of two production lines in one enterprise (MANAR) manufacturing domestic refrigeration equipment from HFC-134a to R-600a | 352,985 | 24,709 |
| Nauru | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 10,500 | 1,365 |
| Nigeria | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 1,902,050 | 133,144 |
| Nigeria | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 130,800 | 17,004 |
| Nigeria | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 705,510 | 49,386 |
| Niue | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 9,250 | 1,202 |
| Oman | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 160,000 | 20,800 |
| Oman | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 30,000 | 2,100 |
| Palau | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 57,500 | 7,475 |
| Rwanda | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 48,400 | 6,292 |
| Rwanda | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 27,500 | 3,575 |
| Samoa | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 66,000 | 8,580 |
| Senegal | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 168,000 | 21,840 |
| Senegal | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 127,500 | 8,925 |
| Solomon Islands | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 74,125 | 9,637 |
| Togo | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 117,500 | 15,275 |
| Togo | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 70,000 | 9,100 |
| Tonga | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 60,750 | 7,898 |
| Türkiye | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 845,445 | 59,181 |
| Türkiye | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 1,943,985 | 136,079 |
| Tuvalu | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 12,250 | 1,592 |
| Uruguay | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 126,927 | 16,500 |
| Uruguay | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 49,860 | 6,482 |
| Vanuatu | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 31,625 | 4,112 |
| Zimbabwe | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 90,000 | 11,700 |
| Zimbabwe | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 151,500 | 19,695 |
| Region: ASP | Australia | INV | KIP | Regional Kigali HFC implementation plan for Pacific Island Countries (stage I, first tranche) | 295,000 | 38,350 |
| Region: ASP | UNEP | TAS | KIP | Regional Kigali HFC implementation plan for Pacific Island Countries (stage I, first tranche) | 247,500 | 32,174 |

Annex II

Pilot projects for energy efficiency (decision 91/65) 
SUBMITTED TO THE 95TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| China | UNDP | INV | EEF | Pilot project to enhance the energy efficiency of cooling technologies in data centres through the demonstration of single-phase immersion cooling system in a data centre (decision 91/65) | 1,790,800 | 125,356 |
| Colombia | UNDP | TAS | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) | 506,319 | 35,442 |
| Costa Rica | UNDP | INV | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) | 260,000 | 18,200 |
| Honduras | UNIDO | INV | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) | 278,068 | 19,465 |
| Malaysia | IBRD | INV | EEF | Pilot project to enhance the energy efficiency of stand-alone commercial refrigeration equipment in Malaysia in the context of the HFC phase-down (investment and non-investment activities) (decisions 91/65) | 500,000 | 35,000 |
| Montenegro | UNIDO | TAS | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) | 120,000 | 10,800 |
| Peru | UNEP | TAS | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) | 115,000 | 14,950 |
| Uganda | United Kingdom of Great Britain and Northern Ireland | INV | EEF | Demonstration of energy-efficient ultra-low GWP technology in a supermarket (decision 91/65) | 435,200 | 56,576 |
| Uruguay | UNDP | INV | EEF | Pilot project to maintain and/or enhance the energy efficiency of technologies in the commercial refrigeration and residential AC sectors in the context of HFC phase-down (non-investment activities) (decision 91/65) | 300,000 | 21,000 |

Annex III

projects for energy efficiency PURSUANT TO decision 94/60
SUBMITTED TO THE 95TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Egypt | UNIDO | PRP | EEF | Preparation of a pilot project on energy efficiency (decision 94/60) | 210,000 | 14,700 |
| Malaysia | IBRD | INV | EEF | Pilot project to enhance the energy efficiency of stand-alone commercial refrigeration equipment in Malaysia in the context of the HFC phase-down (investment and non-investment activities) (decisions 94/60) | 415,689 | 29,098 |
| Nigeria | UNIDO | PRP | EEF | Preparation of a pilot project on energy efficiency (decision 94/60) | 78,000 | 5,460 |
| Thailand | IBRD | PRP | EEF | Preparation of a project for enhancing energy efficiency in manufacturing of light commercial air-conditioning (AC) systems in the context of HFC phase-down (decision 94/60) | 150,000 | 10,500 |
| Tunisia | UNIDO | PRP | EEF | Preparation of a pilot project on energy efficiency (decision 94/60) | 20,000 | 1,400 |
| Türkiye | UNIDO | PRP | EEF | Preparation of a pilot project on energy efficiency (decision 94/60) | 220,000 | 15,400 |

Annex IV

Project preparation for national inventories of banks 
of waste-controlled substances (decision 91/66) 
SUBMITTED TO THE 95TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Bahamas (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Bangladesh | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Bhutan | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Brunei Darussalam | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Congo (the) | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Cook Islands (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Eswatini | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Fiji | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Gambia (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Indonesia | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Kiribati | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Madagascar | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Maldives | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Marshall Islands (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Micronesia (Federated States of) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Mongolia | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Nauru | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Nepal | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Niue | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Palau | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Samoa | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Senegal | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Solomon Islands | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Sri Lanka | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Thailand | IBRD | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Timor-Leste | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Tonga | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Tuvalu | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Uganda | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Vanuatu | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |

UNEP/OzL.Pro/ExCom/95/1

Etapa I del PGEH de Bhután (PNUD y PNUMA); etapa II de los PGEH de las Islas Cook (PNUMA), Kiribati (PNUMA), las Islas Marshall (PNUMA), Micronesia (Estados Federados de) (PNUMA), Nauru (PNUMA), Niue (PNUMA), Palau (PNUMA), la región de los Países Insulares del Pacífico (Australia y PNUMA), Samoa (PNUMA), las Islas Salomón (PNUMA), Tonga (PNUMA), Tuvalu (PNUMA) y Vanuatu (PNUMA); etapa III de los PGEH de Chile (PNUD) y México (Alemania); una preparación de proyecto de la etapa II del PGEH de Dominica (ONUDI); tres actividades de preparación de proyectos de la etapa III de los PGEH de Angola (PNUD) y Bangladesh (PNUD y PNUMA); una preparación de proyecto de la etapa IV del PGEH de Nigeria (Alemania); un proyecto de inversión del PAK de la Argentina (ONUDI); una preparación de proyecto de inversión del PAK de Indonesia (Banco Mundial); cuatro preparaciones de proyecto de la etapa I de los PAK de las Bahamas (PNUMA y ONUDI), Barbados (PNUMA) y China (PNUD); etapa I de los PAK de Benin (PNUMA y ONUDI), el Chad (PNUMA y ONUDI), Guatemala (PNUMA y ONUDI), Mauricio (Alemania), la región de los Países Insulares del Pacífico (Australia y PNUMA), el Senegal (PNUMA y ONUDI) y el Uruguay (PNUD y ONUDI); 16 proyectos de eficiencia energética en el marco de la decisión 89/6 de Bhután (PNUMA), las Islas Cook (PNUMA), Kiribati (PNUMA), las Islas Marshall (PNUMA), Micronesia (Estados Federados de) (PNUMA), Nauru (PNUMA), Niue (PNUMA), Palau (PNUMA), la región de los Países Insulares del Pacífico (Australia y PNUMA), San Vicente y las Granadinas (PNUMA), Samoa (PNUMA), las Islas Salomón (PNUMA), Tonga (PNUMA), Tuvalu (PNUMA) y Vanuatu (PNUMA); y 28 actividades de preparación de proyectos relativos a los inventarios nacionales de bancos de sustancias controladas de desecho en el marco de la decisión 91/66 de las Bahamas (PNUMA), Bangladesh (ONUDI), Bhután (PNUMA), Brunei Darussalam (PNUMA), el Congo (ONUDI), las Islas Cook (PNUMA), Eswatini (PNUMA), Fiji (PNUMA), Gambia (PNUMA), Indonesia (PNUD), Kiribati (PNUMA), Madagascar (ONUDI), las Islas Marshall (PNUMA), Micronesia (Estados Federados de) (PNUMA), Mongolia (PNUMA), Nauru (PNUMA), Nepal (PNUMA), Niue (PNUMA), Palau (PNUMA), Samoa (PNUMA), el Senegal (Alemania), las Islas Salomón (PNUMA), Tailandia (Banco Mundial), Timor-Leste (PNUMA), Tonga (PNUMA), Tuvalu (PNUMA), Uganda (PNUMA) y Vanuatu (PNUMA).