UNEP/OzL.Pro/ExCom/95/23
Annex IV

UNEP/OzL.Pro/ExCom/95/23
Annex IV

UNEP/OzL.Pro/ExCom/95/23
Annex IV

	NACIONES
UNIDAS
	EP

	[image: UNEP][image: A black and white logo with a globe in center

Description automatically generated]
	
Programa de las
Naciones Unidas
para el Medio Ambiente

	
Distr.
GENERAL

UNEP/OzL.Pro/ExCom/95/23
25 de noviembre de 2024

ESPAÑOL 
ORIGINAL: INGLÉS


COMITÉ EJECUTIVO DEL FONDO MULTILATERAL
 PARA LA APLICACIÓN DEL
 PROTOCOLO DE MONTREAL
Nonagésima quinta reunión
Montreal, 4 - 8 de diciembre de 2024
Punto 8 a) del orden del día provisional[footnoteRef:1] [1:  UNEP/OzL.Pro/ExCom/95/1] 




INFORMACIÓN ACTUALIZADA SOBRE EL ESTADO DE EJECUCIÓN DEL PLAN ADMINISTRATIVO CONSOLIDADO DEL FONDO MULTILATERAL PARA 2024-2026
Introducción

En su 93a reunión, el Comité Ejecutivo avaló el plan administrativo consolidado del Fondo Multilateral para el período 2024–2026. En respuesta a la decisión 93/28, la Secretaría ajustó el plan administrativo consolidado correspondiente a 2024–2026 de la forma que se indica en el cuadro 1.
Cuadro 1. Asignación de recursos en el plan administrativo consolidado ajustado del Fondo Multilateral para el período 2024–2026 (USD)*
	Descripción 
	2024
	2025
	2026
	Total 

	Actividades relacionadas con los HCFC
	 
	 
	 
	 

	Planes de gestión para la eliminación de HCFC (PGEH) aprobados
	48.499.466
	50.384.491
	50.158.180
	149.042.137

	Planes de gestión para la eliminación de la producción de HCFC (PGEPH) aprobados
	23.232.000
	0
	0
	23.232.000

	Etapa II del PGEH, preparación 
	134.400
	44.300
	0
	178.700

	Etapa II del PGEH
	4.970.041
	6.870.087
	10.870.876
	22.711.004

	Etapa III del PGEH, preparación 
	522.900
	65.400
	0
	588.300

	Etapa III del PGEH
	15.849.471
	10.765.760
	23.015.282
	49.630.513

	Etapa IV del PGEH, preparación 
	70.000
	0
	0
	70.000

	Etapa IV del PGEH
	0
	0
	3.691.000
	3.691.000

	Verificación de los PGEH**
	588.600
	588.600
	588.600
	1.765.800

	PGEH, eficiencia energética
	3.726.111
	3.305.040
	111.200
	7.142.351

	Subtotal de actividades relacionadas con los HCFC
	97.592.989
	72.023.678
	88.435.138
	258.051.805

	Actividades relacionadas con los HFC
	 
	 
	 
	 

	Planes de aplicación de la Enmienda de Kigali relativa a los HFC (PAK) aprobados
	0
	10.127.716
	6.590.654
	16.718.370

	Control de emisiones de HFC-23 aprobados 
	414.238
	626.900
	572.433
	1.613.571

	HFC, actividades de apoyo
	53.500
	160.500
	0
	214.000

	HFC, asistencia técnica
	678.000
	0
	0
	678.000

	HFC-23 
	8.000.000
	0
	0
	8.000.000

	Etapa I del PAK
	11.458.349
	27.565.521
	6.378.667
	45.402.537

	Etapa I del PAK, preparación de inversión
	32.100
	0
	0
	32.100

	Etapa I del PAK, inversión 
	3.712.616
	0
	0
	3.712.616

	Etapa I del PAK, preparación
	2.891.415
	1.167.771
	211.280
	4.270.466

	Subtotal de las actividades relacionadas con los HFC
	27.240.219
	39.648.408
	13.753.034
	80.641.660

	Otras actividades
	 
	 
	 
	 

	Proyectos piloto de eficiencia energética, demostración 
	1.870.000
	1.000.000
	0
	2.870.000

	Proyectos piloto de eficiencia energética, inversión 
	4.789.988
	248.600
	0
	5.038.588

	Proyectos piloto de eficiencia energética, preparación 
	85.600
	0
	0
	85.600

	Preparación bancos de SAO
	1.232.150
	310.300
	0
	1.542.450

	Subtotal de las actividades relacionadas con los HFC
	7.977.738
	1.558.900
	0
	9.536.638

	Actividades ordinarias
	 
	 
	 
	 

	Fortalecimiento institucional
	22.071.008
	1.830.362
	21.294.756
	45.196.125

	Programa de asistencia al cumplimiento
	11.765.667
	12.113.777
	12.310.330
	36.189.774

	Unidad central
	6.611.529
	6.653.609
	6.095.985
	19.361.122

	Costos de la Secretaría, del Comité Ejecutivo y de supervisión y evaluación menos la contraparte canadiense
	7.202.023
	6.816.624
	6.964.604
	20.983.251

	Tesorería
	500.000
	500.000
	500.000
	1.500.000

	Subtotal de las actividades ordinarias
	48.150.226
	27.914.372
	47.165.675
	123.230.273

	Total general
	180.961.172
	141.145.358
	149.353.846
	471.460.376

	Por organismos
	 
	 
	 
	 

	Australia
	0
	615.610
	0
	615.610

	Austria
	783.667
	0
	0
	783.667

	Francia
	671.075
	0
	0
	671.075

	Alemania
	7.500.449
	2.148.339
	5.834.901
	15.483.689

	PNUD
	44.305.827
	38.729.891
	40.741.817
	123.777.535

	PNUMA
	47.977.295
	27.975.506
	35.097.810
	111.050.611

	ONUDI
	40.363.268
	49.551.567
	30.746.018
	120.660.853

	Banco Mundial
	31.068.968
	14.219.221
	28.880.096
	74.168.285

	Verificación de los PGEH**
	588.600
	588.600
	588.600
	1.765.800

	Costos de la Secretaría, del Comité Ejecutivo y de supervisión y evaluación menos la contraparte canadiense
	7.202.023
	6.816.624
	6.964.604
	20.983.251

	Tesorería
	500.000
	500.000
	500.000
	1.500.000


* Incluidos los gastos de apoyo cuando corresponda
** El financiamiento para la preparación de informes de verificación de los PGEH de los países de bajo consumo se aprueba anualmente por el Comité Ejecutivo.

Estado de ejecución del plan administrativo de 2024

La cuantía total del plan administrativo de 2024 asciende a USD 180.961.172. De esta cantidad, USD 61.332.446 fueron aprobados en la 94a reunión. Además, en la 95a reunión está previsto examinar actividades que ascienden a USD 124.178.563; si se aprobara el financiamiento de todas las propuestas de proyectos presentadas tal como se han comunicado, se excedería en USD 4.549.837 el presupuesto del plan administrativo de 2024, como se muestra en el cuadro 2. 
Cuadro 2. Plan administrativo consolidado de 2024, aprobaciones de la 94a reunión, proyectos recomendados a la 95a reunión y saldo (USD)*
	Partidas presupuestarias
	Monto total en el plan admin.
	Aprobaciones de la 94a reunión
	Actividades recomend. a la 95a reunión
	Saldo (por encima)/por debajo

	Organismos bilaterales
	8.955.191
	7.722.115
	4.501.291
	(3.268.215)

	PNUD
	44.305.827
	16.932.440
	22.592.547
	4.780.840

	PNUMA
	47.977.295
	12.910.251
	34.033.332
	1.033.712

	ONUDI
	40.363.268
	23.196.140
	27.767.338
	(10.600.210)

	Banco Mundial
	31.068.968
	0
	27.582.032
	3.486.936

	Verificación de los PGEH
	588.600
	571.500
	0
	17.100

	Subtotal (organismos)
	173.259.149
	61.332.446
	116.476.540
	(4.549.837)

	Secretaría/Comité Ejecutivo/Supervisión y evaluación (excluyendo la contraparte canadiense)
	7.202.023
	0
	7.202.023
	0

	Tesorería
	500.000
	0
	500.000
	0

	Subtotal (costos corrientes)
	7.702.023
	0
	7.702.023
	0

	Total
	180.961.172
	61.332.446
	124.178.563
	(4.549.837)


* Incluidos los costos de las unidades centrales

El monto de las propuestas de proyectos recomendadas a la 95a reunión (USD 116.476.540) excede en USD 25.156.871 el contemplado en el plan administrativo de 2024 e incluye USD 15.899.209 asociados con propuestas de proyectos que no figuran en el plan administrativo de 2024[footnoteRef:2].  [2:  Etapa I del PGEH de Bhután (PNUD y PNUMA); etapa II de los PGEH de las Islas Cook (PNUMA), Kiribati (PNUMA), las Islas Marshall (PNUMA), Micronesia (Estados Federados de) (PNUMA), Nauru (PNUMA), Niue (PNUMA), Palau (PNUMA), la región de los Países Insulares del Pacífico (Australia y PNUMA), Samoa (PNUMA), las Islas Salomón (PNUMA), Tonga (PNUMA), Tuvalu (PNUMA) y Vanuatu (PNUMA); etapa III de los PGEH de Chile (PNUD) y México (Alemania); una preparación de proyecto de la etapa II del PGEH de Dominica (ONUDI); tres actividades de preparación de proyectos de la etapa III de los PGEH de Angola (PNUD) y Bangladesh (PNUD y PNUMA); una preparación de proyecto de la etapa IV del PGEH de Nigeria (Alemania); un proyecto de inversión del PAK de la Argentina (ONUDI); una preparación de proyecto de inversión del PAK de Indonesia (Banco Mundial); cuatro preparaciones de proyecto de la etapa I de los PAK de las Bahamas (PNUMA y ONUDI), Barbados (PNUMA) y China (PNUD); etapa I de los PAK de Benin (PNUMA y ONUDI), el Chad (PNUMA y ONUDI), Guatemala (PNUMA y ONUDI), Mauricio (Alemania), la región de los Países Insulares del Pacífico (Australia y PNUMA), el Senegal (PNUMA y ONUDI) y el Uruguay (PNUD y ONUDI); 16 proyectos de eficiencia energética en el marco de la decisión 89/6 de Bhután (PNUMA), las Islas Cook (PNUMA), Kiribati (PNUMA), las Islas Marshall (PNUMA), Micronesia (Estados Federados de) (PNUMA), Nauru (PNUMA), Niue (PNUMA), Palau (PNUMA), la región de los Países Insulares del Pacífico (Australia y PNUMA), San Vicente y las Granadinas (PNUMA), Samoa (PNUMA), las Islas Salomón (PNUMA), Tonga (PNUMA), Tuvalu (PNUMA) y Vanuatu (PNUMA); y 28 actividades de preparación de proyectos relativos a los inventarios nacionales de bancos de sustancias controladas de desecho en el marco de la decisión 91/66 de las Bahamas (PNUMA), Bangladesh (ONUDI), Bhután (PNUMA), Brunei Darussalam (PNUMA), el Congo (ONUDI), las Islas Cook (PNUMA), Eswatini (PNUMA), Fiji (PNUMA), Gambia (PNUMA), Indonesia (PNUD), Kiribati (PNUMA), Madagascar (ONUDI), las Islas Marshall (PNUMA), Micronesia (Estados Federados de) (PNUMA), Mongolia (PNUMA), Nauru (PNUMA), Nepal (PNUMA), Niue (PNUMA), Palau (PNUMA), Samoa (PNUMA), el Senegal (Alemania), las Islas Salomón (PNUMA), Tailandia (Banco Mundial), Timor‑Leste (PNUMA), Tonga (PNUMA), Tuvalu (PNUMA), Uganda (PNUMA) y Vanuatu (PNUMA).] 

El monto de las actividades relacionadas con los HFC recomendadas a la 95a reunión asciende a USD 19.833.551, de los que USD 8.720.978 están asociados con propuestas de proyectos no incluidos en el plan administrativo de 2024. En el anexo I del presente documento figura una lista de los proyectos relacionados con los HFC presentados a la 95a reunión por los organismos bilaterales y de ejecución. 
El monto de los proyectos recomendados para la ventana de financiamiento para proyectos piloto de eficiencia energética de acuerdo con la decisión 91/65 es de USD 4.642.176. Teniendo en cuenta las aprobaciones de las reuniones 92a, 93a y 94a por un monto de USD 5.976.489 y las cuantías recomendadas a la 95a reunión, el remanente disponible de esta ventana de financiamiento es USD 9.381.335. En el anexo II del presente documento figura una lista de los proyectos piloto comunicados por los organismos bilaterales y de ejecución a la 95a reunión de acuerdo con la decisión 91/65. 
El monto de los proyectos recomendados para la ventana de financiamiento para eficiencia energética de conformidad con la decisión 94/60 es de USD 1.170.247 y el remanente disponible de esta ventana de financiamiento es de USD 98.829.753. En el anexo III del presente documento figura una lista de los proyectos comunicados por los organismos bilaterales y de ejecución a la 95a reunión de acuerdo con la decisión 94/60. 
El monto de los proyectos recomendados en el marco de la ventana de financiamiento para preparar inventarios nacionales de bancos de sustancias controladas de desecho de conformidad con la decisión 91/66 es USD 2.638.600, una cifra que incluye USD 2.446.500 que no figuran en el plan administrativo de 2024. En el anexo IV del presente documento figura una lista de las actividades de preparación de proyectos presentadas por los organismos bilaterales y de ejecución a la 95a reunión de acuerdo con la decisión 91/66.
Compromisos futuros
El monto total de los compromisos futuros para el periodo de 2024 a 2031 correspondientes a acuerdos plurianuales ya existentes es de USD 336.66 millones, asumiendo que las solicitudes de financiamiento de los acuerdos plurianuales presentadas a la 95a reunión se aprobarán en principio, tal como se indica en el cuadro 3.
Cuadro 3. Compromisos futuros (2024–2031) (en miles de USD)
	Descripción
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	2031
	Total

	Aprobados en principio
	99.643
	50.780
	67.400
	22.538
	20.214
	8.176
	15.120
	57
	283.929

	Presentados a la 95a reunión
	22.866
	0
	0
	24.773
	139
	2.367
	2.583
	0
	52.729

	Total 
	122.510
	50.780
	67.400
	47.312
	20.353
	10.543
	17.703
	57
	336.657



Recomendación 

El Comité Ejecutivo podría desear tomar nota de:
La información actualizada sobre la situación de ejecución del plan administrativo consolidado del Fondo Multilateral para el período 2024-2026 que figura en el documento UNEP/OzL.Pro/ExCom/95/23; y
Que el monto total de las actividades recomendadas a la 95a reunión asciende a USD 116.476.540 (incluidos USD 19.833.551 destinados a actividades relacionadas con los HFC, USD 4.642.176 para proyectos piloto de eficiencia energética de acuerdo con la decisión 91/65, USD 1.170.247 para proyectos de eficiencia energética de acuerdo con la decisión 94/60 y USD 2.638.600 para la preparación de inventarios nacionales de bancos de sustancias controladas de desecho de acuerdo con la decisión 91/66), de los que USD 15.899.209 están asociados con propuestas de proyectos no incluidas en el plan administrativo de 2024.
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Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 95TH MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Argentina
	UNIDO
	INV
	KIP
	Investment project to phase out R‑410A in domestic air conditioner manufacturing sector in Argentina
	5,697,593
	398,832

	Bahamas (the)
	UNEP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	91,000
	11,830

	Bahamas (the)
	UNIDO
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	39,000
	2,730

	Barbados
	UNEP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	130,000
	16,900

	Benin
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	117,500
	15,275

	Benin
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	60,000
	7,800

	Chad
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	141,000
	18,330

	Chad
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	75,000
	9,750

	China
	UNDP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	250,000
	17,500

	Colombia
	Germany
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	258,825
	33,647

	Colombia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	1,066,225
	74,636

	Colombia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (local installation and assembly subsector)
	341,100
	23,877

	Colombia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (manufacturing sector)
	1,023,513
	71,646

	Colombia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	124,148
	8,690

	Cook Islands (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	23,250
	3,023

	Costa Rica
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first trance)
	356,880
	45,029

	Costa Rica
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first trance) (PMU)
	14,088
	1,778

	Guatemala
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	10,000
	1,300

	Guatemala
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	251,019
	17,571

	Indonesia
	IBRD
	PRP
	KIP
	Preparation of a KIP investment project in the domestic and stand-alone commercial refrigerator manufacturing sector
	80,000
	5,600

	Kiribati
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	15,000
	1,950

	Lesotho
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	64,000
	8,320

	Lesotho
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	18,000
	2,340

	Marshall Islands (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	11,750
	1,527

	Mauritius
	Germany
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	103,000
	13,390

	Micronesia (Federated States of)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	63,500
	8,255

	Morocco
	UNIDO
	INV
	KIP
	Conversion of two production lines in one enterprise (MANAR) manufacturing domestic refrigeration equipment from HFC-134a to R-600a
	352,985
	24,709

	Nauru
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	10,500
	1,365

	Nigeria
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	1,902,050
	133,144

	Nigeria
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	130,800
	17,004

	Nigeria
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	705,510
	49,386

	Niue
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	9,250
	1,202

	Oman
	UNEP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	160,000
	20,800

	Oman
	UNIDO
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	30,000
	2,100

	Palau
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	57,500
	7,475

	Rwanda
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	48,400
	6,292

	Rwanda
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	27,500
	3,575

	Samoa
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	66,000
	8,580

	Senegal
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	168,000
	21,840

	Senegal
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	127,500
	8,925

	Solomon Islands
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	74,125
	9,637

	Togo
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	117,500
	15,275

	Togo
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	70,000
	9,100

	Tonga
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	60,750
	7,898

	Türkiye
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	845,445
	59,181

	Türkiye
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	1,943,985
	136,079

	Tuvalu
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	12,250
	1,592

	Uruguay
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	126,927
	16,500

	Uruguay
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	49,860
	6,482

	Vanuatu
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	31,625
	4,112

	Zimbabwe
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	90,000
	11,700

	Zimbabwe
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	151,500
	19,695

	Region: ASP
	Australia
	INV
	KIP
	Regional Kigali HFC implementation plan for Pacific Island Countries (stage I, first tranche)
	295,000
	38,350

	Region: ASP
	UNEP
	TAS
	KIP
	Regional Kigali HFC implementation plan for Pacific Island Countries (stage I, first tranche)
	247,500
	32,174





UNEP/OzL.Pro/ExCom/95/23
Annex I

UNEP/OzL.Pro/ExCom/95/23
Annex I

UNEP/OzL.Pro/ExCom/95/23
Annex I


2

2
Annex II

PILOT PROJECTS FOR ENERGY EFFICIENCY (DECISION 91/65) 
SUBMITTED TO THE 95TH MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	China
	UNDP
	INV
	EEF
	Pilot project to enhance the energy efficiency of cooling technologies in data centres through the demonstration of single-phase immersion cooling system in a data centre (decision 91/65)
	1,790,800
	125,356

	Colombia
	UNDP
	TAS
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	506,319
	35,442

	Costa Rica
	UNDP
	INV
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	260,000
	18,200

	Honduras
	UNIDO
	INV
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	278,068
	19,465

	Malaysia
	IBRD
	INV
	EEF
	Pilot project to enhance the energy efficiency of stand-alone commercial refrigeration equipment in Malaysia in the context of the HFC phase-down (investment and non-investment activities) (decisions 91/65)
	500,000
	35,000

	Montenegro
	UNIDO
	TAS
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	120,000
	10,800

	Peru
	UNEP
	TAS
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	115,000
	14,950

	Uganda
	United Kingdom of Great Britain and Northern Ireland
	INV
	EEF
	Demonstration of energy-efficient ultra‑low GWP technology in a supermarket (decision 91/65)
	435,200
	56,576

	Uruguay
	UNDP
	INV
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of technologies in the commercial refrigeration and residential AC sectors in the context of HFC phase-down (non-investment activities) (decision 91/65)
	300,000
	21,000
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Annex III

PROJECTS FOR ENERGY EFFICIENCY PURSUANT TO DECISION 94/60
SUBMITTED TO THE 95TH MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Egypt
	UNIDO
	PRP
	EEF
	Preparation of a pilot project on energy efficiency (decision 94/60)
	210,000
	14,700

	Malaysia
	IBRD
	INV
	EEF
	Pilot project to enhance the energy efficiency of stand-alone commercial refrigeration equipment in Malaysia in the context of the HFC phase-down (investment and non‑investment activities) (decisions 94/60)
	415,689
	29,098

	Nigeria
	UNIDO
	PRP
	EEF
	Preparation of a pilot project on energy efficiency (decision 94/60)
	78,000
	5,460

	Thailand
	IBRD
	PRP
	EEF
	Preparation of a project for enhancing energy efficiency in manufacturing of light commercial air-conditioning (AC) systems in the context of HFC phase-down (decision 94/60)
	150,000
	10,500

	Tunisia
	UNIDO
	PRP
	EEF
	Preparation of a pilot project on energy efficiency (decision 94/60)
	20,000
	1,400

	Türkiye
	UNIDO
	PRP
	EEF
	Preparation of a pilot project on energy efficiency (decision 94/60)
	220,000
	15,400
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Annex IV

PROJECT PREPARATION FOR NATIONAL INVENTORIES OF BANKS 
OF WASTE‑CONTROLLED SUBSTANCES (DECISION 91/66) 
SUBMITTED TO THE 95TH MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Bahamas (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Bangladesh
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Bhutan
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Brunei Darussalam
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Congo (the)
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Cook Islands (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Eswatini
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Fiji
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Gambia (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Indonesia
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Kiribati
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Madagascar
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Maldives
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Marshall Islands (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Micronesia (Federated States of)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Mongolia
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Nauru
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Nepal
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Niue
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Palau
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Samoa
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Senegal
	Germany
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Solomon Islands
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Sri Lanka
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Thailand
	IBRD
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Timor-Leste
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Tonga
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Tuvalu
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Uganda
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Vanuatu
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100
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