| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/99/17 29 October 2026 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-ninth Meeting

Montreal, 7–11 December 2026

Item 7(a)(v) of the provisional agenda

PROGRESS REPORT OF UNIDO as at 31 december 2025

Introduction

# This document presents the progress report of UNIDO as at 31 December 2025.

# The progress report of UNIDO includes the status of implementation of each ongoing project, reviewed by the Secretariat on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates reported in 2025, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in metric tonnes (mt) and CO2-eq tonnes.

# This document presents a summary of progress in implementation of projects for 2025 and cumulative since 1993 addressing all controlled substances, including Annex F substances (HFCs), under the Montreal Protocol for all projects approved under regular funding and additional voluntary contributions. It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee. As all projects approved under the additional voluntary contributions have been completed and the remaining balances will be returned to the Secretariat, the Secretariat will no longer report on these projects separately.

Progress in implementation of projects for 2025 and cumulative since 1993

# As of 31 December 2025, the Executive Committee had approved US $1.17 billion in projects for UNIDO, consisting of US $1.04 billion for the implementation of investment and non-investment projects, and US $135.53 million for agency support costs (excluding cancelled and transferred projects). Table 1 provides a summary of project implementation since inception through the end of 2025.

# Table 1. Project summary for UNIDO since the inception of the Multilateral Fund

| Items | Cumulative since 1993* |
| --- | --- |
| Number of approvals | 2,336 |
| Number of projects completed | 1,970 |
| Total funds approved (excluding support costs) (US $) | 1,036,830,515 |
| Total funds disbursed (excluding support costs) (US $) | 895,262,429 |
| Total approved phase-out (ODP tonnes)** | 86,379.4 |
| Total actual phase-out (ODP tonnes)** | 83,565.9 |
| Total approved phase-out (mt)*** | 6,490.7 |
| Total actual phase-out (mt)*** | 1,158.3 |
| Total approved phase-out (CO2-eq tonnes)*** | 13,570,921 |
| Total actual phase-out (CO2-eq tonnes)*** | 2,285,325 |

* Excluding cancelled and transferred projects.

** Including consumption and production.

*** For HFC-related projects only (including only consumption).

# In 2025, 117 new projects and activities were approved. This level of funding is expected to result in the phase-out of 86,379 ODP tonnes of consumption and production of ODS and 6,491 mt (13,570,921 CO2-eq tonnes) of consumption of HFCs. Annex I shows the status of project implementation per country in 2025.

# Table 2 shows the status of project implementation including fund disbursement per project cluster as at 31 December 2025. Annex II presents analytical information per year since 1993.

Table 2. Status of project implementation by cluster as at 31 December 2025*

| Clusters | Number of projects |  |  | Funding (US$)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Agency programme | 24 | 23 | 96 | 0 | 0 | 0 | 0 |
| CFC individual | 696 | 696 | 100 | 248,861,816 | 248,861,819 | -3 | 100 |
| CFC phase-out plans | 87 | 87 | 100 | 51,560,736 | 51,560,737 | -1 | 100 |
| CFC production phase-out plans | 4 | 4 | 100 | 31,849,298 | 31,849,298 | 0 | 100 |
| Disposal | 13 | 13 | 100 | 3,791,983 | 3,791,984 | -1 | 100 |
| Emission control 1 | 6 | 2 | 33 | 3,082,494 | 2,690,248 | 392,246 | 87 |
| Energy efficiency | 32 | 2 | 6 | 24,739,295 | 820,879 | 23,918,416 | 3 |
| Government support | 120 | 99 | 82 | 23,983,246 | 18,863,291 | 5,119,955 | 79 |
| HCFC individual | 260 | 243 | 93 | 23,409,236 | 22,974,296 | 434,940 | 98 |
| HCFC phase-out management plan (HPMP) stage I | 273 | 258 | 95 | 218,272,599 | 213,421,278 | 4,851,321 | 98 |
| HPMP stage II | 198 | 77 | 39 | 171,535,530 | 119,898,356 | 51,637,174 | 70 |
| HPMP stage III | 30 | 2 | 7 | 26,164,893 | 3,639,977 | 22,524,916 | 14 |
| HFC individual | 173 | 113 | 65 | 26,595,198 | 19,455,252 | 7,139,946 | 73 |
| Kigali HFC implementation plan (KIP) stage I | 72 | 3 | 4 | 27,816,150 | 2,529,147 | 25,287,003 | 9 |
| Other ODS individual | 234 | 234 | 100 | 60,539,415 | 60,539,411 | 4 | 100 |
| Other ODS production phase-out plans | 12 | 12 | 100 | 18,724,810 | 18,724,810 | 0 | 100 |
| Other ODS sector plans | 102 | 102 | 100 | 75,903,816 | 75,641,646 | 262,170 | 100 |
| Total | 2,336 | 1,970 | 84 | 1,036,830,515 | 895,262,429 | 141,568,086 | 86 |

* Excluding cancelled and transferred projects.

** Excluding agency support costs.

# Implementation of projects and activities by UNIDO for 2025 and cumulative since 1993 up to 31 December 2025 is summarized as follows:

## Phase-out: In 2025, 1,529.1 ODP tonnes of consumption of ODS and 143.8 mt (261,324 CO2-eq tonnes) of consumption of HFCs were phased out and an additional 466.3 ODP tonnes of consumption of ODS and 2,169.3 mt (4,497,089 CO2-eq tonnes) of consumption of HFCs were approved for phase-out. Since 1993, 65,838 ODP tonnes of consumption of ODS and 17,728 ODP tonnes of production of ODS had been phased out, of an expected total of 86,379 ODP tonnes of consumption and production of ODS and 1,158 mt (2,285,325 CO2-eq tonnes) of consumption of HFCs had been phased out, of an expected total of 6,491 mt (13,570,921 CO2-eq tonnes) of consumption of HFCs from projects approved (excluding cancelled and transferred projects). In addition, in 2025, 50 mt (739,303 CO2-eq tonnes) of HFC-23 by-product were destroyed. Since 2022, 364.1 mt (5,388,241 CO2-eq tonnes) had been destroyed of an expected total of 1,274.3 mt (18,858,948 CO2-eq tonnes) of HFC-23 by-product from approved projects;

## Disbursements/approvals: In 2025, US $33.6 million was disbursed, and US $18.78 million was planned for disbursement based on the 2024 progress report, representing a rate of disbursement of 179 per cent of that planned. Cumulatively, US $895.26 million had been disbursed out of the total US $1.04 billion approved for disbursement (excluding agency support costs), representing a rate of disbursement of 86 per cent. In 2025, US $68.48 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1993, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $12.19/kg and for all production sector activities (CFC and methyl bromide (MB)) was US $1.73/kg. The average cost-effectiveness of investment projects per ODP tonne was US $9.06/kg for completed projects and US $17.61/kg for ongoing projects;

## Number of projects completed: In 2025, 47 projects were completed. Since 1993, 1,970 projects of the 2,336 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 84 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2025 were completed on average 80 months after their approval. Since 1993, the average time for completion of investment projects has been 42 months after their approval. First disbursements under these projects occurred, on average, nine months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2025 were completed on average 35 months after their approval. Since 1993, the average time for completion of non-investment projects has been 37 months after their approval. First disbursements under these projects occurred, on average, nine months after they had been approved;

## Project preparation: Of the 692 project preparation activities approved by the end of 2025, 616 have been completed, leaving 76 ongoing activities. In 2025, 20 project preparation activities were completed;

## Implementation delays: A total of 366 projects were under implementation at the end of 2025, experiencing, on average, a delay of three months. Sixty-eight of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation, and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2025, two MYAs for the control and phase-out of HFC-23 emissions, 77 MYAs for HPMPs and 42 MYAs for KIPs were under implementation. Since 1993, 268 MYAs have been approved and 147 MYAs have been completed, representing a completion rate of 55 per cent.

# Table 3 summarizes progress made by UNIDO since 1993.

## Table 3. Progress made by UNIDO since 1993

| Phase-out achieved |  | HFC-23 by-product destroyed | Disburse- ment (US $) | Average CE (US $/kg) |  |  | Number of projects |  | Speed of delivery for completion (months) |  | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes* | CO2-eq tonnes** | CO2-eq tonnes *** |  | Consump- tion | Produc- tion | HFC-23 emissions | Approved | Compl- eted | Invest- ment | Non- investment |  | Appro-ved | Compl- eted |
| 83,566 | 2,285,325 | 5,388,241 | 895,262,429 | 12.19 | 1.73 | 8.47 | 2,336 | 1,970 | 42 | 37 | 3 | 268 | 147 |

* Consumption and production of ODS.

** HFC-related projects.

*** HFC-23 by-product destroyed as reported in the project proposal documents.

HFC-related projects

# As of 31 December 2025, the Executive Committee had approved 245 HFC-related projects (including five investment projects, 108 preparation activities, 60 technical assistance projects and 72 projects related to stage I of KIPs) amounting to US $54,411,348 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 4 to 8.

Table 4. HFC-related projects approved*

| Clusters | Number of projects |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| HFC individual – investment | 5 | 4 | 80 | 11,025,784 | 7,562,857 | 3,462,927 | 69 |
| HFC individual – preparation projects | 108 | 52 | 48 | 9,333,889 | 5,817,289 | 3,516,600 | 62 |
| HFC individual – technical assistance | 60 | 57 | 95 | 6,235,525 | 6,075,106 | 160,419 | 97 |
| KIP stage I | 72 | 3 | 4 | 27,816,150 | 2,529,147 | 25,287,003 | 9 |
| Total | 245 | 116 | 47 | 54,411,348 | 21,984,399 | 32,426,949 | 40 |

* Excluding cancelled and transferred projects.

** Excluding agency support costs.

Note: 6,491 mt (13,570,921 CO2-eq tonnes) of HFCs was approved for phase-out.

# As of the end of 2025, of the 245 projects, four investment projects, 52 preparation activities, 57 technical assistance projects and three projects related to stage I of KIPs have been completed, leaving 129 ongoing. The ongoing projects are at various stages of implementation.

# Of the total cumulative funding approved of US $54,411,348 (excluding agency support costs), US $21,984,399 has been disbursed, representing a disbursement rate of 40 per cent.

Energy-efficiency projects

# As of 31 December 2025, the Executive Committee had approved 32 energy-efficiency projects (including three preparation activities and 19 technical assistance pilot projects under the funding window pursuant to decision 91/65 and six preparation activities and four investment projects under the funding window pursuant to decision 94/60) amounting to US $24,739,295 (excluding agency support costs). A summary of the status of these projects is presented in table 5 and the respective data has already been included in paragraphs 4 to 8.

Table 5. Energy-efficiency projects approved*

| Type | Number of projects |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Pilot projects (decision 91/65) – project preparation | 3 | 0 | 0 | 90,000 | 12,658 | 77,342 | 14 |
| Pilot projects (decision 91/65) – technical assistance | 19 | 1 | 5 | 4,507,649 | 691,648 | 3,816,001 | 15 |
| Manufacturing (decision 94/60) – project preparation | 6 | 1 | 17 | 300,000 | 116,573 | 183,427 | 39 |
| Manufacturing (decision 94/60) – investment | 4 | 0 | 0 | 19,841,646 | 0 | 19,841,646 | 0 |
| Total | 32 | 2 | 6 | 24,739,295 | 820,879 | 23,918,416 | 3 |

* Excluding cancelled projects.

** Excluding agency support costs.

# As of the end of 2025, of the 32 projects, one technical assistance project pursuant to decision 91/65 and one preparation activity pursuant to decision 94/60 have been completed, leaving 30 ongoing. The ongoing projects are at various stages of implementation.

# Of the total cumulative funding approved of US $24,739,295 (excluding agency support costs), US $820,879 has been disbursed, representing a disbursement rate of 3 per cent.

Issues identified in project implementation in 2025

# Further to the review process, several issues were discussed and satisfactorily addressed, except for issues on 68 projects classified as projects with implementation delays (including 67 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); and one technical assistance project). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 100th meeting.

# In addition, issues have been identified regarding projects or tranches of MYAs for the phase-out of HCFCs; and preparation of a national inventory of banks of waste controlled substances and development of a national plan for the management of those substances (decision 91/66). These issues are also presented in annex III. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Details of progress in implementation of projects associated with the HPMPs for China (room air-conditioning manufacturing and heat pump water heaters, and extruded polystyrene foam sectors), Ethiopia, Gabon, Grenada, Iraq, North Macedonia, Qatar, Saudi Arabia, Serbia, and the United Republic of Tanzania, with the KIPs for Cameroon, the Congo, the Dominican Republic, and North Macedonia and reports on projects with specific reporting requirements associated with Argentina (HPMP), Nigeria (HPMP), and Senegal (HPMP) have been submitted to the 99th meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. Outstanding issues for the remaining ongoing projects not included in annex III to the present document, and requests for extension of dates of completion are addressed below.

# Of the 269 ongoing projects, excluding IS and project preparation, 159 projects have revised planned dates of completion since the 2024 progress report.

# In line with decision 95/12(b), UNIDO reported that the IS project for Serbia was delayed due to the political instability; the renewal request is expected to be submitted at the 101st meeting.

# In line with decision 82/11(b), UNIDO has requested the extension of the duration of three projects pursuant to decision 91/66, as shown in table 6.

Table 6. Projects pursuant to decision 91/66 for which an extension of the completion date has been requested

| Country/project code | Disburse-ment (%) | Activities requiring additional time | Original date of completion (mm-yy) | Date of completion requested (mm-yy) |
| --- | --- | --- | --- | --- |
| Preparation of a national inventory of banks of waste controlled substances and development of a national plan for the management of those substances (decision 91/66) |  |  |  |  |
| Bangladesh BGD/HFCIND/66/UNIDO/PRP/DES/95 | 0 | Validation and endorsement of the draft national action plan by the national ozone unit (NOU); completion of capacity-building and training activities | Dec-26 | Dec-27 |
| Iran (Islamic Republic of) IRN/HFCIND/273/UNIDO/PRP/DES/94 | 30 | Completion of data analysis, scenario-building and validation workshop with national stakeholders | Jun-26* | Mar-28 |
| Niger (the) NER/HFCIND/55/UNIDO/PRP/DES/94 | 7 | Finalization of recruitment of national consultant to undertake field survey; completion of data analysis and report preparation | Jun-26* | Dec-27 |

# *Date of completion had already been revised to March 2027 for the Islamic Republic of Iran and to December 2026 for the Niger (decision 97/13(b)(ii) and (iii)).

# Additionally, in line with decision 82/11(b), UNIDO has requested the extension of the duration of four energy-efficiency projects pursuant to decision 91/65 and 12 projects related to HPMPs, as shown in table 7.

Table 7. Projects for which an extension of the completion date has been requested

| Country/project code | Disburse-ment (%) | Activities requiring additional time |  | Original date of completion (mm-yy) | Date of completion requested (mm-yy) |
| --- | --- | --- | --- | --- | --- |
| Energy-efficiency strategy for the Kigali HFC implementation plan (decision 91/65) |  |  |  |  |  |
| Mexico MEX/EE/220/UNIDO/TAS/SRV/93 | 27 | Implementation of the energy consumption diagnostics and related assessments; review/update of the refrigeration and air-conditioning (RAC) standards and development of new standards for centralized cooling systems and chilled water systems | Dec-26 |  | Dec-27 |
| South Africa ZAF/EE/18/UNIDO/TAS/SRV/93 | 4 | Procurement of equipment following endorsement by the beneficiary hospital management; implementation of training activities | Dec-26 |  | Jun-27 |
| Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) |  |  |  |  |  |
| Montenegro MNE/EE/25/UNIDO/TAS/SRV/95 | 4 | Monitoring of the energy performance of the alternative-based equipment | Dec-26 |  | Dec-27 |
| Nigeria NGA/EE/169/UNIDO/TAS/SRV/93 | 49 | Update and enforcement of the refrigerator minimum energy performance standards and other relevant regulations | Dec-26 |  | Jun-27 |
| HCFC phase-out management plans |  |  |  |  |  |
| Mauritania (stage I, first tranche) MRT/HPMP1/29/UNIDO/INV/SRV/88 | 46 | Distribution of tools, equipment, and identifiers to the beneficiaries |  | Dec-24 | Dec-27 |
| Mauritania (stage I, second tranche) MRT/HPMP1/30/UNIDO/INV/SRV/91 | 34 | Completion of training for RAC technicians on hydrocarbon-based technologies and procurement and distribution of recovery and recycling equipment |  | Dec-25 | Dec-27 |
| Montenegro (stage II, first tranche) MNE/HPMP2/17/UNIDO/INV/SRV/85 | 83 | Distribution of R-290-based equipment to the vocational school and beneficiaries; finalization and dissemination of training materials; and completion of reporting activities |  | Jun-23 | Dec-27 |
| Montenegro (stage II, third tranche) MNE/HPMP2/26/UNIDO/INV/SRV/97 | 0 |  |  | Dec-26 | Dec-27 |
| Montenegro (stage II, second tranche) MNE/HPMP2/20/UNIDO/INV/SRV/91 | 32 | Implementation of upgraded national certification programme in coordination with the NOU, vocational institutions and national trainers |  | Dec-25 | Dec-27 |
| Nigeria (stage III, first tranche) (RAC manufacturing sector) NGA/HPMP3/164/UNIDO/INV/REF/91 | 68 | Procurement and distribution of equipment, capacity-building, and establishment of a technical group on low-global-warming-potential refrigerants |  | Dec-25 | Dec-27 |
| Nigeria (stage III, second tranche) (RAC manufacturing sector) NGA/HPMP3/170/UNIDO/INV/REF/94 | 6 |  |  | Dec-26 | Dec-27 |
| Sudan (the) (stage II, first tranche) (foam sector) SDN/HPMP2/38/UNIDO/INV/FOA/75 | 38 | Finalization of an on-site assessment report to determine the feasibility of resuming and completing the remaining activities; submission by UNIDO of an assessment and recommendation report to the Secretariat outlining options to resume implementation in light of the current conflict situation |  | Dec-20 | Dec-27 |
| Syrian Arab Republic (the) (stage I, first tranche) SYR/HPMP1/108/UNIDO/INV/SRV/86 | 23 | Procurement and delivery of equipment to end-users, including universities and local government institutions, and implementation of training activities |  | Dec-23 | Dec-27 |
| Syrian Arab Republic (the) (stage I, second tranche) (AC manufacturing sector) SYR/HPMP1/112/UNIDO/INV/AC/91 | 16 |  |  | Dec-25 | Dec-27 |
| Syrian Arab Republic (the) (stage I, second tranche) (PMU for the investment component) SYR/HPMP1/114/UNIDO/TAS/PMU/91 | 105 |  |  | Dec-25 | Dec-27 |
| Syrian Arab Republic (the) (stage I, second tranche) (polyurethane foam sector) SYR/HPMP1/113/UNIDO/INV/FOA/91 | 0 | Procurement and delivery of equipment to foam manufacturers and implementation of conversion activities |  | Dec-25 | Dec-27 |

# Gender mainstreaming

# UNIDO applies its internal framework (e.g., checklists, indicators) in conjunction with the Multilateral Fund’s policy in this area. All MYA stages and tranches submitted since the 94th meeting, covering approximately 30 countries, have included the mandatory component of the policy. While the overall impact is modest, reported results are tangible and show a positive trend over time.  For example, in the Niger, 20 of 100 technicians and 50 customs officers trained were women; in Tunisia, 16 of 95 certified trainers were women; in Ecuador’s “Women in RAC” training programme, eight of 40 technicians trained were women. In addition, scholarship programmes supporting women in RAC and mobile air-conditioning manufacturing sectors in countries such as Nigeria and South Africa resulted in greater participation of women in various Montreal Protocol-related activities. UNIDO has also noted that dedicated resources can play a catalytic role in increasing women’s participation, particularly in low-volume-consuming countries.

Risk management

# UNIDO systematically addresses project implementation risks and delays and develops action plans to address them. Each delay category is described in terms of its root cause, action taken, and preventive measures. Standing practices include front-loaded procurement processes with realistic clearance timelines; careful beneficiary selection combined with early and sustained industry engagement; the use of in-country project management units and missions where NOU capacity is limited; building relationships across institutions, rather than individuals, to withstand political transitions; the promotion of regional dialogue to address trade-bloc-related issues; the use of local sourcing options (e.g., system houses) to circumvent sanctions; and, in exceptional cases, escalation to UNIDO Legal and the Secretariat to identify feasible solutions.

Recommendation

# The Executive Committee may wish:

## To note the progress report of UNIDO as at 31 December 2025 contained in document UNEP/OzL.Pro/ExCom/99/17;

## To approve the extension of the completion dates of the preparation of a national inventory of banks of waste controlled substances and development of a national plan for the management of those substances (decision 91/66) for the countries listed below to allow completion of the remaining ongoing activities, as reflected in table 6 of document UNEP/OzL.Pro/ExCom/99/17:

### Bangladesh (BGD/HFCIND/66/UNIDO/PRP/DES/95) and the Niger (NER/HFCIND/55/UNIDO/PRP/DES/94), to December 2027;

### Iran (Islamic Republic of) (IRN/HFCIND/273/UNIDO/PRP/DES/94), to March 2028;

## To approve also the extension of the completion dates of the projects listed below to allow completion of the remaining ongoing activities, as reflected in table 7 of document UNEP/OzL.Pro/ExCom/99/17:

### Energy-efficiency strategies for the Kigali HFC implementation plans (decision 91/65) for:

#### Mexico (MEX/EE/220/UNIDO/TAS/SRV/93), to December 2027;

#### South Africa (ZAF/EE/18/UNIDO/TAS/SRV/93), to June 2027;

### Pilot projects to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) for:

Montenegro (MNE/EE/25/UNIDO/TAS/SRV/95), to December 2027;

Nigeria (NGA/EE/169/UNIDO/TAS/SRV/93), to June 2027;

### Projects related to HCFC phase-out management plans, to December 2027, for:

#### Mauritania (stage I, first tranche (MRT/HPMP1/29/UNIDO/INV/SRV/88) and stage I, second tranche (MRT/HPMP1/30/UNIDO/INV/SRV/91));

#### Montenegro (stage II, first tranche (MNE/HPMP2/17/UNIDO/INV/SRV/85), stage II, second tranche (MNE/HPMP2/20/UNIDO/INV/SRV/91) and stage II, third tranche (MNE/HPMP2/26/UNIDO/INV/SRV/97));

#### Nigeria (stage III, first tranche (RAC manufacturing sector) (NGA/HPMP3/164/UNIDO/INV/REF/91) and stage III, second tranche (RAC manufacturing sector) (NGA/HPMP3/170/UNIDO/INV/REF/94));

#### The Sudan (stage II, first tranche (foam sector) (SDN/HPMP2/38/UNIDO/INV/FOA/75));

#### The Syrian Arab Republic (stage I, first tranche (SYR/HPMP1/108/UNIDO/INV/SRV/86), stage I, second tranche (AC manufacturing sector) (SYR/HPMP1/112/UNIDO/INV/AC/91), stage I, second tranche (PMU for the investment component) (SYR/HPMP1/114/UNIDO/TAS/PMU/91) and stage I, second tranche (polyurethane foam sector) (SYR/HPMP1/113/UNIDO/INV/FOA/91)); and

## To approve also the recommendations related to ongoing projects with specific issues contained in annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNIDO

PER COUNTRY FOR 2025

# Table 1 of annex I presents the status of project implementation by country for 2025 in achieved phase-out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation by UNIDO for 2025

| Country | Phased out in 2025 (ODP tonnes) | Phased out in 2025 (CO2-eq tonnes)* | Estimated funds disbursed in 2025 (US$) | Funds disbursed in 2025 (US$) | Percentage of funds disbursed over estimation in 2025 | Percentage of planned projects completed in 2025** |
| --- | --- | --- | --- | --- | --- | --- |
| Afghanistan |  |  | 7 | 21,727 | 310,386 |  |
| Albania |  |  | 125,001 | 166,238 | 133 |  |
| Algeria | 11.1 | 0 | 185,003 | 623,792 | 337 | 100 |
| Argentina | 11.1 | 0 | 982,002 | 3,318,858 | 338 | 33 |
| Armenia | 0.0 | 0 | 116,000 | 131,819 | 114 | 100 |
| Bahamas (the) |  |  | 59,000 | 25,632 | 43 |  |
| Bahrain | 9.0 | 0 | 20,002 | 31,917 | 160 | 100 |
| Bangladesh |  |  | 10,000 | 0 | 0 |  |
| Benin |  |  | 195,001 | 77,918 | 40 |  |
| Bolivia (Plurinational State of) |  |  | 225,000 | 184,474 | 82 |  |
| Bosnia and Herzegovina | 0.6 | 0 | 147,000 | 221,016 | 150 | 100 |
| Botswana | 0.0 | 0 | 62,000 | 35,016 | 56 | 50 |
| Brazil | 0.0 | 0 | 232,700 | 259,496 | 112 | 100 |
| Brunei Darussalam | 0.9 | 0 | 6,000 | 4,409 | 73 | 100 |
| Burkina Faso |  |  | 70,700 | 206 | 0 |  |
| Burundi |  |  | 78,000 | 76,383 | 98 | 0 |
| Cameroon |  |  | 276,700 | 315,247 | 114 | 0 |
| Chad | 0.0 | 0 | 120,000 | 2,421 | 2 | 100 |
| Chile | 3.4 | 0 | 1 | 7,631 | 763,100 | 100 |
| China |  |  | 2,350,002 | 12,556,740 | 534 | 0 |
| Congo (the) |  |  | 148,000 | 122,261 | 83 |  |
| Côte d'Ivoire |  |  | 88,000 | 60,133 | 68 |  |
| Democratic People's Republic of Korea (the) |  |  | 2 | 0 | 0 |  |
| Dominica |  |  | 10,000 | 1,172 | 12 |  |
| Dominican Republic (the) |  |  | 25,000 | 39,435 | 158 |  |
| Ecuador |  |  | 401,500 | 471,945 | 118 |  |
| Egypt | 25.2 | 0 | 3,206,002 | 3,743,707 | 117 | 40 |
| Eritrea |  |  | 60,000 | 65,827 | 110 | 0 |
| Ethiopia |  |  | 36,000 | 14,950 | 42 | 0 |
| Gabon |  |  | 56,000 | 18,451 | 33 | 0 |
| Gambia (the) |  |  | 89,001 | 23,859 | 27 | 0 |
| Grenada | 0.1 | 0 | 51,000 | 39,986 | 78 | 100 |
| Guatemala |  |  | 210,100 | 148,627 | 71 |  |
| Guinea | 0.0 | 0 | 41,201 | 6,016 | 15 | 100 |
| Guinea-Bissau | 0.0 | 0 | 22,000 | 37,269 | 169 | 100 |
| Honduras |  |  | 215,000 | 100,982 | 47 |  |
| Iran (Islamic Republic of) | 0.0 | 0 | 125,000 | 94,639 | 76 | 33 |
| Iraq | 1,455.4 | 0 | 90,001 | 33,754 | 38 | 100 |
| Jordan | 0.0 | 211,513 | 437,005 | 213,511 | 49 | 50 |
| Kuwait |  |  | 50,000 | 10,106 | 20 |  |
| Lebanon |  |  | 1 | 0 | 0 |  |
| Lesotho | 0.0 | 0 | 16,000 | 14,603 | 91 | 100 |
| Liberia |  |  | 56,000 | 19,458 | 35 | 0 |
| Libya |  |  | 150,901 | 258,036 | 171 | 0 |
| Madagascar |  |  | 130,000 | 104,524 | 80 | 0 |
| Malawi |  |  | 65,000 | 8,863 | 14 |  |
| Mauritania |  |  | 27,000 | 64,642 | 239 | 0 |
| Mexico | 0.0 | 0 | 1,106,102 | 2,323,137 | 210 | 50 |
| Mongolia | 0.0 | 0 | 20,000 | 12,284 | 61 | 100 |
| Montenegro |  |  | 128,000 | 137,467 | 107 | 0 |
| Morocco | 0.0 | 0 | 297,000 | 401,140 | 135 |  |
| Mozambique |  |  | 2,001 | 0 | 0 |  |
| Namibia |  |  | 10,000 | 11,461 | 115 | 0 |
| Nicaragua | 1.4 | 28,498 | 9,503 | 10,017 | 105 |  |
| Niger (the) |  |  | 154,003 | 83,195 | 54 | 0 |
| Nigeria |  |  | 500,001 | 491,744 | 98 | 0 |
| North Macedonia | 0.5 | 0 | 250,000 | 282,904 | 113 | 100 |
| Oman |  |  | 90,000 | 127,759 | 142 | 0 |
| Pakistan | 8.2 | 0 | 730,005 | 811,827 | 111 | 33 |
| Philippines (the) |  |  | 24,200 | 3,882 | 16 |  |
| Qatar |  |  | 50,000 | 24,816 | 50 |  |
| Rwanda |  |  | 46,000 | 47,765 | 104 |  |
| Saint Lucia | 0.0 | 0 | 85,500 | 46,931 | 55 | 100 |
| Saint Vincent and the Grenadines |  |  | 20,000 | 14,000 | 70 | 0 |
| Saudi Arabia |  |  | 72,000 | 125,868 | 175 |  |
| Senegal |  |  | 23,901 | 15,201 | 64 | 0 |
| Serbia | 0.0 | 0 | 41,000 | 83,537 | 204 | 100 |
| Sierra Leone |  |  | 43,001 | 19,953 | 46 |  |
| Somalia |  |  | 155,501 | 170,185 | 109 |  |
| South Africa | 0.0 | 0 | 2,111,000 | 2,660,114 | 126 | 50 |
| Sudan (the) |  |  | 2 | 2,342 | 117,100 |  |
| Suriname |  |  | 29,000 | 40,647 | 140 |  |
| Syrian Arab Republic (the) |  |  | 85,001 | 30,630 | 36 |  |
| Togo |  |  | 89,000 | 79,082 | 89 |  |
| Tunisia | 0.0 | 0 | 407,000 | 378,566 | 93 | 100 |
| Türkiye | 0.0 | 0 | 680,000 | 778,915 | 115 | 50 |
| Turkmenistan | 2.2 | 21,313 | 283,002 | 374,821 | 132 | 100 |
| Uganda |  |  | 20,000 | 29,423 | 147 |  |
| United Republic of Tanzania (the) |  |  | 39,000 | 23,697 | 61 | 0 |
| Uruguay |  |  | 10,000 | 3,805 | 38 |  |
| Venezuela (Bolivarian Republic of) |  |  | 80,002 | 141,320 | 177 | 0 |
| Zambia |  |  | 22,002 | 30,958 | 141 | 0 |
| Grand total | 1,529.1 | 261,324 | 18,778,560 | 33,597,089 | 179 | 45 |

*143.8 mt (261,324 CO2-eq tonnes) in 2025 for HFC-related projects. In addition, in 2025, 50 mt (739,303 CO2-eq tonnes) of HFC-23 by-product were destroyed.

** For projects that were planned to be completed in 2025.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNIDO

PER YEAR AS AT 31 DECEMBER 2025

# Table 1 of annex II presents an overview of the status of project implementation by year. All projects and activities approved between 1993 and 2013, have now been completed.

Table 1. Status of project implementation by year*

| Year | Number of projects |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1993 | 22 | 22 | 100 | 11,815,540 | 11,815,540 | 0 | 100 |
| 1994 | 52 | 52 | 100 | 30,645,899 | 30,645,899 | 0 | 100 |
| 1995 | 59 | 59 | 100 | 24,813,052 | 24,813,052 | -1 | 100 |
| 1996 | 46 | 46 | 100 | 19,290,681 | 19,290,681 | 0 | 100 |
| 1997 | 130 | 130 | 100 | 41,563,710 | 41,563,711 | -1 | 100 |
| 1998 | 88 | 88 | 100 | 22,721,130 | 22,721,130 | 0 | 100 |
| 1999 | 123 | 123 | 100 | 33,648,962 | 33,648,962 | 0 | 100 |
| 2000 | 96 | 96 | 100 | 30,072,456 | 30,072,456 | 0 | 100 |
| 2001 | 119 | 119 | 100 | 24,691,911 | 24,691,912 | -1 | 100 |
| 2002 | 76 | 76 | 100 | 35,981,235 | 35,981,235 | 0 | 100 |
| 2003 | 49 | 49 | 100 | 29,985,308 | 29,985,308 | 0 | 100 |
| 2004 | 44 | 44 | 100 | 33,105,459 | 33,105,460 | -1 | 100 |
| 2005 | 74 | 74 | 100 | 52,000,040 | 52,000,038 | 2 | 100 |
| 2006 | 45 | 45 | 100 | 19,740,544 | 19,740,544 | 0 | 100 |
| 2007 | 42 | 42 | 100 | 24,186,740 | 24,186,740 | 0 | 100 |
| 2008 | 77 | 77 | 100 | 32,280,826 | 32,280,829 | -3 | 100 |
| 2009 | 70 | 70 | 100 | 15,343,761 | 15,081,588 | 262,173 | 98 |
| 2010 | 69 | 69 | 100 | 45,012,452 | 45,012,451 | 1 | 100 |
| 2011 | 71 | 71 | 100 | 76,523,376 | 76,523,379 | -3 | 100 |
| 2012 | 52 | 52 | 100 | 32,492,767 | 32,418,247 | 74,520 | 100 |
| 2013 | 37 | 37 | 100 | 31,089,943 | 31,089,943 | 0 | 100 |
| 2014 | 55 | 54 | 98 | 27,133,459 | 27,089,736 | 43,723 | 100 |
| 2015 | 83 | 80 | 96 | 34,672,752 | 32,463,003 | 2,209,749 | 94 |
| 2016 | 58 | 56 | 97 | 34,934,826 | 34,716,653 | 218,173 | 99 |
| 2017 | 49 | 47 | 96 | 18,491,629 | 18,058,499 | 433,130 | 98 |
| 2018 | 75 | 73 | 97 | 32,032,573 | 29,772,051 | 2,260,522 | 93 |
| 2019 | 67 | 59 | 88 | 19,073,008 | 15,879,287 | 3,193,721 | 83 |
| 2020 | 58 | 50 | 86 | 15,225,774 | 14,628,960 | 596,814 | 96 |
| 2021 | 73 | 53 | 73 | 22,900,535 | 20,205,232 | 2,695,303 | 88 |
| 2022 | 66 | 33 | 50 | 20,314,505 | 14,708,257 | 5,606,248 | 72 |
| 2023 | 101 | 20 | 20 | 30,655,606 | 11,789,483 | 18,866,123 | 38 |
| 2024 | 93 | 4 | 4 | 45,908,747 | 8,710,013 | 37,198,734 | 19 |
| 2025 | 117 | 0 | 0 | 68,481,310 | 572,150 | 67,909,160 | 1 |
| Total | 2,336 | 1,970 | 84 | 1,036,830,515 | 895,262,429 | 141,568,086 | 86 |

* Excluding closed and transferred projects.

** Excluding agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNIDO

| Country | Project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- | --- |
| Albania | ALB/KIP1/57/UNIDO/INV/SRV/93 | Kigali HFC implementation plan (stage I, first tranche) | 21 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Argentina | ARG/HPMP2/189/UNIDO/INV/FOA/84 | HCFC phase-out management plan (stage II, second tranche) (foam sector - management and monitoring) | 93 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Argentina | ARG/HPMP2/191/UNIDO/TAS/PMU/84 | HCFC phase-out management plan (stage II, second tranche) (monitoring and reporting of HCFC-22 production) | 6 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Argentina | ARG/HPMP2/192/UNIDO/INV/FOA/84 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | 37 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Argentina | ARG/HPMP2/193/UNIDO/TAS/SRV/84 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 72 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Argentina | ARG/EC1/198/UNIDO/INV/EMS/87 | Control and phase-out of HFC-23 emissions in production of HCFC-22 at FIASA (first tranche) | 86 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Argentina | ARG/HPMP2/200/UNIDO/INV/FOA/92 | HCFC phase-out management plan (stage II, third tranche) (PU foam manufacturing sector) | 27 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Argentina | ARG/HPMP2/201/UNIDO/TAS/PMU/92 | HCFC phase-out management plan (stage II, third tranche) (PMU) | 41 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Argentina | ARG/HPMP2/202/UNIDO/INV/SRV/92 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | 10 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Bahamas (the) | BHS/HPMP2/32/UNIDO/INV/SRV/90 | HCFC phase-out management plan (stage II, first tranche) | 19 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Benin | BEN/HPMP2/45/UNIDO/INV/SRV/90 | HCFC phase-out management plan (stage II, first tranche) | 39 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Benin | BEN/HPMP2/49/UNIDO/TAS/SRVEE/93 | HCFC phase-out management plan (stage II) (Additional activities to maintain and/or enhance energy efficiency under decision 89/6(b)) | 20 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Bolivia (Plurinational State of) | BOL/HPMP2/63/UNIDO/TAS/SRVEE/93 | HCFC phase-out management plan (stage II) (Additional activities to maintain energy efficiency in the refrigeration servicing sector (decision 89/6)) | 59 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Bolivia (Plurinational State of) | BOL/KIP1/65/UNIDO/INV/SRV/93 | Kigali HFC implementation plan (stage I, first tranche) | 36 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Botswana | BWA/HPMP2/28/UNIDO/INV/SRV/86 | HCFC phase-out management plan (stage II, first tranche) | 42 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Brazil | BRA/HPMP3/337/UNIDO/INV/SRV/94 | HCFC phase-out management plan (stage III, first tranche) | 1 | 18 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Cameroon | CMR/HPMP2/48/UNIDO/INV/SRV/88 | HCFC phase-out management plan (stage II, second tranche) | 56 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Cameroon | CMR/EE/55/UNIDO/TAS/SRV/94 | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) | 0 | 18 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Chad | TCD/HPMP2/40/UNIDO/INV/SRV/90 | HCFC phase-out management plan (stage II, first tranche) | 6 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Egypt | EGY/HPMP2/131/UNIDO/INV/FOA/79 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | 92 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Egypt | EGY/HPMP2/149/UNIDO/INV/AC/88 | HCFC phase-out management plan (stage II, third tranche) (residential air-conditioning manufacturing sector) | 90 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Egypt | EGY/HPMP2/151/UNIDO/INV/SRV/88 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector and project management unit) | 90 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Gambia (the) | GMB/HPMP2/50/UNIDO/INV/SRV/93 | HCFC phase-out management plan (stage II, second tranche) | 24 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Gambia (the) | GMB/HPMP2/52/UNIDO/TAS/SRVEE/93 | HCFC phase-out management plan (stage II) (Additional activities to maintain energy efficiency in the refrigeration servicing sector (decision 89/6)) | 0 | 12 and 18 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Guinea | GIN/HPMP2/45/UNIDO/INV/SRV/93 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Iran (Islamic Republic of) | IRN/HPMP2/226/UNIDO/INV/FOA/77 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 65 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Iran (Islamic Republic of) | IRN/HPMP2/237/UNIDO/INV/FOA/84 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | 7 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Iran (Islamic Republic of) | IRN/HPMP2/238/UNIDO/TAS/SRV/84 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 18 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Iran (Islamic Republic of) | IRN/HPMP2/244/UNIDO/INV/FOA/86 | HCFC phase-out management plan (stage II, third tranche) (foam sector) | 94 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Iran (Islamic Republic of) | IRN/HFCIND/273/UNIDO/PRP/DES/94 | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 30 | Slow progress in implementation | To request UNIDO to submit a status report to the 100th meeting on implementation progress |
| Iran (Islamic Republic of) | IRN/HPMP3/276/UNIDO/INV/SRV/96 | HCFC phase-out management plan (stage III, first tranche) | 0 | Slow progress in implementation | To request UNIDO to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Jordan | JOR/KIP1/117/UNIDO/INV/AC/93 | Kigali HFC implementation plan (stage I, first tranche) (residential air-conditioning) | 2 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Jordan | JOR/KIP1/118/UNIDO/INV/REF/93 | Kigali HFC implementation plan (stage I, first tranche) (domestic refrigeration) | 1 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Jordan | JOR/KIP1/119/UNIDO/INV/REF/93 | Kigali HFC implementation plan (stage I, first tranche) (commercial refrigeration) | 2 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Jordan | JOR/KIP1/120/UNIDO/INV/SRV/93 | Kigali HFC implementation plan (stage I, first tranche) (refrigeration servicing and technical assistance) | 3 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Jordan | JOR/KIP1/121/UNIDO/TAS/PMU/93 | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 77 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Jordan | JOR/KIP1/125/UNIDO/INV/REF/93 | Kigali HFC implementation plan (stage I, first tranche) (TA for adoption of low-GWP technology) | 44 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Kuwait | KWT/HPMP2/43/UNIDO/INV/SRV/88 | HCFC phase-out management plan (stage II, first tranche) | 19 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Libya | LBY/HPMP2/46/UNIDO/TAS/PMU/90 | HCFC phase-out management plan (stage II, first tranche) (PMU) | 68 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Libya | LBY/HPMP2/47/UNIDO/INV/SRV/90 | HCFC phase-out management plan (stage II, first tranche) (servicing sector) | 54 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Madagascar | MDG/HPMP2/37/UNIDO/INV/SRV/90 | HCFC phase-out management plan (stage II, first tranche) | 50 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Malawi | MWI/HPMP2/56/UNIDO/INV/SRV/92 | HCFC phase-out management plan (stage II, second tranche) | 26 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Mauritania | MRT/HPMP1/29/UNIDO/INV/SRV/88 | HCFC phase-out management plan (stage I, first tranche) | 46 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Mauritania | MRT/HPMP1/30/UNIDO/INV/SRV/91 | HCFC phase-out management plan (stage I, second tranche) | 34 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Mexico | MEX/KIP1/221/UNIDO/INV/SRV/93 | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 19 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Montenegro | MNE/HPMP2/17/UNIDO/INV/SRV/85 | HCFC phase-out management plan (stage II, first tranche) | 83 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Montenegro | MNE/HPMP2/20/UNIDO/INV/SRV/91 | HCFC phase-out management plan (stage II, second tranche) | 32 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Morocco | MAR/HPMP2/77/UNIDO/INV/SRV/88 | HCFC phase-out management plan (stage II, first tranche) | 86 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Morocco | MAR/HPMP2/79/UNIDO/INV/FOA/91 | HCFC phase-out management plan (stage II): Umbrella project to phase-out HCFC-141b contained in imported pre-blended polyols in the polyurethane foam sector | 41 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Niger (the) | NER/HPMP2/46/UNIDO/TAS/SRV/90 | HCFC phase-out management plan (stage II, first tranche) | 48 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Nigeria | NGA/HPMP3/164/UNIDO/INV/REF/91 | HCFC phase-out management plan (stage III, first tranche) (RAC manufacturing sector) | 68 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Oman | OMN/HPMP3/44/UNIDO/INV/SRV/88 | HCFC phase-out management plan (stage III, first tranche) | 60 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Oman | OMN/HPMP3/49/UNIDO/INV/SRV/93 | HCFC phase-out management plan (stage III, second tranche) | 61 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Pakistan | PAK/HPMP3/111/UNIDO/TAS/PMU/90 | HCFC phase-out management plan (stage III, first tranche) (PMU) | 38 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Pakistan | PAK/HPMP3/112/UNIDO/INV/SRV/90 | HCFC phase-out management plan (stage III, first tranche) (refrigeration servicing sector) | 51 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Philippines (the) | PHL/HPMP3/112/UNIDO/INV/SRV/93 | HCFC phase-out management plan (stage III, first tranche) | 5 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Saint Lucia | LCA/HPMP2/45/UNIDO/TAS/SRVEE/94 | HCFC phase-out management plan (stage II) (Additional activities to maintain energy efficiency in the refrigeration servicing sector (decision 89/6)) | 0 | 18 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Saint Lucia | LCA/KIP1/47/UNIDO/INV/SRV/94 | Kigali HFC implementation plan (stage I, first tranche) | 0 | 18 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Senegal | SEN/HPMP2/49/UNIDO/INV/SRV/88 | HCFC phase-out management plan (stage II, first tranche) | 75 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Sudan (the) | SDN/HPMP2/38/UNIDO/INV/FOA/75 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 38 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Sudan (the) | SDN/HPMP3/50/UNIDO/INV/SRV/88 | HCFC phase-out management plan (stage III, first tranche) | 3 | Slow progress in implementation | To request UNIDO to submit a status report to the 100th meeting on implementation progress and disbursement levels |
| Suriname | SUR/HPMP2/36/UNIDO/INV/SRV/93 | HCFC phase-out management plan (stage II, first tranche) | 54 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Syrian Arab Republic (the) | SYR/HPMP1/108/UNIDO/INV/SRV/86 | HCFC phase-out management plan (stage I, first tranche) | 23 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Syrian Arab Republic (the) | SYR/HPMP1/112/UNIDO/INV/AC/91 | HCFC phase-out management plan (stage I, second tranche) (AC manufacturing sector) | 16 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Syrian Arab Republic (the) | SYR/HPMP1/113/UNIDO/INV/FOA/91 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector) | 0 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Syrian Arab Republic (the) | SYR/HPMP1/114/UNIDO/TAS/PMU/91 | HCFC phase-out management plan (stage I, second tranche) (PMU for the investment component) | 105 | 12 months delays | Noting decision 77/8(j), to request UNIDO to report to the 100th meeting on this project with implementation delays |
| Tunisia | TUN/HPMP2/76/UNIDO/INV/SRV/84 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 95 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Tunisia | TUN/HPMP2/85/UNIDO/INV/SRV/92 | HCFC phase-out management plan (stage II, second tranche) | 36 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Tunisia | TUN/KIP1/87/UNIDO/INV/AC/94 | Kigali HFC implementation plan (stage I, first tranche) (residential RAC manufacturing sector) | 0 | 18 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Türkiye | TUR/HPMP1/111/UNIDO/INV/SRV/84 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing and monitoring) | 68 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |
| Venezuela (Bolivarian Republic of) | VEN/HPMP2/141/UNIDO/INV/SRV/93 | HCFC phase-out management plan (stage II, third tranche) | 72 | 12 months delays | To request UNIDO to report to the 100th meeting on this project with implementation delays |

UNEP/OzL.Pro/ExCom/99/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database, which is provided on the 99th meeting portal on the Multilateral Fund’s website, in the spreadsheet programme, Microsoft Excel.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 99th meeting.

UNIDO became an implementing agency in 1993.

Funded by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

Ongoing projects are all projects that were under implementation as at 31 December 2025. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

Phase-out of ODS is expressed in ODP tonnes and of HFCs in mt and CO2-eq tonnes.

Including 6,491 mt of HFC-related projects. Cost-effectiveness in CO2-eq. is not included due to the limited number of projects approved.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/99/45

UNEP/OzL.Pro/ExCom/99/52

UNEP/OzL.Pro/ExCom/99/53

UNEP/OzL.Pro/ExCom/99/54

UNEP/OzL.Pro/ExCom/99/57

UNEP/OzL.Pro/ExCom/99/65

UNEP/OzL.Pro/ExCom/99/68

UNEP/OzL.Pro/Excom/99/70

UNEP/OzL.Pro/ExCom/99/71

UNEP/OzL.Pro/ExCom/99/76

UNEP/OzL.Pro/Excom/99/44

UNEP/OzL.Pro/Excom/99/47

UNEP/OzL.Pro/Excom/99/50

UNEP/OzL.Pro/ExCom/99/65

UNEP/OzL.Pro/ExCom/99/19 or UNEP/OzL.Pro/ExCom/99/20

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The Executive Committee requested bilateral and implementing agencies to provide a brief report on key gender mainstreaming results achieved as part of their annual progress reports, as of 2023, on the basis of the information available to them (decision 90/48(d)).

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.