| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/97/14 7 November 2025 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-seventh Meeting

Montreal, 1-5 December 2025

Item 7(a)(iv) of the provisional agenda

PROGRESS REPORT OF UNEP AS AT 31 DECEMBER 2024

Introduction

# This document presents the progress report of UNEP as at 31 December 2024.

# The progress report of UNEP includes the status of implementation of projects, including HFC-related projects that have been funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2024, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in metric tonnes (mt) and CO2-eq tonnes.

# This document presents a summary of progress in implementation of projects for 2024 and cumulative since 1991 addressing all controlled substances, including Annex F substances (HFCs), under the Montreal Protocol for all projects approved under regular funding and additional voluntary contributions. It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee. As all projects approved under the additional voluntary contributions have been completed and the remaining balances will be returned to the Secretariat, the Secretariat will no longer report on these projects separately.

Progress in implementation of projects for 2024 and cumulative since 1991

# As of 31 December 2024, the Executive Committee had approved US $498.34 million in projects for UNEP, consisting of US $460.84 million for the implementation of investment and non-investment projects, and US $37.51 million for agency support costs, as shown in table 1.

# Table 1. Approved funding by sector for UNEP as at 31 December 2024

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 882,689 |
| Destruction | 4,090,040 |
| Energy efficiency | 3,510,000 |
| Halon | 767,640 |
| HFC phase-down plan | 10,226,124 |
| Fumigants | 2,614,366 |
| Phase-out plan | 93,199,042 |
| Refrigeration | 13,856,016 |
| Several | 331,492,381 |
| Solvents | 198,860 |
| Sub-total | 460,837,158 |
| Agency support costs | 37,507,755 |
| Total | 498,344,913 |

# In 2024, 216 new projects and activities were approved. This level of funding is expected to result in the phase-out of 2,686 ODP tonnes of consumption of ODS and 705.9 mt (1,436,090 CO2-eq tonnes) of consumption of HFCs. Annex I shows the status of project implementation per country in 2024.

# Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2024. Annex II presents analytical information per year since 1991.

Table 2. Status of project implementation by type as at 31 December 2024

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 94 | 94 | 100 | 2,946,574 | 2,946,574 | 0 | 100 |
| Demonstration | 4 | 3 | 75 | 778,845 | 596,651 | 182,194 | 77 |
| Institutional strengthening (IS) | 1,056 | 948 | 90 | 100,252,858 | 80,620,586 | 19,632,272 | 80 |
| Investment | 6 | 3 | 50 | 722,750 | 549,000 | 173,750 | 76 |
| Project preparation | 373 | 279 | 75 | 20,758,644 | 14,056,041 | 6,702,603 | 68 |
| Technical assistance | 1,405 | 1,172 | 83 | 321,084,929 | 276,406,807 | 44,678,122 | 86 |
| Training | 196 | 196 | 100 | 14,292,557 | 14,292,557 | 0 | 100 |
| Total | 3,134 | 2,695 | 86 | 460,837,158 | 389,468,217 | 71,368,942 | 85 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

# Implementation of projects and activities by UNEP for 2024 and cumulative since 1991 up to 31 December 2024, is summarized as follows:

## Phase-out: In 2024, 119.2 ODP tonnes of consumption of ODS and 7.7 mt (19,893 CO2-eq tonnes) of consumption of HFCs were phased out and an additional 177.7 ODP tonnes of consumption of ODS and 357.7 mt (757,172 CO2-eq tonnes) of consumption of HFCs were approved for phase-out. Since 1991, 2,263 ODP tonnes of consumption of ODS had been phased out, of an expected total of 2,686 ODP tonnes of consumption of ODS and 7.7 mt (19,893 CO2-eq tonnes) of consumption of HFCs had been phased out, of an expected total of 705.9 mt (1,436,090 CO2-eq tonnes) of consumption of HFCs from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2024, US $23.8 million was disbursed and US $23.7 million was planned for disbursement based on the 2023 progress report, representing a rate of disbursement of 100 per cent of that planned. Cumulatively, US $389.47 million had been disbursed out of the total US $460.84 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 85 per cent. In 2024, US $43.76 million was approved for implementation;

## Number of projects completed: In 2024, 101 projects were completed. Since 1991, 2,695 projects of the 3,134 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 86 per cent;

## Speed of delivery – non-investment projects: Projects that were completed in 2024 were completed on average 40 months after their approval. Since 1991, the average time for completion of non-investment projects has been 37 months after their approval. First disbursements under these projects occurred, on average, 12 months after they had been approved;

## Project preparation: Of the 373 project preparation activities approved by the end of 2024, 279 have been completed, leaving 94 ongoing activities. In 2024, 19 project preparation activities were completed;

## Implementation delays: A total of 439 projects were under implementation at the end of 2024, experiencing, on average, a delay of six months. Thirty-one of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2024, 92 MYAs for HCFC phase-out management plans (HPMPs) and 46 Kigali HFC implementation plans (KIPs) were under implementation. Since 1991, 311 MYAs have been approved and 173 MYAs have been completed, representing a completion rate of 56 per cent.

# Table 3 summarizes progress made by UNEP since 1991.

## Table 3. Progress made by UNEP since 1991

| Phase out achieved |  | Disbursement (US $) | Number of projects |  | Speed of delivery for completion for non-investment projects (months) | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes* | CO2-eq tonnes** |  | Approved | Completed |  |  | Approved | Completed |
| 2,263 | 19,893 | 389,468,217 | 3,134 | 2,695 | 37 | 6 | 311 | 173 |

*Consumption of ODS.

** HFC-related projects.

HFC-related projects

# As of 31 December 2024, the Executive Committee had approved 210 HFC-related projects (including one demonstration project, 62 project preparation activities and 147 technical assistance projects) amounting to US $20,545,933 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9.

Table 4. HFC-related projects approved

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Demonstration | 1 | 0 | 0 | 206,000 | 53,806 | 152,194 | 26 |
| Project preparation | 62 | 29 | 47 | 6,612,223 | 3,927,100 | 2,685,123 | 59 |
| Technical assistance** | 147 | 94 | 64 | 13,727,710 | 9,792,886 | 3,934,824 | 71 |
| Total | 210 | 123 | 59 | 20,545,933 | 13,773,792 | 6,772,141 | 67 |

* Excludes agency support costs.

** 705.9 mt (1,436,090 CO2-eq tonnes) of HFCs was approved for phase-out.

# As of the end of 2024, of the 210 projects, 29 project preparation activities and 94 technical assistance projects have been completed, leaving 87 ongoing. Ninety-three of the 147 technical assistance projects are for enabling activities and have been completed. The remaining ongoing activities are at various stages of implementation.

# Of the total cumulative funding approved of US $20,545,933 (excluding agency support costs), US $13,773,792 had been disbursed, representing a disbursement rate of 67 per cent.

Issues identified in project implementation in 2024

# Further to the review process, several issues were discussed and satisfactorily addressed, except for issues on 31 projects classified as projects with implementation delays (including 19 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); 11 technical assistance projects; and one project for additional activities to maintain energy efficiency for the servicing sector under decision 89/6(b)). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 98th meeting.

# In addition, issues have been identified regarding tranches of MYAs for the phase-out of HCFCs; renewal of IS projects; and preparation of HPMPs. These issues are also presented in annex III. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Details of progress in implementation of projects associated with the HPMPs for Brunei Darussalam, Cambodia, Chad, China (servicing), Djibouti, Egypt, Madagascar, Mali, Mauritania, Oman, Peru, Saint Vincent and the Grenadines, Senegal, South Sudan, and Tunisia, with the KIPs for Mexico and the Niger, and reports on projects with specific reporting requirements associated with Armenia, Bahrain and Qatar (HPMP) and Kyrgyzstan (additional activities to maintain energy efficiency for the servicing sector under decision 89/6(b)), have been submitted to the 97th meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. Outstanding issues for the remaining ongoing projects not included in annex III to the present document, and requests for extension of dates of completion are addressed below.

# Of the 237 ongoing projects, excluding IS and project preparation, 54 projects have revised planned dates of completion since the 2023 progress report.

# In line with decision 95/12(b), the Secretariat noted that renewal requests of IS projects had not been submitted for the last three years for six Article 5 countries namely, Algeria, Grenada, Myanmar, Nauru, Peru, and Saint Vincent and the Grenadines. The primary reasons for non-submission included administrative challenges, such as delays in national approval processes for IS project implementation, political instability and security situation, and large remaining balances from previously approved stages of IS projects. UNEP reported that it has been actively supporting these countries and plans to submit these renewal requests by 2026, except for Myanmar, where submission is subject to the country’s political situation and the resumption of activities.

# At its 95th meeting, in approving the second tranche of stage II of the HPMP for Uganda, the Executive Committee noted that UNEP would submit a report on the status of implementation of regulations to prohibit import and sale of HCFC-based equipment as part of its 2024 financial and progress report to be submitted at the second meeting of 2025. UNEP has confirmed that, effective July 2025, the import and sale of HCFC-based equipment are prohibited in the country. To support enforcement of these regulations, awareness-raising and training activities were conducted.

# In line with decision 82/11(b), UNEP has requested the extension of the duration of 16 projects, as shown in table 5.

Table 5. Projects for which an extension of the completion dates has been requested

| Country/project code | Disburs-ement (%) | Activities requiring additional time | Original date of completion | Date of completion requested |
| --- | --- | --- | --- | --- |
| Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) |  |  |  |  |
| Armenia ARM/DES/93/PRP/29 | 39 | Completion of data survey and analysis, and report preparation | Dec-25 | Jun-26 |
| Belize BZE/DES/94/PRP/46 | 0 | Recruitment of expert, completion of data survey and analysis, and report preparation | Jun-26 | Jun-27 |
| Bolivia (Plurinational State of) BOL/DES/93/PRP/57 | 0 | Recruitment of national consultant, completion of data survey and analysis, and report preparation | Dec-25 | Jun-26 |
| Cambodia KAM/DES/94/PRP/47 | 0 | Completion of data survey and analysis, and report preparation | Jun-26 | Jun-27 |
| Costa Rica COS/DES/93/PRP/68 | 5 | Recruitment of national consultant, completion of data survey and analysis, and report preparation | Dec-25 | Dec-26 |
| Dominican Republic (the) DOM/DES/93/PRP/77 | 2 | Recruitment of national expert, completion of data survey and analysis, and report preparation | Dec-25 | Dec-26 |
| El Salvador ELS/DES/93/PRP/47 | 6 | Completion of data survey and analysis, and report preparation | Dec-25 | Dec-26 |
| Grenada GRN/DES/94/PRP/37 | 0 | Recruitment of national and international experts, completion of data survey and analysis, and report preparation | Jun-26 | Jun-27 |
| Guatemala GUA/DES/93/PRP/64 | 0 | Completion of data survey and analysis, and report preparation | Dec-25 | Jun-26 |
| Guyana GUY/DES/94/PRP/40 | 0 | Recruitment of national and international experts, completion of data survey and analysis, and report preparation | Jun-26 | Jun-27 |
| Honduras HON/DES/93/PRP/61 | 7 | Completion of data survey and analysis, and report preparation | Dec-25 | Jun-26 |
| Paraguay PAR/DES/94/PRP/49 | 6 | Recruitment of national consultant, completion of data survey and analysis, and report preparation | Jun-26 | Dec-26 |
| Republic of Moldova (the) MOL/DES/93/PRP/48 | 30 | Completion of data survey and analysis, and report preparation | Dec-25 | Jun-26 |
| Saint Lucia STL/DES/94/PRP/41 | 0 | Completion of data survey and analysis, and report preparation | Jun-26 | Dec-26 |
| Somalia SOM/DES/94/PRP/21 | 0 | Completion of data survey and analysis, and report preparation | Jun-26 | Dec-26 |
| Yemen YEM/DES/93/PRP/48 | 2 | Completion of data survey and analysis, and report preparation | Dec-25 | Jun-26 |

Gender mainstreaming

# UNEP remains committed to promoting gender equality and women’s empowerment through its Compliance Assistance Programme (CAP), in alignment with UNEP’s policy and strategy for gender and the Multilateral Fund’s operational policy on gender mainstreaming for Multilateral Fund-supported projects. OzonAction’s team provides internal guidance to CAP regional teams, while also monitoring and reporting on gender-related data in Multilateral Fund-supported projects. To support national ozone units (NOUs) in implementing the Multilateral Fund’s gender policy, several products and initiatives were delivered under the CAP in 2024, such as a series of factsheets, including the tool for gender assessment for the MYA, funded by the Multilateral Fund and the International Network of Women in Cooling (INWIC).

# OzonAction conducted an analysis of the 18 KIPs approved by the Executive Committee in 2023 and 2024 where UNEP is the lead implementing agency. The analysis broadly indicated that respective mainstreaming efforts were reflected through the development of training materials, targeted capacity-building activities, and information exchange highlighting success stories of women technicians and women as role models across various project activities. Based on the findings of this analysis, UNEP continues to implement projects that incorporate targeted activities to advance women’s participation in alignment with the decisions of the Executive Committee.

Recommendation

# The Executive Committee may wish:

## To note the progress report of UNEP as at 31 December 2024 contained in document UNEP/OzL.Pro/ExCom/97/14;

## To approve the extension of the completion dates of the preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) for the countries listed below to allow completion of the remaining ongoing activities, as reflected in table 5 of document UNEP/OzL.Pro/ExCom/97/14:

### To June 2026, for Armenia (ARM/DES/93/PRP/29); the Plurinational State of Bolivia (BOL/DES/93/PRP/57); Guatemala (GUA/DES/93/PRP/64); Honduras (HON/DES/93/PRP/61); the Republic of Moldova (MOL/DES/93/PRP/48); and Yemen (YEM/DES/93/PRP/48);

### To December 2026, for Costa Rica (COS/DES/93/PRP/68); the Dominican Republic (DOM/DES/93/PRP/77); El Salvador (ELS/DES/93/PRP/47); Paraguay (PAR/DES/94/PRP/49); Saint Lucia (STL/DES/94/PRP/41); and Somalia (SOM/DES/94/PRP/21); and

### To June 2027, for Belize (BZE/DES/94/PRP/46); Cambodia (KAM/DES/94/PRP/47); Grenada (GRN/DES/94/PRP/37); and Guyana (GUY/DES/94/PRP/40); and

## To approve the recommendations related to ongoing projects with specific issues contained in annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNEP

PER COUNTRY FOR 2024

# Table 1 of annex I presents the status of project implementation by country for 2024 in achieved phase-out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation by UNEP for 2024

| Country | Phased out in 2024 (ODP tonnes)* | Phased out in 2024 (CO2-eq tonnes)* | Estimated funds disbursed in 2024 (US$) | Funds disbursed in 2024 (US$) | Percentage of funds disbursed over estimation in 2024 | Percentage of planned projects completed in 2024** |
| --- | --- | --- | --- | --- | --- | --- |
| Albania | 0.0 | 0 | 63,645 | 37,502 | 59 | 100 |
| Algeria | 0.0 | 0 | 164,736 | 100,000 | 61 |  |
| Angola | 0.0 | 0 | 110,000 | 90,088 | 82 | 50 |
| Antigua and Barbuda | 0.0 | 0 | 80,000 | 39,292 | 49 | 100 |
| Armenia | 0.0 | 0 | 62,310 | 92,349 | 148 | 100 |
| Bahamas (the) | 0.0 | 0 | 83,100 | 102,100 | 123 | 100 |
| Bahrain | 0.0 | 0 | 42,375 | 125,008 | 295 | 100 |
| Bangladesh | 0.0 | 0 | 135,370 | 50,683 | 37 |  |
| Barbados | 0.0 | 0 | 141,880 | 123,880 | 87 | 0 |
| Belize | 0.0 | 0 | 82,044 | 115,632 | 141 |  |
| Benin | 0.0 | 0 | 152,954 | 186,953 | 122 | 100 |
| Bhutan | 0.0 | 0 | 73,365 | 70,652 | 96 |  |
| Bolivia (Plurinational State of) | 0.2 | 0 | 147,104 | 91,723 | 62 | 100 |
| Botswana | 0.0 | 0 | 262,522 | 356,961 | 136 | 33 |
| Brunei Darussalam | 0.0 | 0 | 175,108 | 93,095 | 53 | 0 |
| Burkina Faso | 0.0 | 0 | 111,715 | 148,429 | 133 |  |
| Burundi | 0.0 | 0 | 49,950 | 33,200 | 66 | 100 |
| Cabo Verde | 0.0 | 0 | 293,958 | 128,190 | 44 | 0 |
| Cambodia | 0.0 | 0 | 209,096 | 157,878 | 76 |  |
| Chad | 3.2 | 0 | 91,352 | 168,928 | 185 |  |
| Chile | 0.0 | 0 | 134,927 | 29,706 | 22 | 0 |
| China | 92.9 | 0 | 2,296,390 | 1,090,374 | 47 | 33 |
| Colombia | 0.0 | 0 | 0 | 13,243 |  |  |
| Comoros (the) | 0.0 | 0 | 107,220 | 71,290 | 66 | 100 |
| Congo (the) | 0.0 | 0 | 63,958 | 35,000 | 55 | 100 |
| Cook Islands (the) | 0.0 | 0 | 173,811 | 21,686 | 12 | 100 |
| Costa Rica | 0.0 | 0 | 22,500 | 4,061 | 18 |  |
| Cote d’Ivoire | 0.0 | 0 | 114,572 | 97,838 | 85 | 50 |
| Democratic Republic of the Congo (the) | 0.0 | 0 | 143,991 | 88,635 | 62 | 0 |
| Djibouti | 0.0 | 0 | 94,750 | 8,080 | 9 | 0 |
| Dominica | 0.1 | 0 | 212,129 | 156,754 | 74 | 100 |
| Dominican Republic (the) | 0.0 | 0 | 216,175 | 73,385 | 34 |  |
| Egypt | 0.0 | 0 | 155,800 | 144,800 | 93 | 0 |
| El Salvador | 0.3 | 0 | 85,836 | 79,607 | 93 | 50 |
| Equatorial Guinea | 0.0 | 0 | 152,340 | 72,913 | 48 | 50 |
| Eritrea | 0.2 | 0 | 153,750 | 243,035 | 158 |  |
| Eswatini | 0.0 | 0 | 103,000 | 130,400 | 127 |  |
| Ethiopia | 0.0 | 0 | 235,500 | 296,229 | 126 | 67 |
| Fiji | 0.0 | 0 | 190,832 | 93,996 | 49 | 0 |
| Gabon | 0.0 | 0 | 109,577 | 160,000 | 146 | 0 |
| Gambia (the) | 0.0 | 0 | 199,400 | 170,350 | 85 | 0 |
| Georgia | 0.0 | 0 | 32,500 | 48,000 | 148 |  |
| Ghana | 0.0 | 0 | 13,875 | 0 | 0 |  |
| Grenada | 0.0 | 0 | 183,804 | 51,000 | 28 | 50 |
| Guatemala | 0.0 | 0 | 80,944 | 54,859 | 68 |  |
| Guinea | 0.0 | 0 | 128,450 | 190,300 | 148 | 50 |
| Guinea-Bissau | 0.0 | 0 | 89,853 | 17,545 | 20 | 33 |
| Guyana | 0.0 | 0 | 118,925 | 58,000 | 49 | 100 |
| Honduras | 0.0 | 0 | 78,025 | 70,488 | 90 | 0 |
| India | 6.8 | 0 | 733,634 | 339,992 | 46 | 100 |
| Iran (Islamic Republic of) | 0.0 | 0 | 154,543 | 34,802 | 23 | 0 |
| Iraq | 0.0 | 0 | 350,253 | 186,100 | 53 | 100 |
| Jamaica | 0.0 | 0 | 42,500 | 47,909 | 113 | 0 |
| Kenya | 0.0 | 0 | 164,400 | 122,958 | 75 |  |
| Kiribati | 0.0 | 0 | 224,175 | 35,888 | 16 |  |
| Kuwait | 0.0 | 0 | 782,888 | 299,439 | 38 | 0 |
| Kyrgyzstan | 0.0 | 0 | 154,546 | 247,298 | 160 | 50 |
| Lao People's Democratic Republic (the) | 0.0 | 0 | 161,576 | 185,818 | 115 | 75 |
| Lesotho | 0.0 | 0 | 48,247 | 70,747 | 147 | 100 |
| Liberia | 0.0 | 0 | 147,523 | 153,508 | 104 |  |
| Madagascar | 0.0 | 0 | 78,239 | 9,826 | 13 |  |
| Malawi | 0.0 | 0 | 100,750 | 209,793 | 208 |  |
| Maldives | 0.0 | 0 | 159,563 | 102,220 | 64 | 0 |
| Mali | 0.0 | 0 | 109,280 | 28,000 | 26 | 50 |
| Marshall Islands (the) | 0.0 | 0 | 78,540 | 69,284 | 88 | 0 |
| Mauritania | 2.2 | 0 | 46,875 | 80,000 | 171 | 100 |
| Mauritius | 0.0 | 0 | 45,000 | 0 | 0 |  |
| Mexico | 0.0 | 0 | 56,949 | -1 | 0 |  |
| Micronesia (Federated States of) | 0.0 | 0 | 180,180 | 61,633 | 34 | 100 |
| Mongolia | 0.0 | 0 | 195,979 | 132,117 | 67 | 50 |
| Mozambique | 0.0 | 0 | 229,113 | 221,725 | 97 | 100 |
| Myanmar | 0.4 | 0 | 45,000 | 0 | 0 | 50 |
| Namibia | 0.0 | 0 | 168,650 | 100,225 | 59 | 0 |
| Nauru | 0.0 | 0 | 116,395 | 7,030 | 6 | 0 |
| Nepal | 5.4 | 0 | 122,583 | 81,679 | 67 | 50 |
| Nicaragua | 0.5 | 0 | 131,989 | 5,313 | 4 |  |
| Niger (the) | 7.7 | 19,893 | 86,469 | 115,938 | 134 | 100 |
| Niue | 0.0 | 0 | 103,468 | 52,275 | 51 |  |
| Oman | 0.0 | 0 | 141,864 | 81,790 | 58 | 0 |
| Pakistan | 5.4 | 0 | 331,040 | 107,130 | 32 | 100 |
| Palau | 0.0 | 0 | 163,000 | 79,941 | 49 |  |
| Paraguay | 0.7 | 0 | 129,837 | 113,813 | 88 | 100 |
| Peru | 0.0 | 0 | 146,963 | 46,360 | 32 | 0 |
| Philippines (the) | 0.0 | 0 | 167,976 | 82,959 | 49 |  |
| Qatar | 0.0 | 0 | 182,585 | 198,820 | 109 | 100 |
| Republic of Moldova (the) | 0.1 | 0 | 150,167 | 151,418 | 101 | 100 |
| Rwanda | 0.0 | 0 | 138,700 | 182,109 | 131 | 100 |
| Saint Kitts and Nevis | 0.1 | 0 | 113,425 | 168,600 | 149 | 100 |
| Saint Lucia | 0.0 | 0 | 168,053 | 83,000 | 49 | 50 |
| Saint Vincent and the Grenadines | 0.0 | 0 | 199,622 | 59,527 | 30 | 0 |
| Samoa | 0.0 | 0 | 158,482 | 90,621 | 57 |  |
| Sao Tome and Principe | 0.0 | 0 | 92,086 | 0 | 0 | 0 |
| Saudi Arabia | 0.0 | 0 | 153,104 | 263,268 | 172 | 100 |
| Senegal | 0.0 | 0 | 288,305 | 162,372 | 56 | 50 |
| Serbia | 0.0 | 0 | 35,602 | 6,060 | 17 | 0 |
| Seychelles | 0.0 | 0 | 72,400 | 135,000 | 186 | 100 |
| Sierra Leone | 0.0 | 0 | 311,779 | 327,557 | 105 | 50 |
| Solomon Islands | 0.0 | 0 | 217,208 | 84,625 | 39 | 100 |
| Somalia | 0.0 | 0 | 65,450 | 16,000 | 24 | 0 |
| South Sudan | 0.3 | 0 | 124,218 | 154,811 | 125 | 100 |
| Sri Lanka | 0.0 | 0 | 96,243 | 92,042 | 96 | 0 |
| Sudan (the) | 0.0 | 0 | 186,701 | 186,701 | 100 | 100 |
| Suriname | 0.0 | 0 | 158,889 | 0 | 0 | 33 |
| Syrian Arab Republic (the) | 0.0 | 0 | 525,612 | 214,953 | 41 | 0 |
| Timor-Leste | 0.0 | 0 | 130,583 | 89,252 | 68 | 50 |
| Togo | 0.0 | 0 | 142,732 | 113,792 | 80 | 50 |
| Tonga | 0.0 | 0 | 198,940 | 91,901 | 46 |  |
| Tunisia | 0.0 | 0 | 35,000 | 0 | 0 |  |
| Turkmenistan | 0.0 | 0 | 12,523 | 12,103 | 97 |  |
| Tuvalu | 0.0 | 0 | 144,254 | 48,672 | 34 |  |
| Uganda | 0.0 | 0 | 42,603 | 87,948 | 206 | 100 |
| United Republic of Tanzania (the) | 0.0 | 0 | 191,853 | 344,393 | 180 | 33 |
| Vanuatu | 0.0 | 0 | 139,630 | 60,638 | 43 | 100 |
| Viet Nam | 0.0 | 0 | 202,024 | 124,306 | 62 |  |
| Yemen | 0.0 | 0 | 137,607 | 2,404 | 2 |  |
| Zambia | 0.0 | 0 | 90,850 | 118,450 | 130 | 0 |
| Zimbabwe | 0.0 | 0 | 256,749 | 348,496 | 136 | 100 |
| Region: ASP | 0.0 | 0 | 548,694 | 598,678 | 109 | 50 |
| Global | 0.0 | 0 | 3,663,556 | 9,778,915 | 267 | 50 |
| Grand total | 126.9 | 19,893 | 23,701,634 | 23,795,058 | 100 | 54 |

* 7.7 mt (19,893 CO2-eq tonnes) in 2024 for HFC-related projects.

** For projects that were planned to be completed in 2024.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNEP

PER YEAR AS AT 31 DECEMBER 2024

# Table 1 of annex II presents an overview of the status of project implementation by year.  All projects and activities approved between 1991 and 2017 have now been completed.

Table 1. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 11 | 11 | 100 | 1,372,335 | 1,372,335 | 0 | 100 |
| 1992 | 15 | 15 | 100 | 1,711,000 | 1,711,000 | 0 | 100 |
| 1993 | 49 | 49 | 100 | 4,194,343 | 4,194,343 | 0 | 100 |
| 1994 | 58 | 58 | 100 | 4,231,169 | 4,231,169 | 0 | 100 |
| 1995 | 50 | 50 | 100 | 4,047,683 | 4,047,683 | 0 | 100 |
| 1996 | 47 | 47 | 100 | 3,366,039 | 3,366,039 | 0 | 100 |
| 1997 | 87 | 87 | 100 | 7,962,291 | 7,962,291 | 0 | 100 |
| 1998 | 64 | 64 | 100 | 4,669,124 | 4,669,124 | 0 | 100 |
| 1999 | 87 | 87 | 100 | 6,368,983 | 6,368,983 | 0 | 100 |
| 2000 | 85 | 85 | 100 | 6,300,398 | 6,300,398 | 0 | 100 |
| 2001 | 59 | 59 | 100 | 7,411,159 | 7,411,159 | 0 | 100 |
| 2002 | 72 | 72 | 100 | 9,469,401 | 9,469,401 | 0 | 100 |
| 2003 | 78 | 78 | 100 | 11,165,394 | 11,165,394 | 0 | 100 |
| 2004 | 99 | 99 | 100 | 12,362,652 | 12,362,652 | 0 | 100 |
| 2005 | 72 | 72 | 100 | 12,339,483 | 12,339,483 | 0 | 100 |
| 2006 | 108 | 108 | 100 | 12,731,484 | 12,731,484 | 0 | 100 |
| 2007 | 79 | 79 | 100 | 14,611,111 | 14,611,111 | 0 | 100 |
| 2008 | 132 | 132 | 100 | 17,875,070 | 17,875,070 | 0 | 100 |
| 2009 | 115 | 115 | 100 | 17,250,876 | 17,250,876 | 0 | 100 |
| 2010 | 79 | 79 | 100 | 14,361,124 | 14,356,674 | 4,450 | 100 |
| 2011 | 100 | 100 | 100 | 16,782,433 | 16,782,434 | -1 | 100 |
| 2012 | 80 | 80 | 100 | 16,086,261 | 16,086,261 | 0 | 100 |
| 2013 | 90 | 90 | 100 | 14,152,112 | 14,152,112 | -1 | 100 |
| 2014 | 74 | 74 | 100 | 12,339,027 | 12,339,026 | 1 | 100 |
| 2015 | 180 | 180 | 100 | 21,169,099 | 21,169,098 | 1 | 100 |
| 2016 | 95 | 95 | 100 | 19,618,132 | 19,573,249 | 44,883 | 100 |
| 2017 | 88 | 88 | 100 | 15,546,456 | 15,532,085 | 14,371 | 100 |
| 2018 | 173 | 172 | 99 | 23,756,734 | 23,371,744 | 384,990 | 98 |
| 2019 | 110 | 103 | 94 | 15,033,532 | 14,848,023 | 185,510 | 99 |
| 2020 | 130 | 104 | 80 | 15,395,314 | 12,826,242 | 2,569,072 | 83 |
| 2021 | 126 | 99 | 79 | 21,976,825 | 20,017,153 | 1,959,671 | 91 |
| 2022 | 101 | 51 | 50 | 23,069,361 | 16,827,735 | 6,241,626 | 73 |
| 2023 | 125 | 13 | 10 | 28,350,427 | 11,991,037 | 16,359,390 | 42 |
| 2024 | 216 | 0 | 0 | 43,760,329 | 155,349 | 43,604,980 | 0 |
| Total | 3,134 | 2,695 | 86 | 460,837,158 | 389,468,217 | 71,368,942 | 85 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNEP

| Country/project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Bahamas (the) BHA/PHA/94/TAS/35 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 0 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Barbados BAR/PHA/91/TAS/34 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Barbados BAR/PHA/94/TAS/36 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 0 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Benin BEN/PHA/92/TAS/46 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 0 | 18 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Botswana BOT/PHA/86/TAS/26 | HCFC phase-out management plan (stage II, first tranche) | 91 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Cabo Verde CBI/PHA/91/TAS/31 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 0 | 12 and 18 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Chile CHI/PHA/88/TAS/206 | HCFC phase-out management plan (stage III, first tranche) | 38 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Democratic Republic of the Congo (the) DRC/PHA/88/TAS/48 | HCFC phase-out management plan (stage II, first tranche) | 68 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Democratic Republic of the Congo (the) DRC/PHA/92/TAS/50 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 0 | 18 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Dominican Republic (the) DOM/PHA/92/TAS/75 | HCFC phase-out management plan (stage III, second tranche) | 0 | 18 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Gabon GAB/PHA/94/TAS/47 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 0 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Gambia (the) GAM/PHA/86/TAS/40 | HCFC phase-out management plan (stage II, first tranche) | 80 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Grenada GRN/PHA/90/TAS/32 | HCFC phase-out management plan (stage II, first tranche) | 0 | 12 and 18 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Grenada GRN/PHA/94/TAS/36 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 0 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Guyana GUY/PHA/92/TAS/35 | HCFC phase-out management plan (stage II, third tranche) | 0 | 18 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Guyana GUY/PHA/94/TAS/39 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 0 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Honduras HON/EEF/92/TAS/60 | HCFC phase-out management plan (stage II, second tranche) (energy efficiency - related activities under decision 89/6) | 0 | 18 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Honduras HON/PHA/92/TAS/57 | HCFC phase-out management plan (stage II, second tranche) | 0 | 18 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/86/TAS/248 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | 56 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Kiribati KIR/PHA/86/TAS/17 | HCFC phase-out management plan for PIC countries through regional approach (stage II, first tranche) | 2 | Slow progress in implementation | To request UNEP to submit a status report to the 98th meeting on implementation progress and disbursement levels |
| Kiribati KIR/SEV/92/INS/19 | Renewal of institutional strengthening project (phase IX: 1/2024-12/2026) | 0 | Slow progress in implementation | To request UNEP to submit a status report to the 98th meeting on implementation progress and disbursement levels |
| Kuwait KUW/PHA/88/TAS/42 | HCFC phase-out management plan (stage II, first tranche) | 42 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Lao People’s Democratic Republic (the) LAO/PHA/86/TAS/37 | HCFC phase-out management plan (stage II, first tranche) | 97 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Maldives MDV/EEF/91/TAS/38 | Technical assistance: additional activities to maintain energy efficiency for the servicing sector under decision 89/6(b) | 47 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Myanmar MYA/SEV/84/INS/22 | Extension of institutional strengthening project (phase V: 7/2020-6/2022) | 47 | Political situation resulting in lack of progress | To request UNEP to submit a status report to the 98th meeting on the resumption of activities |
| Nepal NEP/PHA/86/TAS/43 | HCFC phase-out management plan (stage II, first tranche) | 39 | Challenges related to transfer of funds to the Government | To request UNEP to submit a status report to the 98th meeting on the resolution of challenges related to the transfer of funds to the Government |
| Pakistan PAK/PHA/90/TAS/114 | HCFC phase-out management plan (stage III, first tranche) (refrigeration servicing sector) | 0 | 18 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Saint Lucia STL/PHA/87/TAS/34 | HCFC phase-out management plan (stage II, first tranche) | 50 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Saint Vincent and the Grenadines STV/PHA/92/TAS/28 | Verification report on the implementation of the HCFC phase-out management plan | 0 | 18 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Sao Tome and Principe STP/PHA/88/TAS/33 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 0 | 12 and 18 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Sierra Leone SIL/PHA/87/TAS/41 | HCFC phase-out management plan (stage II, first tranche) | 85 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| South Sudan SSD/PHA/93/PRP/09 | Preparation of an HCFC phase-out management plan (stage II) (Overarching) | 0 | Slow progress in preparation of HPMP | To request UNEP to submit a status report to the 98th meeting on the completion of the preparation of stage II of the HPMP |
| Suriname SUR/PHA/92/TAS/33 | HCFC phase-out management plan (stage I, fourth tranche) | 0 | 18 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Syrian Arab Republic SYR/PHA/86/TAS/106 | HCFC phase-out management plan (stage I, first tranche) | 75 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Syrian Arab Republic SYR/PHA/91/TAS/114 | HCFC phase-out management plan (stage I, second tranche) | 0 | 18 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Togo TOG/PHA/91/TAS/42 | Verification report on the implementation of stage I of the HCFC phase-out management plan | 99 | 12 months delays | To request UNEP to report to the 98th meeting on this project with implementation delays |
| Yemen YEM/SEV/93/INS/47 | Extension of the institutional strengthening project (phase IX: 1/2024-12/2026) | 0 | Slow progress in implementation and political uncertainties | To request UNEP to submit a status report to the 98th meeting on implementation progress |

UNEP/OzL.Pro/ExCom/97/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database, which is provided on the 97th meeting portal on the Multilateral Fund’s website, in the spreadsheet programme, Microsoft Excel.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 97th meeting.

Ongoing projects are all projects that were under implementation as at 31 December 2024. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

Phase-out of ODS is expressed in ODP tonnes and of HFCs in mt and CO2-eq tonnes.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/97/40

UNEP/OzL.Pro/ExCom/97/41

UNEP/OzL.Pro/ExCom/97/43

UNEP/OzL.Pro/ExCom/97/44

UNEP/OzL.Pro/ExCom/97/47

UNEP/OzL.Pro/ExCom/97/49

UNEP/OzL.Pro/ExCom/97/57

UNEP/OzL.Pro/ExCom/97/58

UNEP/OzL.Pro/ExCom/97/59

UNEP/OzL.Pro/ExCom/97/67

UNEP/OzL.Pro/ExCom/97/70

UNEP/OzL.Pro/ExCom/97/72

UNEP/OzL.Pro/ExCom/97/73

UNEP/OzL.Pro/ExCom/97/78

UNEP/OzL.Pro/ExCom/97/80

UNEP/OzL.Pro/ExCom/97/60

UNEP/OzL.Pro/ExCom/97/65

UNEP/OzL.Pro/ExCom/97/17 or UNEP/OzL.Pro/ExCom/97/18

Decision 95/34(a)(viii), annex XVII of UNEP/OzL.Pro/ExCom/95/94

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The Executive Committee requested bilateral and implementing agencies to provide a brief report on key gender mainstreaming results achieved as part of their annual progress reports, as of 2023, on the basis of the information available to them (decision 90/48(d)).

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.