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اللجنــة التنفيـذيــــة للصنــدوق المــتعــدد الأطـــراف
لتنفيـــذ بروتوكـول مونتريــال 
الاجتمــــــاع الثالث والتسعــــون 
[bookmark: _Hlk128756171]مونتريال، 15-19 ديسمبر/كانون الأول 2023
المادة 4(ب) من جدول الأعمال المؤقت[footnoteRef:1] [1:  الوثيقة: UNEP/OzL.Pro/ExCom/93/1.] 



تقرير عن الأرصدة وتوافر الموارد

مقدمة
تعرض هذه الوثيقة موجزاً للتعديلات المالية التي أشارت إليها الوكالات الثنائية والوكالات المنفذة على النحو الذي وافقت عليه الأمانة. وهي تتضمن بيانات إحصائية[footnoteRef:2] من جميع المشاريع التي لديها أرصدة تم الاحتفاظ بها لأكثر من 12 شهراً بعد إنجاز المشروع، على النحو المطلوب بموجب المقررين 28/7 و56/2(ج). وتتناول الوثيقة الأرصدة التي يتعين إعادتها مقابل المشاريع على سبيل المتابعة للمقررات ذات الصلة (المشار إليها باسم مشاريع "صادر بها مقررات" في هذه الوثيقة). كما تشير إلى مستوى الموارد المتاحة للجنة التنفيذية نقداً على النحو المسجل في وثيقة حالة الاشتراكات والمدفوعات[footnoteRef:3]، على النحو المطلوب في المقرر 41/92(ب)، وتقدم توصية في هذا الصدد. وترد في المرفقين الأول والثاني، على التوالي، المبالغ التي تحتفظ بها الوكالات المنفذة، للمشاريع المنجزة، وللمشاريع الصادر بها مقررات، ومشاريع التبرعات الإضافية. ويعرض المرفق الثالث الأموال التي أعادتها الوكالات الثنائية والوكالات المنفذة للمشاريع المنجزة، وللمشاريع الصادر بها مقررات، ولمشاريع التبرعات الإضافية. [2:  تستند البيانات المعروضة إلى نموذج الإبلاغ الذي تم إعداده عملاً بالمقرر 31/2]  [3:  الوثيقة: UNEP/OzL.Pro/ExCom/93/3.] 

الأموال التي يتعين إعادتها إلى الاجتماع الثالث والتسعين
يبلغ مجموع الأموال التي يتعين إعادتها 4,286,636 دولاراً أمريكياً (أي ما يعادل 50,850 دولاراً أمريكياً من الوكالات الثنائية، و4,235,786 دولاراً أمريكياً من الوكالات المنفذة) من المشاريع المنجزة، والمشاريع الصادر بها مقررات، ومشاريع التبرعات الإضافية.
الأموال التي يتعين أن تعيدها الوكالات المنفذة
يبلغ مجموع الأموال التي يتعين أن تعيدها الوكالات المنفذة 4,235,786 دولار أمريكي على النحو المبين في الجدول 1.
الجدول 1: الأموال التي يتعين أن تعيدها الوكالات المنفذة إلى الاجتماع الثالث والتسعين (دولار أمريكي)
	الوكالة
	تكلفة المشروع
	تكلفة دعم الوكالة
	مجموع التكاليف

	اليوئنديبي
	562,920
	39,505
	602,425

	اليونيب
	2,245,847
	175,064
	2,420,911

	اليونيدو
	551,323
	38,603
	589,926

	البنك الدولي
	320,000
	302,524
	622,524

	المجموع
	3,680,090
	555,696
	4,235,786



الأرصدة التي تحتفظ بها الوكالات المنفذة

يرد في الجدول 2 معلومات عن أرصدة المشاريع المنجزة ومشاريع التبرعات الإضافية التي تحتفظ بها الوكالات المنفذة.
الجدول 2: أرصدة المشاريع المنجزة ومشاريع التبرعات الإضافية التي تحتفظ بها الوكالات الثنائية (بما في ذلك تكاليف دعم الوكالة)
	سنة الإنجاز
	اليوئنديبي
	اليونيدو
	المجموع

	
	عدد المشاريع
	(دولار أمريكي)
	عدد المشاريع
	(دولار أمريكي)
	عدد المشاريع
	(دولار أمريكي)

	المشاريع المنجزة منذ أكثر من سنتين

	2019
	1
	6,306
	
	
	1
	6,306

	2020
	1
	40,434
	
	
	1
	40,434

	1 يناير إلى
31 أكتوبر 2021
	5
	63,190
	2
	1,828,437
	7
	1,891,627

	المجموع الفرعي
	7
	109,930
	2
	1,828,437
	9
	1,938,367

	المشاريع التي مضى على إنجازها أقل من سنتين

	1 نوفمبر إلى
31 ديسمبر 2021
	5
	37,308
	4
	39,841
	9
	77,149

	2022
	20
	277,877
	25
	558,563
	45
	836,440

	المجموع الفرعي
	25
	315,185
	29
	598,404
	54
	913,589

	المجموع
	32
	425,115
	31
	2,426,841
	63
	2,851,956

	مشاريع التبرعات الإضافية

	
	2
	7,953
	5
	122,134
	7
	130,087

	المجموع العام
	34
	433,068
	36
	2,548,975
	70
	2,982,043


الأموال التي يتعين أن تعيدها الوكالات الثنائية إلى الاجتماع الثالث والتسعين
يبلغ أجمالي الأموال التي يتعين أن تعيدها الوكالات الثنائية مبلغاً قدره 50,850 دولاراً أمريكياً من المشاريع المنجزة كما هو موضح في الجدول 3.
	الوكالة
	تكلفة المشروع
	تكلفة دعم الوكالة
	المجموع

	فرنسا
	45,000
	5,850
	50,850


الجدول 3. الأموال التي يتعين أن تعيدها الوكالات الثنائية (دولار أمريكي)


توافر الموارد
تشير وثيقة حالة المساهمات والمصروفات إلى رصيد متاح قدره 523,322,098 دولار أمريكي حتى 8 نوفمبر/تشرين الثاني 2023. ويبلغ إجمالي الرصيد الذي أعادته الوكالات الثنائية والوكالات المنفذة إلى الاجتماع الثالث والتسعين 4,286,636 دولاراً أمريكياً. ولذلك، وباستثناء مبلغ 246 مليون دولار أمريكي متعلق بالأموال المتبقية من فترة الثلاث سنوات 2018-2020 التي سيتم استخدامها بعد عام 2023، فإن المستوى الإجمالي للموارد المتاحة للموافقات في الاجتماع الثالث والتسعين هو 281,608,734 دولاراً أمريكياً.
تعليقات الأمانة
ذَكَّرت الأمانة الوكالات المنفذة بأنه ينبغي إعادة أرصدة المشاريع الصادر بها مقررات والمشاريع التي أنجزت قبل عام واحد وأكثر، ومشاريع التبرعات الإضافية إلى الصندوق المتعدد الأطراف في أقرب وقت ممكن.
وبالنظر إلى أن المستوى الإجمالي لتمويل المشاريع والأنشطة المقدمة إلى الاجتماع الثالث والتسعين حتى 22 أكتوبر/تشرين الأول 2023 هو 122,704,590 دولاراً أمريكياً، فهناك موارد كافية متاحة للموافقات في الاجتماع الثالث والتسعين.
التوصية

قد ترغب اللجنة التنفيذية فيما يلي:
أن تُحيط علماً بـ:
(1) التقرير المتعلق بالأرصدة وتوافر الموارد الوارد في الوثيقة UNEP/OzL.Pro/ExCom/93/4؛
(2) أن المستوى الصافي للأموال التي يتعين أن تعيدها الوكالات المنفذة في الاجتماع الثالث والتسعين هو 4,235,786 دولار أمريكي وهو مبلغ يتألف من 562,920 دولاراً أمريكياً، بالإضافة إلى تكاليف دعم الوكالة البالغة 39,505 دولاراً أمريكياً من اليوئنديبي؛ و 2,245,847 دولار أمريكي، بالإضافة إلى تكاليف دعم الوكالة البالغة 175,064 دولاراً أمريكياً من اليونيب؛ و551,323 دولاراً أمريكياً، بالإضافة إلى تكاليف دعم الوكالة البالغة 38,603 دولاراً أمريكياً من اليونيدو؛ و320,000 دولاراً أمريكياً، بالإضافة إلى تكاليف دعم الوكالة البالغة 302,524 دولاراً أمريكياً من البنك الدولي؛
(3) أن اليوئنديبي يحتفظ بأرصدة قدرها 109,930 دولاراً أمريكياً، بما في ذلك تكاليف دعم الوكالة، لسبعة مشاريع تم إنجازها قبل أكثر من عامين، و7,953 دولاراً أمريكياً، بما في ذلك تكاليف دعم الوكالة، لمشروعين منجزين تم تمويلهما باستخدام التبرعات الإضافية التي قدمتها مجموعة من البلدان المانحة لتمويل أنشطة البداية السريعة لتنفيذ التخفيض التدريجي للهيدروفلوروكربون؛
(4) أن اليونيدو تحتفظ بأرصدة قدرها 1,828,437 دولاراً أمريكياً، بما في ذلك تكاليف دعم الوكالة، لمشروعين منجزين تم تمويلهما قبل أكثر من سنتين، و122,134 دولاراً أمريكياً، بما في ذلك تكاليف دعم الوكالة لخمسة مشاريع ممولة باستخدام التبرعات الإضافية التي قدمتها مجموعة من البلدان المانحة لتمويل أنشطة البداية السريعة لتنفيذ التخفيض التدريجي للهيدروفلوروكربون؛ و
(5) أن مستوى الأموال التي أعادتها حكومة فرنسا في الاجتماع الثالث والتسعين هو 50,850 دولاراً أمريكياً، وهو مبلغ يتألف من 45,000 دولاراً أمريكياً، بالإضافة إلى تكاليف دعم الوكالة البالغة 5,850 دولاراً أمريكياً.
أن تطلب:
إلى اليوئنديبي واليونيدو:
1. المضي قدماً في صرف أو إلغاء المبالغ الملتزم بها أو غير الملتزم بها غير الضرورية للمشاريع المنجزة، وإعادة الأرصدة ذات الصلة في الاجتماع الرابع والتسعين؛
2. المضي قدماً في صرف أو إلغاء المبالغ الملتزم بها الخاصة بالمشاريع المنجزة قبل أكثر من سنتين، وإعادة الأرصدة ذات الصلة في الاجتماع الرابع والتسعين؛
3. المضي قدماً في صرف أرصدة المشاريع المنجزة الممولة من التبرعات الإضافية أو إعادتها في الاجتماع الرابع والتسعين؛
إلى أمين الخزانة أن يتابع مع حكومة فرنسا، إعادة مبلغ 50,850 دولاراً أمريكياً المشار إليه في الفقرة الفرعية (أ)(5) أعلاه نقداً.
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إن وثائق ما قبل دورات اللجنة التنفيذية للصندوق المتعدد الأطراف لتنفيذ بروتوكول مونتريال 
قد تصدر دون إخلال بأي قرار تتخذه اللجنة التنفيذية بعد صدورها. 
4
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Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR COMPLETED PROJECTS

	Code
	Project title
	Date completed (Actual)
	Approved funding plus adjustments as of 
31 Dec 2022
 (US $)
	Funds disbursed as of 
93rd meeting (US $)
	Balances committed as per 
93rd meeting (US $)
	Balances not-committed as per 
93rd meeting (US $)
	Support cost on balances committed and not committed as per
93rd meeting (US $)
	Why any balances could not be returned?
	When they could be returned?
	Project subject to decision

	UNDP

	ANG/PHA/84/TAS/22
	Verification report on the implementation of the HCFC phase-out management plan
	Dec-21
	30,000
	22,149
	7,851
	
	707
	
	
	

	ARG/SEV/82/INS/188
	Extension for institutional strengthening project (phase X: 1/2019-12/2020)
	Dec-22
	398,806
	384,407
	14,399
	
	1,008
	
	
	

	BGD/SEV/81/TAS/52
	Enabling activities for HFC phase-down
	Jun-22
	14,000
	3,249
	10,751
	
	753
	
	
	

	BRA/DES/72/DEM/305
	Pilot demonstration project on ODS waste management and disposal
	Dec-22
	1,490,600
	1,488,205
	2,395
	
	168
	
	
	

	BRU/PHA/85/INV/26
	HCFC phase-out management plan (stage I, fourth tranche)
	Dec-22
	6,600
	149
	6,451
	
	581
	
	
	

	BZE/SEV/85/TAS/37
	Enabling activities for HFC phase-down
	Oct-22
	55,000
	49,576
	5,424
	
	380
	
	
	

	CHI/PHA/81/INV/197
	HCFC phase-out management plan (stage II, second tranche) (foam sector)
	Dec-22
	1,290,468
	1,203,966
	86,502
	
	6,055
	
	
	

	COL/PHA/84/TAS/108
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector, project management and monitoring)
	Dec-22
	635,749
	623,148
	12,601
	
	882
	
	
	

	CUB/PHA/82/PRP/61
	Preparation of a HCFC phase-out management plan (stage II)
	Oct-21
	60,000
	38,281
	21,719
	
	1,520
	
	
	

	CUB/SEV/83/INS/62
	Extension of institutional strengthening project (phase XI: 7/2019-6/2021)
	Dec-22
	190,804
	190,442
	362
	
	25
	
	
	

	DOM/PHA/83/PRP/68
	Preparation of a HCFC phase-out management plan (stage III)
	Jun-21
	60,000
	47,408
	12,592
	
	881
	
	
	

	DRC/PHA/79/PRP/42
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-21
	17,143
	16,296
	847
	
	59
	
	
	

	EGY/PHA/79/INV/135
	HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector)
	Jul-22
	967,352
	933,070
	34,282
	
	2,400
	
	
	

	FIJ/PHA/77/INV/31
	HCFC phase-out management plan (stage I, third tranche)
	Dec-19
	59,850
	54,065
	5,785
	
	521
	
	
	

	FIJ/PHA/82/PRP/34
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-21
	30,000
	26,442
	3,558
	
	249
	
	
	

	FIJ/PHA/86/INV/38
	HCFC phase-out management plan (stage I, fourth tranche)
	Dec-22
	19,950
	0
	19,950
	
	1,795
	
	
	

	GEO/PHA/85/INV/42
	HCFC phase-out management plan (stage I, fourth tranche)
	Dec-22
	31,500
	25,577
	5,923
	
	444
	
	
	

	GHA/SEV/86/INS/49
	Extension of the institutional strengthening project (phase XIV: 1/2021-12/2022)
	Dec-22
	178,048
	177,873
	175
	
	12
	
	
	

	HAI/SEV/84/TAS/23
	Enabling activities for HFC phase-down
	Dec-21
	95,000
	90,311
	4,689
	
	328
	
	
	

	JAM/PHA/81/PRP/38
	Preparation of a HCFC phase-out management plan (stage II)
	Jul-21
	40,000
	33,501
	6,499
	
	455
	
	
	

	MOL/PHA/86/INV/43
	HCFC phase-out management plan (stage II, third tranche)
	Dec-21
	17,450
	0
	17,450
	
	1,570
	
	
	

	MOL/PHA/86/TAS/42
	Verification report for implementation of stage II of the HCFC phase-out management plan
	Dec-22
	30,000
	21,459
	8,541
	
	769
	
	
	

	MOL/SEV/85/TAS/41
	Enabling activities for HFC phase-down
	Dec-22
	50,000
	38,716
	11,284
	
	790
	
	
	

	NEP/PHA/86/INV/44
	HCFC phase-out management plan (stage I, third tranche)
	Dec-22
	8,400
	0
	8,400
	
	756
	
	
	

	NIR/PHA/83/PRP/154
	Preparation of a HCFC phase-out management plan (stage III)
	Dec-22
	22,500
	11,717
	10,783
	
	755
	
	
	

	PAN/PHA/83/PRP/49
	Preparation of a HCFC phase-out management plan (stage III)
	Jun-21
	60,000
	42,695
	17,305
	
	1,211
	
	
	

	SRL/SEV/86/INS/57
	Extension of the institutional strengthening project (phase XIII: 1/2021-12/2022)
	Dec-22
	171,592
	171,357
	235
	
	16
	
	
	

	SWA/PHA/83/PRP/27
	Preparation of a HCFC phase-out management plan (stage II)
	Jun-21
	10,000
	9,059
	941
	
	66
	
	
	

	URU/PHA/77/INV/67
	HCFC phase-out management plan (stage II, first tranche) (foam sector)
	Dec-20
	100,000
	62,211
	37,789
	
	2,645
	
	
	

	URU/PHA/85/INV/75
	HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector and implementation and monitoring)
	Dec-22
	111,268
	104,570
	6,698
	
	469
	
	
	

	URU/SEV/84/INS/74
	Extension of institutional strengthening project (phase XIII: 1/2020-12/2021)
	Apr-22
	193,024
	181,625
	11,399
	
	798
	
	
	

	VEN/SEV/82/INS/136
	Renewal of institutional strengthening project (phase XIV: 1/2019-12/2020)
	Dec-22
	365,414
	363,110
	2,305
	
	162
	
	
	

	TOTAL UNDP
	
	
	
	
	395,885
	
	29,230
	
	
	

	UNIDO[footnoteRef:4] [4:  1: Funds returned in previous meetings; no action needed. 2: Financial closure-initiated funds not returned due to ongoing unpaid obligations. 3: Since funds can be returned up to one year after operational completion, funds will be returned in 94th meeting.
] 


	AFG/PHA/77/INV/20
	HCFC phase-out management plan (stage I, second tranche)
	Sep-21
	131,938
	131,427
	511
	
	46
	2
	94
	

	ALG/SEV/84/TAS/83
	Enabling activities for HFC phase-down
	Jun-22
	150,000
	145,808
	4,192
	
	293
	2
	94
	

	ARG/PHA/79/INV/180
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	Jun-22
	645,746
	642,391
	3,355
	
	235
	2
	94
	

	BDI/PHA/85/PRP/40
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-22
	10,000
	9,815
	185
	
	13
	3
	94
	

	BHE/PHA/72/INV/29
	HCFC phase-out management plan (stage I, second tranche) (activities in the refrigeration servicing sector including policy actions)
	Dec-22
	128,979
	128,879
	100
	
	7
	2
	94
	

	BHE/PHA/76/INV/33
	HCFC phase-out management plan (stage I, third tranche) (activities in the refrigeration servicing sector including policy actions)
	Dec-22
	117,692
	117,416
	276
	
	19
	2
	94
	

	BHE/PHA/82/INV/36
	HCFC phase-out management plan (stage I, fourth tranche) (activities in the refrigeration servicing sector including policy actions)
	Dec-22
	31,000
	30,339
	661
	
	46
	2
	94
	

	BOT/PHA/75/INV/18
	HCFC phase-out management plan (stage I, first tranche)
	Dec-22
	140,000
	132,272
	7,728
	
	541
	3
	94
	

	GAB/PHA/79/INV/34
	HCFC phase-out management plan (stage I, third tranche)
	Dec-22
	119,900
	108,729
	11,171
	
	1,005
	2
	94
	

	GLO/REF/80/DEM/344
	Global chiller replacement project (Argentina)
	Dec-22
	808,438
	554,732
	253,706
	
	19,028
	2
	94
	82/21(d),  86/17(h) and 88/15(b)(ii)

	GUI/PHA/85/INV/34
	HCFC phase-out management plan (stage I, third tranche)
	Jul-22
	125,000
	120,432
	4,568
	
	320
	2
	94
	

	IRQ/PHA/58/INV/09
	National phase-out plan (first tranche)
	Jun-21
	4,353,530
	2,653,177
	1,700,353
	
	127,527
	2
	94
	71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c)

	IRQ/PHA/74/INV/23
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector)
	Dec-21
	230,000
	229,936
	64
	
	5
	2
	94
	

	IRQ/PHA/84/INV/29
	HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector)
	Dec-21
	210,000
	177,225
	32,775
	
	2,458
	2
	94
	

	IVC/PHA/84/INV/45
	HCFC phase-out management plan (stage I, third tranche)
	Dec-22
	460,000
	451,891
	8,109
	
	568
	2
	94
	90/32(a)

	JOR/PHA/77/INV/100
	HCFC phase-out management plan (stage II, first tranche) (polyurethane spray foam sector)
	Dec-22
	164,485
	164,374
	111
	
	8
	3
	94
	

	JOR/PHA/84/INV/106
	HCFC phase-out management plan (stage II, second tranche) (polyurethane spray foam sector)
	Dec-22
	246,727
	239,272
	7,455
	
	522
	3
	94
	

	KUW/PHA/66/INV/21
	HCFC phase-out management plan (stage I, first tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company)
	Jun-22
	3,510,450
	3,506,188
	4,262
	
	320
	2
	94
	

	KUW/PHA/74/INV/24
	HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector phase-out: Kuwait polyurethane Industry Co.; Kirby Building Systems, technical assistance to spray foam users and other small users)
	Jun-22
	643,382
	637,195
	6,187
	
	433
	2
	94
	

	KUW/PHA/74/INV/25
	HCFC phase-out management plan (stage I, second tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company)
	Jun-22
	2,706,000
	2,703,464
	2,536
	
	177
	2
	94
	

	KUW/PHA/83/TAS/37
	HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector)
	Jun-22
	218,000
	28,335
	189,665
	
	13,277
	2
	94
	

	KUW/PHA/88/INV/45
	HCFC phase-out management plan (stage I, fourth tranche) (extruded polystyrene foam sector phase-out)
	Jun-22
	877,675
	876,444
	1,231
	
	86
	2
	94
	

	KUW/PHA/88/INV/46
	HCFC phase-out management plan (stage I, fourth tranche) (polyurethane foam sector phase-out)
	Jun-22
	42,325
	42,289
	36
	
	3
	2
	94
	

	MAG/PHA/84/PRP/33
	Preparation of a HCFC phase-out management plan (stage II)
	Dec-22
	20,000
	19,232
	768
	
	54
	3
	94
	

	MOZ/PHA/66/INV/23
	HCFC phase-out management plan (stage I, first tranche)
	Dec-22
	75,000
	74,225
	775
	
	70
	3
	94
	

	MYA/PHA/80/INV/19
	HCFC phase-out management plan (stage I, second tranche)
	Dec-22
	60,000
	53,880
	6,120
	
	551
	3
	94
	

	NER/KIP/87/PRP/40
	Preparation of Kigali HFC implementation plan
	Dec-22
	170,000
	169,632
	368
	
	26
	3
	94
	

	SEN/PHA/85/INV/41
	HCFC phase-out management plan (stage I, third tranche)
	Dec-21
	50,000
	48,582
	1,418
	
	106
	2
	94
	

	SEN/PHA/85/PRP/43
	Preparation of a HCFC phase-out management plan (stage II)
	Jun-22
	20,000
	13,145
	6,855
	
	480
	2
	94
	

	SOM/PHA/77/INV/12
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector)
	Dec-22
	141,500
	141,442
	58
	
	4
	3
	94
	88/40(a)

	SYR/REF/62/INV/103
	Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group
	Dec-21
	1,465,361
	1,462,556
	2,805
	
	210
	2
	94
	

	TOTAL UNIDO
	
	
	
	
	2,258,404
	
	168,437
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Annex II
COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS
	CODE
	Project title
	Approved funding plus adjustments as of 
31 December 2022 (US $) 
	Funds disbursed as of 
93rd meeting (US $)
	Balances committed as per 
93rd meeting (US $)
	Balances not- committed as per 93rd meeting (US $)
	Support cost on balances committed and not-committed as per 
93rd meeting (US $) 
	Why any balances could not be returned?
	When they could be returned?

	UNDP

	CHI/SEV/80/TAS/03+
	Enabling activities for HFC phase-down
	33,000
	27,058
	5,942
	
	416
	
	

	URU/SEV/80/TAS/02+
	Enabling activities for HFC phase-down
	100,000
	98,509
	1,491
	
	104
	
	

	TOTAL UNDP
	
	
	
	7,433
	
	520
	
	

	UNIDO[footnoteRef:5] [5:  1: Financial closure-initiated fund not returned due to ongoing unpaid obligations.  
] 


	ARG/REF/81/INV/01+
	Conversion project for replacement of HFC-134a with isobutane 
(R-600a)/propane (R-290)-based refrigerant in the manufacture of domestic and commercial refrigeration equipment at Briket, Bambi and Mabe-Kronen
	1,840,755
	1,835,494
	5,261
	
	368
	1
	94

	ARG/SEV/81/TAS/02+
	Enabling activities for HFC phase-down
	250,000
	199,189
	50,811
	
	3,557
	1
	94

	EGY/SEV/81/TAS/02+
	Enabling activities for HFC phase-down
	105,000
	101,318
	3,682
	
	258
	1
	94

	MOR/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	150,000
	95,809
	54,191
	
	3,793
	1
	94

	VEN/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	250,000
	249,800
	200
	
	14
	1
	94

	TOTAL UNIDO
	
	
	
	114,144
	
	7,990
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Annex III

DETAILS ON COMPLETED, BY DECISIONS AND ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES

	Code
	Project title
	Project costs returned (US $)
	Agency support costs (US $)
	Total (US $)

	BGD/SEV/83/INS/55
	Renewal of the institutional strengthening project (phase IX: 7/2019-6/2021)
	18
	1
	19

	BZE/PHA/50/PRP/17
	Project preparation for a terminal phase-out management plan in the refrigeration servicing sector
	1
	0
	1

	BZE/PHA/82/PRP/34
	Preparation of a HCFC phase-out management plan (stage II)
	1,250
	87
	1,338

	CHI/SEV/83/INS/198
	Extension of the institutional strengthening project (phase XIII: 7/2019-6/2021)
	169
	12
	181

	COL/PHA/81/INV/102
	HCFC phase-out management plan (stage II, second tranche) (foam sector)
	542,962
	38,007
	580,969

	COL/SEV/79/INS/101
	Extension of institutional strengthening project 
(phase XI: 11/2017-10/2019)
	773
	54
	827

	COL/SEV/83/INS/106
	Extension of institutional strengthening project 
(phase XII: 11/2019-10/2021)
	2,624
	184
	2,808

	COS/SEV/84/INS/62
	Extension of institutional strengthening project 
(phase XIII: 1/2020-12/2021)
	362
	25
	387

	ELS/PHA/79/TAS/36
	Verification report for stage I of HCFC phase-out management plan
	835
	75
	910

	GUY/PHA/75/INV/28
	HCFC phase-out management plan (stage II, first tranche)
	1,893
	133
	2,026

	IDS/SEV/84/INS/215
	Extension of institutional strengthening project 
(phase XII: 1/2020-12/2021)
	2,244
	157
	2,401

	IND/SEV/84/INS/478
	Extension of institutional strengthening project 
(phase XII: 12/2019-11/2021)
	1,547
	108
	1,655

	IRA/SEV/82/INS/231
	Extension of the institutional strengthening project (phase XII: 4/2019-3/2021)
	474
	33
	507

	JAM/PHA/84/TAS/39
	Verification report on the implementation of the HCFC phase-out management plan
	3,421
	308
	3,729

	JAM/PHA/85/INV/41
	HCFC phase-out management plan (stage I, fourth tranche)
	3,102
	233
	3,335

	MAL/SEV/84/INS/188
	Extension of institutional strengthening project 
(phase XIII: 1/2020-12/2021)
	438
	31
	469

	PAN/SEV/80/INS/45
	Extension of institutional strengthening project 
(phase VIII: 12/2017-11/2019)
	1
	0
	1

	TOG/PHA/48/PRP/13
	Project preparation for a terminal phase-out management plan in the refrigeration servicing sector
	1
	0
	1

	TRI/PHA/82/PRP/36
	Preparation of a HCFC phase-out management plan (stage II)
	806
	56
	862

	Total completed projects
	
	562,920
	39,505
	602,425

	TOTAL UNDP
	
	562,920
	39,505
	602,425

	AFG/SEV/83/INS/26
	Extension of institutional strengthening project 
(phase IX: 1/2020-12/2021)
	38,119
	0
	38,119

	ALB/SEV/84/INS/38
	Renewal of institutional strengthening project 
(phase IX: 7/2020-6/2022)
	1,109
	0
	1,109

	BDI/SEV/85/TAS/39
	Enabling activities for HFC phase-down
	50,000
	3,500
	53,500

	BEN/PHA/84/PRP/37
	Preparation of a HCFC phase-out management plan (stage II)
	9,800
	1,274
	11,074

	BGD/SEV/81/TAS/54
	Enabling activities for HFC phase-down
	3,582
	251
	3,833

	BHA/PHA/84/PRP/30
	Preparation of a HCFC phase-out management plan (stage II)
	4,850
	631
	5,481

	BHU/PHA/76/TAS/25
	HCFC phase-out management plan (third tranche)
	10
	1
	11

	BHU/SEV/83/INS/28
	Extension of institutional strengthening project 
(phase VIII: 12/2019-11/2021)
	2,407
	0
	2,407

	BOT/PHA/82/TAS/22
	HCFC phase-out management plan (stage I, second tranche)
	9,481
	1,232
	10,713

	BOT/PHA/83/PRP/23
	Preparation of a HCFC phase-out management plan (stage II)
	3,255
	423
	3,678

	BOT/PHA/86/TAS/25
	HCFC phase-out management plan (stage I, third tranche)
	47,627
	6,192
	53,819

	BOT/SEV/76/INS/19
	Extension of institutional strengthening project 
(phase V: 6/2016-7/2018)
	65,956
	0
	65,956

	BRU/PHA/82/TAS/24
	HCFC phase-out management plan (stage I, third tranche)
	5,977
	777
	6,754

	CKI/PHA/74/TAS/11
	HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Cook Islands)
	3,169
	412
	3,581

	CKI/PHA/85/TAS/16
	HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche)
	2,500
	325
	2,825

	CKI/SEV/84/INS/15
	Extension of the institutional strengthening project (phase VII: 7/2020-6/2022)
	5,000
	0
	5,000

	DJI/PHA/88/TAS/28
	HCFC phase-out management plan (stage I, fourth tranche)
	95
	12
	107

	DRC/SEV/87/INS/47
	Extension of the institutional strengthening project (phase X: 7/2021-6/2023)
	200
	0
	200

	ELS/PHA/86/TAS/40
	HCFC phase-out management plan (stage I, fourth tranche)
	32
	1
	33

	EQG/PHA/86/TAS/17
	Verification report on the implementation of the HCFC phase-out management plan
	240
	31
	271

	FSM/PHA/85/TAS/15
	HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche)
	142
	18
	161

	FSM/SEV/84/INS/13
	Renewal of institutional strengthening project 
(phase VII: 7/2020-6/2022)
	1,987
	0
	1,987

	GAB/PHA/87/TAS/41
	HCFC phase-out management plan (stage I, fifth tranche)
	200
	26
	226

	GLO/SEV/84/TAS/350
	Compliance Assistance Programme: 2020 budget
	79,692
	6,375
	86,067

	GLO/SEV/86/TAS/356
	Compliance Assistance Programme: 2021 budget
	212,006
	16,960
	228,967

	GLO/SEV/88/TAS/357
	Compliance Assistance Programme: 2022 budget
	599,922
	47,994
	647,915

	GRN/PHA/82/PRP/25
	Preparation of a HCFC phase-out management plan (stage II)
	9,800
	1,274
	11,074

	GRN/PHA/82/TAS/26
	Verification report on the implementation of the HCFC phase-out management plan
	18,890
	2,456
	21,346

	GUI/SEV/85/TAS/36
	Enabling activities for HFC phase-down
	50,000
	3,500
	53,500

	HAI/SEV/75/INS/20
	Extension of the institutional strengthening project (phase IV: 11/2015-10/2017)
	73,671
	0
	73,671

	HON/PHA/86/TAS/51
	HCFC phase-out management plan (stage I, fifth tranche)
	255
	33
	288

	IND/PHA/77/TAS/470
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector plan)
	144
	17
	161

	IND/PHA/87/PRP/490
	Preparation of HCFC phase-out management plan (stage III) (Overarching)
	2,000
	260
	2,260

	IRA/SEV/82/TAS/233
	Enabling activities for HFC phase-down
	30,333
	2,123
	32,457

	IVC/PHA/90/TAS/48
	HCFC phase-out management plan (stage I, fifth tranche)
	380
	46
	426

	KAM/PHA/84/TAS/38
	Verification report on the implementation of the HCFC phase-out management plan
	4,900
	637
	5,537

	KUW/PHA/66/TAS/19
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector and monitoring and verification)
	50,071
	5,988
	56,059

	KUW/PHA/74/TAS/23
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector and monitoring and verification)
	113,335
	13,553
	126,888

	KUW/PHA/88/TAS/44
	HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing sector)
	24,000
	2,870
	26,870

	LAO/PHA/85/TAS/34
	HCFC phase-out management plan (stage I, third tranche)
	5,055
	657
	5,712

	MAG/PHA/84/PRP/34
	Preparation of a HCFC phase-out management plan (stage II)
	14,900
	1,937
	16,837

	MAS/PHA/74/TAS/11
	HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Marshall Islands)
	3,370
	438
	3,809

	MAS/PHA/85/TAS/16
	HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche)
	2,900
	377
	3,277

	MAU/PHA/80/TAS/24
	HCFC phase-out management plan (stage I, first tranche)
	155
	20
	175

	MLI/PHA/83/TAS/40
	HCFC phase-out management plan (stage I, fourth tranche)
	200
	26
	226

	MLI/PHA/86/TAS/43
	Verification report on the implementation of the HCFC phase-out management plan
	205
	27
	232

	MLW/PHA/85/TAS/47
	HCFC phase-out management plan (stage II, first tranche)
	510
	66
	576

	MOZ/PHA/86/TAS/35
	Verification report on the implementation of the HCFC phase-out management plan
	26
	3
	30

	NAU/PHA/74/TAS/10
	HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Nauru)
	5,776
	751
	6,527

	NAU/PHA/85/TAS/13
	HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche)
	4,370
	568
	4,938

	NEP/PHA/75/TAS/34
	HCFC phase-out management plan (stage I, second tranche)
	10,575
	1,375
	11,950

	NEP/PHA/86/TAS/42
	HCFC phase-out management plan (stage I, third tranche)
	6,487
	843
	7,330

	NIU/PHA/85/TAS/15
	HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche)
	3,051
	397
	3,448

	PAK/PHA/76/TAS/93
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	2,525
	328
	2,853

	PAK/PHA/85/PRP/104
	Preparation of a HCFC phase-out management plan (stage III)
	4,583
	596
	5,179

	PAR/PHA/86/TAS/40
	HCFC phase-out management plan (stage I, third tranche)
	44
	6
	50

	PAR/SEV/82/INS/38
	Extension of institutional strengthening project 
(phase IX: 1/2019-12/2020)
	3,805
	0
	3,805

	PER/PHA/80/TAS/54
	HCFC phase-out management plan (stage II, first tranche)
	48
	6
	54

	SAU/PHA/68/TAS/16
	HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring)
	3,375
	418
	3,793

	SAU/PHA/77/TAS/32
	HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring)
	4,125
	511
	4,636

	SEN/PHA/85/PRP/42
	Preparation of a HCFC phase-out management plan (stage II)
	42
	5
	47

	SIL/PHA/84/PRP/35
	Preparation of a HCFC phase-out management plan (stage II)
	4,658
	606
	5,264

	SOI/PHA/74/TAS/11
	HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Solomon Islands)
	3,234
	420
	3,654

	SOI/PHA/85/TAS/17
	HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche)
	13
	2
	14

	SSD/PHA/84/TAS/05
	Verification report on the implementation of the HCFC phase-out management plan
	42
	6
	48

	SUD/SEV/81/INS/43
	Extension of institutional strengthening 
(phase IX: 7/2018-6/2020)
	18
	0
	18

	SUR/PHA/86/TAS/31
	Verification report on the implementation of the HCFC phase-out management plan
	4,750
	618
	5,368

	SWA/PHA/86/TAS/30
	Verification report on the implementation of the HCFC phase-out management plan
	42
	6
	48

	TLS/SEV/82/TAS/19
	Enabling activities for HFC phase-down
	3,331
	233
	3,565

	TLS/SEV/84/INS/20
	Extension of institutional strengthening 
(phase V: 7/2020-6/2022)
	2,746
	0
	2,746

	TOG/PHA/83/PRP/34
	Preparation of a HCFC phase-out management plan (stage II)
	9,800
	1,274
	11,074

	TOG/PHA/87/TAS/36
	HCFC phase-out management plan (stage I, fifth tranche)
	120
	16
	136

	TON/PHA/74/TAS/10
	HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Tonga)
	1,891
	246
	2,137

	TUV/PHA/74/TAS/11
	HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Tuvalu)
	1,981
	257
	2,238

	TUV/PHA/85/TAS/16
	HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche)
	2,000
	260
	2,260

	VAN/PHA/85/TAS/17
	HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche)
	3,750
	487
	4,237

	VAN/SEV/84/INS/15
	Extension of institutional strengthening project 
(phase VII: 7/2020-6/2022)
	5,000
	0
	5,000

	Total completed projects
	
	1,644,641
	132,980
	1,777,621

	AFG/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	13,112
	918
	14,030

	BEN/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	21,115
	1,478
	22,593

	BOT/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	53,352
	3,735
	57,087

	CBI/SEV/82/TAS/01+
	Enabling activities for HFC phase-down
	15,962
	1,117
	17,079

	CHD/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	19,800
	1,386
	21,186

	CKI/SEV/82/TAS/01+
	Enabling activities for HFC phase-down
	2,290
	160
	2,450

	COI/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	4,758
	333
	5,091

	DJI/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	27,578
	1,930
	29,508

	DRC/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	17,766
	1,244
	19,010

	EQG/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	36,846
	2,579
	39,425

	GAB/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	15,798
	1,106
	16,904

	GBS/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	24,197
	1,694
	25,891

	GUY/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	40,000
	2,800
	42,800

	IVC/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	14,395
	1,008
	15,403

	KEN/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	652
	46
	698

	KIR/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	17,102
	1,197
	18,299

	LAO/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	40,918
	2,864
	43,782

	MAG/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	34,446
	2,411
	36,857

	MAS/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	12,418
	869
	13,287

	MAU/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	47,662
	3,336
	50,998

	MDV/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	199
	14
	213

	MLI/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	1,931
	135
	2,066

	MYA/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	41,377
	2,896
	44,273

	NEP/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	7,835
	548
	8,383

	PAR/SEV/81/TAS/02+
	Enabling activities for HFC phase-down
	4,343
	304
	4,647

	SOI/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	6,345
	444
	6,789

	SRL/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	977
	68
	1,045

	STP/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	11,085
	776
	11,861

	SUD/SEV/80/TAS/02+
	Enabling activities for HFC phase-down
	5,833
	408
	6,241

	SUR/SEV/80/TAS/01+
	Enabling activities for HFC phase-down
	29,350
	2,055
	31,405

	SYR/SEV/83/TAS/01+
	Enabling activities for HFC phase-down
	31,765
	2,224
	33,989

	Total “additional voluntary contributions” projects
	
	601,206
	42,084
	643,290


	TOTAL UNEP
	
	2,245,847
	175,064
	2,420,911

	BAH/FOA/84/PRP/35
	Preparation for HCFC phase-out investment activities (stage II) (foam sector)
	687
	48
	735

	BHE/PHA/87/INV/40
	HCFC phase-out management plan (stage I, fifth tranche)
	6,105
	427
	6,532

	BHE/SEV/80/INS/34
	Extension of the institutional strengthening project (phase VI: 3/2018-2/2020)
	32
	3
	35

	CHD/PHA/82/PRP/33
	Preparation of a HCFC phase-out management plan (stage II)
	857
	60
	917

	CPR/PHA/75/INV/564
	HCFC phase-out management plan (stage I, fifth tranche) (room air conditioner manufacturing sector plan)
	22,180
	1,553
	23,733

	EQG/PHA/84/PRP/15
	Preparation of a HCFC phase-out management plan (stage II)
	1,602
	112
	1,715

	GAM/PHA/82/PRP/37
	Preparation of a HCFC phase-out management plan (stage II)
	770
	54
	824

	GBS/PHA/81/PRP/23
	Preparation of a HCFC phase-out management plan (stage II)
	89
	6
	95

	KUW/PHA/83/INV/36
	HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector phase-out)
	17,780
	1,245
	19,024

	MOR/FOA/73/PRP/71
	Preparation for HCFC phase-out investment activities (stage II) (foam sector)
	11,672
	817
	12,489

	MOR/PHA/73/PRP/70
	Preparation of a HCFC phase-out management plan (stage II)
	23,633
	1,654
	25,287

	NIR/PHA/81/INV/146
	HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector and project management unit)
	90
	8
	98

	PAK/PHA/85/PRP/105
	Preparation of a HCFC phase-out management plan (stage III) (foam sector)
	7,363
	515
	7,878

	PRC/PHA/81/PRP/34
	Preparation of a HCFC phase-out management plan (stage II)
	481
	34
	514

	SAU/PHA/72/INV/20
	HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring)
	25,449
	1,782
	27,231

	SAU/PHA/75/INV/24
	HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan)
	200,387
	14,027
	214,414

	SUD/PHA/82/INV/44
	HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector)
	2,170
	152
	2,322

	TOG/PHA/79/INV/30
	HCFC phase-out management plan (stage I, third tranche)
	1,951
	146
	2,097

	VEN/PHA/76/TAS/132
	HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector)
	166
	12
	177

	Total completed projects
	
	323,465
	22,654
	346,119

	SAU/REF/76/DEM/28
	Demonstration project on promoting HFO‑based low-global warming potential refrigerants for air-conditioning sector in high ambient temperatures. 
	114,237
	7,997
	122,234

	Total “by-decision” projects
	
	114,237
	7,997
	122,234

	LIB/SEV/81/TAS/01+
	Enabling activities for HFC phase-down
	2,492
	174
	2,667

	MEX/REF/81/INV/04+
	Conversion of commercial refrigeration manufacturing in two facilities from the use of HFC-134a and R-404A as the refrigerants to propane (R-290) and isobutane (R-600a) at Imbera
	92,426
	6,469
	98,895

	PHI/SEV/83/TAS/02+
	Enabling activities for HFC phase-down
	18,703
	1,309
	20,012

	Total “additional voluntary contributions” projects
	
	113,621
	7,952
	121,573

	TOTAL UNIDO
	
	551,323
	38,603
	589,926

	GLO/SEV/88/TAS/358
	Core unit budget (2022)
	0
	280,124
	280,124

	JOR/PHA/88/PRP/112
	Preparation of HCFC phase-out management plan (stage III) (commercial refrigeration manufacturing)
	30,000
	2,100
	32,100

	MAL/KIP/91/PRP/194
	Preparation of HFC investment projects in firefighting sector
	150,000
	10,500
	160,500

	VIE/KIP/92/PRP/85
	Preparation of a KIP investment project in the commercial refrigeration sector for Sanaky
	30,000
	2,100
	32,100

	VIE/KIP/92/PRP/86
	Preparation of a KIP investment project in the domestic refrigeration sector for Aqua Electrical Appliances, Darling Electronics, and Hoa Phat Refrigeration Engineering
	80,000
	5,600
	85,600

	VIE/KIP/92/PRP/88
	Conversion of refrigerator manufacture from CFC-11 to cyclopentane foam blowing agent and CFC-12 to R-134a refrigerant at Domestic Appliances Ltd. (DAL)
	30,000
	2,100
	32,100

	Total completed projects
	
	320,000
	302,524
	622,524

	TOTAL 
WORLD BANK
	
	320,000
	302,524
	622,524

	LAO/PHA/74/INV/28
	HCFC phase-out management plan (stage I, second tranche)
	40,500
	5,265
	45,765

	LAO/PHA/85/TAS/35
	HCFC phase-out management plan (stage I, third tranche)
	4,500
	585
	5,085

	TOTAL FRANCE
	
	45,000
	5,850
	50,850
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