| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/95/30 10 November 2024 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-fifth Meeting

Montreal, 4-8 December 2024

Item 8(d)(v) of the provisional agenda

THE WORLD BANK Business plan for 2025–2027

# Introduction

# This document presents the World Bank business plan for 2025–2027 and includes the planned activities for the reduction of controlled substances and other activities under the Montreal Protocol during the period 2025-2027. The narrative of the World Bank’s business plan for 2025–2027 is attached to the present document.

# This document consists of the following sections:

- Planned activities during the period 2025–2027

- Secretariat’s comments

- Proposed adjustments by the Secretariat

- Performance indicators

- Recommendation

I.	Planned activities during the period 2025–2027

# Table 1 sets out, by year, the value of activities included in the World Bank’s business plan.

Table 1. Resource allocation in the World Bank business plan for 2025–2027 (US $)* – as submitted

| Description | 2025 | 2026 | 2027 | Total (2025–2027) | Total after 2027 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 5,536,763 | 9,426,894 | 0 | 14,963,657 | 1,479,869 |
| HCFC production phase-out management plan (HPPMP) stage III – project preparation (PRP) | 321,000 | 0 | 0 | 321,000 | 0 |
| HPPMP stage III | 0 | 0 | 23,540,000 | 23,540,000 | 23,540,000 |
| HPMP stage III | 4,280,000 | 0 | 10,700,000 | 14,980,000 | 10,700,000 |
| HCFC activities subtotal | 10,137,763 | 9,426,894 | 34,240,000 | 53,804,657 | 35,719,869 |
| HFC activities |  |  |  |  |  |
| Approved Kigali HFC implementation plans (KIPs) | 3,473,530 | 1,619,110 | 2,500,221 | 7,592,861 | 1,253,464 |
| Kigali HFC implementation plan for the production sector (KIPP) stage I – PRP | 321,000 | 0 | 0 | 321,000 | 0 |
| KIP stage I | 6,420,000 | 0 | 11,770,000 | 18,190,000 | 11,770,000 |
| HFC activities subtotal | 10,214,530 | 1,619,110 | 14,270,221 | 26,103,861 | 13,023,464 |
| Other activities |  |  |  |  |  |
| Energy efficiency (decision 94/60) | 0 | 648,215 | 0 | 648,215 | 0 |
| National inventories of banks of waste-controlled substances – PRP (decision 91/66) | 107,000 | 0 | 0 | 107,000 | 0 |
| Other activities subtotal | 107,000 | 648,215 | 0 | 755,215 | 0 |
| Standard activities |  |  |  |  |  |
| Core unit | 1,959,375 | 1,771,691 | 1,784,092 | 5,515,158 | 0 |
| Institutional strengthening (IS) | 982,829 | 0 | 0 | 982,829 | 0 |
| Standard activities subtotal | 2,942,204 | 1,771,691 | 1,784,092 | 6,497,988 | 0 |
| Total | 23,401,497 | 13,465,910 | 50,294,313 | 87,161,721 | 48,743,333 |

* Including agency support costs where applicable.

# II.	Secretariat’s comments

II.1	HCFC activities

Stage III of HPPMP

# A total of US $47.08 million is planned for stage III of the HPPMP for one country, including US $23.54 million for 2025–2027 and US $23.54 million for the period after 2027. A total of US $321,000 is also included in the business plan for project preparation for stage III of the HPPMP for this country in 2025.

# Stage III of HPMPs

# A total of US $25.68 million is planned for stage III of the HPMP for one country, including US $14.98 million for 2025–2027 and US $10.7 million for the period after 2027. Inclusion of stage III of HPMPs in the business plan including project preparation is allowed for countries for which stage II of the HPMP had been approved and which had a reduction target beyond 2024 (decision 88/34(d)).

II.2	HFC-related activities

Project preparation for stage I of a KIPP

# A total of US $321,000 is included in the business plan for project preparation for stage I of the KIPP for one country in 2025.

Stage I of KIPs

# A total of US $29.96 million is included in the business plan for stage I of KIPs for two countries (including US $18.19 million for 2025–2027 and US $11.77 million for the period after 2027). All these countries have ratified the Kigali Amendment.

II.3	Other activities

Energy efficiency (decision 94/60)

# A total of US $648,215 is included in the business plan under the funding window for energy efficiency per decision 94/60 for 2026 for one country. This project was submitted to the 95th meeting and therefore, has been removed from the business plan.

Project preparation for national inventories of banks of waste-controlled substances (decision 91/66)

# A total of US $107,000 is included in the business plan for the preparation of national inventories of banks of waste-controlled substances for 2025 for one country.

# II.4	Core unit costs

# The core unit costs are expected to increase at an annual rate of 0.7 per cent as agreed, and include additional core unit funding in the amount of US $200,000 in 2025 for 2026, pursuant to decision 93/95(b).

III.	Proposed adjustments by the Secretariat

# The adjustments to the World Bank business plan for 2025–2027 were based on relevant decisions of the Executive Committee. In reviewing the revised business plan of the World Bank for 2025–2027, the Secretariat noted that the following adjustments were not included:

Table 2. Adjustments to the World Bank business plan for 2025–2027 (US $)* – as proposed by the Secretariat

| Adjustment | 2025–2027 | After 2027 |
| --- | --- | --- |
| Energy efficiency per decision 94/60 submitted to the 95th meeting | (648,215) | 0 |

* Including agency support costs where applicable.

# Table 3 presents the results of the Secretariat’s proposed adjustments to the World Bank business plan for 2025–2027, which are also addressed in the context of the consolidated business plan of the Multilateral Fund for 2025–2027.

Table 3. Resource allocation in the World Bank’s adjusted business plan for 2025–2027 (US $)*

| Description | 2025 | 2026 | 2027 | Total (2025–2027) | Total after 2027 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HPMPs | 5,536,763 | 9,426,894 | 0 | 14,963,657 | 1,479,869 |
| HPPMP stage III – PRP | 321,000 | 0 | 0 | 321,000 | 0 |
| HPPMP stage III | 0 | 0 | 23,540,000 | 23,540,000 | 23,540,000 |
| HPMP stage III | 4,280,000 | 0 | 10,700,000 | 14,980,000 | 10,700,000 |
| HCFC activities subtotal | 10,137,763 | 9,426,894 | 34,240,000 | 53,804,657 | 35,719,869 |
| HFC activities |  |  |  |  |  |
| Approved KIPs | 3,473,530 | 1,619,110 | 2,500,221 | 7,592,861 | 1,253,464 |
| KIPP stage I – PRP | 321,000 | 0 | 0 | 321,000 | 0 |
| KIP stage I | 6,420,000 | 0 | 11,770,000 | 18,190,000 | 11,770,000 |
| HFC activities subtotal | 10,214,530 | 1,619,110 | 14,270,221 | 26,103,861 | 13,023,464 |
| Other activities |  |  |  |  |  |
| Energy efficiency (decision 94/60) | 0 | 0 | 0 | 0 | 0 |
| National inventories of banks of waste-controlled substances – PRP (decision 91/66) | 107,000 | 0 | 0 | 107,000 | 0 |
| Other activities subtotal | 107,000 | 0 | 0 | 107,000 | 0 |
| Standard activities |  |  |  |  |  |
| Core unit | 1,959,375 | 1,771,691 | 1,784,092 | 5,515,158 | 0 |
| IS | 982,829 | 0 | 0 | 982,829 | 0 |
| Standard activities subtotal | 2,942,204 | 1,771,691 | 1,784,092 | 6,497,988 | 0 |
| Total | 23,401,497 | 12,817,695 | 50,294,313 | 86,513,506 | 48,743,333 |

* Including agency support costs where applicable.

IV.	Performance indicators

# The World Bank submitted performance indicators pursuant to decision 93/8(d) in its business plan narrative. The Secretariat informed the World Bank of the targets shown in table 4.

Table 4. Performance indicators for the World Bank for 2025

| Type of indicator | Short title | Calculation | 2025 target |
| --- | --- | --- | --- |
| Planning-Approval | Tranches approved | Number of tranches approved vs. those planned* | 6 |
| Planning-Approval | Individual projects/ activities approved | Number of projects/activities approved vs. those planned (including project preparation activities) | 5 |
| Implementation | Funds disbursed | Based on estimated disbursement in progress reports | 17,987,381 |
| Implementation | ODS phase-out for HCFC-related projects | ODS phase-out for HCFC-related projects in ODP tonnes vs. those planned per progress reports | 5,996.9 ODP tonnes |
| Implementation | HFC phase-down for HFC-related projects | HFC phase-down for HFC-related projects in CO2-eq tonnes vs. those planned per progress reports | zero CO2-eq tonne |
| Implementation | Project operational completion | Project operational completion vs. planned in progress reports for all activities (excluding project preparation)** | 8 |
| Implementation | Gender mainstreaming | Operational policy on gender mainstreaming applied to all approved projects | 100% |
| Administrative | Speed of financial completion | The extent to which projects are financially completed within 12 months after project operational completion | 12 months after operational completion |
| Administrative | Timely submission of project completion reports | Timely submission of project completion reports based on the progress report | 0 |
| Administrative | Timely submission of progress reports and business plans | Timely submission of progress reports and business plans and responses unless otherwise agreed | On time |

- * The targets of an agency will be reduced if it cannot submit a tranche owing to another cooperating agency or lead agency or if the HCFC phase-out management plan or Kigali HFC implementation plan submitted for consideration by the Executive Committee is not approved as a result of factors beyond the control of the national ozone unit and agency.

- ** The targets of an agency will be reduced if an extension of the completion date has been approved by the Executive Committee.

V.	Recommendation

# The Executive Committee may wish:

## To note the World Bank business plan for 2025–2027 contained in document UNEP/OzL.Pro/ExCom/95/30; and

## To approve the performance indicators for the World Bank set out in table 4 of document UNEP/OzL.Pro/ExCom/95/30.

UNEP/OzL.Pro/ExCom/95/1

The Executive Committee established a funding window for projects developed and implemented under the operational framework to support maintaining and/or enhancing energy efficiency while phasing down HFCs.

The Executive Committee established a funding window and criteria for the preparations of national inventories of banks of used or unwanted controlled substances and a plan for the collection, transport, and disposal of such substances.

The World Bank’s 2025 core unit costs will be considered at the 95th meeting (UNEP/OzL.Pro/ExCom/95/84).

The Executive Committee approved an increase in the core unit funding for the World Bank by US $200,000, for each year of the triennium 2024–2026, for the strengthening of its capacity to provide technical and policy support to Article 5 countries, on the understanding that the increase only applied to the triennium 2024–2026.

UNEP/OzL.Pro/ExCom/95/25