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اللجنــة التنفيـذيــــة للصنــدوق المــتعــدد الأطـــراف
لتنفيـــذ بروتوكـول مونتريــال 
الاجتمــــــاع الثامن والثمانون
مونتريال،  من 15 إلى 19 نوفمبر/ تشرين الثاني 2021 [footnoteRef:1] [1:   ستعقد اجتماعات عبر الإنترنت وعملية الموافقة فيما بين الدورات في نوفمبر/ تشرين الثاني وديسمبر/ كانون الأول بسبب  فيروس  كورونا  (كوفيد‑19)

] 





[bookmark: _GoBack]تعديلات برنامج عمل برنامج الأمم المتحدة الإنمائي لعام 2021


تعليقات أمانة الصندوق وتوصيتها
1. يطلب برنامج الأمم المتحدة للبيئة (اليونيب) موافقة اللجنة التنفيذية على المبلغ 2,753,347 دولاراً أمريكياً بالإضافة إلى تكاليف دعم الوكالة بقيمة 193,334 دولاراً أمريكياً لتعديلات برنامج عمله للعام 2021 المدرج في الجدول 1. والطلب مرفق بهذه الوثيقة. 
الجدول 1: التعديلات المدخلة على برنامج عمل برنامج الأمم المتحدة الإنمائي لعام 2021
	البلد
	النشاط/المشروع
	المبلغ المطلوب (دولار أمريكي)
	المبلغ الموصى به (دولار أمريكي)

	القسم ألف: الأنشطة الموصى بالموافقة الشاملة عليها

	ألف-1: مشروعات تجديد التعزيز المؤسسي

	بنغلاديش
	تجديد مشروع التعزيز المؤسسي (المرحلة العاشرة) 
	166,400
	166,400

	كولومبيا
	تجديد مشروع التعزيز المؤسسي (المرحلة الثالثة عشرة) 
	352,768
	352,768

	كوستاريكا
	تجديد مشروع التعزيز المؤسسي (المرحلة الحادية عشرة) 
	179,857
	179,857

	الهند
	تجديد مشروع التعزيز المؤسسي (المرحلة الثالثة عشرة) 
	477,734
	477,734

	ماليزيا
	تجديد مشروع التعزيز المؤسسي (المرحلة الحادية عشرة) 
	357,760
	357,760

	ترينيداد وتوباغو
	تجديد مشروع التعزيز المؤسسي (المرحلة الحادية عشرة) 
	85,000
	85,000

	أوروغواي
	تجديد مشروع التعزيز المؤسسي (المرحلة الحادية عشرة) 
	193,024
	193,024

	المجموع الفرعي لـ ألف-1
	1,812,543
	1,812,543

	تكاليف دعم الوكالة
	126,878
	126,878

	مجموع ألف-1
	1,939,421
	1,939,421

	ألف-2: إعداد المشروع لخطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية

	البرازيل أ ب
	إعداد خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية (المرحلة الثالثة)
	40,000
	40,000

	المجموع الفرعي لــ ألف-2
	40,000
	40,000

	تكاليف دعم الوكالة
	2,800
	2,800

	مجموع ألف-2
	42,800
	42,800

	ألف-3: المساعدة التقنية المقدمة لإعداد تقارير التحقق من استهلاك الهيدروكلوروفلوروكربون

	كوبا
	تقرير التحقق للمرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية
	30,000
	30,000

	المجموع الفرعي لـ ألف-3
	30,000
	30,000

	تكاليف دعم الوكالة
	2,700
	2,700

	مجموع ألف-3
	32,700
	32,700

	ألف-4: إعداد المشروعات لخطط تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون

	البلد
	النشاط/المشروع
	المبلغ المطلوب (دولار أمريكي)
	المبلغ الموصى به (دولار أمريكي)

	أنغولا
	إعداد خطة تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون (المرحلة الأولى)
	170,000
	170,000

	كمبوديا
	إعداد خطة تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون (المرحلة الأولى)
	35,000
	35,000

	شيلي د
	إعداد خطة تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون (المرحلة الأولى)
	170,000
	170,000

	السلفادور
	إعداد خطة تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون (المرحلة الأولى)
	170,000
	170,000

	فيجي د
	إعداد خطة تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون (المرحلة الأولى)
	95,000
	95,000

	غرينادا
	إعداد خطة تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون (المرحلة الأولى)
	40,000
	40,000

	المجموع الفرعي لـ ألف-4
	680,000
	680,000

	تكاليف دعم الوكالة
	47,600
	47,600

	مجموع ألف-4
	727,600
	727,600

	المجموع الكلي (ألف-1 وألف-2 وألف-3 وألف-4)
	2,742,521
	2,742,521


أ   حكومة ألمانيا بوصفها وكالة ثنائية متعاونة
ب اليونيدو بوصفها وكالة منفذة متعاونة
ج اليونيب بوصفه الوكالة المنفذة الرئيسية
د اليونيب بوصفه وكالة منفذة متعاونة

القسم ألف: الأنشطة الموصى بالموافقة الشاملة عليها
ألف-1: مشروعات تجديد التعزيز المؤسسي 
وصف المشروع
قدم البرنامج الإنمائي طلبات لتجديد مشروعات التعزيز المؤسسي للبلدان المدرجة في الفرع ألف-1 من الجدول 1. وترد أوصاف هذه المشروعات في المرفق الأول بهذه الوثيقة.
تعليقات الأمانة
استعرضت الأمانة طلبات تجديد سبعة مشروعات للتعزيز المؤسسي نيابة عن الحكومات المعنية وفقا للمبادئ التوجيهية والقرارات المتعلقة باستيفاء  الاشتراطات ومستويات التمويل. وجرى التحقق من الطلبات مقارنةً بخطط عمل التعزيز المؤسسي الأصلية الخاصة بالمرحلة السابقة وبيانات البرنامج القطري وبيانات المادة 7، وآخر تقرير عن تنفيذ خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية، والتقرير المرحلي للوكالة، وأي مقررات ذات صلة صادرة عن اجتماع الأطراف. ولوحظ أن هذه البلدان قد قدمت بيانات برامجها القطرية لعام 2020، وأنها ممتثلة لأهداف الرقابة بموجب بروتوكول مونتريال، وأن استهلاكها السنوي من الهيدروكلوروفلوروكربون لا يتجاوز الحد الأقصى السنوي المسموح به للاستهلاك المشار إليه في اتفاقات خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية التي أبرمتها مع اللجنة التنفيذية. وعلاوةً على ذلك، شملت الطلبات المقدمة مؤشرات أداء للأنشطة المقررة للمرحلة التالية من مشروعات التعزيز المؤسسي، وفقاً للمقرر 74/51 (هـ).
توصية الأمانة
توصي الأمانة بالموافقة الشاملة على طلبات تجديد التعزيز المؤسسية لبنغلاديش وكولومبيا وكوستاريكا والهند وماليزيا وترينيداد وتوباغو وأوروغواي بمستوى التمويل المشار إليه في الفرع ألف1 من الجدول 1 من هذه الوثيقة. وقد ترغب اللجنة التنفيذية في أن تعرب للحكومات المذكورة أعلاه التعليقات الواردة في المرفق الثاني بهذه الوثيقة.
ألف 2: إعداد مشروع خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية
وصف المشروع
قدم البرنامج الإنمائي طلبا لإعداد المرحلة الثالثة من  خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية للبرازيل بوصفه الوكالة المنفذة الرئيسية، مع حكومة ألمانيا واليونيدو بوصفهما وكالتين متعاونتين. ويرد هذا الطلب في القسم ألف-2 من الجدول 1.
وقد طلبت حكومة ألمانيا، بوصفها وكالة متعاونة، مبلغا إجماليا قدره 25,000 دولارا أمريكيا، بالإضافة إلى تكاليف دعم الوكالة التي تبلغ 3,250 دولاراً أمريكياً في إطار التعاون الثنائي؛[footnoteRef:2] وطلبت اليونيدو مبلغ 25,000 دولار أمريكي، بالإضافة إلى تكاليف دعم الوكالة البالغة 1,750 دولاراً أمريكياً في تعديلات برنامج عملها لعام 2021.[footnoteRef:3] [2:  UNEP/OzL.Pro/ExCom/88/29]  [3:  UNEP/OzL.Pro/ExCom/88/32] 

وتضمن العرض: مبررات للتمويل المطلوب لإعداد المشروع؛ وتقريرا مرحليا عن تنفيذ المرحلة الثانية من خطط كل منها لإدارة إزالة المواد الهيدروكلوروفلوروكربونية للبرازيل؛ والأنشطة المحتملة والنفقات المصاحبة. 
تعليقات الأمانة
عند استعراض هذا الطلب، أخذت الأمانة في الاعتبار المبادئ التوجيهية لتمويل إعداد خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية للبلدان العاملة بالمادة 5 الواردة في المقرر 71/42، [footnoteRef:4]والمرحلة الثانية من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية للبرازيل، وحالة تنفيذ الشرائح عند إعداد الوثيقة الحالية، والمقرر 84/46(هـ).[footnoteRef:5] ولاحظت الأمانة أن التمويل المطلوب يتماشى مع المقرر 71/42 وأن اليونيدو أكدت أن شرائح التمويل المتبقية لهذه البلدان ستُقدم على النحو المقرر في اتفاق حكومة البرازيل مع اللجنة التنفيذية.  [4:  المبادئ التوجيهية لتمويل إعداد المرحلة الثانية من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية في البلدان العاملة بالمادة 5.]  [5:  لا يسمح بإدراج المرحلة الثالثة من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية إلا للبلدان التي وافقت على المرحلة الثانية من الخطط التي تقل أهداف التخفيض فيها عن أهداف الامتثال لعام 2025.] 

وأكد البرنامج الإنمائي أن المرحلة الثالثة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية  للبرازيل ستلغى تدريجيا 100 في المائة من خط الأساس للهيدروكلوروفلوروكربون بحلول 1 كانون الثاني/يناير 2030، باستثناء متابعة الخدمة. 
توصيات الأمانة
توصي الأمانة بالموافقة الشاملة على مشروع إعداد المرحلة الثالثة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية للبرازيل على أساس التمويل الوارد في القسم ألف-2 من الجدول 1.

ألف-3: المساعدة التقنية لإعداد تقارير التحقق من استهلاك الهيدروكلوروفلوروكربون
وصف المشروع
طلبت اللجنة التنفيذية إلى الوكالات الثنائية والتنفيذية ذات الصلة أن تدرج في كل منها تعديلات برنامج العمل لتقديمها إلى الاجتماع الثامن والثمانين، وتمويل إعداد تقارير التحقق لبلدان مختارة من البلدان العاملة بالمادة 5. ويطلب البرنامج الإنمائي بوصفه الوكالة المنفذة الرئيسية تمويلا للتحقق من المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لكوبا.[footnoteRef:6]  [6:  المقرر87/27 ] 

تعليقات الأمانة
أشارت الأمانة إلى أن التمويل المطلوب يتوافق مع الأموال الموافق عليها لعمليات التحقق المماثلة الخاصة باجتماعات سابقة. ولاحظت كذلك أنه يتعيَّن تقديم تقرير التحقق قبل 10 أيام على الأقل من اجتماع اللجنة التنفيذية ذي الصلة الذي تُطلب فيه شريحة التمويل التالية لخطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية.
توصية الأمانة
توصي الأمانة بالموافقة الشاملة مقابل تقرير التحقق للمرحلة الثانية من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية لكوبا بمستوى التمويل الوارد في القسم ألف-2 من الجدول 1، على أن يكون مفهوما أنه ينبغي تقديم تقرير التحقق قبل 10 أيام على الأقل من اجتماع اللجنة التنفيذية الذي ستُطلب فيه شريحة التمويل التالية لخطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية لتلك البلدان.
ألف4: إعداد المشروعات لخطط تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون
وصف المشروع
قدم البرنامج الإنمائي طلبات لإعداد المرحلة الأولى من خطط تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون لبلدين من بلدان المادة 5 باعتباره وكالة منفذة معينة، ولبلدين من بلدان المادة 5  باعتباره وكالة منفذة رئيسية، ولبلدين من بلدان المادة 5  باعتباره وكالة منفذة متعاونة، كما هو مبين في الفرع ألف-4 من الجدول 1. واليونيب بوصفه الوكالة المنفذة الرئيسية لكمبوديا وغرينادا؛ وبوصفه وكالة منفذة متعاونة لشيلي وفيجي، طلب 250,000 دولار أمريكي، إضافة إلى تكاليف دعم الوكالة التي بلغت 32,500 دولار أمريكي في تعديلات برنامج عمله لعام 2021.[footnoteRef:7]  [7:  UNEP/OzL.Pro/ExCom/88/31] 

تعليقات الأمانة
عند استعراض هذا الطلب، أخذت الأمانة في الاعتبار المبادئ التوجيهية لإعداد مشروعات خطط تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون على النحو الوارد في المقرر 87/50؛ والأنشطة المقترحة لإعداد المشروعات وعلاقتها بالأنشطة التمكينية وغيرها من المشروعات المتعلقة بالهيدروفلوروكربون في البلدان. وذكرت الأمانة أن طلب التمويل يتماشى مع المقرر 87/50، وأن البرنامج الإنمائي، بوصفه الوكالة المنفذة المعينة أو الرئيسية، قدم وصفا للأنشطة اللازمة لإعداد الاستراتيجيات الشاملة خطط تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون التي تنفذها أنغولا وشيلي والسلفادور وفيجي، باستخدام شكل طلبات إعداد المشروعات لتلك الخطط. وتضمنت العروض معلومات عن الاستهلاك التقديري للمواد الهيدروفلوروكربونية ومزيج الهيدروفلوروكربون المستوردة بين عامي  2014 و 2020 أو عامي  2016 و2020 استنادا إلى البيانات التي جمعت أثناء تنفيذ الأنشطة التمكينية؛ ويقترح وضع الاستراتيجية الشاملة، وتحليل التوزيع القطاعي واستهلاك المواد الهيدروفلوروكربونية، وإجراء مع مشاورات أصحاب المصلحة؛ ووضع خطط للاتصالات والتوعية؛ وتقييم التدريب والاعتماد لثلاثة بلدان (أنغولا وشيلي والسلفادور)؛ وإدماج النظم والإجراءات الوطنية، والتدريب على ممارسة التبريد الجيدة، والاسترداد وإعادة التدوير في بلدين (شيلي والسلفادور)؛ وتقييم القدرات الجمركية ونظم الحصص اللازم لمراقبة المواد الهيدروفلوروكربونية في بلد واحد (شيلي)؛ وإجراء دراسة استقصائية وطنية لجمع البيانات، والتشاور مع أصحاب المصلحة، وتحليل البيانات في بلد واحد (فيجي). ويستند التمويل المطلوب إلى المبادئ التوجيهية لإعداد خطط تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون.[footnoteRef:8]  [8:  المقرر87/50] 

وأوضح البرنامج الإنمائي أن إعداد المشروعات للاستراتيجيات الشاملة للتخفيض التدريجي للهيدروفلوروكربون بالنسبة للبلدان الأربعة سوف يعتمد على الأنشطة المنفذة في إطار الأنشطة التمكينية، لأن هذه هي الإجراءات الأولى المرتبطة بالتخفيض التدريجي للمواد الهيدروفلوروكربونية، وقد أسهم ذلك في التصديق على تعديل كيغالي. 
وعقب هذا الاستعراض، ذكرت الأمانة أن جميع البلدان الستة صدقت على تعديل كيغالي؛[footnoteRef:9] وأن البلدان قدمت خطابات تأييد تشير إلى اعتزامها اتخاذ إجراء مبكر بشأن التخفيض التدريجي للهيدروفلوروكربون؛ وأن التمويل المطلوب يتوافق مع المقرر 87/50. [9:  تاريخ التصديق على تعديل كيغالي (أو قبوله): أنغولا، 16 نوفمبر/تشرين الثاني2020؛ كمبوديا، 8 أبريل/نيسان 2021؛  شيلي، 19 سبتمبر/أيلول2017؛ السلفادور، 13 سبتمبر/أيلول 2021؛ فيجي، 16 يونيه/حزيران 2020؛ وغرينادا، 29 مايو/أيار 2018.  ] 

توصية الأمانة
توصي الأمانة بالموافقة الشاملة على إعداد مشروعات خطط تنفيذ تعديل كيغالي فيما يخص الهيدروفلوروكربون لأنغولا وكمبوديا وشيلي والسلفادور وفيجي وغرينادا بمستوى التمويل المبين في القسم ألف-4 من الجدول 1.
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Annex I
INSTITUTIONAL STRENGTHENING PROJECT PROPOSALS[footnoteRef:10] [10:  Data as at December 2020 are based on document UNEP/OzL.Pro/ExCom/88/12.] 

Bangladesh: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Sept-94
	150,000

	Phase II:
	Nov-99
	100,000

	Phase III:
	Dec-01
	100,000

	Phase IV:
	Dec-04
	130,000

	Phase V:
	Nov-07
	130,000

	Phase VI:
	Jul-10
	130,000

	Phase VII:
	Dec-13
	130,000

	Phase VIII:
	Dec-16
	166,400

	Phase IX:
	May-19
	166,400

	Total:
	1,202,800

	Amount requested for renewal (phase X) (US $):
	166,400

	Amount recommended for approval for phase X (US $): 
	166,400

	Agency support costs (US $):
	11,648

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	178,048

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2018

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.9

	Annex C, Group I (HCFCs) (average 2009-2010)
	72.6

	Annex E, (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	46.53

	Annex E, (methyl bromide)
	0.00

	Total:
	46.53

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	14,025,051

	Amount disbursed (as at December 2020) (US $):
	11,032,529

	ODS to be phased out (as at July 2021) (ODP tonnes):
	735.9

	ODS phased out (as at December 2020) (ODP tonnes):
	724.4



1. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	9,455,248

	(b)
	Institutional strengthening:
	1,202,800

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	3,367,003

		Total:
	14,025,051

	(d)
	HFC activities funded from additional voluntary contributions
	3,131,610



Progress report
During phase IX, Bangladesh has continued its efforts towards implementation of the Montreal Protocol obligations and ODS phase-out activities through the institutional strengthening project. The NOU continued to monitor the controlled substances consumption and their related phase-out, phase-down and enabling projects. It provided coordination support to the completion of the first HFC phase-down investment project, which supported Bangladesh to phase-out 230 metric tonnes of HFC-134a in the domestic refrigerator manufacturing sector. The Government of Bangladesh continued to control the consumption of ODS with an operational licensing and quota system and achieved the 2020 reduction targets for stage II of its HPMP and sustained the consumption reduction of HCFCs. Bangladesh ratified the Kigali Amendment on 8 June 2020, and, despite delays caused by the COVID-19 pandemic, advanced in the implementation of the enabling activity project. The NOU reported consumption data to both the Fund and Ozone Secretariats, was active in regional and global meetings and organized the celebrations for the International Day for the Preservation of the Ozone Layer in 2019 and 2020. Of the 20 performance indicators, all were fully achieved. 
Plan of action
Phase X will continue implementation of ODS phase-out activities including stage II of the HPMP, leading towards achieving and sustaining the 2023 obligations, and reporting consumption data to both the Fund and Ozone Secretariats. The NOU will assist, coordinate, consult and engage with ministries, organizations, and industry associations for implementation of the Montreal Protocol and related regulations; planning and implementation of information outreach activities; and supporting the completion of the enabling activities project, the enforcement of the HFCs control system and the reporting of the HFCs consumption.
Colombia: Renewal of institutional strengthening
	 Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-94
	317,790

	Phase II:
	Mar-98
	212,000

	Phase III:
	Mar-00
	212,000

	Phase IV:
	Nov-02
	275,600

	Phase V:
	Apr-05
	275,600

	Phase VI:
	Jul-07
	275,600

	Phase VII:
	Jul-09 
	275,600

	Phase VIII:
	Jul-11
	275,600

	Phase IX:
	Jul-13
	275,600

	Phase X:
	May-15
	275,600

	Phase XI:
	Jul-17
	352,768

	Phase XII:
	May-19
	352,768

	Total:
	3,376,526

	Amount requested for renewal (phase XIII) (US $):
	352,768

	Amount recommended for approval for phase XIII (US $): 
	352,768

	Agency support costs (US $):
	24,694

	Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $):
	377,462

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan (stage I):
	2010

	Date of approval of HCFC phase-out management plan (stage II):
	2015

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.6

	Annex C, Group I (HCFCs) (average 2009-2010)
	225.6

	Annex E, (methyl bromide) (average 1995-1998)
	110.1

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	63.21

	Annex E, (methyl bromide)
	0.00

	Total:
	63.21

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	38,699,988

	Amount disbursed (as at December 2020) (US $):
	33,774,257

	ODS to be phased out (as at July 2021) (ODP tonnes):
	2,058.6

	ODS phased out (as at December 2020) (ODP tonnes):
	1,951.9



2. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	27,300,686

	(b)
	Institutional strengthening:
	3,376,526

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	8,022,776

		Total:
	38,699,988

	(d)
	HFC activities funded from additional voluntary contributions
	250,000



Progress report
During phase IX, Colombia continued implementation of the Montreal Protocol and ODS phase‑out activities; reported consumption data to both the Fund and Ozone Secretariats; the Government has achieved its HCFC consumption reduction targets through implementation of activities under stage II of the HPMP and maintained the total phase-out of other ODS. Colombia has ratified of the Kigali Amendment and continued participating in regional and global Montreal Protocol meetings. The country fully achieved all its performance indicators during the current phase.
Plan of action
In phase X, Colombia will work to continue achieving and maintaining the 65 per cent reduction in HCFCs consumption from 2021 and will continue the compliance with the phase-out commitment in stage III of the HPMP. The NOU will assist in reinforcing inter-institutional coordination with the Customs authority through monitoring trade, coordinating the collection, analysis, verification and submission of progress reports on the implementation of country programmes and reporting consumption under Article 7 of the Montreal Protocol; strengthening of the legal framework to control and monitor HCFC consumption through import/export licensing and quota systems and new regulations; and completing a roadmap to comply with the measures of the Kigali Amendment including consideration of synergies with climate change initiatives. The NOU will continue participation in Montreal Protocol related meetings.
Costa Rica: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Oct-92
	213,160

	Phase II:
	Feb-97
	108,087

	Phase III:
	Mar-99
	108,087

	Phase IV:
	Dec-01
	108,087

	Phase V:
	Dec-03
	140,513

	Phase VI:
	Nov-05
	140,513

	Phase VII:
	Nov-07
	140,513

	Phase VIII:
	Nov-09
	140,513

	Phase IX:
	Nov-11
	140,513

	Phase X:
	Dec-13
	140,513

	Phase XI:
	Nov-15
	179,857

	Phase XII:
	Nov-17
	179,857

	Phase XIII:
	Dec-19
	179,857

		Total:
	1,920,071

	Amount requested for renewal (phase XIV) (US $):
	179,857

	Amount recommended for approval for phase XIV (US $): 
	179,857

	Agency support costs (US $):
	12,590

	Total cost of institutional strengthening phase XIV to the Multilateral Fund (US $):
	192,447

	Date of approval of country programme:
	1992

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2019

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	14.1

	(f)	Annex E (methyl bromide) (average 1995-1998)
	342.5

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.0

	(e)	Annex C, Group I (HCFCs)
	4.04

	(f)	Annex E (methyl bromide)
	0.0

		Total:
	4.04

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	12,712,372

	Amount disbursed (as at December 2020) (US $):
	12,136,916

	ODS to be phased out (as at July 2021) (ODP tonnes):
	810.114994

	ODS phased out (as at December 2020) (ODP tonnes):
	799.4



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	7,877,281

	(b)
	Institutional strengthening:
	1,920,071

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	2,915,020

		Total:
	12,712,372

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase XIII HCFC imports were reduced by 72 per cent by December 2020; workshops were organized for Customs officers and the Fiscal Control Police to reduce the risk of illicit ODS trafficking. Costa Rica ratified the Kigali Amendment in 2017; efforts were made to prepare new regulations and increase awareness. Nineteen voluntary standards were adopted for the refrigeration and air-conditioning sector on the environment and safety; In 2021, the celebration of World Ozone Day was organized jointly between Panama, Nicaragua, Honduras, Guatemala and Costa Rica. Costa Rica also submitted Article 7 and country programme data to the respective Secretariats. The NOU considered the issues of gender equity by using inclusive language in all documents and correspondence and promoting the participation of women in its work and training sessions. Of 21 indicators selected for this phase, two indicators related to the layout of virtual technical training courses were pending completion during 2021 and one indicator will be transferred to the next phase for completion. All other indicators were completed successfully. 
Plan of action
During phase XIV, Costa Rica will continue implementing the licensing process for the control of HCFCs and HFCs, making complementary use of virtual training modules for Customs, in order to reduce the risk of illicit trafficking. Development of preparatory activities for the implementation of the Kigali Amendment will continue and the acquisition of the use of sustainable technologies will be promoted. A strategy will be developed to implement the national plan for efficient and sustainable refrigeration and air‑conditioning. Coordination will be established to strengthen other technical training centres; and Article 7 and country programme data will be submitted to the respective Secretariats. The commemoration of World Ozone Day will continue increasing awareness. Gender equality will also continue to be an integral part of the work during the upcoming phase.
India: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Oct-92
	430,600

	Phase II:
	Oct-96
	287,100

	Phase III:
	Mar-99
	287,100

	Phase IV:
	Jul-01
	287,100

	Phase V:
	Dec-03
	373,230

	Phase VI:
	Nov-05
	373,230

	Phase VII
	Apr-08
	373,230

	Phase VIII:
	Apr-10 & Nov-11
	373,230

	Phase IX:
	Apr-12
	373,230

	Phase X:
	May-14
	373,230

	Phase XI:
	May-16
	477,734

	Phase XII:
	Dec-19
	477,734

		Total:
	4,486,748

	Amount requested for renewal (phase XIII) (US $):
	477,734

	Amount recommended for approval for phase XIII (US $): 
	477,734

	Agency support costs (US $):
	33,441

	Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $):
	511,175

	Date of approval of country programme:
	1993

	Date of approval of HCFC phase-out management plan (stage I):
	2012

	Date of approval of HCFC phase-out management plan (stage II):
	2016

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	122.2

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	1,608.2

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	297.49

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	297.49

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	311,993,169

	Amount disbursed (as at December 2020) (US $):
	269,199,60

	ODS to be phased out (as at July 2021) (ODP tonnes):
	24635.36

	ODS phased out (as at December 2020) (ODP tonnes):
	28672.6



3. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	292,019,461

	(b)
	Institutional strengthening:
	4,486,748

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	15,486,960

		Total:
	311,993,169

	(d)
	HFC activities funded from additional voluntary contributions
	0



Progress report
Under phase XII, India continued its efforts in the implementation of the Montreal Protocol and ODS phase-out activities. The Ozone Cell achieved the 2019 and 2020 compliance obligations under the Protocol and in line with its agreement with the Executive Committee.  The IS project provided tools for coordinated and complementary actions for competency enhancement of small and medium sized enterprises in the foam sector. The Ozone Cell also carried out awareness campaigns at national and state levels to sensitize stakeholders on ODS phase-out in various sectors. Mechanisms for prevention of illegal trade in ODS including competency enhancement of customs and enforcement agencies were undertaken and several knowledge products, including “The Montreal Protocol- India’s Success Story” were developed and launched. The Ozone Cell submitted Article 7 and country programme data to the respective Secretariats, and participated in Montreal Protocol meetings. Fiscal measures covering Customs and Excise duty exemptions on capital goods for establishment of industry with non-ODS technology continued and the Ozone Cell organized the World Ozone Day celebrations during 2020 and 2021. All 27 indicators for the phase were completed successfully.
Plan of action
The objectives of phase XIII include continuing implementation of ODS phase-out activities, leading towards sustaining the ODS phase-out; submitting Article 7 and country programme data to the respective Secretariats; completing implementation of stage II of the HPMP and finalizing the project preparation for stage III and implementation after its approval; assisting, coordinating, consulting and engaging with concerned ministries, organizations and industry associations, for implementation of the Montreal Protocol and national regulations; planning and implementation of information outreach activities and executing the national strategy for phase-down of HFCs in coordination with stakeholders.
Malaysia: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-93
	322,520

	Phase II:
	Oct-96
	215,000

	Phase III:
	Nov-98
	215,000

	Phase IV:
	Dec-00
	215,000

	Phase V:
	Nov-02
	279,500

	Phase VI:
	Dec-04
	279,500

	Phase VII:
	Nov-07
	279,500

	Phase VIII:
	Jul-09 
	279,500

	Phase IX:
	Jul-11
	279,500

	Phase X:
	Jul-13
	279,500

	Phase XI:
	Nov-15
	357,760

	Phase XII:
	Nov-17
	357,760

	Phase XIII:
	Dec-19
	357,760

		Total:
	3,717,800

	Amount requested for renewal (phase XIV) (US $):
	357,760

	Amount recommended for approval for phase XIV (US $): 
	357,760

	Agency support costs (US $):
	25,043

	Total cost of institutional strengthening phase XIV to the Multilateral Fund (US $):
	382,803

	Date of approval of country programme:
	1992

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2016

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	49.5

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	515.8

	(f)	Annex E (methyl bromide) (average 1995-1998)
	14.6

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.0

	(e)	Annex C, Group I (HCFCs)
	228.41

	(f)	Annex E (methyl bromide)
	0.0

		Total:
	228.41

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	66,964,243

	Amount disbursed (as at December 2020) (US $):
	60,816,800

	ODS to be phased out (as at July 2021) (ODP tonnes):
	7,042.17

	ODS phased out (as at December 2020) (ODP tonnes):
	6,892.90



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	53,640,742

	(b)
	Institutional strengthening:
	3,717,800

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	9,605,701

		Total:
	66,964,243

	(d)
	HFC activities funded from additional voluntary contributions
	250,000



Progress report
During phase XII, the Government of Malaysia has successfully implemented the activities under the IS project, which was critical to support the management of ODS phase-out activities and ensure compliance with Montreal Protocol obligations. The NOU submitted Article 7 and country programme data to the respective Secretariats, and worked with other agencies and stakeholders to ensure monitoring of ODS phase-out and implemented various activities for awareness and training, HCFC phase-out in small and medium-sized enterprises in the foam and the refrigeration and air-conditioning servicing sectors. The NOU assisted in preparation for stage III of the HPMP and for its Kigali HFC implementation plans. Malaysia ratified the Kigali Amendment during this phase. In spite of the difficult COVID-19 situation, all 16 indicators for the phase were completed successfully.
Plan of action
During phase XIV, the IS activities will support continuing effective management, monitoring and enforcement of ODS phase-out activities including sustainability of the ODS phase-out and HFC phase‑down; submitting Article 7 and country programme data to the respective Secretariats; monitoring implementation of the HCFC phase-out management plan, sustaining the sectors ban on the polyurethane foam and the air-conditioning manufacturing sectors, strengthening institutional engagement in order to support achieving the compliance targets; continuing implementation and enforcement of the ODS legal framework; and continuing the awareness-raising and outreach activities.
Trinidad and Tobago: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Oct-96
	66,000

	Phase II:
	Dec-00
	44,000

	Phase III:
	Nov-02
	57,200

	Phase IV:
	Dec-04
	60,000

	Phase V
	Nov-06
	60,000

	Phase VI:
	Nov-09 and Dec‑10
	60,000

	Phase VII:
	Dec-12
	60,000

	Phase VIII:
	Nov-14
	60,000

	Phase IX:
	Jul-17
	85,000

	Phase X:
	May-19
	85,000

	Total:
	637,200

	Amount requested for renewal (phase XI) (US $):
	85,000

	Amount recommended for approval for phase XI (US $): 
	85,000

	Agency support costs (US $):
	5,950

	Total cost of institutional strengthening phase XI to the Multilateral Fund (US $):
	90,950

	Date of approval of country programme:
	1996

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2021

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.7

	Annex C, Group I (HCFCs) (average 2009-2010)
	46.0

	Annex E, (methyl bromide) (average 1995-1998)
	1.7

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	14.5

	Annex E, (methyl bromide)
	0.00

	Total:
	14.5

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	4,662,453

	Amount disbursed (as at December 2020) (US $):
	3,429,371

	ODS to be phased out (as at July 2021) (ODP tonnes):
	141.7

	ODS phased out (as at December 2020) (ODP tonnes):
	131.4



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	2,343,059

	(b)
	Institutional strengthening:
	637,200

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,682,194

		Total:
	4,662,453

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase X, the Government of Trinidad and Tobago, through its NOU at the Ministry of Planning and Development has successfully implemented the IS activities. The NOU submitted Article 7 and country programme data to the respective Secretariats, assisted in the implementation of the first tranche of stage II of its HPMP including an effective licensing and quota system of HCFC management, assuring compliance with HCFC reductions targets of the Montreal Protocol and its Agreement with the Executive Committee. The NOU also performed work on sustainable cooling and energy efficiency efforts, linking the Montreal Protocol with the climate change agenda. During this phase, all 11 indicators were achieved.
Plan of action
Phase XI will provide support for the reinforcement of the ODS licensing and quota system for the import of ODS and will allow the country to continue the implementation of training programmes on good refrigeration practices and the expansion of its certification programme for refrigeration and air‑conditioning technicians. The NOU will continue submitting Article 7 and country programme data to the respective Secretariats, training border control officials on ODS regulation and HFC phase-down; assist in implementing the first tranche of stage II of the HPMP; and continue its active participation in global and regional network meetings, relevant trainings and meetings for the promotion of the Montreal Protocol in the country.
Uruguay: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNDP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jun-93 & May-96
	202,800

	Phase II:
	Oct-96
	116,000

	Phase III:
	Jul-98
	116,000

	Phase IV:
	Jul-00
	116,000

	Phase V:
	Jul-02
	150,800

	Phase VI:
	Jul-04
	150,800

	Phase VII:
	Jul-06
	150,800

	Phase VIII:
	Nov-08
	150,800

	Phase IX:
	Nov-11
	150,800

	Phase X:
	Dec-13
	150,800

	Phase XI:
	Nov-15
	193,024

	Phase XII:
	Nov-17
	193,024

	Phase XIII:
	Dec-19
	193,024

		Total:
	2,034,672

	Amount requested for renewal (phase XIV) (US $):
	193,024

	Amount recommended for approval for phase XIV (US $): 
	193,024

	Agency support costs (US $):
	13,512

	Total cost of institutional strengthening phase XIV to the Multilateral Fund (US $):
	206,536

	Date of approval of country programme:
	1993

	Date of approval of HCFC phase-out management plan (stage I):
	2011

	Date of approval of HCFC phase-out management plan (stage II):
	2016

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	23.4

	(f)	Annex E (methyl bromide) (average 1995-1998)
	11.2

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.0

	(e)	Annex C, Group I (HCFCs)
	11.15

	(f)	Annex E (methyl bromide)
	0.0

		Total:
	11.15

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at July 2021) (US $):
	10,189,347

	Amount disbursed (as at December 2020) (US $):
	8,213,152

	ODS to be phased out (as at July 2021) (ODP tonnes):
	537.6

	ODS phased out (as at December 2020) (ODP tonnes):
	448.5



Summary of activities and funds approved by the Executive Committee:
	Summary of activities
	Funds approved (US $)

	(a)
	Investment projects:
	4,982,902

	(b)
	Institutional strengthening:
	2,034,672

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	3,171,773

		Total:
	10,189,347

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
Phase XIII was successfully implemented with 10 out of 12 performance indicators fully achieved and two partially achieved. The NOU continued the implementation of the quota system, improving the tools for reviewing and collecting information in close cooperation with the National Customs Directorate. The NOU established communication with stakeholders which assist in the exchange of information on the implementation of the Montreal Protocol. Uruguay reported the 2019 and 2020 country programme and Article 7 data to the respective Secretariats and continued with implementation of stage II of the HPMP and the enabling activities projects. Stage III of the HPMP was prepared and approved by the Executive Committee. Uruguay participated in international Montreal Protocol meetings. The COVID-19 pandemic impacted the implementation of the Montreal Protocol projects, but the Ozone Unit took the required measures to ensure that implementation of the projects continued.
Plan of action
During phase XIV, the Government of Uruguay will maintain control of ODS already banned and the reduction in HCFC consumption already achieved. The NOU will report country programme and Article 7 data to the respective Secretariats, will work with public and private entities to enforce HCFC consumption control measures and coordinate activities including investment projects and the enabling activities for HFC phase-down, incorporating the preparation of the Kigali HFC implementation plan. The Government of Uruguay will complete the implementation of stage II of the HPMP and begin the implementation of stage III in coordination with all stakeholders. Uruguay will continue its participation in Montreal Protocol meetings.
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المرفق الثاني 
مشروع الآراء التي أعربت عنها اللجنة التنفيذية فيما يتعلق بتجديد مشروعات التعزيز المؤسسي المقدمة إلى الاجتماع الثامن والثمانين

بنغلاديش
1. استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي (المرحلة التاسعة) لبنغلاديش ولاحظت مع التقدير أن حكومة بنغلاديش أبلغت عن بيانات تنفيذ البرنامج القطري وبيانات المادة 7، التي تشير إلى أن البلد حقق هدفه المتمثل في تخفيض الهيدروكلوروفلوروكربون لعام 2020 على النحو المتفق عليه. وأحاطت اللجنة علما أيضا بالجهود التي يبذلها البلد باستمرار في إنفاذ تدابير الرقابة من أجل إزالة المواد المستنفدة للأوزون، مع تحديث القواعد والنظم ونظام ترخيص وحصص الهيدروكلوروفلوروكربون. وأثنت اللجنة على بنغلاديش لما اتخذته من خطوات نحو التصديق على تعديل كيغالي في عام 2020 والانتهاء في الوقت المناسب من تنفيذ أول مشروع استثماري يخص إزالة الهيدروفلوروكربون وإزالة استهلاك الهيدروفلوروكربون-134أ في قطاع تصنيع الثلاجات المحلية. ولذلك، فإن اللجنة التنفيذية على ثقة من أن حكومة بنغلاديش ستواصل تنفيذ خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية وأنشطة مشروعات التعزيز المؤسسي، على صعيدي السياسات والمشروعات على حد سواء من أجل تحقيق الغايات التالية لبروتوكول مونتريال.
كولومبيا
ﺍﺳﺘﻌﺮﺿﺖ ﺍﻟﻠﺠﻨﺔ ﺍﻟﺘﻨﻔﻴﺬﻳﺔ ﺍﻟﺘﻘﺮﻳﺮ ﺍﻟﻤﻘﺪﻡ ﻣﻊ ﻁﻠﺐ ﺗﺠﺪﻳﺪ ﻣﺸﺮﻭﻉ ﺍﻟﺘﻌﺰﻳﺰ ﺍﻟﻤﺆﺳﺴﻲ ﻓﻲ كولومبيا (ﺍﻟﻤﺮﺣﻠﺔ الثانية ﻋﺸﺮة) ﻭأحاطت ﻋﻠﻤﺎ ﻣﻊ ﺍﻟﺘﻘﺪﻳﺮ ﺑﺄﻥ كولومبيا قدمت إلى أمانة ﺍﻷﻭﺯﻭﻥ ﺒﻴﺎﻧﺎﺕ عامي 2019 و2020 التي تشير إلى أن البلد في حالة امتثال لبروتوكول مونتريال، وقدمت إلى أمانة الصندوق بيانات التنفيذ. ولاحظت اللجنة التنفيذية كذلك أن حكومة كولومبيا قد اتخذت خطوات لإزالة استهلاك المواد المستنفدة للأوزون بما في ذلك تنفيذ تدابير مراقبة واردت الهيدروكلوروفلوروكربون بموجب نظام التراخيص والحصص، وتدريب موظفي الجمارك وفنيي التبريد. وأقرت اللجنة أيضا مع التقدير بالأنشطة التي بدأت لتيسير تنفيذ تعديل كيغالي، وبمشاركة البلد في اجتماعات بروتوكول مونتريال. وأقرت اللجنة التنفيذية بجهود حكومة كولومبيا، ولذلك فإنها تأمل أن تواصل خلال السنتين المقبلتين تنفيذ خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية وأنشطة مشروعات التعزيز المؤسسي بنجاح من أجل الحفاظ على خفض استهلاك الهيدروكلوروفلوروكربون بنسبة 65 في المائة المطلوب بحلول 1 يناير/كانون الثاني 2021.
كوستاريكا
استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لكوستاريكا (المرحلة الرابعة عشرة) ولاحظت مع التقدير أن حكومة كوستاريكا قدمت إلى أمانة الأوزون بيانات عامي 2019 و2020 التي تشير إلى أن البلد في حالة امتثال لبروتوكول مونتريال، وقدمت إلى أمانة الصندوق بيانات التنفيذ. ولاحظت اللجنة كذلك أن حكومة كوستاريكا اتخذت خطوات لإزالة استهلاك المواد المستنفدة للأوزون بحظر استيراد المعدات القائمة على الهيدروكلوروفلوروكربون بحلول عام 2020. وأثنت اللجنة على تصديق كوستاريكا على تعديل كيغالي وأدرجت المواد الهيدروفلوروكربونية في نظام الترخيص بما يتماشى مع الالتزامات المنصوص عليها في التعديل. وأقرت اللجنة بجهود حكومة كوستاريكا، وقالت إنها، لذلك، تأمل في أن تواصل حكومة كوستاريكا تنفيذ المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية وأنشطة مشروعاتها من أجل تحقيق أهداف خفض استهلاك الهيدروكلوروفلوروكربون على النحو المحدد في اتفاقها المبرم مع اللجنة التنفيذية. 
الهند
استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي للهند (المرحلة الثالثة عشرة) ولاحظت مع التقدير أن حكومة الهند أبلغت عن بيانات تنفيذ البرامج القطرية وبيانات المادة 7 التي تشير إلى أن البلد حقق هدفه المتمثل في خفض المواد الهيدروكلوروفلوروكربونية في عام 2020. ولاحظت اللجنة أيضا الجهود المتواصلة التي يبذلها البلد في إنفاذ تدابير الرقابة ومواصلة إزالة المواد المستنفدة للأوزون، بما في ذلك رصد نظام حصص وترخيص المواد المستنفدة للأوزون. ولاحظت اللجنة كذلك التقدم الذي أحرزه البلد في تنفيذ المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية وأنشطة التنسيق والرقابة التي تقوم بها الحكومة لضمان تنفيذ مؤشرات الأداء وتحقيقها. وأقرت اللجنة بمشاركة حكومة الهند في الاجتماعات ذات الصلة ببروتوكول مونتريال. وأثنت اللجنة على الهند لتصديقها مؤخرا على تعديل كيغالي، وقالت إنها، لذلك، على ثقة من أن حكومة الهند ستواصل أنشطتها لتحقيق الأهداف المستقبلية لبروتوكول مونتريال.
ماليزيا
استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لماليزيا (المرحلة الرابعة عشرة) ولاحظت مع التقدير أن حكومة ماليزيا قدمت إلى أمانة الأوزون في الوقت المناسب بيانات عام 2019 و2020 التي تشير إلى أن البلد في حالة امتثال لبروتوكول مونتريال، وقدمت إلى أمانة الصندوق بيانات التنفيذ. ولاحظت اللجنة أيضا الجهود التي تبذلها حكومة ماليزيا لرصد ومراقبة إزالة المواد المستنفدة للأوزون من خلال مختلف الأنشطة السياساتية والتنظيمية، بما في ذلك نقل التكنولوجيا وأنشطة التوعية. ولاحظت اللجنة كذلك أنه على الرغم من الوضع الصعب الناجم عن جائحة كوفيد-19، فإن حكومة ماليزيا تكفل استمرار التنفيذ كما هو مخطط له لإزالة استهلاك المواد المستنفدة للأوزون، وصدقت على تعديل كيغالي وشرعت في اتخاذ إجراءات التخفيض التدريجي للهيدروفلوروكربون. وتسلم اللجنة بجهود حكومة ماليزيا، ولذلك، فإنها تأمل أن تواصل حكومة ماليزيا، في غضون السنتين المقبلتين، أنشطة بروتوكول مونتريال بنجاح، بما في ذلك تنفيذ المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية ووضع المرحلة الثالثة، ووضع خطة التنفيذ وفقا لتعديل كيغالي  فيما يخص الهيدروفلوروكربون وتنفيذ أنشطة مشروعات التعزيز المؤسسي.
ترينيداد وتوباغو
استعرضت اللجنة التنفيذية التقرير المقدم مع طلب مشروع التعزيز المؤسسي لترينيداد وتوباغو (المرحلة الحادية عشرة) ولاحظت مع التقدير أن حكومة ترينيداد وتوباغو قدمت في الوقت المناسب إلى أمانة الأوزون بيانات 2019 و2020 التي تشير إلى أن البلد في حالة امتثال لبروتوكول مونتريال وقدمت بيانات تنفيذ البرنامج القطري إلى أمانة الصندوق،  وأن البلد يتخذ الخطوات اللازمة للوفاء بتدابير الرقابة المنصوص عليها في بروتوكول مونتريال فيما يتعلق بالمواد الهيدروكلوروفلوروكربونية وتنفيذ تدابير رقابة  الهيدروفلوروكربون. ولاحظت اللجنة أيضا الجهود المبذولة لتنفيذ أنشطة خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية؛ ووضع نظم استيراد المواد المستنفدة للأوزون، وخلائط المواد المستنفدة للأوزون، والمعدات القائمة على المواد المستنفدة للأوزون، علاوة على معيارها الإلزامي المتعلق بوضع العلامات على حاويات التبريد؛ والتدريب على الممارسات الجيدة في مجال التبريد؛ والإضطلاع بأنشطة لتوعية الجمهور ومشاركته في اجتماعات بروتوكول مونتريال. وقالت اللجنة إنها، لذلك، تأمل في أن تواصل حكومة ترينيداد وتوباغو، في غضون السنتين المقبلتين، تنفيذ أنشطة مشروع خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية والتعزيز المؤسسي بنجاح من أجل الحفاظ على خفض استهلاك الهيدروكلوروفلوروكربون الذي تحقق حتى الآن.
أوروغواي
استعرضت اللجنة التنفيذية التقرير المقدم مع طلب مشروع التعزيز المؤسسي لأوروغواي (المرحلة الثالثة عشرة) ولاحظت مع التقدير أن حكومة أوروغواي قدمت إلى أمانة الأوزون بيانات عامي 2019 و2020 التي تشير إلى أن البلد في حالة امتثال لبروتوكول مونتريال، وقدمت إلى أمانة الصندوق بيانات التنفيذ. ولاحظت اللجنة كذلك أن حكومة أوروغواي اتخذت خطوات بشأن تنفيذ تدابير مراقبة واردت الهيدروكلوروفلوروكربون من خلال نظام الترخيص والحصص، وتدريب موظفي الجمارك وفنيي التبريد. ولاحظت اللجنة أيضا مع التقدير تنفيذ الأنشطة المتصلة بتعديل كيغالي، ومشاركة البلد في بروتوكول مونتريال. وأقرت اللجنة بجهود حكومة أوروغواي، وقالت إنها، لذلك، تأمل في أن تواصل حكومة أوروغواي، في غضون السنتين المقبلتين، تنفيذ المرحلتين الثانية والثالثة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية وأنشطة مشروعات التعزيز المؤسسي بنجاح من أجل الحفاظ على خفض استهلاك الهيدروكلوروفلوروكربون الذي تحقق حتى الآن. 
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