| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/86/30 16 February 2021 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-sixth Meeting

Montreal, 2-6 November 2020

Postponed to 8-12 March 2021

THE WORLD BANK Business plan for 2021–2023

# This document presents the World Bank business plan for 2021–2023 and includes: the planned activities for the phase-out of controlled substances under the Montreal Protocol (controlled substances) during the 2021–2023 period; the business plan performance indicators; and a recommendation for consideration by the Executive Committee. The narrative of the World Bank’s business plan for 2021–2023 is attached to the present document.

Planned activities during the 2021–2023 period

# Table 1 sets out, by year, the value of activities included in the World Bank’s business plan.

Table 1. Resource allocation in the World Bank business plan for 2021–2023 as submitted (US $000s)*

| Description | 2021 | 2022 | 2023 | Total (2021–2023) | Total after 2023 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 12,255 | 4,888 | 8,484 | 25,627 | 11,697 |
| HCFC production project preparation (PRP) – stage I | 128 | 0 | 0 | 128 | 0 |
| HCFC production – stage I | 1,070 | 2,140 | 2,140 | 5,350 | 0 |
| HCFC production – stage II | 0 | 23,232 | 0 | 23,232 | 23,232 |
| HPMP preparation – stage III | 268 | 214 | 0 | 482 | 0 |
| HCFC activities subtotal | 13,721 | 30,474 | 10,624 | 54,819 | 34,929 |
| HFC activities |  |  |  |  |  |
| HFC phase-down preparation | 535 | 0 | 0 | 535 | 0 |
| HFC activities subtotal | 535 | 0 | 0 | 535 | 0 |
| Standard activities |  |  |  |  |  |
| Core unit | 1,747 | 1,759 | 1,772 | 5,278 | 0 |
| Institutional strengthening (IS) | 677 | 0 | 677 | 1,353 | 475 |
| Standard activities subtotal | 2,424 | 1,759 | 2,448 | 6,631 | 475 |
| Total | 16,680 | 32,233 | 13,072 | 61,985 | 35,404 |

* Including agency support costs where applicable.

# Secretariat’s comments

# HCFC production – project preparation and stage I

# A total of US $128,400 for project preparation and US $5.35 million for the period of 2021 to 2023 is included for stage I of the HCFC production phase-out management plan (HPPMP) for India. A request for a technical audit of the production sector in India has been submitted and will be considered by the Sub-group on the Production Sector in the margins of the 86th meeting.

# HCFC production – stage II

# A total of US $46.46 million is included for the HPPMP for China, i.e., US $23.23 million for 2021–2023 and US $23.23 million for after 2023. These values correspond to the draft Agreement submitted to the 86th meeting.

# At its 81st meeting, the Executive Committee inter alia approved on an exceptional basis, US $24.29 million (including agency support costs) for the HPPMP for China, and noted that this amount would be deducted from the funding of stage II.

# The request for funding for stage II of the HPPMP for China has been resubmitted to the 86th meeting in accordance with decision 84/69(b).

# HPMP stage III – project preparation

# A total of US $481,500 is included for project preparation for stage III of HPMPs in the 2021–2023 business plan for countries with an approved stage II of HPMPs with reduction targets below the 2025 compliance targets (decision 84/46(e)).

HFC-related activities

# A total of US $535,000 is included for HFC phase-down project preparation activities in the 2021-2023 business plan for two countries (Thailand and Viet Nam). Of the two countries, only Viet Nam has ratified the Kigali Amendment and Thailand has submitted the required letter from its Government indicating its intent to make best efforts to ratify the Kigali Amendment.

# Core unit costs

# The core unit costs are expected to increase at an annual rate of 0.7 per cent as agreed.

Proposed adjustments by the Secretariat

# The adjustments to the World Bank business plan for 2021–2023 were based on relevant decisions of the Executive Committee. Further adjustments may be required pending a decision by the Parties on the level of the replenishment of the Multilateral Fund for the 2021–2023 triennium. In reviewing the revised World Bank business plan for 2021–2023, the Secretariat noted that the following adjustments were not included:

Table 2. Adjustments to the World Bank business plan for 2021–2023 (US $000)

| Adjustment | 2021–2023 | After 2023 |
| --- | --- | --- |
| HPMP values to reflect the actual amounts approved under the Agreements | (30) | 0 |
| PRP for stage III of HPMPs pursuant to decision 71/42 | (55) | 0 |
| PRP for HFC phase-down pursuant to decision 56/16(c) | (173) | 0 |
| IS values after 2023 have been removed | 0 | (475) |

# Table 3 presents the results of the Secretariat’s proposed adjustments to the World Bank business plan for 2021–2023, which are also addressed in the context of the Consolidated business plan of the Multilateral Fund for 2021–2023.

# Table 3. Resource allocation in the World Bank’s adjusted business plan for 2021–2023 (US $000s)*

| Description | 2021 | 2022 | 2023 | Total (2021–2023) | Total after 2023 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HPMPs | 12,225 | 4,888 | 8,484 | 25,597 | 11,697 |
| HCFC production PRP – stage I | 128 | 0 | 0 | 128 | 0 |
| HCFC production – stage I | 1,070 | 2,140 | 2,140 | 5,350 | 0 |
| HCFC production – stage II | 0 | 23,232 | 0 | 23,232 | 23,232 |
| HPMP preparation – stage III | 213 | 214 | 0 | 427 | 0 |
| HCFC activities subtotal | 13,636 | 30,474 | 10,624 | 54,734 | 34,929 |
| HFC activities |  |  |  |  |  |
| HFC phase-down preparation | 362 | 0 | 0 | 362 | 0 |
| HFC activities subtotal | 362 | 0 | 0 | 362 | 0 |
| Standard activities |  |  |  |  |  |
| Core unit | 1,747 | 1,759 | 1,772 | 5,278 | 0 |
| IS | 677 |  | 677 | 1,353 | 0 |
| Standard activities subtotal | 2,424 | 1,759 | 2,448 | 6,631 | 0 |
| Total | 16,422 | 32,233 | 13,072 | 61,728 | 34,929 |

* Including agency support costs where applicable.

Performance indicators

# The World Bank submitted performance indicators pursuant to decision 71/28 in its business plan narrative. The Secretariat informed the World Bank of the targets shown in Table 4.

Table 4. Performance indicators for the World Bank for 2021

| Type of indicator | Short title | Calculation | 2021 target |
| --- | --- | --- | --- |
| Planning-- Approval | Tranches approved | Number of tranches approved vs. those planned* | 6 |
| Planning-- Approval | Projects/activities approved | Number of projects/activities approved vs. those planned (including project preparation activities)** | 8 |
| Implementation | Funds disbursed | Based on estimated disbursement in progress report | US $18,159,693 |
| Implementation | ODS phase-out | ODS phase-out for the tranche when the next tranche is approved vs. those planned per business plans | 722.42 ODP tonnes |
| Implementation | Project completion for activities | Project completion vs. planned in progress reports for all activities (excluding project preparation) | 5 |
| Administrative | Speed of financial completion | The extent to which projects are financially completed 12 months after project completion | 90% |
| Administrative | Timely submission of project completion reports | Timely submission of project completion reports vs. those agreed | On time (13) |
| Administrative | Timely submission of progress reports | Timely submission of progress reports and business plans and responses unless otherwise agreed | On time |

* The target of an agency would be reduced if it could not submit a tranche owing to another cooperating or lead agency, if agreed by that agency.

# ** Project preparation should not be assessed if the Executive Committee has not taken a decision on its funding.

RECOMMENDATION

# The Executive Committee may wish:

## To note the World Bank business plan for 2021–2023, contained in document UNEP/OzL.Pro/ExCom/86/30; and

## To approve the performance indicators for the World Bank as set out in Table 4 of document UNEP/OzL.Pro/ExCom/86/30.

Due to coronavirus disease (COVID-19)

Given the constraints imposed by the COVID-19 pandemic, the Secretariat’s comments on the initial submission of the World Bank business plan for 2021–2023 were addressed through bilateral discussions and numerous exchanges of electronic messages. All issues were satisfactorily addressed.

Decision 81/71(b) and (c).

Funding for the preparation of national implementation plans to meet initial reduction obligations for the phase-down of HFCs could be provided, at the earliest, five years prior to those obligations, after a country had ratified the Kigali Amendment and on the basis of guidelines to be approved in the future (decision 79/46(b)(iii)). In addition, decision 84/46(f) allowed the inclusion of HFC phase-down preparation activities in the business plan for countries that had not ratified the Kigali Amendment but had submitted a letter indicating their Government’s intent to make best efforts to ratify the Kigali Amendment.

The World Bank’s 2021 core unit cost has been approved at the intersessional approval process for the 86th meeting (UNEP/OzL.Pro/ExCom/86/37).

In the absence of a decision by the Parties on the level of the replenishment of the Multilateral Fund for the 2021-2023 triennium, and in light of decision XXXII/1, the indicative budget for resource allocation of the business plan for 2021–2023 was assumed at the same level of the replenishment of the 2018–2020 triennium. This issue is discussed in UNEP/OzL.Pro/ExCom/86/25.

UNEP/OzL.Pro/ExCom/86/25