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UPDATE ON THE IMPLEMENTATION OF THE 2017-2019 BUSINESS PLANS

Introduction

At its 77th meeting, the Executive Committee endorsed the consolidated business plan of the Multilateral Fund for 2017-2019. In response to decision 77/27(b), the Secretariat adjusted the consolidated 2017-2019 business plan[footnoteRef:1], as shown in Table 1.  [1:  The adjusted consolidated 2017-2019 business plan was posted on the Secretariat’s website on 29 December 2016.] 

Table 1. Resource allocation of the of the adjusted 2017-2019 business plans of the Multilateral Fund (US $)
	Description
	2017
	2018
	2019
	Total
	Approved MYAs after 2019

	Required for compliance

	Approved multi-year agreements (MYAs)
	93,837,860
	133,829,823
	74,338,005
	302,005,688
	342,891

	HCFC production phase-out management plan (HPPMP) preparation – stage I
	107,000
	0
	0
	107,000
	 

	HPPMP – stage I
	0
	532,500
	532,500
	1,065,000
	 

	HPPMP – stage II
	21,874,286
	21,874,286
	21,874,286
	65,622,857
	 

	HCFC phase-out management plan (HPMP) preparation – stage II
	836,571
	4,183,986
	163,411
	5,183,968
	 

	HPMP preparation – stage I
	36,697
	0
	0
	36,697
	 

	HPMPs and HPMP investment projects – stage I
	1,527,557
	1,190,748
	8,000
	2,726,306
	 

	HPMPs and HPMP investment projects – stage II
	12,832,243
	33,131,211
	24,574,373
	70,537,827
	 

	HPMP verification
	588,600
	588,600
	588,600
	1,765,800
	 

	Sub-total
	131,640,814
	195,331,154
	122,079,175
	449,051,143
	 

	Standard costs

	United Nations Environment Programme (UN Environment) compliance assistance programme (CAP)
	10,930,665
	11,258,585
	11,596,342
	33,785,592
	 

	Core unit (UNDP, UNIDO, World Bank)
	5,863,770
	5,904,816
	5,946,150
	17,714,736
	 

	Institutional strengthening (IS)
	11,360,704
	9,948,013
	11,180,876
	32,489,593
	 

	Secretariat/Executive Committee/ Monitoring and Evaluation  costs (excluding Canadian counterpart funding)
	6,505,874
	6,585,930
	6,718,640
	19,810,443
	 

	Treasurer 
	500,000
	500,000
	500,000
	1,500,000
	 

	Sub-total
	35,161,013
	34,197,344
	35,942,008
	105,300,365
	 

	Grand total
	166,801,827
	229,528,498
	158,021,183
	554,351,507
	 

	BY AGENCY

	Bilateral
	2,743,010
	10,388,715
	1,115,458
	14,247,183
	 

	UNDP
	43,340,791
	58,670,963
	35,054,984
	137,066,738
	 

	UN Environment
	27,575,568
	26,963,622
	23,907,026
	78,446,216
	 

	UNIDO
	45,184,709
	71,224,415
	42,721,017
	159,130,141
	 

	World Bank
	40,363,275
	54,606,253
	47,415,458
	142,384,986
	 

	HPMP verification reports*
	588,600
	588,600
	588,600
	1,765,800
	 

	Secretariat/Executive Committee/
Monitoring and Evaluation  costs (excluding Canadian counterpart funding)
	6,505,874
	6,585,930
	6,718,640
	19,810,443
	 

	Treasurer
	500,000
	500,000
	500,000
	1,500,000
	 


* Funding for the preparation of HPMP verification reports for low-volume-consuming countries is approved by the Executive Committee on an annual basis.

Status of implementation of the 2017 business plans
Table 2 sets out the submissions by agency to the 79th meeting (as at 7 June 2017), and the balance of funds from projects in the 2017 business plans.
Table 2. 2017 consolidated business plan, submissions to the 79th meeting, and balance (US $)*
	Budget items
	Total value in business plan
	79th meeting submissions**
	Balance (above)/below business plan levels

	Bilateral agencies
	2,743,010
	958,090
	1,784,920

	UNDP
	43,340,791
	 12,364,034 
	30,976,757

	UN Environment
	27,575,568
	 1,823,795 
	25,751,773

	UNIDO
	45,184,709
	 7,532,411 
	37,652,298

	World Bank
	40,363,275
	45,651,763
	(5,288,488)

	HPMP verification reports
	588,600
	32,700
	555,900

	Sub-total (agencies)
	159,795,953
	68,362,793
	91,433,160

	Secretariat/Executive Committee/
Monitoring and Evaluation costs 
(excluding Canadian counterpart)
	6,505,874
	
	6,505,874

	Treasurer
	500,000
	
	500,000

	Sub-total (standard costs)
	7,005,874
	0
	7,005,874

	Total
	166,801,827
	68,362,793
	98,439,034


* Including core unit costs.
** As at 7 June 2017. Funding requests associated with new stage II of HPMPs were still under discussion between the Secretariat and the relevant bilateral and implementing agencies. 
The total funding submitted by bilateral and implementing agencies to the 79th meeting (as at 7 June 2017) amounts to US $68,362,793, which is US $37,306,323 above the value for these activities in the consolidated 2017 business plan. This amount includes US $15,619,827 associated with the following activities which were not in the 2017 business plan: 
(a) Tranches of stage I of the HPMPs for Afghanistan (UNIDO; 
(b) Tranches of stage II of the HPMPs for Argentina (Italy) and Egypt (UN Environment and UNIDO); 
IS for Mexico and Qatar (UNIDO); 
HFC conversion investment projects for Bangladesh and Colombia (UNDP); and
Preparation for HFC-related projects for China (UNDP), Ecuador (UNIDO), Lebanon (UNIDO), Mexico (UNDP and UNIDO) and Viet Nam (UNIDO).
Annex I to the present document lists HFC-related projects in the manufacturing sector pursuant decision 78/3(g) submitted by the implementing agencies to the 79th meeting, and not required for compliance.
Table 3 presents the value for activities[footnoteRef:2] included in the 2017 consolidated business plan but not submitted to the 79th meeting. The list of these activities is contained in Annex II to the present report. [2:  These activities include: 113 HCFC activities for 42 countries (US $102.36 million), 66 IS activities (US $9.55 million), core unit (US $5.86 million) and CAP (US $10.93 million).] 

 Table 3. Activities in the 2017 consolidated business plan not yet submitted 
	Agency 
	Value (US $)

	Bilateral 
	2,067,420

	UNDP
	39,984,426

	UN Environment
	26,050,908

	UNIDO
	43,448,458

	World Bank
	16,599,672

	HPMP verification reports
	555,900

	Total
	128,706,784



Resources remaining at the end of the 2015-2017 triennium
The Parties to the Montreal Protocol adopted a budget of US $507,500,000 for the 2015-2017 replenishment of the Multilateral Fund, on the understanding that US $64,000,000 will be provided from anticipated contributions due to the Fund and other sources from the 2012‑2014 triennium, and that US $6,000,000 will be provided from interest accruing to the Fund during the 2015‑2017 triennium (decision XXVI/10). 

Taking into account approvals in 2015 and 2016, the business plans activities and the Secretariat’s/Executive Committee’s/Treasurer’s costs in 2017, the unutilized resource allocation at the end of the 2015-2017 triennium would be US $9.2 million, as shown in Table 4.

Table 4. Resource allocation for 2017 (US$)
	Description
	2017

	Revised resource allocation*
	153,800,000

	Carry-over from 2015 and 2016
	22,173,546

	Total allocation for 2017 (a)
	175,973,546

	Project costs
	 

	Business plans values (b)
	159,795,953

	Recurrent costs
	 

	Secretariat/Executive Committee/Monitoring and evaluation
	6,505,874

	Treasurer
	500,000

	Subtotal recurrent costs (c)
	7,005,874

	Total costs (d) = (b) + (c)
	166,801,827

	Balance (e) = (a) – (d)
	9,171,719


(*) Resources available from the 2015-2017 replenishment approved by the Parties, including US $6 million from interest accruing to the Fund.

However, the following factors would impact the level of resources remaining at the end of the 2015‑2017 triennium: interest accrued, gains/losses due to the fixed-exchange rate mechanism (FERM) and non-payment of pledged contributions in full in 2017. Based on information provided by the Treasurer, in 2015 and 2016, US $3,010,762 has been received from interest accrued (including US $419,032 by the Government of China).  If the level of interest expected to be accrued in 2017 is US $1.6 million, the interest expected for the triennium of US $4,610,762 would be US $1,389,238 below the level expected by the Parties. US $13,207,828 in losses is expected due to the FERM for 2017.  The shortfall of interest accrued and losses due to the FERM might cause a shortage in resources allocation for this triennium to cover all the activities in the 2017 business plan and other activities not included therein. The shortfall might be increased due to non-payment in full of pledge contributions expected during the 2015-2017 triennium. This has not taken into account countries with long outstanding contributions that were not expected to make the payment during the 2015-2017 triennium.
The Secretariat notes that the 2017 business plan values for stage II of the HPMP for China were based on agency support costs of 7 per cent for UNDP, UNIDO and the World Bank. If the Executive Committee decides to approve the support costs at a level lower than 7 per cent, the total values for the 2017 business plan would be slightly reduced (the total funding associated with the second tranche request by the three implementing agencies amounts to US $59.1 million).

Forward commitments 
The Secretariat will issue an addendum to the present document providing more accurately forward commitments associated with new stage II of HPMPs submitted to the 79th meeting. 
RECOMMENDATIONS

The Executive Committee may wish to note: 
(c) The update on the implementation of the 2017-2019 business plans contained in document UNEP/OzL.Pro/ExCom/79/17; 
[bookmark: _GoBack]That US $9,700,228 in HFC-related activities in the manufacturing sector pursuant to decision 78/3(g) was submitted to the 79th meeting that had not been included in the 2017-2019 business plans; and
(d) That an addendum will be issued to address forward commitments associated with new stage II of HCFC phase-out management plans.
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Annex I

HFC-RELATED PROJECTS 

	Country
	Agency
	Type
	Sector
	Project title
	Amount requested including support costs 
(US $)

	Bangladesh
	UNDP
	INV
	REF
	Conversion of reciprocating compressor of HFC-134a to inverter based on high energy efficient compressor (isobutane) in Walton Hi-Tech Industries Limited
	5,282,062

	China
	UNDP
	PRP
	REF
	Preparation for conversion from HFC-134a to HC-290 in a freezer manufacturer
	32,100

	China
	UNDP
	PRP
	REF
	Project preparation for air-conditioning and production line optimization from HFC-134a to HFO‑1234yf as refrigerant in a mobile air‑conditioning manufacturer
	32,100

	China
	UNDP
	PRP
	FOA
	Project preparation for conversion from HFC-245fa to HFO as a foam agent in a refrigerator manufacturer
	32,100

	Colombia
	UNDP
	INV
	REF
	Conversion from HFC-134a to isobutane in the manufacture of domestic refrigerators at Mabe
	4,097,166

	Ecuador
	UNIDO
	PRP
	REF
	Preparation for HFC-related projects in the manufacturing sector at Ecasa and Indurama to gain experience in incremental costs associated with the phase-down of HFCs
	64,200

	Lebanon
	UNIDO
	PRP
	REF
	Preparation for a HFC-related project in the manufacturing sector at Lematic Industries to gain experience in incremental costs associated with the phase-down of HFCs in domestic refrigeration
	32,100

	Mexico
	UNDP
	PRP
	REF
	Project preparation for HFC phase-out in the production of refrigerators at Mabe
	32,100

	Mexico
	UNIDO
	PRP
	REF
	Preparation for HFC-related projects in the manufacturing sector at Fersa and Imbera to gain experience in incremental costs associated with the phase-down of HFCs
	64,200

	Viet Nam
	UNIDO
	PRP
	REF
	Preparation for a HFC-related project in the manufacturing sector at Nagakawa Vietnam Company to gain experience in incremental costs associated with the phase-down of HFCs
	32,100

	Total
	 
	 
	 
	 
	9,700,228
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Annex II

REMAINING ACTIVITIES IN THE 2017 BUSINESS PLAN 

	Country
	Agency
	Sector and Subsector
	Value ($000) 2017 

	Afghanistan
	UN Environment
	Several Ozone unit support
	192

	Algeria
	UN Environment
	Several Ozone unit support
	329

	Algeria
	UNIDO
	HPMP Stage I
	155

	Algeria
	UNIDO
	FOA-Rigid PU foam  - Stage II
	54

	Algeria
	UNIDO
	REF-Manufacturing  - Stage II
	54

	Algeria
	UNIDO
	REF-Servicing  - Stage II
	64

	Angola
	UN Environment
	Several Ozone unit support
	172

	Antigua and Barbuda
	UN Environment
	Stage 2 - HCFC Phase-out Management Plan (implementation)
	45

	Antigua and Barbuda
	UN Environment
	HPMP Stage I
	7

	Antigua and Barbuda
	UN Environment
	Several Ozone unit support
	85

	Bahamas (the)
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	66

	Bahamas (the)
	UNIDO
	HPMP Stage I
	39

	Bahrain
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	141

	Bahrain
	UNIDO
	REF-Air conditioning - Stage I
	899

	Bahrain
	UNIDO
	REF-Servicing - Stage I
	1,002

	Bangladesh
	UNDP
	Stage II HPMP (air conditioning)
	344

	Bangladesh
	UNDP
	Stage II HPMP (servicing)
	28

	Bangladesh
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	20

	Barbados
	UNDP
	Stage I HPMP
	41

	Barbados
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	54

	Barbados
	UN Environment
	Several Ozone unit support
	150

	Belize
	UN Environment
	Several Ozone unit support
	98

	Benin
	UN Environment
	Several Ozone unit support
	85

	Bolivia (Plurinational State of)
	UNDP
	Stage I HPMP Preparation (foam)
	37

	Bolivia (Plurinational State of)
	UN Environment
	Several Ozone unit support
	101

	Bosnia and Herzegovina
	UNIDO
	Several Ozone unit support
	131

	Brazil
	Germany
	Ref-Servicing - Stage II
	763

	Brazil
	UNDP
	Stage II HPMP
	4,417

	Brazil
	UNDP
	Several Ozone unit support
	481

	Brunei Darussalam
	UNDP
	Stage I Investment proj./Sector Plans (Servicing Sector)
	36

	Brunei Darussalam
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	8

	Burkina Faso
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	142

	Burkina Faso
	UNIDO
	HPMP Stage I
	109

	Burundi
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	40

	Burundi
	UN Environment
	Several Ozone unit support
	85

	Burundi
	UNIDO
	HPMP Stage I
	87

	Cameroon
	UN Environment
	Several Ozone unit support
	179

	Cameroon
	UNIDO
	REF-Assembly and charging of refrigeration equipment - Stage II
	755

	Cameroon
	UNIDO
	REF-Servicing - Stage I
	64

	Cameroon
	UNIDO
	REF-Servicing - Stage II
	374

	Cabo Verde
	UN Environment
	Several Ozone unit support
	85

	Central African Republic (the)
	UN Environment
	Several Ozone unit support
	85

	Chad
	UN Environment
	Several Ozone unit support
	85

	China
	Germany
	HPMP Stage II - XPS  foam
	300

	China
	World Bank
	HPMP Stage II - PU Foam 
	8,195

	China
	Japan
	HPMP Stage II - Refrigeration servicing sector
	90

	China
	UNDP
	HPMP Stage II - ICR 
	24,404

	China
	UNDP
	HPMP Stage II - Solvent 
	3,784

	China
	UN Environment
	HPMP Stage II - Refrigeration servicing sector
	5,032

	China
	UNIDO
	HPMP Stage II - RAC 
	14,962

	China
	UNIDO
	HPMP Stage II - XPS  foam
	9,804

	Comoros (the)
	UN Environment
	Several Ozone unit support
	85

	Congo (the)
	UN Environment
	Several Ozone unit support
	85

	Costa Rica
	UNDP
	Stage I HPMP
	114

	Costa Rica
	UNDP
	Stage I HPMP (foam sector)
	277

	Costa Rica
	UNDP
	Several Ozone unit support
	192

	Cote d'Ivoire
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	168

	Cote d'Ivoire
	UNIDO
	HPMP Stage I
	492

	Cuba
	UNDP
	HCFC-INV: AC Manufacturing - Stage I
	128

	Cuba
	UNDP
	Several Ozone unit support
	204

	Democratic People's Republic of Korea (the)
	UNIDO
	HCFC Production Preparation - Stage I
	107

	Democratic Republic of the Congo (the)
	UNDP
	HPMP Stage I
	26

	Democratic Republic of the Congo (the)
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	27

	Djibouti
	UN Environment
	Several Ozone unit support
	85

	Dominica
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	74

	Dominica
	UN Environment
	Several Ozone unit support
	85

	Equatorial Guinea
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	40

	Equatorial Guinea
	UN Environment
	Several Ozone unit support
	102

	Equatorial Guinea
	UNIDO
	HPMP Stage I
	82

	Ethiopia
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	62

	Gabon
	UN Environment
	Several Ozone unit support
	85

	Georgia
	UNDP
	Stage I HPMP
	128

	Georgia
	UNDP
	Several Ozone unit support
	91

	Global
	ALL
	HPMP Verification
	556

	Global
	World Bank
	Core Unit
	1,725

	Global
	UNDP
	Core Unit
	2,069

	Global
	UN Environment
	Global CAP 2017 work programme
	10,931

	Global
	UNIDO
	Core Unit
	2,069

	Grenada
	UN Environment
	Several Ozone unit support
	85

	Guatemala
	UN Environment
	Several Ozone unit support
	160

	Guinea
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	73

	Guinea
	UN Environment
	Several Ozone unit support
	85

	Guinea
	UNIDO
	HPMP Stage I
	172

	Haiti
	UN Environment
	Several Ozone unit support
	128

	Honduras
	UN Environment
	Several Ozone unit support
	85

	Indonesia
	UNDP
	Several Ozone unit support
	371

	Iraq
	UN Environment
	Stage 2 - HCFC Phase-out Management Plan (implementation)
	493

	Iraq
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	248

	Iraq
	UNIDO
	REF-Manufacturing - Stage II
	629

	Iraq
	UNIDO
	REF-Servicing - Stage I
	226

	Iraq
	UNIDO
	REF-Servicing - Stage II
	467

	Jamaica
	UN Environment
	Several Ozone unit support
	85

	Kenya
	France
	HCFC Phase Out Plan (Stage I)
	101

	Kenya
	UN Environment
	Several Ozone unit support
	194

	Kuwait
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	372

	Kuwait
	UN Environment
	Stage 2 - HCFC Phase-out Management Plan (preparation) 
	68

	Kuwait
	UNIDO
	FOA-XPS - Stage I
	1,129

	Kuwait
	UNIDO
	REF-Servicing - Stage II
	32

	Kuwait
	UNIDO
	FOA-Rigid PU foam  - Stage II
	86

	Kuwait
	UNIDO
	REF-Air Conditioning  - Stage II
	86

	Lesotho
	Germany
	Ref-Servicing - Stage I
	95

	Liberia
	UN Environment
	Several Ozone unit support
	109

	Libya
	UNIDO
	FOA-Rigid PU foam  - Stage II
	87

	Libya
	UNIDO
	REF-Servicing  - Stage II
	95

	Malaysia
	UNDP
	Several Ozone unit support
	383

	Maldives
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	57

	Mali
	UN Environment
	Several Ozone unit support
	85

	Marshall Islands
	UN Environment
	Several Ozone unit support
	85

	Mauritania
	UNDP
	Stage I HPMP
	42

	Mauritania
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	86

	Morocco
	UN Environment
	Several Ozone unit support
	200

	Morocco
	UNIDO
	REF-Servicing and FOA - Stage I
	38

	Mozambique
	UN Environment
	HPMP Stage I
	34

	Mozambique
	UNIDO
	HPMP Stage I
	82

	Myanmar
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	36

	Myanmar
	UN Environment
	Several Ozone unit support
	85

	Myanmar
	UNIDO
	HPMP Stage I
	65

	Nauru
	UN Environment
	Several Ozone unit support
	85

	Nicaragua
	UN Environment
	Several Ozone unit support
	85

	Niger (the)
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	141

	Niger (the)
	UN Environment
	Several Ozone unit support
	85

	Niger (the)
	UNIDO
	REF-Servicing - Stage I
	97

	Nigeria
	Italy
	Stage II HPMP (foam)
	226

	Nigeria
	Italy
	Stage II HPMP (servicing)
	39

	Nigeria
	UNDP
	Stage II HPMP (foam)
	574

	Nigeria
	UNDP
	Stage II HPMP (servicing)
	626

	Nigeria
	UNIDO
	REF-Manufacturing - Stage II
	1,634

	Nigeria
	UNIDO
	REF-Manufacturing FOA - Stage II
	214

	Niue
	UN Environment
	Several Ozone unit support
	85

	Oman
	UNIDO
	Several Ozone unit support
	94

	Palau
	UN Environment
	Several Ozone unit support
	85

	Panama
	UNDP
	Several Ozone unit support
	191

	Paraguay
	UNDP
	Stage I HPMP (foam)
	96

	Peru
	UNDP
	Stage II HPMP (servicing)
	251

	Peru
	UNDP
	Stage II HPMP Preparation (foam)  - Stage II
	60

	Peru
	UN Environment
	Stage 2 - HCFC Phase-out Management Plan (implementation)
	14

	Peru
	UN Environment
	Several Ozone unit support
	171

	Philippines (the)
	UN Environment
	HPMP Stage I
	26

	Qatar
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	232

	Qatar
	UNIDO
	REF-Servicing - Stage I
	160

	Qatar
	UNIDO
	HPMP Stage I
	572

	Rwanda
	UN Environment
	Several Ozone unit support
	85

	Saint Kitts and Nevis
	UN Environment
	Several Ozone unit support
	85

	Saint Lucia
	UN Environment
	Several Ozone unit support
	85

	Saint Vincent and the Grenadines
	UN Environment
	Several Ozone unit support
	85

	Samoa
	UN Environment
	Several Ozone unit support
	85

	Saudi Arabia
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	138

	Saudi Arabia
	UN Environment
	Several Ozone unit support
	256

	Saudi Arabia
	UNIDO
	REF-Air conditioning - Stage I
	910

	Senegal
	UN Environment
	Several Ozone unit support
	195

	Serbia
	UNIDO
	Several Ozone unit support
	180

	Seychelles
	UN Environment
	Several Ozone unit support
	85

	Sierra Leone
	UN Environment
	Several Ozone unit support
	110

	Solomon Islands
	UN Environment
	Several Ozone unit support
	85

	Sudan (the)
	UN Environment
	Several Ozone unit support
	187

	Sudan (the)
	UNIDO
	HPMP Stage I
	43

	Suriname
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	40

	Suriname
	UNIDO
	HPMP Stage I
	32

	Syrian Arab Republic
	UNIDO
	Several Ozone unit support
	279

	Thailand
	World Bank
	FOA - Rigid PU foam & REF-Air conditioning - Stage I
	4,348

	Timor-Leste
	UNDP
	HPMP Stage I
	12

	Timor-Leste
	UN Environment
	Stage 2 - HCFC Phase-out Management Plan (implementation)
	121

	Timor-Leste
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	19

	Tonga
	UN Environment
	Several Ozone unit support
	85

	Trinidad and Tobago
	UNDP
	Stage I HPMP
	156

	Tunisia
	France
	HCFC Phase Out Plan (Stage I)
	79

	Tunisia
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	17

	Tunisia
	UNIDO
	REF-Servicing, RAC-Manuf., FOA-Rigid PU foam - Stage I
	116

	Tunisia
	UNIDO
	Several Ozone unit support
	339

	Turkey
	UN Environment
	Stage 2 - HCFC Phase-out Management Plan (implementation) 
	740

	Turkey
	UNIDO
	REF-Servicing - Stage I
	1,605

	Turkey
	UNIDO
	HPMP Stage I
	1,711

	Turkey
	UNIDO
	Several Ozone unit support
	356

	Uganda
	UN Environment
	Several Ozone unit support
	85

	United Republic of Tanzania
	UN Environment
	Several Ozone unit support
	85

	Uruguay
	UNDP
	Several Ozone unit support
	207

	Venezuela (Bolivarian Republic of)
	UNDP
	Stage II HPMP
	214

	Venezuela (Bolivarian Republic of)
	UNIDO
	RAC-Manufacturing - Stage II
	615

	Viet Nam
	World Bank
	FOA - Rigid PU foam & REF (Air conditioning/Commercial ref/Servicing) - Stage II
	2,332

	Viet Nam
	Japan
	REF-Servicing - Stage II
	185

	Yemen
	UN Environment
	HCFC Phase-out Management Plan (implementation) - Stage I
	186

	Yemen
	UN Environment
	Several Ozone unit support
	218

	Zimbabwe
	Germany
	Ref-Servicing - Stage I
	188
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