| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/79/17 7 June 2017 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Seventy-ninth Meeting

Bangkok, 3-7 July 2017

UPDATE ON THE IMPLEMENTATION OF THE 2017-2019 BUSINESS PLANS

Introduction

# At its 77th meeting, the Executive Committee endorsed the consolidated business plan of the Multilateral Fund for 2017-2019. In response to decision 77/27(b), the Secretariat adjusted the consolidated 2017-2019 business plan, as shown in Table 1.

Table 1. Resource allocation of the of the adjusted 2017-2019 business plans of the Multilateral Fund (US $)

| Description | 2017 | 2018 | 2019 | Total | Approved MYAs after 2019 |
| --- | --- | --- | --- | --- | --- |
| Required for compliance |  |  |  |  |  |
| Approved multi-year agreements (MYAs) | 93,837,860 | 133,829,823 | 74,338,005 | 302,005,688 | 342,891 |
| HCFC production phase-out management plan (HPPMP) preparation – stage I | 107,000 | 0 | 0 | 107,000 |  |
| HPPMP – stage I | 0 | 532,500 | 532,500 | 1,065,000 |  |
| HPPMP – stage II | 21,874,286 | 21,874,286 | 21,874,286 | 65,622,857 |  |
| HCFC phase-out management plan (HPMP) preparation – stage II | 836,571 | 4,183,986 | 163,411 | 5,183,968 |  |
| HPMP preparation – stage I | 36,697 | 0 | 0 | 36,697 |  |
| HPMPs and HPMP investment projects – stage I | 1,527,557 | 1,190,748 | 8,000 | 2,726,306 |  |
| HPMPs and HPMP investment projects – stage II | 12,832,243 | 33,131,211 | 24,574,373 | 70,537,827 |  |
| HPMP verification | 588,600 | 588,600 | 588,600 | 1,765,800 |  |
| Sub-total | 131,640,814 | 195,331,154 | 122,079,175 | 449,051,143 |  |
| Standard costs |  |  |  |  |  |
| United Nations Environment Programme (UN Environment) compliance assistance programme (CAP) | 10,930,665 | 11,258,585 | 11,596,342 | 33,785,592 |  |
| Core unit (UNDP, UNIDO, World Bank) | 5,863,770 | 5,904,816 | 5,946,150 | 17,714,736 |  |
| Institutional strengthening (IS) | 11,360,704 | 9,948,013 | 11,180,876 | 32,489,593 |  |
| Secretariat/Executive Committee/ Monitoring and Evaluation costs (excluding Canadian counterpart funding) | 6,505,874 | 6,585,930 | 6,718,640 | 19,810,443 |  |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |  |
| Sub-total | 35,161,013 | 34,197,344 | 35,942,008 | 105,300,365 |  |
| Grand total | 166,801,827 | 229,528,498 | 158,021,183 | 554,351,507 |  |
| BY AGENCY |  |  |  |  |  |
| Bilateral | 2,743,010 | 10,388,715 | 1,115,458 | 14,247,183 |  |
| UNDP | 43,340,791 | 58,670,963 | 35,054,984 | 137,066,738 |  |
| UN Environment | 27,575,568 | 26,963,622 | 23,907,026 | 78,446,216 |  |
| UNIDO | 45,184,709 | 71,224,415 | 42,721,017 | 159,130,141 |  |
| World Bank | 40,363,275 | 54,606,253 | 47,415,458 | 142,384,986 |  |
| HPMP verification reports* | 588,600 | 588,600 | 588,600 | 1,765,800 |  |
| Secretariat/Executive Committee/ Monitoring and Evaluation costs (excluding Canadian counterpart funding) | 6,505,874 | 6,585,930 | 6,718,640 | 19,810,443 |  |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |  |

* Funding for the preparation of HPMP verification reports for low-volume-consuming countries is approved by the Executive Committee on an annual basis.

Status of implementation of the 2017 business plans

# Table 2 sets out the submissions by agency to the 79th meeting (as at 7 June 2017), and the balance of funds from projects in the 2017 business plans.

Table 2. 2017 consolidated business plan, submissions to the 79th meeting, and balance (US $)*

| Budget items | Total value in business plan | 79th meeting submissions** | Balance (above)/below business plan levels |
| --- | --- | --- | --- |
| Bilateral agencies | 2,743,010 | 958,090 | 1,784,920 |
| UNDP | 43,340,791 | 12,364,034 | 30,976,757 |
| UN Environment | 27,575,568 | 1,823,795 | 25,751,773 |
| UNIDO | 45,184,709 | 7,532,411 | 37,652,298 |
| World Bank | 40,363,275 | 45,651,763 | (5,288,488) |
| HPMP verification reports | 588,600 | 32,700 | 555,900 |
| Sub-total (agencies) | 159,795,953 | 68,362,793 | 91,433,160 |
| Secretariat/Executive Committee/ Monitoring and Evaluation costs (excluding Canadian counterpart) | 6,505,874 |  | 6,505,874 |
| Treasurer | 500,000 |  | 500,000 |
| Sub-total (standard costs) | 7,005,874 | 0 | 7,005,874 |
| Total | 166,801,827 | 68,362,793 | 98,439,034 |

* Including core unit costs.

** As at 7 June 2017. Funding requests associated with new stage II of HPMPs were still under discussion between the Secretariat and the relevant bilateral and implementing agencies.

# The total funding submitted by bilateral and implementing agencies to the 79th meeting (as at 7 June 2017) amounts to US $68,362,793, which is US $37,306,323 above the value for these activities in the consolidated 2017 business plan. This amount includes US $15,619,827 associated with the following activities which were not in the 2017 business plan:

## Tranches of stage I of the HPMPs for Afghanistan (UNIDO;

## Tranches of stage II of the HPMPs for Argentina (Italy) and Egypt (UN Environment and UNIDO);

## IS for Mexico and Qatar (UNIDO);

## HFC conversion investment projects for Bangladesh and Colombia (UNDP); and

## Preparation for HFC-related projects for China (UNDP), Ecuador (UNIDO), Lebanon (UNIDO), Mexico (UNDP and UNIDO) and Viet Nam (UNIDO).

# Annex I to the present document lists HFC-related projects in the manufacturing sector pursuant decision 78/3(g) submitted by the implementing agencies to the 79th meeting, and not required for compliance.

# Table 3 presents the value for activities included in the 2017 consolidated business plan but not submitted to the 79th meeting. The list of these activities is contained in Annex II to the present report.

# Table 3. Activities in the 2017 consolidated business plan not yet submitted

| Agency | Value (US $) |
| --- | --- |
| Bilateral | 2,067,420 |
| UNDP | 39,984,426 |
| UN Environment | 26,050,908 |
| UNIDO | 43,448,458 |
| World Bank | 16,599,672 |
| HPMP verification reports | 555,900 |
| Total | 128,706,784 |

# Resources remaining at the end of the 2015-2017 triennium

# The Parties to the Montreal Protocol adopted a budget of US $507,500,000 for the 2015-2017 replenishment of the Multilateral Fund, on the understanding that US $64,000,000 will be provided from anticipated contributions due to the Fund and other sources from the 2012-2014 triennium, and that US $6,000,000 will be provided from interest accruing to the Fund during the 2015-2017 triennium (decision XXVI/10).

# Taking into account approvals in 2015 and 2016, the business plans activities and the Secretariat’s/Executive Committee’s/Treasurer’s costs in 2017, the unutilized resource allocation at the end of the 2015-2017 triennium would be US $9.2 million, as shown in Table 4.

Table 4. Resource allocation for 2017 (US$)

| Description | 2017 |
| --- | --- |
| Revised resource allocation* | 153,800,000 |
| Carry-over from 2015 and 2016 | 22,173,546 |
| Total allocation for 2017 (a) | 175,973,546 |
| Project costs |  |
| Business plans values (b) | 159,795,953 |
| Recurrent costs |  |
| Secretariat/Executive Committee/Monitoring and evaluation | 6,505,874 |
| Treasurer | 500,000 |
| Subtotal recurrent costs (c) | 7,005,874 |
| Total costs (d) = (b) + (c) | 166,801,827 |
| Balance (e) = (a) – (d) | 9,171,719 |

(*) Resources available from the 2015-2017 replenishment approved by the Parties, including US $6 million from interest accruing to the Fund.

# However, the following factors would impact the level of resources remaining at the end of the 2015-2017 triennium: interest accrued, gains/losses due to the fixed-exchange rate mechanism (FERM) and non-payment of pledged contributions in full in 2017. Based on information provided by the Treasurer, in 2015 and 2016, US $3,010,762 has been received from interest accrued (including US $419,032 by the Government of China).  If the level of interest expected to be accrued in 2017 is US $1.6 million, the interest expected for the triennium of US $4,610,762 would be US $1,389,238 below the level expected by the Parties. US $13,207,828 in losses is expected due to the FERM for 2017.  The shortfall of interest accrued and losses due to the FERM might cause a shortage in resources allocation for this triennium to cover all the activities in the 2017 business plan and other activities not included therein. The shortfall might be increased due to non-payment in full of pledge contributions expected during the 2015-2017 triennium. This has not taken into account countries with long outstanding contributions that were not expected to make the payment during the 2015-2017 triennium.

# The Secretariat notes that the 2017 business plan values for stage II of the HPMP for China were based on agency support costs of 7 per cent for UNDP, UNIDO and the World Bank. If the Executive Committee decides to approve the support costs at a level lower than 7 per cent, the total values for the 2017 business plan would be slightly reduced (the total funding associated with the second tranche request by the three implementing agencies amounts to US $59.1 million).

# Forward commitments

# The Secretariat will issue an addendum to the present document providing more accurately forward commitments associated with new stage II of HPMPs submitted to the 79th meeting.

# RECOMMENDATIONS

# The Executive Committee may wish to note:

## The update on the implementation of the 2017-2019 business plans contained in document UNEP/OzL.Pro/ExCom/79/17;

## That US $9,700,228 in HFC-related activities in the manufacturing sector pursuant to decision 78/3(g) was submitted to the 79th meeting that had not been included in the 2017-2019 business plans; and

## That an addendum will be issued to address forward commitments associated with new stage II of HCFC phase-out management plans.

Annex I

HFC-RELATED PROJECTS

| Country | Agency | Type | Sector | Project title | Amount requested including support costs (US $) |
| --- | --- | --- | --- | --- | --- |
| Bangladesh | UNDP | INV | REF | Conversion of reciprocating compressor of HFC-134a to inverter based on high energy efficient compressor (isobutane) in Walton Hi-Tech Industries Limited | 5,282,062 |
| China | UNDP | PRP | REF | Preparation for conversion from HFC-134a to HC-290 in a freezer manufacturer | 32,100 |
| China | UNDP | PRP | REF | Project preparation for air-conditioning and production line optimization from HFC-134a to HFO-1234yf as refrigerant in a mobile air-conditioning manufacturer | 32,100 |
| China | UNDP | PRP | FOA | Project preparation for conversion from HFC-245fa to HFO as a foam agent in a refrigerator manufacturer | 32,100 |
| Colombia | UNDP | INV | REF | Conversion from HFC-134a to isobutane in the manufacture of domestic refrigerators at Mabe | 4,097,166 |
| Ecuador | UNIDO | PRP | REF | Preparation for HFC-related projects in the manufacturing sector at Ecasa and Indurama to gain experience in incremental costs associated with the phase-down of HFCs | 64,200 |
| Lebanon | UNIDO | PRP | REF | Preparation for a HFC-related project in the manufacturing sector at Lematic Industries to gain experience in incremental costs associated with the phase-down of HFCs in domestic refrigeration | 32,100 |
| Mexico | UNDP | PRP | REF | Project preparation for HFC phase-out in the production of refrigerators at Mabe | 32,100 |
| Mexico | UNIDO | PRP | REF | Preparation for HFC-related projects in the manufacturing sector at Fersa and Imbera to gain experience in incremental costs associated with the phase-down of HFCs | 64,200 |
| Viet Nam | UNIDO | PRP | REF | Preparation for a HFC-related project in the manufacturing sector at Nagakawa Vietnam Company to gain experience in incremental costs associated with the phase-down of HFCs | 32,100 |
| Total |  |  |  |  | 9,700,228 |

Annex II

REMAINING ACTIVITIES IN THE 2017 BUSINESS PLAN

| Country | Agency | Sector and Subsector | Value ($000) 2017 |
| --- | --- | --- | --- |
| Afghanistan | UN Environment | Several Ozone unit support | 192 |
| Algeria | UN Environment | Several Ozone unit support | 329 |
| Algeria | UNIDO | HPMP Stage I | 155 |
| Algeria | UNIDO | FOA-Rigid PU foam - Stage II | 54 |
| Algeria | UNIDO | REF-Manufacturing - Stage II | 54 |
| Algeria | UNIDO | REF-Servicing - Stage II | 64 |
| Angola | UN Environment | Several Ozone unit support | 172 |
| Antigua and Barbuda | UN Environment | Stage 2 - HCFC Phase-out Management Plan (implementation) | 45 |
| Antigua and Barbuda | UN Environment | HPMP Stage I | 7 |
| Antigua and Barbuda | UN Environment | Several Ozone unit support | 85 |
| Bahamas (the) | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 66 |
| Bahamas (the) | UNIDO | HPMP Stage I | 39 |
| Bahrain | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 141 |
| Bahrain | UNIDO | REF-Air conditioning - Stage I | 899 |
| Bahrain | UNIDO | REF-Servicing - Stage I | 1,002 |
| Bangladesh | UNDP | Stage II HPMP (air conditioning) | 344 |
| Bangladesh | UNDP | Stage II HPMP (servicing) | 28 |
| Bangladesh | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 20 |
| Barbados | UNDP | Stage I HPMP | 41 |
| Barbados | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 54 |
| Barbados | UN Environment | Several Ozone unit support | 150 |
| Belize | UN Environment | Several Ozone unit support | 98 |
| Benin | UN Environment | Several Ozone unit support | 85 |
| Bolivia (Plurinational State of) | UNDP | Stage I HPMP Preparation (foam) | 37 |
| Bolivia (Plurinational State of) | UN Environment | Several Ozone unit support | 101 |
| Bosnia and Herzegovina | UNIDO | Several Ozone unit support | 131 |
| Brazil | Germany | Ref-Servicing - Stage II | 763 |
| Brazil | UNDP | Stage II HPMP | 4,417 |
| Brazil | UNDP | Several Ozone unit support | 481 |
| Brunei Darussalam | UNDP | Stage I Investment proj./Sector Plans (Servicing Sector) | 36 |
| Brunei Darussalam | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 8 |
| Burkina Faso | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 142 |
| Burkina Faso | UNIDO | HPMP Stage I | 109 |
| Burundi | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 40 |
| Burundi | UN Environment | Several Ozone unit support | 85 |
| Burundi | UNIDO | HPMP Stage I | 87 |
| Cameroon | UN Environment | Several Ozone unit support | 179 |
| Cameroon | UNIDO | REF-Assembly and charging of refrigeration equipment - Stage II | 755 |
| Cameroon | UNIDO | REF-Servicing - Stage I | 64 |
| Cameroon | UNIDO | REF-Servicing - Stage II | 374 |
| Cabo Verde | UN Environment | Several Ozone unit support | 85 |
| Central African Republic (the) | UN Environment | Several Ozone unit support | 85 |
| Chad | UN Environment | Several Ozone unit support | 85 |
| China | Germany | HPMP Stage II - XPS foam | 300 |
| China | World Bank | HPMP Stage II - PU Foam | 8,195 |
| China | Japan | HPMP Stage II - Refrigeration servicing sector | 90 |
| China | UNDP | HPMP Stage II - ICR | 24,404 |
| China | UNDP | HPMP Stage II - Solvent | 3,784 |
| China | UN Environment | HPMP Stage II - Refrigeration servicing sector | 5,032 |
| China | UNIDO | HPMP Stage II - RAC | 14,962 |
| China | UNIDO | HPMP Stage II - XPS foam | 9,804 |
| Comoros (the) | UN Environment | Several Ozone unit support | 85 |
| Congo (the) | UN Environment | Several Ozone unit support | 85 |
| Costa Rica | UNDP | Stage I HPMP | 114 |
| Costa Rica | UNDP | Stage I HPMP (foam sector) | 277 |
| Costa Rica | UNDP | Several Ozone unit support | 192 |
| Cote d'Ivoire | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 168 |
| Cote d'Ivoire | UNIDO | HPMP Stage I | 492 |
| Cuba | UNDP | HCFC-INV: AC Manufacturing - Stage I | 128 |
| Cuba | UNDP | Several Ozone unit support | 204 |
| Democratic People's Republic of Korea (the) | UNIDO | HCFC Production Preparation - Stage I | 107 |
| Democratic Republic of the Congo (the) | UNDP | HPMP Stage I | 26 |
| Democratic Republic of the Congo (the) | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 27 |
| Djibouti | UN Environment | Several Ozone unit support | 85 |
| Dominica | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 74 |
| Dominica | UN Environment | Several Ozone unit support | 85 |
| Equatorial Guinea | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 40 |
| Equatorial Guinea | UN Environment | Several Ozone unit support | 102 |
| Equatorial Guinea | UNIDO | HPMP Stage I | 82 |
| Ethiopia | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 62 |
| Gabon | UN Environment | Several Ozone unit support | 85 |
| Georgia | UNDP | Stage I HPMP | 128 |
| Georgia | UNDP | Several Ozone unit support | 91 |
| Global | ALL | HPMP Verification | 556 |
| Global | World Bank | Core Unit | 1,725 |
| Global | UNDP | Core Unit | 2,069 |
| Global | UN Environment | Global CAP 2017 work programme | 10,931 |
| Global | UNIDO | Core Unit | 2,069 |
| Grenada | UN Environment | Several Ozone unit support | 85 |
| Guatemala | UN Environment | Several Ozone unit support | 160 |
| Guinea | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 73 |
| Guinea | UN Environment | Several Ozone unit support | 85 |
| Guinea | UNIDO | HPMP Stage I | 172 |
| Haiti | UN Environment | Several Ozone unit support | 128 |
| Honduras | UN Environment | Several Ozone unit support | 85 |
| Indonesia | UNDP | Several Ozone unit support | 371 |
| Iraq | UN Environment | Stage 2 - HCFC Phase-out Management Plan (implementation) | 493 |
| Iraq | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 248 |
| Iraq | UNIDO | REF-Manufacturing - Stage II | 629 |
| Iraq | UNIDO | REF-Servicing - Stage I | 226 |
| Iraq | UNIDO | REF-Servicing - Stage II | 467 |
| Jamaica | UN Environment | Several Ozone unit support | 85 |
| Kenya | France | HCFC Phase Out Plan (Stage I) | 101 |
| Kenya | UN Environment | Several Ozone unit support | 194 |
| Kuwait | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 372 |
| Kuwait | UN Environment | Stage 2 - HCFC Phase-out Management Plan (preparation) | 68 |
| Kuwait | UNIDO | FOA-XPS - Stage I | 1,129 |
| Kuwait | UNIDO | REF-Servicing - Stage II | 32 |
| Kuwait | UNIDO | FOA-Rigid PU foam - Stage II | 86 |
| Kuwait | UNIDO | REF-Air Conditioning - Stage II | 86 |
| Lesotho | Germany | Ref-Servicing - Stage I | 95 |
| Liberia | UN Environment | Several Ozone unit support | 109 |
| Libya | UNIDO | FOA-Rigid PU foam - Stage II | 87 |
| Libya | UNIDO | REF-Servicing - Stage II | 95 |
| Malaysia | UNDP | Several Ozone unit support | 383 |
| Maldives | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 57 |
| Mali | UN Environment | Several Ozone unit support | 85 |
| Marshall Islands | UN Environment | Several Ozone unit support | 85 |
| Mauritania | UNDP | Stage I HPMP | 42 |
| Mauritania | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 86 |
| Morocco | UN Environment | Several Ozone unit support | 200 |
| Morocco | UNIDO | REF-Servicing and FOA - Stage I | 38 |
| Mozambique | UN Environment | HPMP Stage I | 34 |
| Mozambique | UNIDO | HPMP Stage I | 82 |
| Myanmar | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 36 |
| Myanmar | UN Environment | Several Ozone unit support | 85 |
| Myanmar | UNIDO | HPMP Stage I | 65 |
| Nauru | UN Environment | Several Ozone unit support | 85 |
| Nicaragua | UN Environment | Several Ozone unit support | 85 |
| Niger (the) | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 141 |
| Niger (the) | UN Environment | Several Ozone unit support | 85 |
| Niger (the) | UNIDO | REF-Servicing - Stage I | 97 |
| Nigeria | Italy | Stage II HPMP (foam) | 226 |
| Nigeria | Italy | Stage II HPMP (servicing) | 39 |
| Nigeria | UNDP | Stage II HPMP (foam) | 574 |
| Nigeria | UNDP | Stage II HPMP (servicing) | 626 |
| Nigeria | UNIDO | REF-Manufacturing - Stage II | 1,634 |
| Nigeria | UNIDO | REF-Manufacturing FOA - Stage II | 214 |
| Niue | UN Environment | Several Ozone unit support | 85 |
| Oman | UNIDO | Several Ozone unit support | 94 |
| Palau | UN Environment | Several Ozone unit support | 85 |
| Panama | UNDP | Several Ozone unit support | 191 |
| Paraguay | UNDP | Stage I HPMP (foam) | 96 |
| Peru | UNDP | Stage II HPMP (servicing) | 251 |
| Peru | UNDP | Stage II HPMP Preparation (foam) - Stage II | 60 |
| Peru | UN Environment | Stage 2 - HCFC Phase-out Management Plan (implementation) | 14 |
| Peru | UN Environment | Several Ozone unit support | 171 |
| Philippines (the) | UN Environment | HPMP Stage I | 26 |
| Qatar | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 232 |
| Qatar | UNIDO | REF-Servicing - Stage I | 160 |
| Qatar | UNIDO | HPMP Stage I | 572 |
| Rwanda | UN Environment | Several Ozone unit support | 85 |
| Saint Kitts and Nevis | UN Environment | Several Ozone unit support | 85 |
| Saint Lucia | UN Environment | Several Ozone unit support | 85 |
| Saint Vincent and the Grenadines | UN Environment | Several Ozone unit support | 85 |
| Samoa | UN Environment | Several Ozone unit support | 85 |
| Saudi Arabia | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 138 |
| Saudi Arabia | UN Environment | Several Ozone unit support | 256 |
| Saudi Arabia | UNIDO | REF-Air conditioning - Stage I | 910 |
| Senegal | UN Environment | Several Ozone unit support | 195 |
| Serbia | UNIDO | Several Ozone unit support | 180 |
| Seychelles | UN Environment | Several Ozone unit support | 85 |
| Sierra Leone | UN Environment | Several Ozone unit support | 110 |
| Solomon Islands | UN Environment | Several Ozone unit support | 85 |
| Sudan (the) | UN Environment | Several Ozone unit support | 187 |
| Sudan (the) | UNIDO | HPMP Stage I | 43 |
| Suriname | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 40 |
| Suriname | UNIDO | HPMP Stage I | 32 |
| Syrian Arab Republic | UNIDO | Several Ozone unit support | 279 |
| Thailand | World Bank | FOA - Rigid PU foam & REF-Air conditioning - Stage I | 4,348 |
| Timor-Leste | UNDP | HPMP Stage I | 12 |
| Timor-Leste | UN Environment | Stage 2 - HCFC Phase-out Management Plan (implementation) | 121 |
| Timor-Leste | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 19 |
| Tonga | UN Environment | Several Ozone unit support | 85 |
| Trinidad and Tobago | UNDP | Stage I HPMP | 156 |
| Tunisia | France | HCFC Phase Out Plan (Stage I) | 79 |
| Tunisia | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 17 |
| Tunisia | UNIDO | REF-Servicing, RAC-Manuf., FOA-Rigid PU foam - Stage I | 116 |
| Tunisia | UNIDO | Several Ozone unit support | 339 |
| Turkey | UN Environment | Stage 2 - HCFC Phase-out Management Plan (implementation) | 740 |
| Turkey | UNIDO | REF-Servicing - Stage I | 1,605 |
| Turkey | UNIDO | HPMP Stage I | 1,711 |
| Turkey | UNIDO | Several Ozone unit support | 356 |
| Uganda | UN Environment | Several Ozone unit support | 85 |
| United Republic of Tanzania | UN Environment | Several Ozone unit support | 85 |
| Uruguay | UNDP | Several Ozone unit support | 207 |
| Venezuela (Bolivarian Republic of) | UNDP | Stage II HPMP | 214 |
| Venezuela (Bolivarian Republic of) | UNIDO | RAC-Manufacturing - Stage II | 615 |
| Viet Nam | World Bank | FOA - Rigid PU foam & REF (Air conditioning/Commercial ref/Servicing) - Stage II | 2,332 |
| Viet Nam | Japan | REF-Servicing - Stage II | 185 |
| Yemen | UN Environment | HCFC Phase-out Management Plan (implementation) - Stage I | 186 |
| Yemen | UN Environment | Several Ozone unit support | 218 |
| Zimbabwe | Germany | Ref-Servicing - Stage I | 188 |

The adjusted consolidated 2017-2019 business plan was posted on the Secretariat’s website on 29 December 2016.

These activities include: 113 HCFC activities for 42 countries (US $102.36 million), 66 IS activities (US $9.55 million), core unit (US $5.86 million) and CAP (US $10.93 million).