| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/97/16 7 November 2025 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-seventh Meeting

Montreal, 1-5 December 2025

Item 7(a)(vi) of the provisional agenda

PROGRESS REPORT OF THE WORLD BANK AS AT 31 DECEMBER 2024

Introduction

# This document presents the progress report of the World Bank as at 31 December 2024.

# The progress report of the World Bank includes the status of implementation of projects, including HFC-related projects that have been funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2024, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in metric tonnes (mt) and CO2-eq tonnes.

# This document presents a summary of progress in implementation of projects for 2024 and cumulative since 1991 addressing all controlled substances, including Annex F substances (HFCs), under the Montreal Protocol for all projects approved under regular funding and additional voluntary contributions. It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee. As all projects approved under the additional voluntary contributions have been completed and the remaining balances will be returned to the Secretariat, the Secretariat will no longer report on these projects separately.

Progress in implementation of projects for 2024 and cumulative since 1991

# As of 31 December 2024, the Executive Committee had approved US $1.36 billion in projects for the World Bank, consisting of US $1.23 billion for the implementation of investment and non-investment projects and US $131.02 million for agency support costs, as shown in table 1.

# Table 1. Approved funding by sector for the World Bank as at 31 December 2024

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 22,984,030 |
| Destruction | 600,000 |
| Energy efficiency | 1,095,689 |
| Foam | 136,059,064 |
| Halon | 70,221,038 |
| HFC phase-down plan | 5,665,704 |
| Fumigants | 5,837,887 |
| Multiple sectors | 2,341,168 |
| Other | 5,059,360 |
| Phase-out plan | 223,065,129 |
| Process agent | 114,342,497 |
| Production | 422,973,496 |
| Refrigeration | 180,473,484 |
| Several | 30,181,553 |
| Solvents | 10,237,394 |
| Sterilant | 661,227 |
| Sub-total | 1,231,798,720 |
| Agency support costs | 131,018,159 |
| Total | 1,362,816,878 |

# In 2024, nine new projects and activities were approved. This level of funding is expected to result in the phase-out of 318,886 ODP tonnes of consumption and production of ODS and 759.2 mt (1,400,833 CO2-eq tonnes) of consumption of HFCs. Annex I shows the status of project implementation per country in 2024.

# Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2024. Annex II presents analytical information per year since 1991.

Table 2. Status of project implementation by type as at 31 December 2024

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance *** | % disbursed |
| Country programme | 29 | 29 | 100 | 1,627,732 | 1,627,732 | 0 | 100 |
| Demonstration | 8 | 8 | 100 | 6,172,901 | 6,172,901 | 0 | 100 |
| Institutional strengthening (IS) | 50 | 49 | 98 | 10,013,716 | 9,890,357 | 123,359 | 99 |
| Investment | 659 | 638 | 97 | 1,170,814,855 | 1,132,471,849 | 38,343,006 | 97 |
| Project preparation | 307 | 299 | 97 | 28,358,320 | 27,425,716 | 932,604 | 97 |
| Technical assistance | 83 | 80 | 96 | 14,505,430 | 16,580,108 | -2,074,678 | 114 |
| Training | 4 | 4 | 100 | 305,766 | 305,766 | 0 | 100 |
| Total | 1,140 | 1,107 | 97 | 1,231,798,720 | 1,194,474,428 | 37,324,292 | 97 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

***Negative balances are due to the distribution of funds balances among different tranches of the same HCFC phase-out management plan (HPMP).

# Implementation of projects and activities by the World Bank for 2024 and cumulative since 1991 up to 31 December 2024, is summarized as follows:

## Phase-out: In 2024, 7,909.2 ODP tonnes of consumption and production of ODS were phased out  and an additional 748.4 ODP tonnes of consumption and 4,690.0 ODP tonnes of production of ODS were approved for phase-out. Since 1991, 150,322 ODP tonnes of consumption of ODS and 193,943 ODP tonnes of production of ODS had been phased out, of an expected total of 318,886 ODP tonnes of consumption and production of ODS, and 8.8 mt (12,555 CO2-eq tonnes) had been phased out, of an expected total of 759.2 mt (1,400,833 CO2-eq tonnes) of consumption of HFCs, from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2024, US $26.44 million was disbursed and US $17.99 million was planned for disbursement based on the 2023 progress report, representing a rate of disbursement of 147 per cent of that planned. Cumulatively, US $1.19 billion had been disbursed out of the total US $1.23 billion approved for disbursement (excluding agency support costs), representing a rate of disbursement of 97 per cent. In 2024, US $24.28 million was approved for implementation;

## Cost-effectiveness (in ODP):  Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $5.50/kg and for the production sector was US $4.77/kg. The average cost-effectiveness of investment projects per ODP tonne was US $3.24/kg for completed projects and US $6.92/kg for ongoing projects;

## Number of projects completed: In 2024, seven projects were completed. Since 1991, 1,107 projects of the 1,140 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 97 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2024 were completed on average 50 months after their approval. Since 1991, the average time for completion of investment projects has been 40 months after their approval. First disbursements under these projects occurred, on average, 24 months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2024 were completed on average 12 months after their approval. Since 1991, the average time for completion of non-investment projects has been 35 months after their approval. First disbursements under these projects occurred, on average, 21 months after they had been approved;

## Project preparation: Of the 307 project preparation activities approved by the end of 2024, 299 have been completed, leaving eight ongoing activities. In 2024, one project preparation activity was completed;

## Implementation delays: A total of 33 projects were under implementation at the end of 2024, experiencing, on average, a delay of eight months. Three of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation, and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2024, three MYAs for HPMPs, one HCFC production phase-out management plan (HPPMP) and two Kigali HFC implementation plans (KIPs) were under implementation. Since 1991, 43 MYAs have been approved and 37 MYAs have been completed, representing a completion rate of 86 per cent.

# Table 3 summarizes progress made by the World Bank since 1991.

## Table 3. Progress made by the World Bank since 1991

| Phase out achieved |  | Disbursement (US $) | Average CE (US$/kg) |  | Number of projects |  | Speed of delivery for completion (months) |  | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes* | CO2-eq tonnes** |  | Consump- tion | Produc- tion | Approved | Completed | Investment | Non- investment |  | Approved | Completed |
| 344,265 | 12,555 | 1,194,474,428 | 5.50 | 4.77 | 1,140 | 1,107 | 40 | 35 | 8 | 43 | 37 |

*Consumption and production of ODS.

** HFC related projects.

HFC-related projects

# As of 31 December 2024, the Executive Committee had approved 25 HFC-related projects amounting to US $7,718,987 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9.

Table 4. HFC-related projects approved

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 11 | 1 | 9 | 5,699,907 | 183,514 | 5,516,393 | 3 |
| Project preparation | 11 | 7 | 64 | 1,275,000 | 707,919 | 567,081 | 56 |
| Technical assistance | 3 | 3 | 100 | 744,080 | 744,080 | 0 | 100 |
| Total | 25 | 11 | 44 | 7,718,987 | 1,635,513 | 6,083,474 | 21 |

* Excludes agency support costs.

** 759.2 mt (1,400,833 CO2-eq tonnes) of HFCs was approved for phase-out.

# Of the total cumulative funding approved of US $7,718,987, US $1,635,513 had been disbursed, representing a disbursement rate of 21 per cent. Seven of the 11 preparation activities were completed. The remaining four are expected to be completed in 2025 and 2026. All the technical assistance projects were completed. One of the 11 investment projects was completed. The remaining 10 investment projects (including eight projects for stage I of KIPs, one pilot project for energy efficiency per decision 91/65, and one pilot project for energy efficiency per decision 94/60) are expected to be completed in 2026 and 2027.

Issues identified in project implementation in 2024

# Further to the review process, several issues were discussed and satisfactorily addressed, except for issues on three projects related to components of MYAs, classified as projects with implementation delays that are subject to procedures for project cancellation, in line with decision 84/45(c). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 98th meeting.

# In addition, issues have been identified regarding projects or tranches of MYAs for the phase-out of HCFCs and HFCs. These issues are also presented in annex III. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Details of progress in implementation of projects associated with the HPMP for China (polyurethane foam sector plan) have been submitted to the 97th meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. Outstanding issues for the remaining ongoing projects not included in annex III to the present document, and requests for extension of dates of completion are addressed below.

# Of the 24 ongoing projects, excluding IS and project preparation, five projects have revised planned dates of completion since the 2023 progress report.

# In line with decision 82/11(b), the World Bank has requested the extension of the duration of one project, as shown in table 5.

Table 5. Project for which an extension of the completion date has been requested

| Country/ project code | Disbursement (%) | Activities requiring additional time | Original date of completion | Date of completion requested |
| --- | --- | --- | --- | --- |
| Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) |  |  |  |  |
| Viet Nam VIE/DES/93/PRP/94 | 4 | Recruitment of consultants, completion of data collection and analysis, and development of plan of action | Dec-25 | Dec-26 |

Gender mainstreaming

# The World Bank reported that in 2024, 19 projects in four countries were reporting on gender mainstreaming during both for preparation and implementation of activities.  In the KIP and HPMP project documentation, measures are taken to ensure alignment with both the Multilateral Fund’s and the World Bank’s gender policies to promote gender mainstreaming. Consultations are conducted with relevant national stakeholders to appropriately incorporate gender mainstreaming consideration. In Malaysia and Viet Nam, the respective executing agencies have agreed to monitor the participation of women in the activities under the KIP and the HPMP. In Thailand, the national ozone unit systematically monitors the participation of women and men in workshops, stakeholder consultations, and public events it organizes, wherever feasible, to ensure inclusivity and monitor progress. In China, the Foreign Economic Cooperation Office collects disaggregated data for all activities under its management, including workshops, training sessions, and stakeholder consultations, and promotes women’s participation in technical and decision-making roles. In Indonesia, women’s participation was actively considered during the preparation of the KIP, which commenced in 2024. Enterprises participating in the project have committed to providing equal access to employment opportunities across all levels and agreed to continue reporting on the female-to-male employment ratio throughout the implementation period.

Recommendation

# The Executive Committee may wish:

## To note the progress report of the World Bank as at 31 December 2024 contained in document UNEP/OzL.Pro/ExCom/97/16;

## To approve the extension of the completion date, to December 2026, of the preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) for Viet Nam (VIE/DES/93/PRP/94) to allow completion of the remaining ongoing activities, as reflected in table 5 of document UNEP/OzL.Pro/ExCom/97/16; and

## To approve the recommendations related to ongoing projects with specific issues contained in annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR THE WORLD BANK

PER COUNTRY FOR 2024

# Table 1 of annex I presents the status of project implementation by country for 2024 in achieved phase-out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation by the World Bank for 2024

| Country | Phased out in 2024 (ODP tonnes)* | Phased out in 2024 (CO2-eq tonnes)* | Estimated funds disbursed in 2024 (US$) | Funds disbursed in 2024 (US$) | Percentage of funds disbursed over estimation in 2024 | Percentage of planned projects completed in 2024** |
| --- | --- | --- | --- | --- | --- | --- |
| China | 7,834.3 | 0 | 15,050,000 | 24,547,213 | 163 | 100 |
| Indonesia | 32.3 | 0 | 150,000 | 132,919 | 89 |  |
| Jordan | 42.6 | 0 | 732,704 | 753,459 | 103 | 75 |
| Malaysia | 0.0 | 0 | 84,905 | 56,905 | 67 |  |
| Thailand | 0.0 | 0 | 1,904,772 | 948,439 | 50 |  |
| Viet Nam | 0.0 | 0 | 65,000 | 4,746 | 7 |  |
| Global*** | 0.0 | 0 | 0 | 0 |  | 100 |
| Total | 7,909.2 | 0 | 17,987,381 | 26,443,681 | 147 | 86 |

* Including 1,962.2 ODP tonnes of consumption and 5,947.0 of production of ODS. No phase-out in 2024 for HFC-related projects.

** For projects that were planned to be completed in 2024.

*** 2024 core unit.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR THE WORLD BANK

PER YEAR AS AT 31 DECEMBER 2024

# Table 1 of annex II presents an overview of the status of project implementation by year. All projects and activities approved between 1991 and 2017, 2019 and 2020, have now been completed.

Table 1. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 42 | 42 | 100 | 5,429,404 | 5,429,404 | 0 | 100 |
| 1992 | 76 | 76 | 100 | 28,047,705 | 28,047,705 | 0 | 100 |
| 1993 | 79 | 79 | 100 | 42,538,405 | 42,538,405 | 0 | 100 |
| 1994 | 91 | 91 | 100 | 41,081,267 | 41,081,267 | 0 | 100 |
| 1995 | 112 | 112 | 100 | 47,224,186 | 47,224,186 | 0 | 100 |
| 1996 | 55 | 55 | 100 | 29,319,479 | 29,319,479 | 0 | 100 |
| 1997 | 95 | 95 | 100 | 56,173,102 | 56,173,103 | -1 | 100 |
| 1998 | 59 | 59 | 100 | 35,959,418 | 35,959,417 | 1 | 100 |
| 1999 | 73 | 73 | 100 | 64,173,138 | 64,173,138 | 0 | 100 |
| 2000 | 67 | 67 | 100 | 36,982,134 | 36,982,133 | 1 | 100 |
| 2001 | 29 | 29 | 100 | 55,212,853 | 55,212,854 | -1 | 100 |
| 2002 | 32 | 32 | 100 | 64,357,778 | 64,357,778 | 0 | 100 |
| 2003 | 24 | 24 | 100 | 72,734,119 | 72,734,119 | 0 | 100 |
| 2004 | 29 | 29 | 100 | 77,111,770 | 77,111,770 | 0 | 100 |
| 2005 | 28 | 28 | 100 | 68,592,865 | 68,592,865 | 0 | 100 |
| 2006 | 22 | 22 | 100 | 64,473,260 | 64,473,260 | 0 | 100 |
| 2007 | 25 | 25 | 100 | 66,005,270 | 66,005,270 | 0 | 100 |
| 2008 | 28 | 28 | 100 | 39,934,666 | 39,934,666 | 0 | 100 |
| 2009 | 22 | 22 | 100 | 25,529,554 | 25,529,554 | 0 | 100 |
| 2010 | 16 | 16 | 100 | 1,148,623 | 1,148,623 | 0 | 100 |
| 2011 | 10 | 10 | 100 | 44,201,956 | 44,335,997 | -134,041 | 100 |
| 2012 | 10 | 10 | 100 | 11,698,145 | 11,698,145 | 0 | 100 |
| 2013 | 7 | 7 | 100 | 43,736,999 | 43,602,958 | 134,041 | 100 |
| 2014 | 13 | 13 | 100 | 28,336,509 | 28,336,509 | 0 | 100 |
| 2015 | 13 | 13 | 100 | 62,990,648 | 62,990,648 | 0 | 100 |
| 2016 | 18 | 18 | 100 | 12,601,632 | 12,601,632 | 0 | 100 |
| 2017 | 6 | 6 | 100 | 2,202,713 | 2,202,713 | 0 | 100 |
| 2018 | 8 | 5 | 63 | 26,839,050 | 26,546,080 | 292,970 | 99 |
| 2019 | 3 | 3 | 100 | 2,579,179 | 2,579,179 | 0 | 100 |
| 2020 | 2 | 2 | 100 | 2,067,012 | 2,067,012 | 0 | 100 |
| 2021 | 7 | 6 | 86 | 9,608,235 | 9,562,359 | 45,876 | 100 |
| 2022 | 7 | 6 | 86 | 22,867,594 | 22,666,881 | 200,713 | 99 |
| 2023 | 23 | 4 | 17 | 15,764,363 | 3,255,320 | 12,509,043 | 21 |
| 2024 | 9 | 0 | 0 | 24,275,689 | 0 | 24,275,689 | 0 |
| Total | 1,140 | 1,107 | 97 | 1,231,798,720 | 1,194,474,428 | 37,324,292 | 97 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR THE WORLD BANK

| Country/project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Thailand THA/PHA/92/INV/181 | HCFC phase-out management plan (stage II, second tranche) (PMU) | 100 | 12 months delays | Noting decision 77/8(j), to request the World Bank to report to the 98th meeting on this project with implementation delays |
| Thailand THA/PHA/92/INV/182 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 40 | 12 months delays | To request the World Bank to report to the 98th meeting on this project with implementation delays |
| Thailand THA/PHA/92/INV/183 | HCFC phase-out management plan (stage II, second tranche) (Spray foam manufacturing sector) | 0 | 12 and 18 months delays | To request the World Bank to report to the 98th meeting on this project with implementation delays |
| Viet Nam VIE/KIP/93/INV/90 | Kigali HFC implementation plan (stage I, first tranche) (industrial refrigeration sector) | 0 | Delays due to administrative matters and related approvals from the Government | To request the World Bank to submit a status report to the 98th meeting on implementation progress and disbursement |
| Viet Nam VIE/KIP/93/INV/91 | Kigali HFC implementation plan (stage I, first tranche) (rail mobile air-conditioning conversion) | 0 |  |  |
| Viet Nam VIE/KIP/93/INV/95 | Kigali HFC implementation plan (stage I, first tranche) (servicing sector) | 0 |  |  |
| Viet Nam VIE/KIP/93/INV/96 | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 0 |  |  |
| Viet Nam VIE/PHA/93/INV/92 | HCFC phase-out management plan (stage III, first tranche) (PMU) | 0 |  |  |
| Viet Nam VIE/PHA/93/INV/93 | HCFC phase-out management plan (stage III, first tranche) (servicing sector) | 0 |  |  |

UNEP/OzL.Pro/ExCom/97/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database, which is provided on the 97th meeting portal on the Multilateral Fund’s website, in the spreadsheet programme, Microsoft Excel.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 97th meeting.

Ongoing projects are all projects that were under implementation as at 31 December 2024. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

Phase-out of ODS is expressed in ODP tonnes and of HFCs in mt and CO2-eq tonnes.

Including 1,962.2 ODP tonnes of consumption and 5,947.0 of production of ODS. No phase-out in 2024 for HFC-related projects.

No phase-out approved in 2024 for HFC-related projects.

Including 759.2 mt of HFC-related projects. Cost-effectiveness in CO2-eq. is not included due to the limited number of projects approved.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/97/44

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The Executive Committee requested bilateral and implementing agencies to provide a brief report on key gender mainstreaming results achieved as part of their annual progress reports, as of 2023, on the basis of the information available to them (decision 90/48(d)).

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.