| NATIONS UNIES |  | EP |
| --- | --- | --- |
|  | Programme des Nations Unies pour l’environnement | Distr. GÉNÉRALE UNEP/OzL.Pro/ExCom/90/4 3 juin 2022 FRANÇAIS ORIGINAL: ANGLAIS |

COMITÉ EXÉCUTIF 
  DU FONDS MULTILATÉRAL AUX FINS 
  D’APPLICATION DU PROTOCOLE DE MONTRÉAL
Quatre-vingt-dixième réunion

Montréal, 20-23 juin 2022

Point 4(b) de l’ordre du jour provisoire

# RAPPORT SUR LES SOLDES ET DISPONIBILITE DES RESSOURCES

# Introduction

# Ce document présente un résumé des ajustements financiers communiqués par les agences bilatérales et d’exécution, et approuvés par le Secrétariat. Il comprend des données statistiques de tous les projets dont les soldes ont été détenus pendant plus de 12 mois après l’achèvement du projet, conformément aux décisions 28/7 et 56/2(c). Il examine les soldes à restituer provenant de projets au titre du suivi donné à des décisions les concernant (appelés projets « soumis à décision » dans le présent document). Le document suit également le sujet de la recommandation du Bureau des services de contrôle interne (BSCI) sur la clôture financière des projets (décision 88/1(d)). Il indique également au Comité exécutif le niveau des ressources disponibles en liquidités enregistrées dans le document État des contributions et décaissements conformément à la décision 41/92(b), et présente une recommandation. Les montants détenus par les agences d’exécution et bilatérales pour les projets achevés et pour les projets soumis à décision sont respectivement inclus à l’Annexe I et l’Annexe II. L’Annexe III présente les fonds restitués par les agences bilatérales et d’exécution provenant de projets achevés, de projets soumis à décision, et de projets financés par des contributions volontaires supplémentaires.

Fonds à restituer à la 90e réunion

# Le total des fonds devant être restitués par les agences d’exécution s’élève à 3 360 846 $ US, comme l’indique le tableau 1.

# Tableau 1. Fonds à restituer à la 90e réunion par les agences d’exécution ($ US)

| Agence | Coûts de projet | Coûts d’appui à l’agence | Coût total |
| --- | --- | --- | --- |
| PNUD | 2 156 038 | 161 346 | 2 317 384 |
| PNUE | (17 118) | 23 719 | 6 601 |
| ONUDI | 968 631 | 68 230 | 1 036 861 |
| Total | 3 107 551 | 253 295 | 3 360 846 |

Fonds retenus par les agences d’exécution et bilatérales

# Le tableau 2 présente des renseignements sur les soldes des projets achevés, par décision et financés au titre des contributions volontaires supplémentaires qui sont retenus par les agences d’exécution. L’Annexe I donne des explications pour les retards de décaissement des montants engagés ou pour la non restitution des montants non engagés et l’Annexe II se rapporte aux décisions du Comité exécutif quant aux retards de restitution des fonds un an après l’achèvement des projets.

Tableau 2. Soldes encore détenus par les agences d’exécution pour des projets achevés, des projets soumis à décision ou des projets financés par des contributions volontaires supplémentaires (coûts d’appui d’agence inclus)

| Année d’achèvement | PNUD |  | PNUE |  | ONUDI |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Nombre | ($ US) | Nombre | ($ US) | Nombre | ($ US) | Nombre | ($ US) |
| Projets achevés depuis plus de deux ans |  |  |  |  |  |  |  |  |
| 2018 |  |  | 1 | 23 215 |  |  | 1 | 23 215 |
| 2019 |  |  | 1 | 31 296 | 1 | 46 514 | 2 | 77 810 |
| Du 1er janvier au 31 mai 2020 | 2 | 31 206 |  |  |  |  | 2 | 31 206 |
| Sous-total | 2 | 31 206 | 2 | 54 511 | 1 | 46 514 | 5 | 132 231 |
| Projets achevés depuis moins de deux ans |  |  |  |  |  |  |  |  |
| Du 1er juin au 31 déc. 2020 | 4 | 14 520 | 9 | 455 895 | 4 | 989 199 | 17 | 1 459 614 |
| Sous-total | 4 | 14 520 | 9 | 455 895 | 4 | 989 199 | 17 | 1 459 614 |
| Total | 6 | 45 726 | 11 | 510 406 | 5 | 1 035 713 | 22 | 1 591 845 |
| Projets soumis à décision (en cours) |  |  |  |  |  |  |  |  |
|  | 1 | 119 016 | 3 | 240 643 | 15 | 3 473 032 | 19 | 3 832 691 |
| Total global | 7 | 164 742 | 14 | 751 049 | 20 | 4 508 745 | 41 | 5 424 536 |

Soldes retenus par les agences bilatérales

# Le Japon retient le solde d’un projet achevé en 2020, d’un montant de 50 059 $ US, coûts d’appui d’agence inclus.

Suivi de la décision 88/1(d)

# À la 88e réunion, dans le contexte de l’audit du Fonds multilatéral par le BSCI, le Comité exécutif a demandé au Secrétariat du Fonds, au trésorier et aux agences bilatérales et d’exécution d’achever la mise en œuvre de la recommandation 5 formulée par le BSCI et d’intégrer les éléments du plan d’action pour le traitement des retards de clôture financière des projets au-delà de la limite de douze mois définie par le Comité exécutif, et d’intégrer les informations appropriées dans les documents de réunion pertinents (décision 88/1(d)). En traitant cette recommandation du BSCI, le 12 novembre 2021, le Secrétariat du Fonds a envoyé une communication officielle aux agences bilatérales et d’exécution pour leur rappeler de mettre rigoureusement en œuvre tous les éléments du plan d’action en place depuis la 28e réunion et de respecter toutes les décisions suivantes, ainsi que de clôturer financièrement tous les projets dans la limite des douze mois définie par le Comité exécutif. Cette recommandation a également été traitée par le Secrétariat à la Réunion de coordination inter-agences, qui a eu lieu du 31 mars au 1er avril 2022. Le Secrétariat a également envoyé une liste des projets achevés en 2020 et avant, avec leurs soldes, aux agences d’exécution, pour action. Le Secrétariat a également rappelé aux agences le besoin d’informer le Secrétariat de manière continue en cas de problèmes prévus avec la clôture financière, de sorte que des mesures puissent être prises rapidement. Les statistiques partagées avec le BSCI indiquent que le PNUD a réalisé la clôture financière de tous les projets achevés en 2018 et 2019, et s’est engagé à clôturer 10 projets de tranches d’Accord pluriannuel, que le PNUE a atteint un taux de conformité de 96 pour cent avec la recommandation de l’audit et s’est engagé à clôturer quatre projets supplémentaires, et que l’ONUDI avait clôturé 38 projets et s’est engagé à en clôturer neuf de plus, alors que la Banque mondiale ne retient aucun solde de projets achevés. Ensuite, le BSCI a convenu de clôturer l’observation des retards de clôture financière des projets au-delà de la limite de douze mois définie par le Comité exécutif.

Disponibilité des ressources

# L’état des contributions et des décaissements indique un solde restant de 424 470 206 $ US au 5 mai 2022. Le solde total restitué par les agences d’exécution à la 90e réunion s’élève à 3 360 846 $ US. Par conséquent, le niveau total des ressources disponibles pour les approbations lors de la 90e réunion est de 427 831 052 $ US.

Observations du Secrétariat

# Le Secrétariat a rappelé aux agences bilatérales et d’exécution que les soldes des projets soumis à décision et des projets achevés depuis un an ou plus doivent être restitués dès que possible au Fonds multilatéral.

# Compte tenu du fait que le niveau de financement total des projets et activités soumis à la 90e réunion au 2 juin 2022 s’élève à 18 550 280 $ US, il y a suffisamment de ressources disponibles pour les approbations lors de cette réunion.

Recommandation

# Le Comité exécutif pourrait envisager :

  - de prendre note :

- du Rapport sur les soldes et la disponibilité des ressources, figurant dans le document UNEP/OzL.Pro/ExCom/90/4 ;

- que le montant net des fonds restitués à la 90e réunion par les agences d’exécution s’élève à 3 360 846 $ US, soit 2 156 038 $ US plus des coûts d’appui d’agence de 161 346 $ US par le PNUD ; (17 118) $ US plus des coûts d’appui d’agence de 23 719 $ US par le PNUE ; et 968 631 $ US plus des coûts d’appui d’agence de 68 230 $ US par l’ONUDI ;

- que le PNUD retient des soldes de 31 206 $ US, coûts d’appui d’agence inclus, pour deux projets achevés depuis plus de deux ans et 119 016 $ US, coûts d’appui d’agence inclus, pour un projet « soumis à décisions du Comité exécutif » ;

- que le PNUE retient des soldes de 54 511 $ US, coûts d’appui d’agence inclus, pour deux projets achevés depuis plus de deux ans et 240 643 $ US, coûts d’appui d’agence inclus, pour trois projets « soumis à décisions du Comité exécutif » ; et

- que l’ONUDI retient des soldes de 46 514 $ US, coûts d’appui d’agence inclus, pour un projet achevé depuis plus de deux ans et 3 473 032 $ US, coûts d’appui d’agence inclus, pour 15 projets « soumis à décisions du Comité exécutif » ;

## de demander :

    - aux agences bilatérales et d’exécution de procéder au décaissement ou d’annuler les sommes engagées et non engagées qui ne sont pas nécessaires aux projets achevés et à ceux achevés « par décision du Comité exécutif », et de restituer les soldes correspondants à la 91e réunion ;

### au PNUD de procéder au décaissement ou à l’annulation des engagements pour les deux projets restants achevés depuis plus de deux ans, et de restituer les soldes à la 91e réunion ;

### au PNUE de procéder au décaissement ou d’annuler ses engagements pour les deux projets restants achevés depuis plus de deux ans, et de restituer les soldes à la 91e réunion ; et

### à l’ONUDI de procéder au décaissement ou d’annuler ses engagements pour le projet restant, achevé depuis plus de deux ans.

Annexe I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES AND BILATERAL AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 December 2020 (US $) | Funds disbursed as of 90th meeting (US $) | Balances committed as per 90th meeting (US $) | Balances not-committed as per 90th meeting (US $) | Support cost on balances committed and not committed as per 90th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| COS/PHA/83/INV/59 | HCFC phase-out management plan (stage I, fifth tranche) | Dec-20 | 56,000 | 47,445 | 8,555 |  | 642 |  |  |  |
| FIJ/PHA/77/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 59,850 | 48,708 | 11,142 |  | 1,003 |  |  |  |
| FIJ/PHA/82/TAS/35 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 27,859 | 2,141 |  | 193 | The updated status will be reported to the 91st meeting for Fiji once the open commitment is closed /disbursed |  |  |
| GUY/PHA/75/INV/28 | HCFC phase-out management plan (stage II, first tranche) | Dec-19 | 159,750 | 141,936 | 17,814 |  | 1,247 |  |  |  |
| SRL/PHA/82/PRP/52 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 40,000 | 38,157 | 1,843 |  | 129 |  |  |  |
| SRL/PHA/82/TAS/51 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 29,067 | 933 |  | 84 | The project balances are currently fully disbursed and projects financially closed. |  |  |
| TOTAL UNDP |  |  |  |  | 42,429 |  | 3,297 |  |  |  |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| ASP/REF/76/DEM/59 | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | Dec-19 | 375,000 | 342,491 | 27,696 |  | 3,600 |  |  | 83/37(c) and 85/18(b) |
| BZE/PHA/82/PRP/36 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 20,000 | 5,000 | 15,000 |  | 1,950 |  |  |  |
| GAM/PHA/82/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 20,000 | 5,000 | 15,000 |  | 1,950 |  |  |  |
| GLO/SEV/84/TAS/350 | Compliance Assistance Programme: 2020 budget | Dec-20 | 8,899,977 | 6,029,262 | 259,175 |  | 20,734 |  |  |  |
| KUW/REF/75/TAS/29 | Comparative analysis of three not-in-kind technologies for use in central air-conditioning (feasibility study for district cooling) | Jun-18 | 27,223 | 6,679 | 20,544 |  | 2,671 |  |  | 82/24(c)(ii) and 83/38(b) |
| NIC/SEV/81/INS/35 | Renewal of institutional strengthening project (phase IX: 7/2018-6/2020) | Dec-20 | 85,000 | 68,000 | 17,000 |  | - |  |  |  |
| RWA/PHA/81/PRP/29 | Preparation of a HCFC phase-out management plan (stage II) | Nov-20 | 22,000 | 7,000 | 15,000 |  | 1,950 |  |  |  |
| SAU/PHA/68/TAS/18 | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Dec-20 | 43,150 | 17,134 | 25,880 |  | 3,206 |  |  | 86/16(f)(i) |
| UGA/PHA/82/PRP/24 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 20,000 | 44 | 19,956 |  | 2,594 |  |  |  |
| ZAM/PHA/83/PRP/38 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 20,000 | 5,000 | 15,000 |  | 1,950 |  |  |  |
| ZIM/PHA/83/PRP/59 | Preparation of a HCFC phase-out management plan (stage II) | Dec-20 | 40,000 | 5,000 | 35,000 |  | 4,550 |  |  |  |
| TOTAL UNEP |  |  |  |  | 465,251 |  | 45,155 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| JOR/REF/81/INV/103 | Conversion of large commercial unitary roof top air-conditioning units of up to 400kW manufacturing facility from HFC (R134a, R407c, R410a) to propane R290 as refrigerant at Petra Engineering Industries Co. | Jun-20 | 1,637,610 | 1,524,521 | 113,089 |  | 7,916 | 4 |  |  |
| MOG/PHA/84/TAS/14 | Verification report on the implementation of the HCFC phase-out management plan | Dec-20 | 30,000 | 21,661 | 8,339 |  | 751 | 2 |  |  |
| SAU/PHA/72/INV/21 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Dec-20 | 2,693,674 | 2,052,598 | 641,076 |  | 44,875 | 2 |  | 86/17(i)(i) |
| SAU/REF/76/DEM/28 | Demonstration project on promoting HFO-based low-global warming potential refrigerants for air-conditioning sector in high ambient temperatures | Dec-20 | 1,300,000 | 1,138,176 | 161,824 |  | 11,328 | 3 |  | 83/33(c), 85/17(c) and 88/27(c) |
| SOA/PHA/71/INV/05 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Dec-19 | 2,042,620 | 1,999,149 | 43,471 |  | 3,043 | 3 |  |  |
| TOTAL UNIDO |  |  |  |  | 967,799 |  | 67,913 |  |  |  |
| JAPAN |  |  |  |  |  |  |  |  |  |  |
| CPR/PHA/77/TAS/582 | HCFC phase-out management plan (stage II, first tranche) (refrigeration and air-conditioning servicing sector plan and enabling component) | Dec-20 | 80,000 | 35,700 | 44,300 |  | 5,759 | The balance is fully committed to the partner pending financial reporting. | The implementing partner has confirmed that they will provide the financial report by the date of ExCom 91 to enable financially complete the project. |  |
| TOTAL JAPAN |  |  |  |  | 44,300 |  | 5,759 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR BY-DECISIONS PROJECTS

| Code | Project title | Financial date of completion per decision | Approved funding plus adjustments as of 31 December 2020 (US $) | Funds disbursed as of 90th meeting (US $) | Balances committed as per 90th meeting (US $) | Balances not- committed as per 90th meeting (US $) | Support cost on balances committed and not-committed as per 90th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BRA/DES/72/DEM/305 | Pilot demonstration project on ODS waste management and disposal | Dec-23 | 1,490,600 | 1,379,370 | 111,230 |  | 7,786 |  |  | 79/18(c)(i) and 81/24(e)(ii) |
| TOTAL UNDP |  |  |  |  | 111,230 |  | 7,786 |  |  |  |
| UNEP |  |  |  |  |  |  |  |  |  |  |
| BAH/PHA/84/TAS/36 | HCFC phase-out management plan (stage I, third and fourth tranches) (policy, refrigeration servicing, monitoring and verification) | 91st meeting | 180,000 | 70,000 | 110,000 |  | 14,300 |  |  | 88/45(b) |
| SAU/PHA/68/TAS/16 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | 87th meeting | 233,674 | 182,206 | 32,350 |  | 4,007 |  |  | 86/16(f)(i) |
| SAU/PHA/77/TAS/32 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring) | 87th meeting | 130,400 | 50,589 | 71,170 |  | 8,816 |  |  | 86/16(f)(i) |
| TOTAL UNEP |  |  |  |  | 213,520 |  | 27,123 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| BHA/PHA/80/INV/25 | HCFC phase-out management plan (stage I, third tranche) | Dec-23 | 35,828 | 15,823 | 20,005 |  | 1,800 |  |  | 88/40(a) |
| BRA/PHA/75/INV/311 | HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector) | 90th meeting | 1,674,275 | 1,427,334 | 44,841 |  | 3,139 |  |  | 88/61(a)(iii) |
| CPR/PHA/64/INV/513 | HCFC phase-out management plan (room air-conditioner manufacturing sector plan) (stage I, first tranche) | Dec-22 | 36,430,000 | 36,429,917 | 83 |  | 6 |  |  | 84/68(d)(i) and 86/33(d) |
| CPR/PHA/71/INV/536 | HCFC phase-out management plan (stage I, third tranche) (room air-conditioner manufacturing sector plan) | Dec-22 | 8,495,000 | 8,494,893 | 107 |  | 8 |  |  | 84/68(d)(i) and 86/33(d) |
| CPR/PHA/75/INV/564 | HCFC phase-out management plan (stage I, fifth tranche) (room air-conditioner manufacturing sector plan) | Dec-22 | 11,250,000 | 11,274,379 | (24,379) |  | (1,706) |  |  | 84/68(d)(i) and 86/33(d) |
| GLO/REF/80/DEM/344 | Global chiller replacement project (Argentina) | Dec-21 | 808,438 | 121,667 | 686,771 |  | 51,508 |  |  | 82/21(d) |
| IRA/PHA/86/INV/246 | HCFC phase-out management plan (stage II, third tranche) (foam sector) |  | 524,000 | 0 | 148,299 |  | 10,381 |  |  |  |
| IRQ/PHA/58/INV/09 | National phase-out plan (first tranche) | Dec-18 | 4,353,530 | 3,998,281 | 355,249 |  | 26,644 | 2 | 91 | 71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c) |
| PHI/PHA/83/INV/104 | HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector) | 89th Meeting | 736,129 | 95,414 | 442,442 |  | 30,971 |  |  | 87/19(c) |
| PHI/PHA/83/TAS/105 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 89th Meeting | 273,894 | 132,310 | 141,584 |  | 9,911 |  |  | 87/19(c) |
| SAU/FOA/62/INV/13 | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Al-Watania Plastics | 89th Meeting | 1,103,578 | 585,281 | 518,297 |  | 38,872 |  |  | 86/17(i)(i) |
| SAU/PHA/72/INV/20 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring) | 87th Meeting | 270,000 | 235,670 | 34,330 |  | 2,403 | 2 | 91 | 86/17(i)(i) |
| SAU/PHA/75/INV/24 | HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan) | 87th Meeting | 1,100,000 | 655,813 | 444,187 |  | 31,093 | 2 | 91 | 86/17(i)(i) |
| SAU/PHA/77/INV/31 | HCFC phase-out management plan (stage I, fourth tranche) (polyurethane foam sector plan) | 87th Meeting | 989,600 | 576,629 | 412,971 |  | 28,908 |  |  | 86/17(i)(i) |
| SOM/PHA/77/INV/12 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Second meeting in 2023 | 141,500 | 128,129 | 13,371 |  | 936 |  |  | 88/40(a) |
| TOTAL UNIDO |  |  |  |  | 3,238,159 |  | 234,873 |  |  |  |

Annex III

DETAILS ON COMPLETED PROJECTS, BY-DECISION AND PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES AND BILATERAL AGENCIES

| Code | Project title | Project costs returned (US $) | Agency support costs (US $) | Total (US $) |
| --- | --- | --- | --- | --- |
| BHU/PHA/76/TAS/26 | HCFC phase-out management plan (third tranche) | 641 | 58 | 699 |
| BRA/SEV/75/INS/314 | Extension of institutional strengthening project (phase VIII: 12/2015-11/2017) | 5,511 | 386 | 5,896 |
| COS/PHA/81/PRP/58 | Preparation of a HCFC phase-out management plan (stage II) | 1,117 | 78 | 1,196 |
| COS/SEV/80/INS/56 | Extension of institutional strengthening project (phase XII: 1/2018-12/2019) | 5,398 | 378 | 5,776 |
| CUB/PHA/68/INV/50 | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b contained in formulated polyols in the foam sector) | 1,665 | 125 | 1,790 |
| EGY/PHA/68/INV/117 | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | 70,928 | 5,320 | 76,248 |
| EGY/PHA/82/INV/139 | HCFC phase-out management plan (stage I, third tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | 118,460 | 8,884 | 127,344 |
| GHA/PHA/81/PRP/44 | Preparation of a HCFC phase-out management plan (stage II) | 230 | 16 | 246 |
| GHA/SEV/82/INS/47 | Extension of the institutional strengthening project (phase XIII: 1/2018-12/2020) | 607 | 42 | 649 |
| IDS/PHA/71/TAS/200 | HCFC phase-out management plan (project management and coordination) (stage I, second tranche) | 159,291 | 11,947 | 171,238 |
| IDS/PHA/76/INV/208 | HCFC phase-out management plan (stage I, third tranche) (refrigeration and air-conditioning sector) | 267,832 | 20,087 | 287,919 |
| IDS/SEV/80/INS/212 | Extension of institutional strengthening project (phase XI: 1/2018-12/2019) | 3,891 | 272 | 4,163 |
| IND/SEV/76/INS/467 | Extension of institutional strengthening project (phase X: 4/2016-3/2018) | 52 | 4 | 56 |
| MEX/PHA/71/INV/168 | HCFC phase-out management plan (stage I, third tranche) (foam sector plan for systems houses and local customers) | 314,646 | 23,598 | 338,244 |
| MEX/PHA/75/INV/178 | HCFC phase-out management plan (stage I, fifth tranche) (foam sector plan for systems houses and local customers) | 1,122,503 | 84,188 | 1,206,691 |
| MEX/REF/81/INV/187 | Conversion of domestic refrigeration manufacturing facility from HFC-134a to isobutane as a refrigerant and conversion of compressors manufacturing facility from HFC-134a-based to isobutane-based at Mabe Mexico | 5,237 | 367 | 5,603 |
| MLI/PHA/76/INV/38 | HCFC phase-out management plan (stage I, third tranche) | 14,107 | 1,058 | 15,165 |
| NEP/PHA/75/INV/35 | HCFC phase-out management plan (stage I, second tranche) | 2,684 | 242 | 2,926 |
| PAR/PHA/74/INV/34 | HCFC phase-out management plan (stage I, second tranche) | 1,858 | 139 | 1,997 |
| SRL/SEV/82/INS/53 | Extension of the institutional strengthening project (phase XII: 1/2019-12/2020) | 99 | 7 | 106 |
| URU/SEV/80/INS/70 | Extension of institutional strengthening project (phase XII: 1/2018-12/2019) | 295 | 21 | 316 |
| VEN/SEV/77/INS/135 | Renewal of institutional strengthening project (phase XIII: 1/2017-12/2018) | 2,099 | 147 | 2,246 |
| ZIM/PHA/83/PRP/58 | Preparation of a HCFC phase-out management plan (stage II) | 8,565 | 600 | 9,165 |
| Total completed projects |  | 2,107,715 | 157,963 | 2,265,678 |
| PAN/PHA/76/INV/44 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 43,153 | 3,021 | 46,174 |
| Total “by decision” projects |  | 43,153 | 3,021 | 46,174 |
| COS/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 5,170 | 362 | 5,532 |
| Total “additional voluntary contributions” projects |  | 5,170 | 362 | 5,532 |
| TOTAL UNDP |  | 2,156,038 | 161,346 | 2,317,384 |
| ASP/PHA/81/PRP/61 | Development of stage II of HCFC phase-out management plans for PIC countries through regional approach | 129,990 | 16,899 | 146,888 |
| ECU/PHA/85/TAS/73 | HCFC phase-out management plan (stage I, fifth tranche) | (10,000) | (1,300) | (11,300) |
| ECU/PHA/86/TAS/74 | HCFC phase-out management plan (stage II, first tranche) | (24,000) | (3,120) | (27,120) |
| ECU/SEV/83/INS/71 | Extension of institutional strengthening project (phase VII: 7/2019-6/2021) | (226,305) | - | (226,305) |
| ELS/PHA/65/TAS/28 | HCFC phase-out management plan (stage I, first tranche) | 8,258 | 290 | 8,548 |
| KUW/PHA/52/TAS/10 | Terminal phase-out management plan for Annex A Group I substances (first tranche) | 60,820 | 7,907 | 68,727 |
| LAO/PHA/74/TAS/27 | HCFC phase-out management plan (stage I, second tranche) | 11,000 | 1,430 | 12,430 |
| LAO/PHA/82/TAS/32 | Verification report on the implementation of the HCFC phase-out management plan | 6,308 | 820 | 7,128 |
| MOL/SEV/77/INS/36 | Extension of the institutional strengthening project (phase IX: 1/2017-12/2018) | 708 | - | 708 |
| MON/PHA/82/TAS/28 | Verification report on the implementation of the HCFC phase-out management plan | 58 | 8 | 66 |
| NAM/SEV/79/INS/24 | Extension of institutional strengthening project (phase IX: 7/2017-6/2019) | 20,000 | - | 20,000 |
| QAT/PHA/65/TAS/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 6,045 | 786 | 6,831 |
| Total completed projects |  | (17,118) | 23,719 | 6,601 |
| TOTAL UNEP |  | (17,118) | 23,719 | 6,601 |
| BAH/PHA/84/PRP/38 | Preparation of a HCFC phase-out management plan (stage II) | 154 | 11 | 165 |
| BEN/PHA/84/PRP/39 | Preparation of a HCFC phase-out management plan (stage II) | 106 | 7 | 113 |
| BOL/PHA/86/INV/49 | HCFC phase-out management plan (stage I, fifth tranche) | 58 | 5 | 63 |
| ECU/PHA/85/INV/72 | HCFC phase-out management plan (stage I, fifth tranche) | 1,686 | 127 | 1,812 |
| EQG/PHA/82/INV/14 | HCFC phase-out management plan (stage I, third and fourth tranches) | 1,695 | 153 | 1,848 |
| ERI/PHA/84/PRP/18 | Preparation of a HCFC phase-out management plan (stage II) | 15 | 1 | 16 |
| GRN/PHA/77/INV/23 | HCFC phase-out management plan (stage I, second tranche) | 711 | 64 | 775 |
| KUW/REF/84/PRP/38 | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sector) | 78,239 | 5,477 | 83,715 |
| MDN/PHA/84/INV/42 | HCFC phase-out management plan (phase I, ninth tranche) | 38 | 3 | 41 |
| MOR/PHA/65/INV/68 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | 433 | 32 | 465 |
| MOR/PHA/68/INV/69 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | 615 | 46 | 661 |
| NER/PHA/82/TAS/34 | Verification report on the implementation of the HCFC phase-out management plan | 231 | 21 | 252 |
| OMA/PHA/75/INV/32 | HCFC phase-out management plan (stage II, first tranche) | 557 | 39 | 596 |
| OMA/PHA/82/INV/37 | HCFC phase-out management plan (stage II, second tranche) | 87 | 6 | 93 |
| OMA/PHA/86/INV/43 | HCFC phase-out management plan (stage II, third tranche) | 664 | 46 | 710 |
| PAK/PHA/76/TAS/95 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 5,645 | 395 | 6,040 |
| QAT/PHA/73/PRP/21 | Preparation of a HCFC phase-out management plan (stage II) | 347 | 24 | 372 |
| RWA/PHA/77/INV/27 | HCFC phase-out management plan (stage I, third tranche) | 233 | 21 | 254 |
| RWA/PHA/81/PRP/30 | Preparation of a HCFC phase-out management plan (stage II) | 808 | 57 | 865 |
| SAU/PHA/68/INV/17 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | (6,628) | (464) | (7,092) |
| SIL/PHA/76/INV/31 | HCFC phase-out management plan (stage I, third tranche) | 1,090 | 98 | 1,188 |
| SOA/PHA/67/TAS/04 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | 4,409 | 308 | 4,717 |
| STL/PHA/82/PRP/31 | Preparation of a HCFC phase-out management plan (stage II) | 83 | 6 | 89 |
| TUN/PHA/84/INV/78 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | 4,797 | 336 | 5,132 |
| TUR/SEV/80/INS/109 | Extension of institutional strengthening project (phase VIII: 12/2017-11/2019) | 5,082 | 356 | 5,438 |
| URT/PHA/76/INV/35 | HCFC phase-out management plan (stage I, second tranche) | 103 | 9 | 113 |
| YUG/PHA/84/INV/51 | HCFC phase-out management plan (stage I, fourth tranche) | 301 | 23 | 324 |
| YUG/SEV/80/INS/48 | Extension of institutional strengthening project (phase VI: 12/2017-11/2019) | 3,014 | 211 | 3,225 |
| Total completed projects |  | 104,572 | 7,418 | 111,990 |
| BRA/PHA/75/INV/311 | HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector) | 202,100 | 14,147 | 216,247 |
| EGY/PHA/82/INV/140 | HCFC phase-out management plan (stage I, third tranche) (enabling activities in the refrigeration and air-conditioning sector) | 1,987 | 149 | 2,136 |
| IRA/PHA/86/INV/246 | HCFC phase-out management plan (stage II, third tranche) (foam sector) | 375701 | 26299 | 402,000 |
| IRQ/REF/57/INV/07 | Replacement of refrigerant CFC-12 with isobutane and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigerators and chest freezers at Light Industries Company | 63,547 | 4,766 | 68,313 |
| PHI/PHA/83/INV/104 | HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector) | 198,273 | 13,879 | 212,152 |
| SAU/PHA/75/INV/25 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing and monitoring) | 1134 | 79 | 1,213 |
| Total “by decision” projects |  | 842,742 | 59,320 | 902,062 |
| CMR/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 676 | 47 | 724 |
| GAM/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 53 | 4 | 57 |
| LEB/REF/81/INV/03+ | Conversion from HFC-134a and HFC-404A to R-600a and R-290 in domestic refrigeration at Lematic Industries | 13,984 | 979 | 14,963 |
| PRC/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 159 | 11 | 171 |
| SUD/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 344 | 24 | 369 |
| YUG/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 6,100 | 427 | 6,528 |
| Total “additional voluntary contributions” projects |  | 21,318 | 1,492 | 22,810 |
| TOTAL UNIDO |  | 968,631 | 68,230 | 1,036,861 |

Document UNEP/OzL.Pro/ExCom/90/1.

Les données présentées s’appuient sur le format de rapport élaboré conformément à la décision 31/2.

UNEP/OzL.Pro/ExCom/90/3

2: Financial completion initiated; 3: Financial completion to be initiated after settlement of all pending issues; 4: Project is ongoing and extension is in discussion