| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/86/27 16 February 2021 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-sixth Meeting

Montreal, 2-6 November 2020

Postponed to 8-12 March 2021

UNDP BUSINESS PLAN FOR 2021–2023

# This document presents the UNDP business plan for 2021–2023 and includes: the planned activities for the phase-out of controlled substances under the Montreal Protocol (controlled substances) during the 2021–2023 period; the business plan performance indicators; policy issues; and a recommendation for consideration by the Executive Committee. The narrative of UNDP’s business plan for 2021–2023 is attached to the present document.

Planned activities during the 2021–2023 period

# Table 1 sets out, by year, the value of activities included in UNDP’s business plan.

Table 1. Resource allocation in the UNDP business plan for 2021–2023 as submitted (US $000s)*

| Description | 2021 | 2022 | 2023 | Total (2021–2023) | Total after 2023 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 23,773 | 9,066 | 17,420 | 50,259 | 22,371 |
| HPMP project preparation (PRP) – stage II | 10 | 0 | 0 | 10 | 0 |
| HPMP stage II | 1,161 | 204 | 871 | 2,237 | 188 |
| HPMP PRP – stage III | 563 | 399 | 192 | 1,155 |  |
| HPMP stage III | 75 | 7,013 | 33,418 | 40,506 | 67,883 |
| HCFC activities subtotal | 25,582 | 16,682 | 51,902 | 94,166 | 90,442 |
| HFC activities |  |  |  |  |  |
| HFC phase-down plan – PRP | 1,319 | 1,246 | 377 | 2,942 | 0 |
| HFC phase-down plans | 0 | 22,918 | 24,512 | 47,430 | 16,467 |
| HFC activities subtotal | 1,319 | 24,164 | 24,889 | 50,372 | 16,467 |
| Standard activities |  |  |  |  |  |
| Institutional strengthening (IS) | 4,100 | 1,752 | 4,100 | 9,953 | 0 |
| Core unit | 2,128 | 2,143 | 2,158 | 6,429 | 0 |
| Standard activities subtotal | 6,228 | 3,895 | 6,258 | 16,382 | 0 |
| Total | 33,130 | 44,740 | 83,049 | 160,920 | 106,909 |

* Including agency support costs where applicable.

# Secretariat’s comments

# Stage II of HPMPs

# The total levels of funding for stage II of HPMPs for low-volume-consuming (LVC) countries to meet the 67.5 per cent reduction of the HCFC baseline amount to US $627,003 for 2021–2023, and to meet a 100 per cent reduction amount to US $1.28 million (including US $1.09 million for 2021–2023).

# The total levels of funding for stage II of HPMPs for non-LVC countries amount to US $522,000 for the refrigeration servicing sector for the period 2021–2023 only.

# Stage III of HPMPs

# A total of US $108.39 million is included in the business plan for stage III of the HPMPs for 10 countries (Brazil, Colombia, India, Indonesia, Islamic Republic of Iran, Lebanon, Malaysia, Mexico, Nigeria, and the Republic of Moldova) (including US $40.51 million for 2021–2023). Inclusion of stage III of HPMPs in the business plan is allowed only for those countries with an approved stage II of HPMPs with reduction targets below the 2025 compliance targets (decision 84/46(e)).

HFC-related activities

# HFC activities include HFC phase-down plan preparation for 26 countries amounting to US $2.94 million in 2021–2023; and HFC phase-down management plans for 39 countries amounting to US $63.90 million (including US $47.43 million in 2021–2023).

# Fifteen of the 26 countries for which preparation activities for HFC phase-down have been included have not ratified the Kigali Amendment. Three of the 15 countries have not submitted the required letter from the Government indicating their intent to make best efforts to ratify the Kigali Amendment.

# Regarding HFC phase-down management plans, decision 84/46(g) allowed inclusion of such plans in the business plan only for countries that had ratified the Kigali Amendment. Fifteen of the 39 countries included in the business plan have not ratified the Kigali Amendment.

Core unit costs

# The core unit costs are expected to increase at an annual rate of 0.7 per cent as agreed.

Proposed adjustments by the Secretariat

# The adjustments to the UNDP business plan for 2021–2023 were based on relevant decisions of the Executive Committee. Further adjustments may be required pending a decision by the Parties on the level of the replenishment of the Multilateral Fund for the 2021–2023 triennium.

# In reviewing the revised UNDP business plan for 2021–2023, the Secretariat noted that the following adjustments were not included:

Table 3. Adjustments to the UNDP business plan for 2021–2023 (US $000)

| Adjustment | 2021–2023 | After 2023 |
| --- | --- | --- |
| HPMP values to reflect the actual amounts approved under the Agreements | (279) | 0 |
| Stage II of HPMPs for LVC countries to the maximum allowable value to meet the 100 per cent reduction of the HCFC baseline, based on decision 74/50(c)(xii) | (55) | 0 |
| PRP for stage III of HPMPs pursuant to decision 84/46(e) | (192) | 0 |
| Stage III of HPMPs for non-LVC countries with the refrigeration servicing sector based on a maximum cost-effectiveness of US $4.80/kg | (84) | (103) |
| PRP for HFC phase-down plans pursuant to decision 56/16(c) or decision 84/46(f) | (917) | 0 |
| HFC phase-down management plans pursuant to decision 84/46(g) | (21,895) | (6,620) |
| IS pursuant to decision 74/51(c) | 1,068 | 0 |

# Table 4 presents the results of the Secretariat’s proposed adjustments to the UNDP business plan for 2021–2023, which are also addressed in the context of the Consolidated business plan of the Multilateral Fund for 2021–2023.

Table 4. Resource allocation in UNDP’s adjusted business plan for 2021–2023 (US $000s)*

| Description | 2021 | 2022 | 2023 | Total (2021–2023) | Total after 2023 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 23,908 | 9,128 | 16,945 | 49,981 | 22,371 |
| HPMP project preparation (PRP) – stage II | 10 | 0 | 0 | 10 | 0 |
| HPMP stage II | 1,157 | 199 | 825 | 2,182 | 188 |
| HPMP PRP – stage III | 563 | 399 | 0 | 962 |  |
| HPMP stage III | 75 | 6,957 | 33,390 | 40,421 | 67,780 |
| HCFC activities subtotal | 25,713 | 16,683 | 51,160 | 93,556 | 90,339 |
| HFC activities |  |  |  |  |  |
| HFC phase-down plan – PRP | 1,099 | 814 | 112 | 2,025 | 0 |
| HFC phase-down plans | 0 | 22,918 | 2,617 | 25,535 | 9,847 |
| HFC activities subtotal | 1,099 | 23,732 | 2,729 | 27,560 | 9,847 |
| Standard activities |  |  |  |  |  |
| Institutional strengthening (IS) | 4,635 | 1,752 | 4,635 | 11,021 | 0 |
| Core unit | 2,128 | 2,143 | 2,158 | 6,429 | 0 |
| Standard activities subtotal | 6,763 | 3,895 | 6,792 | 17,450 | 0 |
| Total | 33,575 | 44,310 | 60,681 | 138,566 | 100,186 |

* Including agency support costs where applicable.

Performance indicators

# UNDP submitted performance indicators pursuant to decision 71/28 in its business plan narrative. The Secretariat informed UNDP of the targets shown in Table 5.

Table 5. Performance indicators for UNDP for 2021

| Type of indicator | Short title | Calculation | 2021 target |
| --- | --- | --- | --- |
| Planning--Approval | Tranches approved | Number of tranches approved vs. those planned* | 28 |
| Planning--Approval | Projects/activities approved | Number of projects/activities approved vs. those planned (including project preparation activities)** | 37 |
| Implementation | Funds disbursed | Based on estimated disbursement in progress report | US $22,419,984 |
| Implementation | ODS phase-out | ODS phase-out for the tranche when the next tranche is approved vs. those planned per business plans | 368.84 ODP tonnes |
| Implementation | Project completion for activities | Project completion vs. planned in progress reports for all activities (excluding project preparation) | 49 |
| Administrative | Speed of financial completion | The extent to which projects are financially completed 12 months after project completion | 70% |
| Administrative | Timely submission of project completion reports | Timely submission of project completion reports vs. those agreed | On time (3) |
| Administrative | Timely submission of progress reports | Timely submission of progress reports and business plans and responses unless otherwise agreed | On time |

* The target of an agency would be reduced if it could not submit a tranche owing to another lead or cooperating agency, if agreed by that agency.

** Project preparation should not be assessed if the Executive Committee has not taken a decision on its funding.

Policy issues

# UNDP presents the following policy issues related to the cost guidelines for HFC phase-down under consideration by the Executive Committee:

## Funding the market transformation by using the incremental operating cost in a more flexible and inclusive manner, rather than bundled with specific eligible industries;

## Challenges of LVC countries in terms of the demonstration of alternative technologies and ability to scale up with limited funding available;

## Special attention to the assembly sub-sector in the servicing sector and treating activities in this sub-sector differently from other activities in the servicing sector; and

## In the context of the Kigali Amendment, taking into account cost-effectiveness based on CO2-equivalent, and the coordination and synergy with the broader climate actions and institutions at the national and international levels in the preparation and implementation of HFC phase-down management plans.

RECOMMENDATION

# The Executive Committee may wish:

## To note the UNDP business plan for 2021–2023, contained in document UNEP/OzL.Pro/ExCom/86/27; and

## To approve the performance indicators for UNDP as set out in Table 5 of document UNEP/OzL.Pro/ExCom/86/27.

Due to coronavirus disease (COVID-19)

Given the constraints imposed by the COVID-19 pandemic, the Secretariat’s comments on the initial submission of the UNDP business plan for 2021–2023 were addressed through bilateral discussions and numerous exchanges of electronic messages. All issues were satisfactorily addressed.

Funding for the preparation of national implementation plans to meet initial reduction obligations for the phase-down of HFCs could be provided, at the earliest, five years prior to those obligations, after a country had ratified the Kigali Amendment and on the basis of guidelines to be approved in the future (decision 79/46(b)(iii)). In addition, decision 84/46(f) allowed the inclusion of HFC phase-down preparation activities in the business plan for countries that had not ratified the Kigali Amendment but had submitted a letter indicating their Government’s intent to make best efforts to ratify the Kigali Amendment.

UNDP’s 2021 core unit cost has been approved at the intersessional approval process for the 86th meeting (UNEP/OzL.Pro/ExCom/86/37).

In the absence of a decision by the Parties on the level of the replenishment of the Multilateral Fund for the 2021-2023 triennium, and in light of decision XXXII/1, the indicative budget for resource allocation of the business plan for 2021–2023 was assumed at the same level of the replenishment of the 2018–2020 triennium. This issue is discussed in UNEP/OzL.Pro/ExCom/86/25.

UNEP/OzL.Pro/ExCom/86/25