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اللجنــة التنفيـذيــــة للصنــدوق المــتعــدد الأطـــراف
لتنفيـــذ بروتوكـول مونتريــال 
الاجتمــــــاع الثالث والتسعــــون 
[bookmark: _Hlk128756171]مونتريال، 15 - 19 ديسمبر / كانون الأول 2023
البند 9(ج) من جدول الأعمال المؤقت[footnoteRef:1] [1:  الوثيقة UNEP/OzL.Pro/ExCom/93/1.] 



تعديلات برنامج عمل برنامج الأمم المتحدة للبيئة لعام 2023




تعليقات وتوصية أمانة الصندوق
1. [bookmark: _Hlk151807544]يطلب برنامج الأمم المتحدة للبيئة (اليونيب) موافقة اللجنة التنفيذية على مبلغ 5,618,157 دولارا أمريكيا زائدا تكاليف دعم الوكالة البالغة186,030  دولارا أمريكيا لتعديلات برنامج عملها لعام 2023 المدرجة في الجدول 1. ويرفق التقديم بهذه الوثيقة.   
الجدول 1: تعديلات برنامج عمل اليونيب لعام 2023
	البلد
	النشاط/ المشروع
	المبلغ المطلوب (بالدولار الأمريكي)
	المبلغ الموصي به (بالدولار الأمريكي)

	القسم ألف: الأنشطة الموصي بالموافقة الشمولية عليها

	ألف 1: تجديد مشروعات التعزيز المؤسسي

	أنتيغوا وبربودا
	تجديد مشروعات التعزيز المؤسسي (المرحلة السادسة)
	180,000
	180,000

	بنن
	تجديد مشروعات التعزيز المؤسسي (المرحلة الثالثة عشرة)
	180,000
	180,000

	 بوليفيا (دولة - المتعددة القوميات)
	تجديد مشروعات التعزيز المؤسسي (المرحلة الثانية عشرة)
	208,966
	208,966

	بوركينا فاسو
	تجديد مشروعات التعزيز المؤسسي (المرحلة الخامسة عشرة)
	191,858
	191,858

	[bookmark: _Hlk151838735]جزر كوك
	تجديد مشروعات التعزيز المؤسسي (المرحلة التاسعة)
	180,000
	180,000

	دومينيكا
	تجديد مشروعات التعزيز المؤسسي (المرحلة الثامنة)
	180,000
	180,000

	غابون
	تجديد مشروعات التعزيز المؤسسي (المرحلة الثانية عشرة)
	180,000
	180,000

	غيانا
	تجديد مشروعات التعزيز المؤسسي (المرحلة التاسعة)
	180,000
	180,000

	العراق
	تجديد مشروعات التعزيز المؤسسي (المرحلة السادسة)
	635,904
	635,904

	مدغشقر
	تجديد مشروعات التعزيز المؤسسي (المرحلة العاشرة)
	180,000
	180,000

	موريشيوس
	تجديد مشروعات التعزيز المؤسسي (المرحلة الثامنة)
	180,000
	180,000

	ميكرونيزيا (ولايات - الموحدة) 
	تجديد مشروعات التعزيز المؤسسي (المرحلة التاسعة)
	180,000
	180,000

	باراغواي
	تجديد مشروعات التعزيز المؤسسي (المرحلة الحادية عشرة)
	180,000
	180,000

	سانت لوسيا
	تجديد مشروعات التعزيز المؤسسي (المرحلة الثانية عشرة)
	180,000
	180,000

	جزر سليمان
	تجديد مشروعات التعزيز المؤسسي (المرحلة العاشرة)
	180,000
	180,000

	الصومال
	تجديد مشروعات التعزيز المؤسسي (المرحلة السادسة)
	180,000
	180,000

	 تيمور- ليشتي

	تجديد مشروعات التعزيز المؤسسي (المرحلة السابعة)
	180,000
	180,000

	توغو
	تجديد مشروعات التعزيز المؤسسي (المرحلة الثانية عشرة)
	180,000
	180,000

	اليمن
	تجديد مشروعات التعزيز المؤسسي (المرحلة التاسعة)
	450,429
	450,429

	المجموع الكلي للقسم ألف-1
	4,187,157
	4,187,157

	[bookmark: _Hlk151822904]القسم ألف-2: إعداد المشروعات لخطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية 

	جنوب السودان أ
	إعداد خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية (المرحلة الثانية)
	20,000
	20,000

	المجموع الفرعي للقسم ألف-2
	20,000
	20,000

	تكاليف دعم الوكالة
	2,600
	2,600

	المجموع الكلي للقسم ألف-2
	22,600
	22,600

	[bookmark: _Hlk151822952][bookmark: _Hlk151838091]القسم ألف-3: إعداد المشروعات لخطط كيغالي لتنفيذ المواد الهيدروفلوروكربونية

	إريتريا ب
	الإعداد لخطط تنفيذ كيغالي (المرحلة الأولى)
	91,000
	91,000

	جورجيا
	الإعداد لخطط تنفيذ كيغالي (المرحلة الأولى)
	130,000
	130,000

	كينيا ج
	الإعداد لخطط تنفيذ كيغالي (المرحلة الأولى)
	95,000
	95,000

	مالي أ
	الإعداد لخطط تنفيذ كيغالي (المرحلة الأولى)
	135,000
	135,000

	جمهورية مولدوفا 
	الإعداد لخطط تنفيذ كيغالي (المرحلة الأولى)
	130,000
	130,000

	سانت فنسنت وجزر غرينادين ب
	الإعداد لخطط تنفيذ كيغالي (المرحلة الأولى)
	70,000
	70,000

	المجموع الفرعي للقسم ألف-3
	651,000
	651,000

	تكاليف دعم الوكالة
	84,630
	84,630

	المجموع الكلي للقسم ألف-3
	735,630
	735,630

	[bookmark: _Hlk151826882]القسم ألف-4: إعداد جرد وطني لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها وخطة لجمع هذه المواد ونقلها والتخلص منها[footnoteRef:2] [2:  يشار إليه هنا بإعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها.] 


	ألبانيا
	إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها
	80,000
	80,000

	أرمينيا
	إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها
	90,000
	90,000

	بوليفيا (دولة - المتعددة القوميات) د
	إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها
	35,000
	35,000

	كوستاريكا
	إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها
	90,000
	90,000

	الجمهورية الدومينيكية 
	إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها
	90,000
	90,000

	السلفادور
	إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها
	90,000
	90,000

	غواتيمالا د
	إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها
	35,000
	35,000

	هندوراس د
	إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها
	35,000
	35,000

	نيكاراغوا د
	إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها
	35,000
	35,000

	جمهورية مولدوفا 
	إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها
	80,000
	80,000

	اليمن
	إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها
	100,000
	100,000

	المجموع الفرعي للقسم ألف-4
	760,000
	760,000

	تكاليف دعم الوكالة
	98,800
	98,800

	المجموع الكلي للقسم ألف-4
	858,800
	858,800

	المجموع الكلي للأقسام ألف-1، وألف-2، وألف-3، وألف4
	5,618,157
	5,618,157

	تكاليف دعم الوكالة للأقسام ألف-1، وألف-2، وألف-3، وألف4
	186,030
	186,030

	المجموع الإجمالي
	5,804,187
	5,804,187


أ اليوئنديبي بوصفه وكالة منفذة ومتعاونة.
ب اليونيدو بوصفها وكالة منفذة متعاونة.
ج حكومة ألمانيا بوصفها وكالة ثنائية رئيسية.
د اليونيدو بوصفها وكالة منفذة رائدة.
الأنشطة الموصي بالموافقة الشمولية عليها
ألف-1: تجديد مشروعات التعزيز المؤسسي
وصف المشروع
1. [bookmark: _Hlk151818828]قدم اليونيب طلبات لتجديد مشروعات التعزيز المؤسسي للبلدان المدرجة في القسم ألف-1 من الجدول 1. ويرد وصف هذه المشروعات في المرفق الأول لهذه الوثيقة.
تعليقات الأمانة
1. [bookmark: _Hlk151819112][bookmark: _Hlk151818930]استعرضت الأمانة طلبات تجديد 19 مشروعا للتعزيز المؤسسي قدمها اليونيب نيابة عن الحكومات المعنية في ضوء المبادئ التوجيهية[footnoteRef:3] والقرارات ذات الصلة المتعلقة بالأهلية ومستويات التمويل. وتم فحص الطلبات مقابل خطط العمل الأصلية للمرحلة السابقة، والبرنامج القطري وبيانات المادة 7، وأحدث تقرير عن تنفيذ خطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية، والتقرير المرحلي للوكالة، وأي مقررات ذات صلة صادرة عن اجتماعات الأطراف. وقد لوحظ أن جميع البلدان التسعة عشر قد قدمت بياناتها الخاصة بالبرامج القطرية لعام 2022 وهي في حالة امتثال لأهداف الرقابة بموجب بروتوكول مونتريال وأبلغت عن استهلاك سنوي للمواد الهيدروكلوروفلوروكربونية لا يتجاوز الحد الأقصى السنوي للاستهلاك المسموح به والمشار إليه في اتفاقات خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية مع اللجنة التنفيذية. وعلاوة على ذلك، تضمنت جميع الطلبات المقدمة تقييما لمؤشرات الأداء ومخاطر المشروع واستدامته وتحقيق أهداف التعزيز المؤسسي، وفقاً للمقرر 91/63(ب).  [3:  المقرر 91/63: (ب) الموافقة على الشكل المنقح للتقارير النهائية وطلبات تمديد تمويل التعزيز المؤسسي ومؤشرات الأداء المقابلة؛ و(ج) مطالبة البلدان المدرجة في المادة 5، من خلال الوكالات الثنائية والوكالات المنفذة، باستخدام النموذج المنقح المشار إليه في الفقرة الفرعية (ب) أعلاه لجميع طلبات تجديد التعزيز المؤسسي اعتبارا من الاجتماع الأول للجنة التنفيذية في عام 2023.] 

توصية الأمانة
1. توصي الأمانة العامة بالموافقة الشمولية على طلبات تجديد التعزيز المؤسسي لأنتيغوا وبربودا، وبنن، وبوليفيا (دولة - المتعددة القوميات)، وبوركينا فاسو، وجزر كوك، ودومينيكا، وغابون، وغيانا، والعراق، ومدغشقر، وموريشيوس، وميكرونيزيا (ولايات - الموحدة)، وباراغواي. وسانت لوسيا وجزر سليمان والصومال وتيمور- ليشتي وتوغو واليمن بمستويات التمويل المبينة في القسم ألف-1 من الجدول 1 من هذه الوثيقة. وقد ترغب اللجنة التنفيذية في أن تعرب للحكومات المذكورة أعلاه عن التعليقات الواردة في المرفق الثاني لهذه الوثيقة.
ألف-2: إعداد المشروعات لخطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية 
وصف المشروع
1. قدم اليونيب طلبا لإعداد المرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية لجنوب السودان باعتباره الوكالة المنفذة الرئيسية، كما هو مبين في القسم ألف-2 من
الجدول 1. وقد طلب برنامج الأمم المتحدة الإنمائي (اليوئنديبي) باعتباره الوكالة المنفذة المتعاونة لجنوب السودان مبلغ 10,000 دولار أمريكي، بالإضافة إلى تكاليف دعم الوكالة البالغة 700 دولار أمريكي في تعديلات برنامج عمله لعام 2023.[footnoteRef:4] [4:   UNEP/OzL.Pro/ExCom/93/35] 

1. [bookmark: _Hlk151820399]قدم اليونيب وصفا للأنشطة لدعم طلب إعداد المشروع للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية لجنوب السودان، والتي تضمنت: مبرر التمويل المطلوب لإعداد المشروع؛ وتقرير مرحلي عن تنفيذ المرحلة الأولى من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية؛ وقائمة الأنشطة التي سيتم الاضطلاع عليها أثناء إعداد المشروع والميزانيات المقابلة باستخدام نموذج طلبات إعداد المشروع لخطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية.
تعليقات الأمانة
1. عند استعراض هذا الطلب، قامت الأمانة بمراعاة المبادئ التوجيهية للتمويل الواردة في المقرر 71/42، والتقدم المحرز في المرحلة الأولى من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية بما في ذلك حالة تنفيذ الشرائح حتى إعداد هذه الوثيقة؛ والمقرر 84/46(هـ).[footnoteRef:5] وأشارت الأمانة إلى أن التمويل المطلوب يتماشى مع المقرر 71/42. وقد تم تمديد تاريخ اتمام المرحلة الأولى من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية لجنوب السودان إلى 31 ديسمبر/كانون الأول 2025 في الاجتماع الحادي والتسعين،[footnoteRef:6] وأشارت الأمانة إلى أن الطلب يتوافق مع المقرر 82/45 الذي يسمح بتقديم طلبات لإعداد المشروع للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية قبل عامين من تاريخ اتمام المرحلة الأولى من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية. [5:  يُسمح بإدراج المرحلة الثالثة من خطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية في خطة العمل فقط لتلك البلدان التي لديها المرحلة الثانية المعتمدة من خطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية مع أهداف خفض أقل من أهداف الامتثال لعام 2025.]  [6:  المرفق السابع عشر من الوثيقة UNEP/OzL.Pro/ExCom/91/72.] 

1. [bookmark: _Hlk151822023]وأشارت الأمانة كذلك إلى أن الاستهلاك السنوي المبلغ عنه للمواد الهيدروكلوروفلوروكربونية لعام 2022 للبلد البالغ 1.24 طن من قدرات استنفاد الأوزون يتجاوز الحد الأقصى السنوي للاستهلاك المسموح به وهو 1.07 طن من قدرات استنفاد الأوزون المشار إليه في الاتفاق المحدث لخطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية مع اللجنة التنفيذية لنفس العام. وأوضح اليونيب أن وحدة الأوزون الوطنية أعادت حساب البيانات المقدمة واكتشفت أنه تم إحصاء مستورد واحد مرتين وأن الحكومة كانت تعيد تقديم البيانات المصححة بمقدار 1.02 طن من قدرات استنفاد الأوزون وهو ضمن الحد الأقصى المسموح به للاستهلاك. وقد طلبت حكومة جنوب السودان رسميا مراجعة بيانات المادة 7 لتعكس الاستهلاك الصحيح للمواد الهيدروكلوروفلوروكربونية لعام 2022.
1. [bookmark: _Hlk151822127]وأكد اليونيب أن المرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية لجنوب السودان ستتخلص تدريجيا بنسبة 100 في المئة من خط الأساس للمواد الهيدروكلوروفلوروكربونية بحلول 1 يناير/ كانون الثاني 2030.
توصية الأمانة
1. توصي الأمانة بالموافقة الشمولية على إعداد المشروع للمرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية في جنوب السودان بمستوى التمويل المبين في القسم ألف-2 من الجدول 1.
[bookmark: _Hlk151823137][bookmark: _Hlk151827912]ألف-3: إعداد المشروعات لخطط كيغالي لتنفيذ المواد الهيدروفلوروكربونية
وصف المشروع
1. [bookmark: _Hlk151823875][bookmark: _Hlk151823643]قدم اليونيب طلبات لإعداد المرحلة الأولى من خطة كيغالي لتنفيذ المواد الهيدروفلوروكربونية لستة بلدان عاملة بالمادة 5، ولبلدين باعتباره الوكالة المنفذة المعينة؛ ولثلاثة بلدان باعتباره الوكالة المنفذة الرئيسية مع اليونيدو باعتبارها الوكالة المتعاونة لإريتريا وسانت فنسنت وجزر غرينادين؛ ومع اليوئنديبي باعتباره الوكالة المتعاونة لمالي؛ ولبلد واحد باعتباره الوكالة المنفذة المتعاونة، مع حكومة ألمانيا باعتبارها الوكالة المنفذة الرائدة. وترد هذه الطلبات في القسم ألف-3 من الجدول 1.
1. [bookmark: _Hlk151880663]وطلبت اليونيدو، باعتبارها الوكالة المنفذة المتعاونة لإريتريا وسانت فنسنت وجزر غرينادين، مبلغ 69,000 دولار أمريكي، بالإضافة إلى تكاليف دعم الوكالة البالغة 4,830 دولارا أمريكيا،[footnoteRef:7] وطلب اليوئنديبي باعتباره الوكالة المنفذة المتعاونة لمالي مبلغ 35,000 دولار أمريكي، بالإضافة إلى تكاليف دعم الوكالة البالغة 2,450 دولارا أمريكيا[footnoteRef:8] في تعديلات برنامج عملها لعام 2023. وطلبت حكومة ألمانيا، باعتبارها الوكالة المنفذة الرئيسية لكينيا، مبلغ 95,000 دولار أمريكي، بالإضافة إلى تكاليف دعم الوكالة البالغة12,350  دولارا أمريكيا وقدمت وصفا للأنشطة المطلوبة لإعداد خطة كيغالي لتنفيذ المواد الهيدروفلوروكربونية لكينيا والتكاليف المقابلة لكل نشاط في إطار التعاون الثنائي؛[footnoteRef:9] وترد هنا أيضا تعليقات الأمانة. [7:   UNEP/OzL.Pro/ExCom/93/37]  [8:   UNEP/OzL.Pro/ExCom/93/35]  [9:   UNEP/OzL.Pro/ExCom/93/32] 

تعليقات الأمانة
1. ولدى استعراض هذه الطلبات، نظرت الأمانة في المبادئ التوجيهية لإعداد خطط كيغالي لتنفيذ المواد الهيدروفلوروكربونية على النحو الوارد في المقرر 87/50؛ والأنشطة المقترحة لإعداد المشروعات وارتباطها بالأنشطة التمكينية والمشروعات الأخرى ذات الصلة بالمواد الهيدروفلوروكربونية في البلدان ذات الصلة.
1. [bookmark: _Hlk151826535][bookmark: _Hlk151824791][bookmark: _Hlk151826363]وقام اليونيب، باعتباره الوكالة المعينة/ المنفذة الرئيسية، بوصف الأنشطة المطلوبة لإعداد استراتيجيات شاملة لخطط كيغالي لتنفيذ المواد الهيدروفلوروكربونية لإريتريا وجورجيا ومالي وجمهورية مولدوفا وسانت فنسنت وجزر غرينادين باستخدام نموذج لطلبات إعداد المشروعات لخطط كيغالي لتنفيذ المواد الهيدروفلوروكربونية. وتضمنت التقديمات بيانات عن استهلاك المواد الهيدروفلوروكربونية وخليط للمواد الهيدروفلوروكربونية لجميع البلدان. وتضمنت أنشطة إعداد المشروعات لجميع البلدان الخمسة إجراء مسح وطني وجمع بيانات عن استهلاك المواد الهيدروفلوروكربونية، وتحليل استخدام المواد الهيدروفلوروكربونية والبدائل؛ واجتماعات تشاورية مع أصحاب المصلحة؛ واجتماعات التحقق من صحة البيانات؛ وجمع البيانات وتحليل قدرات قطاع خدمات التبريد وتكييف الهواء ووضع استراتيجية شاملة للتخفيض التدريجي للمواد الهيدروفلوروكربونية. وبالإضافة إلى تلك الأنشطة المذكورة أعلاه، شملت أنشطة الإعداد في بعض البلدان تحليل احتياجات وقدرات هياكل الجمارك/التجارة/إنفاذ القانون؛ ووضع خطط عمل لتعميم مراعاة المنظور الجنساني؛ واستعراضات للسياسات والتشريعات؛ وتقييم القدرة على الاسترداد وإعادة التدوير والتدمير؛ وإعداد السياسات واللوائح الأولية المتعلقة بالمواد الهيدروفلوروكربونية بما في ذلك نظام الحصص؛ وتعزيز البدائل ذات القدرة المنخفضة على إحداث الاحترار العالمي من خلال تحليل الحوافز والمثبطات. 
1. [bookmark: _Hlk151826593][bookmark: _Hlk151826809]وأشارت الأمانة إلى أن جميع البلدان الخمسة حيث اليونيب هو الوكالة المعينة/الرئيسية المنفذة قد صادقت على تعديل كيغالي؛[footnoteRef:10] وأن البلدان قد قدمت خطابات تأييد تشير إلى عزمها على اتخاذ إجراءات بشأن التخفيض التدريجي للمواد الهيدروفلوروكربونية؛ وأن التمويل المطلوب يتوافق مع المقرر 87/50(ج). وأوضح اليونيب أن إعداد المشروع للاستراتيجيات الشاملة لخطط كيغالي لتنفيذ المواد الهيدروفلوروكربونية في جميع البلدان الخمسة سوف يعتمد على الأنشطة المنفذة في إطار الأنشطة التمكينية، حيث إن هذه كانت الإجراءات الأولى المرتبطة بالتخفيض التدريجي للمواد الهيدروفلوروكربونية وساهمت في التصديق على تعديل كيغالي.  [10:  تاريخ التصديق (أو القبول) على تعديل كيغالي: إريتريا (7 فبراير/شباط 2023)، وجورجيا (11 يوليو/تموز 2023)، ومالي (22 سبتمبر/أيلول 2023)، ومولدوفا (22 سبتمبر/أيلول 2023)، وسانت فنسنت وجزر غرينادين (7 نوفمبر/تشرين الثاني 2023). ] 

توصية الأمانة
1. توصي الأمانة بالموافقة الشمولية على إعداد المشروعات للمرحلة الأولى من خطط كيغالي لتنفيذ المواد الهيدروفلوروكربونية لإريتريا وجورجيا وكينيا ومالي وجمهورية مولدوفا وسانت فنسنت وجزر غرينادين بمستويات التمويل المبينة في القسم ألف-3 من الجدول 1.
ألف-4: إعداد جرد وطني لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها وخطة لجمع هذه المواد ونقلها والتخلص منها
وصف المشروع
1. قدم اليونيب طلبات لإعداد جرد وطني لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها وخطة لسبعة بلدان باعتباره الوكالة المنفذة المعينة؛ ولأربعة بلدان باعتباره الوكالة المنفذة المتعاونة مع اليونيدو باعتبارها الوكالة المنفذة الرئيسية، كما هو مبين في القسم ألف-4 من الجدول 1.
1. وطلبت اليونيدو، باعتبارها الوكالة المنفذة الرئيسية لبوليفيا (دولة - المتعددة القوميات) وغواتيمالا وهندوراس ونيكاراغوا، مبلغ 220,000 دولار أمريكي، بالإضافة إلى تكاليف دعم الوكالة البالغة15,400  دولار أمريكي في تعديلات برنامج عملها لعام 2023.[footnoteRef:11] [11:  المرجع نفسه.] 

تعليقات الأمانة 
1. [bookmark: _Hlk151834883]عند استعراض هذه الطلبات، قامت الأمانة بمراعاة معايير إعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها في المقرر 91/66 والأنشطة المقترحة لإعداد المشروع وارتباطها بخطط التخلص التدريجي/ التخفيض التدريجي (أي خطط إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية أو خطط كيغالي لتنفيذ المواد الهيدروفلوروكربونية) في البلدان. وأشارت الأمانة إلى أن كل طلب تمويل يتماشى مع المقرر 91/66. 
1. وقدم اليونيب باعتباره الوكالة المنفذة المعينة وصفا للأنشطة المطلوبة لإعداد خطة وطنية وجرد لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها لألبانيا وأرمينيا وكوستاريكا والجمهورية الدومينيكية والسلفادور وجمهورية مولدوفا واليمن باستخدام نماذج التقديم ذات الصلة لمقترحات المشروعات.
1. [bookmark: _Hlk151835525]وتضمنت الأنشطة الواردة في طلبات التمويل للبلدان السبعة إعداد الجرد الوطني وخطة العمل والتقرير النهائي؛ والتقييمات التنظيمية لتحديد احتياجات الرقابة على مخازن المواد المستنفدة للأوزون  والمواد الهيدروفلوروكربونية غير المرغوب فيها؛ والمشاورات مع أصحاب المصلحة المعنيين؛ جمع البيانات وتحليلها بشأن كميات غازات التبريد غير المستخدمة أو غير المرغوب فيها من أنواع ومصادر المعدات المحددة والتحقق منها؛ وتحديد نموذج التكلفة المستدامة والتمويل اللازم للتنفيذ؛ وتحديد المختبرات القادرة على تحليل تركيبة المواد المستنفدة للأوزون والمواد الهيدروفلوروكربونية المستخدمة أو غير المرغوب فيها، والحاجة إلى تطوير هذه المختبرات؛ واعتبارات تعميم مراعاة المنظور الجنساني. وبالإضافة إلى تلك الأنشطة، شملت أنشطة الإعداد لبعض البلدان عقد ورشة عمل إقليمية لتبادل الخبرات مع بلدان أمريكا الوسطى الأخرى؛ وتنفيذ اختبارات التدمير في مصانع الأسمنت للتحقق مما إذا كانت المعالجة المشتركة تمتثل لمعايير الانبعاثات.
توصية الأمانة
1. توصي الأمانة بالموافقة الشمولية على إعداد جرد وطني لمخازن المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها وخطة لجمع هذه المواد ونقلها والتخلص منها وذلك لألبانيا وأرمينيا وبوليفيا (دولة - المتعددة القوميات) وكوستاريكا والجمهورية الدومينيكية والسلفادور وغواتيمالا وهندوراس ونيكاراغوا وجمهورية مولدوفا واليمن بمستوى التمويل المبين في القسم ألف-4 من الجدول 1.
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إن وثائق ما قبل دورات اللجنة التنفيذية للصندوق المتعدد الأطراف لتنفيذ بروتوكول مونتريال 
قد تصدر دون إخلال بأي قرار تتخذه اللجنة التنفيذية بعد صدورها. 
2
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		المرفق الأول
Annex I
INSTITUTIONAL STRENGTHENING PROJECT PROPOSALS[footnoteRef:12] [12:  Data as at December 2022 are based on document UNEP/OzL.Pro/ExCom/93/17.] 

Antigua and Barbuda: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-98
	36,000

	Phase II:
	Nov-02
	31,187

	Phase III:
	Dec-04
	60,000

	Phase IV:
	Dec-12
	30,000

	Phase V:
	Nov-14
	60,000

		Total:
	217,187

	Amount requested for renewal (phase VI) (US $):
	180,000

	Amount recommended for approval for phase VI (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VI to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	1998

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex A, Group I (CFCs) (average 1995-1997)
	10.7

	(b)	Annex A, Group II (halons) (average 1995-1997)
	0.3

	(c)	Annex B, Group II (carbon tetrachloride) (average 1998-2000)
	0.0

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.3

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	(g)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	Not available

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex A, Group I (CFCs)
	0

	(b)	Annex A, Group II (halons)
	0

	(c)	Annex B, Group II (carbon tetrachloride)
	0

	(d)	Annex B, Group III (methyl chloroform)
	0

	(e)	Annex C, Group I (HCFCs)
	0

	(f)	Annex E (methyl bromide)
	0

		Total:
	0

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7
	Not available

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	626,740

	Amount disbursed (as at December 2022) (US $):
	566,740

	ODS to be phased out (as at June 2023) (ODP tonnes):
	3.0

	ODS phased out (as at December 2022) (ODP tonnes):
	3.0



1. Summary of activities and funds approved by the Executive Committee:
	[bookmark: _Hlk115777276]Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	62,987

	(b)	Institutional strengthening:
	217,187

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	346,566

		Total:
	626,740

	(d)	HFC activities funded from additional voluntary contributions
	0


Progress report
23. Phase V of the institutional strengthening (IS) project for Antigua and Barbuda supported the country’s efforts to maintain the implementation of Montreal Protocol activities. Phase V experienced delays in implementation owing to the COVID-19 global pandemic and administrative challenges within the national ozone unit (NOU) and Government. However, during UNEP’s May 2023 mission, the country recommitted to the implementation of Montreal Protocol projects including IS. The NOU monitored the implementation of the licensing and quota system, monitored its borders to guard against illegal ODS trade, and collected, verified and submitted its country programme and Article 7 data, allowing Antigua and Barbuda to maintain compliance under the Montreal Protocol. During phase V, the country fully achieved the IS indicators apart from those that were rated as “not applicable” as there was no active HCFC phaseout management plan (HPMP) being implemented during the period.  
Plan of action
24. Under phase VI, the Government of Antigua and Barbuda will continue to support activities to phase out HCFCs and promote related issues. Ratification of the Kigali Amendment is anticipated to be achieved. The newly created Independent Oversight Advisory Committee (following UNEP’s mission) is expected to play a greater role in guiding and supporting the NOU with implementation of activities. As a result of the global COVID-19 pandemic, the NOU will increase the use of virtual tools to diversify its outreach and visibility. The following actions will be undertaken during the new phase: continue to strengthen coordination within the NOU and with relevant stakeholders; implement the licensing and quota system for HCFCs and the licensing system for HFCs and share more information regarding the Kigali Amendment; coordinate and monitor programme activities under the HPMP; work closely with stakeholders in the refrigeration servicing sector; implement public awareness campaigns through virtual and print media. During the next phase, the NOU will maintain its timely country programme and Article 7 data reporting and will participate in meetings related to the Montreal Protocol. Additionally, the Government will promote participation of women in the refrigeration servicing sector. 
Sustainability and risk assessment
25. The NOU is located within the Ministry of Foreign Affairs, Agriculture, Trade and Barbuda Affairs and is under the direct supervision of the Office of the Permanent Secretary. The work programme of the NOU is incorporated within that of the Ministry. With the installation of the Independent Oversight Advisory Committee with the Permanent Secretary as the Chair, this confirms the importance of this committee and its role in ensuring support to the NOU. These factors contribute to the sustainability of the IS and the framework to assess risks ahead of time and plan for suitable interventions in advance. Additionally, UNEP requires interim reports as part of the Small-scale Funding Agreement (SSFA) with the country. These reports contain a section where the country is required to identify in advance, any issues that it is experiencing or where the activities are not proceeding as planned, so that UNEP as implementing agency may support, assess and intervene where necessary. 
Benin: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-95
	50,000

	Phase II:
	Jul-99
	33,333

	Phase III:
	Mar-01
	33,333

	Phase IV:
	Jul-03
	43,333

	Phase V:
	Jul-06
	60,000

	Phase VI:
	Nov-08
	60,000

	Phase VII:
	Dec-10
	60,000

	Phase VIII:
	Dec-13
	60,000

	Phase IX:
	Nov-15
	85,000

	Phase X:
	Nov-17
	82,337

	Phase XI:
	Dec-19
	85,000

	Phase XII:
	Nov-21
	85,000

		Total:
	737,335

	Amount requested for renewal (phase XIII) (US $):
	180,000

	Amount recommended for approval for phase XIII (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	1995

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	23.8

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	1,763,273

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	10.93

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	10.93

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7
	1,230,484

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	3,230,824

	Amount disbursed (as at December 2022) (US $):
	2,614,005

	ODS to be phased out (as at June 2023) (ODP tonnes):
	87.8

	ODS phased out (as at December 2022) (ODP tonnes):
	75.3



26. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	770,609

	(b)	Institutional strengthening:
	737,335

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	1,722,880

		Total:
	3,230,824

	(d)	HFC activities funded from additional voluntary contributions
	150,000


Progress report
27. Under phase XII of its IS project, Benin's NOU achieved all seven performance objectives. The NOU collected ODS and HFC import data and submitted country programme and Article 7 data to the Fund and Ozone Secretariats, respectively; held annual meetings with stakeholders, including the National Ozone Committee, for effective coordination; and supervised training for 106 refrigeration and air-conditioning (RAC) technicians and 34 customs officers. The NOU implemented continuing activities including raising awareness about HCFC alternatives, relevant laws and regulations; and actively observed World Ozone Day and engaged in Montreal Protocol-related meetings. 
Plan of action
28. During phase XIII of the IS project, the NOU will focus on: continuing information dissemination and awareness activities; coordinating the implementation of stage II of the HPMP; promoting and enforcing the licensing and quota system, providing importers with annual quota information; establishing the technician certification program; sustaining monitoring and evaluation efforts; conducting annual stakeholder workshops to promote low-GWP HCFC alternatives; timely data collection and reporting to the Ozone and Fund Secretariats, and preparation of the overarching strategy for the Kigali HFC implementation plan (KIP).
Sustainability and risk assessment
29. The Government of Benin is actively regulating HCFC and HFC consumption in line with the Montreal Protocol targets. Training centres have been equipped for technicians, and customs officers are being trained to monitor HCFC and HFC imports and potential illegal trade.  These actions are expected to mitigate risks of project implementation experienced in the past. UNEP as implementing agency continues to support Benin in timely project implementation. Despite all challenges, online meetings and training have been effective. 
Bolivia (Plurinational State of): Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-95
	91,000

	Phase II:
	Nov-98
	60,670

	Phase III:
	Jul-01
	60,670

	Phase IV:
	Jul-03
	100,000

	Phase V:
	Nov-05
	78,867

	Phase VI:
	Nov-07
	78,867

	Phase VII:
	Nov-09 
	78,868

	Phase VIII:
	Jul-12
	78,867

	Phase IX:
	Nov-14
	78,867

	Phase X:
	Nov-17
	100,950

	Phase XI:
	Dec-19
	100,950

		Total:
	908,576

	Amount requested for renewal (phase XII) (US $):
	209,000

	Amount recommended for approval for phase XII (US $): 
	209,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XII to the Multilateral Fund (US $):
	209,000

	Date of approval of country programme:
	1995

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	6.1

	(c)	Annex E, (methyl bromide) (average 1995-1998)
	0.6

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	677,884

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.0

	(b)	Annex C, Group I (HCFCs)
	1.4

	(c)	Annex E (methyl bromide)
	0.0

		Total:
	1.4

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7
	736,368

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	3,928,893

	Amount disbursed (as at December 2022) (US $):
	3,603,748

	ODS to be phased out (as at June 2023) (ODP tonnes):
	114.2

	ODS phased out (as at December 2022) (ODP tonnes):
	108.4



30. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	1,293,424

	(b)	Institutional strengthening:
	908,576

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	1,726,893

		Total:
	3,928,893

	(d)	HFC activities funded from additional voluntary contributions
	150,000



[bookmark: _Hlk115777232]Progress report
31. The implementation of Montreal Protocol activities in Bolivia (Plurinational State of) continued with significant progress under phase XI of the IS project. The NOU worked to achieve broad consensus on revised national ODS legislation. An operational ODS import/export licensing and HCFC quota system is in place and the licensing system includes HFC substances. Article 7 and country programme data were submitted to the Ozone and Fund Secretariats, respectively, accurately and in a timely manner. The enabling activities for HFC phase-down project was completed in June 2022. NOU staff also coordinated activities for the final tranches of stage I of the HPMP, and the first tranche of stage II. Several training sessions for customs officers were organized. The country has encouraged the continued participation of stakeholders in the implementation of the Montreal Protocol at the national level, and organized awareness-raising activities as well as World Ozone Day celebrations and participated in regional network meetings and events. 
Plan of action
32. Bolivia will continue implementing HCFC phase-out and submit its Kigali HFC implementation plan in an effective manner to meet the HCFC phase‑out and HFC phase-down targets, while ensuring gender mainstreaming in implementation of those projects. In addition, it will continue strengthening the controlled substances legislation to fulfill the requirements of the stage II of the HPMP and the Kigali Amendment, and the development of national capacities to allow the efficient implementation of all its provisions. The action plan also includes strict monitoring and control of the imports and use of HCFCs and HFCs, as well as facilitating access to and use of new alternative substances and technologies. The NOU will continue public awareness-raising activities especially with the education sector and with a gender focus during the celebration of World Refrigeration Day and World Ozone Day as well as national events. 
Sustainability and risk assessment
33. The frequent changes in Government, and in national entities, have threatened compliance with the commitments made under the Montreal Protocol and the sustainability of the project. Therefore, the NOU has been working to ensure the continuity of the actions included in the HPMP implementation plan and to raise awareness of the new authorities on the importance of the project for the country’s compliance with the Montreal Protocol and for the ozone layer protection. One of the positive results achieved is the strengthening of the regulatory framework for the control of substances controlled by the Montreal Protocol and the products/equipment that depend on them, guaranteeing the sustainability of the achievements achieved so far. In addition, to ensure the long‑term sustainability of the HCFC phase‑out and mitigate the risks to project implementation, the NOU maintains good communication with and has support from the Customs Agency to ensure control of HCFC substances. 


Burkina Faso: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-93
	83,500 

	Phase II:
	May-97
	55,700 

	Phase III:
	Mar-99
	55,700 

	Phase IV
	Mar-01
	55,700 

	Phase V:
	Nov-02
	72,410 

	Phase VI:
	Dec-04
	72,410 

	Phase VII:
	Nov-06
	72,410 

	Phase VIII:
	Nov-08
	72,410 

	Phase IX:
	Dec-10
	72,410 

	Phase X:
	Dec-12
	72,410 

	Phase XI:
	May-15
	72,410 

	Phase XII:
	Jul-17
	92,612 

	Phase XIII:
	May-19
	92,685 

	Phase XIV:
	Jul-21
	92,685 

	Total:
	1,035,452

	Amount requested for renewal (phase XV) (US $):
	192,000

	Amount recommended for approval for phase XV (US $): 
	192,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XV to the Multilateral Fund (US $):
	192,000

	Date of approval of country programme:
	1993

	Date of approval of HCFC phase-out management plan (stage I):
	2010

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	28.9

	(c)	Annex E, (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	1,049,523

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	5.31

	Annex E, (methyl bromide)
	0.00

		Total:
	5.31

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7 
	401,625

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	3,552,379

	Amount disbursed (as at December 2022) (US $):
	2,844,219

	ODS to be phased out (as at June 2023) (ODP tonnes):
	84.0

	ODS phased out (as at December 2022) (ODP tonnes):
	78.8



34. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	620,630

	(b)	Institutional strengthening:
	1,035,452

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	1,896,296

	Total:
	3,552,379

	(d)	HFC activities funded from additional voluntary contributions
	150,000





Progress report
35. Burkina Faso's NOU implemented phase XIV of the IS project, achieving six out of seven performance objectives. The NOU collected ODS and HFC import data and submitted country programme and Article 7 data to the Fund and Ozone Secretariats, respectively. Annual meetings with stakeholders, including the National Ozone Committee, were held for effective coordination. The NOU oversaw training for 116 RAC technicians and 106 customs officers. Ongoing activities included raising awareness about HCFC alternatives, relevant laws and regulations. Burkina Faso actively observed World Ozone Day and engaged in Montreal Protocol-related meetings. 
Plan of action
36. In Phase XV of the IS project, the NOU will focus on: continuing information dissemination and awareness activities; coordinating the implementation of stage II of the HPMP; promoting and enforcing the licensing and quota system, providing importers with annual quota information; establishing the technician certification programme; sustaining monitoring and evaluation efforts; conducting annual stakeholder workshops to promote low-GWP HCFC alternatives; timely data collection and reporting to the Ozone and Fund Secretariats; and preparation of the overarching strategy for the KIP.
Sustainability and risk assessment
37. The IS project can be successfully implemented in Burkina Faso under conditions of stable funding. Stakeholders, relevant associations, ministries and agencies actively participate in the development of recommendations and amendments to laws and regulations, as well as public awareness and promotional activities. The NOU is continuously guided by the National Ozone Steering Committee which comprises of key line Ministries, the RAC sector and other relevant agencies.  
Cook Islands: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Dec-04 & Nov-06
	30,000

	Phase II:
	Nov-07 & Nov-09
	47,500

	Phase III:
	Dec-10
	60,000

	Phase IV:
	Jul-12
	60,000

	Phase V:
	May-14
	55,000

	Phase VI:
	Dec-16
	80,000

	Phase VII:
	Dec-19
	85,000

	Phase VIII:
	Nov-21
	85,000

		Total:
	502,500

	Amount requested for renewal (phase IX) (US $):
	180,000

	Amount recommended for approval for phase IX (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	2004

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.1

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	6,461

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0

	(b)	Annex C, Group I (HCFCs)
	0

	(c)	Annex E (methyl bromide)
	0

		Total:
	0

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7 
	8,065

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	880,001

	Amount disbursed (as at December 2022) (US $):
	623,088

	ODS to be phased out (as at June 2023) (ODP tonnes):
	1.4

	ODS phased out (as at December 2022) (ODP tonnes):
	0.5



38. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	0

	(b)	Institutional strengthening:
	502,500

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	377,501

		Total:
	880,001

	(d)	HFC activities funded from additional voluntary contributions
	50,000



Progress report
39. Phase VIII of the IS project demonstrated the high level of national organization that the Government has achieved through the NOU. The Government implemented recommendations from the verification of HCFC consumption to further strengthen HFC trade control and sustain compliance with the Montreal Protocol HCFC phase‑out obligations and maximum allowable consumption as agreed. The country fulfilled its data reporting obligations to the Ozone and Fund Secretariats in a timely manner and has sustained compliance with the HCFC reduction targets. The national ozone officer worked in close collaboration with the Customs Department, Cook Islands Refrigeration and Air‑Conditioning (CIRAC) Association and other stakeholders in expediting implementation and sustain compliance with the Montreal Protocol. All the planned activities included in phase VIII made progress and fulfilled the objectives.
Plan of action
40. Phase IX will include: implementing the HFC licensing and quota system; adoption of the Pacific Harmonized Commodity Description and Coding System 2022 (PACHS22) to have individual HS code for HFCs and blends; timely submission of Article 7 and country programme data; active engagement of key stakeholders and RAC association in the implementation of Montreal Protocol projects; coordination with stakeholders for the implementation of the HPMP and preparation of the KIP; organization of the World Ozone Day celebration and development of awareness materials; and participation in regional and international meetings. Gender mainstreaming will be integrated into implementation of the project activities.
Sustainability and risk assessment
41. The IS project can be successfully implemented in the Cook Islands under conditions of stable funding. Stakeholders, relevant associations, ministries and agencies actively participate in the development of recommendations and amendments to laws and regulations, as well as public awareness and promotional activities. The NOU is continuously guided by the National Ozone Committee which is comprised of key inline Ministries, the RAC sector and other relevant agencies. Since the Cook Islands has yet to adopt and put the WCO HS 2022 into effect, there are risks that HFC imports will not be accurately identified and recorded in the customs system. There might be some challenges with customs declarations due to the different types of HFCs as opposed to one type of HCFC; this is being discussed between the NOU and Customs. Therefore, it is crucial that the NOU strengthens cooperation with the Customs Department in monitoring HFCs through targeted awareness-raising for importers and customs brokers on identifying HFCs being imported with their proper HS codes.
Dominica: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-98
	30,000

	Phase II:
	Apr-04 and Apr-05
	26,000

	Phase III:
	Nov-06
	60,000

	Phase IV:
	Nov-08
	60,000

	Phase V:
	Dec-10
	60,000

	Phase VI:
	May-14 
	30,000

	
	Nov-17
	20,000*

	Phase VII:
	Jun-18
	85,000

		Total:
	371,000

	Amount requested for renewal (phase VIII) (US $):
	180,000

	Amount recommended for approval for phase VIII (US $): 	
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	1998

	Date of approval of HCFC phase-out management plan:
	2010

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.4

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	Not available

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	0.03

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	0.03

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7 
	24,230

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	982,386

	Amount disbursed (as at December 2022) (US $):
	659,362

	ODS to be phased out (as at June 2023) (ODP tonnes):
	0.8

	ODS phased out (as at December 2022) (ODP tonnes):
	0.7


 * Additional emergency assistance for institutional strengthening of US $20,000 was approved at the 80th meeting.

42. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	56,208

	(b)	Institutional strengthening:
	371,000

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	555,178

	Total:
	982,386

	(d)	HFC activities funded from additional voluntary contributions
	50,000





Progress report
43. Phase VII of the IS project in Dominica was key in supporting the country’s efforts to maintain the implementation of the Montreal Protocol activities. The phase experienced delays in its implementation due to lingering effects of Hurricane Maria compounded by the COVID-19 global pandemic and administrative changes within the NOU and Government. However, during UNEP’s mission in June 2023, technical and policy experts from relevant government ministries were engaged and demonstrated their commitment to the implementation of the Montreal Protocol. The following was implemented: ODS legislation and regulation to control and monitor ODS consumption and measures towards controlling HFCs; data collection, analysis, and submission; consultations and coordination with other national agencies/stakeholders; coordination of HPMP implementation activities; awareness‑raising and information exchange; and regional cooperation and participation in Montreal Protocol meetings. Currently, the country is continuing to work towards achieving favourable ratings of the indicators except where rated “not applicable” as the country worked only to a limited extent on the integration of the Multilateral Fund gender mainstreaming policies.
Plan of action
44. Under phase VIII, the Government will continue to support activities to phase out HCFCs and promote Montreal Protocol activities. Through continued key stakeholder engagement, ratification of the Kigali Amendment is anticipated to be achieved. The NOU and line ministry are planning the organization of a steering committee comprised of the Permanent Secretary, senior technical advisor, and senior policy advisor to support the NOU with the implementation of activities. As a result of the COVID-19 pandemic, the NOU will increase the use of virtual tools to broaden its outreach and visibility. During the new phase, the NOU will continue: to strengthen coordination with stakeholders; to implement the licensing and quota system for HCFCs and begin the implementation of a licensing system for HFCs; to coordinate and monitor programme activities under the HPMP; to work closely with stakeholders in the refrigeration servicing sector including capacity development; and to implement public awareness campaigns through virtual and print media. The NOU will also maintain its timely country programme and Article 7 data reporting to the Fund and Ozone Secretariats, respectively, participate in Montreal Protocol-related meetings and promote women's participation in the refrigeration servicing sector. 
Sustainability and risk assessment
45. The NOU is located within the Ministry of Environment, Rural Modernisation, Kalinago Upliftment, and Constituency Empowerment under the direct supervision of the Office of the Permanent Secretary. The work programme of the NOU is incorporated within this Ministry. The planned organization of a National Ozone Steering Committee with the Permanent Secretary as a member, confirms the importance of this committee and its intended role in providing direct support to the NOU. These factors contribute to the sustainability of the IS project and the framework to assess risks ahead of time and plan for suitable interventions in advance. Additionally, UNEP requires interim reports as part of the SSFA with the country. These reports allow the country to identify in advance, any issues that it is experiencing or where the activities are not progressing as planned, providing an early indication where UNEP as implementing agency may support, assess and intervene where necessary. 
Gabon: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	May-97
	45,600

	Phase II:
	Dec-00
	30,400

	Phase III:
	Jul-02
	39,520

	Phase IV:
	Dec-04
	60,000

	Phase V:
	Nov-06
	60,000

	Phase VI:
	Nov-08
	60,000

	Phase VII:
	Dec-10
	60,000

	Phase VIII
	Dec-13
	60,000

	Phase IX:
	Nov-15
	84,703

	Phase X:
	Jun-18
	85,000

	Phase XI:
	Jul-21
	85,000

		Total:
	670,223

	Amount requested for renewal (phase XII) (US $):
	180,000

	Amount recommended for approval for phase XII (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XII to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	1997

	Date of approval of HCFC phase-out management plan:
	2010

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	30.2

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	2,182,210

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	7.37

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	7.37

	[bookmark: _Hlk143269971]Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7 
	740,030

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	2,529,071

	Amount disbursed (as at December 2022) (US $):
	2,209,446

	ODS to be phased out (as at June 2023) (ODP tonnes):
	33.0

	ODS phased out (as at December 2022) (ODP tonnes):
	27.3



46. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	333,142

	(b)	Institutional strengthening:
	670,223

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	1,525,706

	Total: 
	2,529,071

	(d)	HFC activities funded from additional voluntary contributions
	150,000



Progress report
47. During phase XI of the IS project in Gabon, the NOU collected ODS and HFC import data and submitted country programme and Article 7 data to the Fund and Ozone Secretariats, respectively. Annual meetings with stakeholders, including the National Ozone Committee, were held for effective coordination. The NOU oversaw training for 17 customs officers; raised awareness about HCFC alternatives, relevant laws and regulations; organized World Ozone Day celebrations and engaged in Montreal Protocol-related meetings. Gabon achieved five out of seven IS performance objectives with two indicators partially achieved.


Plan of action
48. During phase XII of the IS project, the NOU will focus on: continuing information dissemination and awareness activities; coordinating the implementation of stage II of the HPMP; promoting and enforcing the licensing and quota system, providing importers with annual quota information; establishing the technician certification programme; sustaining monitoring and evaluation efforts; conducting annual stakeholder workshops to promote low-GWP HCFC alternatives; timely data collection and reporting to the Ozone and Fund Secretariats; and preparation of the overarching strategy for the KIP for Gabon. 
Sustainability and risk assessment
49. The Government is actively regulating HCFC and HFC consumption in line with the Montreal Protocol targets. Training centres have been equipped for technicians, and customs officers are being trained to monitor HCFC and HFC imports and potential illegal trade of those substances. These actions are expected to mitigate the risks of project implementation experienced in the past. UNEP as implementing agency continues to support Gabon in timely project implementation. Despite the challenges, online meetings and training have been effective. 
Guyana: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-97
	65,000

	Phase II:
	Jul-01
	43,400

	Phase III:
	Apr-06
	56,333

	Phase IV:
	Nov-09 
	60,000

	Phase V:
	Dec-12
	60,000

	Phase VI:
	May-15
	60,000

	Phase VII:
	Jul-17
	85,000

	Phase VIII:
	Dec-19
	85,000

	Total:
	514,733

	Amount requested for renewal (phase IX) (US $):
	180,000

	Amount recommended for approval for phase IX (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	1997

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	1.8

	(c)	Annex E, (methyl bromide) (average 1995-1998)
	1.4

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	146,169

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	0.62

	(c)	Annex E, (methyl bromide)
	0.00

		Total:
	0.62

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7 
	156,067

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	2,465,818

	Amount disbursed (as at December 2022) (US $):
	2,044,848

	ODS to be phased out (as at June 2023) (ODP tonnes):
	68.0

	ODS phased out (as at December 2022) (ODP tonnes):
	60.6



50. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	514,733

	(b)	Institutional strengthening:
	1,075,022

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	876,063

		Total:
	2,465,818

	(d)	HFC activities funded from additional voluntary contributions
	95,000


Progress report
51. Phase VIII of the IS project for Guyana was instrumental in aiding the country’s efforts to maintain the implementation of Montreal Protocol activities. During the phase, the project experienced delays in implementation owing to the lingering effects of the COVID-19 pandemic and administrative challenges within the NOU and Government. However, with the support of UNEP, the NOU continued to engage with technical and political intergovernmental focal points towards the implementation of the Montreal Protocol project portfolios. During the phase, the NOU continued: implementation of ODS legislation and regulation to control and monitor ODS consumption and took measures towards controlling HFCs; data collection, analysis, and submission; consultations and coordination with other national agencies/stakeholders; coordination of HPMP implementation activities as scheduled; awareness‑raising and information exchange; and regional cooperation and participation in Montreal Protocol meetings. Of the seven IS indicators, three were fully achieved, three partially achieved and one was not achieved.
Plan of action
52. As part of phase IX, the Government will continue to support activities to phase out HCFCs and promote related issues. Through continued public and key stakeholder engagement, ratification of the Kigali Amendment is anticipated to be achieved by April 2024. Although a steering committee to support the NOU is not operational, the Minister of Agriculture, as a member of the Cabinet and Parliament, represents the interests of the National Ozone Action Unit at the various policy levels to support the NOU with the implementation of activities. As one of the lessons learned during the COVID19 pandemic, the NOU will continue the use of various virtual tools to broaden its outreach and visibility including radio and television. The following actions will be undertaken during the new phase: continue to strengthen coordination works of the NOU; continue to implement the licensing and quota system for HCFCs and begin the implementation of a licensing and quota system for HFCs; continue to coordinate and monitor programme activities under the HPMP; work closely with stakeholders in the refrigeration servicing sector including training and capacity development; and implement public awareness campaigns through virtual and print media. During the next phase, the NOU will continue to maintain its timely reporting of country programme and Article 7 data to the Fund and Ozone Secretariats, respectively, and will maintain active participation in the meetings related to the Montreal Protocol and the promotion of women's participation in the refrigeration servicing sector. 
Sustainability and risk assessment
53. The NOU functions under the Ministry of Agriculture through the Hydrometeorological Service under the direct supervision of the Chief Hydrometeorological Office with oversight from the office of the Permanent Secretary. The work programme of the NOU is incorporated within this department and Ministry and is also provided with in-kind support from the Government of Guyana. This integration contributes to the sustainability of the IS project and the framework to assess risks ahead of time and plan for suitable interventions in advance. Additionally, the country provides interim progress reports to the implementing agency as part of the SSFA with the country. These reports allow the country to identify in advance, any issues that is it experiencing or where the activities are not progressing as planned, providing an early indication where UNEP may support, assess, and intervene where necessary. 
Iraq: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Apr-08 & Apr-09
	298,641

	Phase II:
	Apr-13
	240,000

	Phase III:
	May-16
	300,000

	Phase IV:
	Dec-18
	307,200

	Phase V:
	Jul-21
	307,200

		Total:
	1,453,041

	Amount requested for renewal (phase VI) (US $):
	635,904

	Amount recommended for approval for phase VI (US $): 
	635,904

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VI to the Multilateral Fund (US $):
	635,904

	Date of approval of country programme:
	2009

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	108.4

	(c)	Annex E (methyl bromide) (average 1995-1998)
	4.6

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	Not available

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	66.39

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	66.39

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7 
	Not available

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	11,571,667

	Amount disbursed (as at December 2022) (US $):
	10,460,106

	ODS to be phased out (as at June 2023) (ODP tonnes):
	1,490.0

	ODS phased out (as at December 2022) (ODP tonnes):
	1,481.6



54. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	7,611,820

	(b)	Institutional strengthening:
	1,453,041

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	2,506,805

		Total:
	11,571,667

	(d)	HFC activities funded from additional voluntary contributions
	0


Progress report
55. During the implementation of phase V of the IS project, Iraq effectively implemented ODS control measures and the HCFC licensing and quota system; submitted timely country programme and Article 7 data to the relevant Secretariats; participated in regional networks other Montreal Protocol-related meetings.; and conducted extensive public awareness and information dissemination activities to facilitate full access of users and stakeholders to information on ozone layer protection and related non-ODS technologies, to enable a smooth implementation of the phase-out programme. Iraq has successfully implemented phase V and has fully achieved four and partially achieved three of the IS performance objectives.
Plan of action
56. During phase VI, the Ozone Unit will continue to work with all stakeholders and update them on recent developments under the Montreal Protocol and ensure their full engagement in implementing the ongoing HPMP and other Multilateral Fund‑supported activities. The Ozone Unit will continue the effective operation of the HCFC quota and licensing system to ensure full compliance with the agreed HCFC reduction steps, will enforce the updated system that includes HFCs as required under the Kigali Amendment, facilitate the ratification process of the Kigali Amendment and pursue efforts to identify feasible alternatives suitable for high ambient temperature countries with emphasis on the non-in-kind technologies. The Ozone Unit will also intensify its efforts to ensure the proper implementation of remaining activities under stage I of the HPMP to achieve the upcoming phase‑out targets; and will continue raising public and industry awareness and preparing Montreal Protocol reports. 
Sustainability and risk assessment
57. The main risk would be the delayed ratification of the Kigali Amendment and adoption of feasible alternatives for the high ambient temperature conditions. UNEP Compliance Assistance Programme will continue to provide all required support to facilitate the process for the ratification of the Kigali Amendment and thus support the country to prepare and adopt all required policies, regulations, and standards to facilitate full compliance. Support will also continue to ensure timely implementation of the ongoing HPMP and facilitate the approval of the second tranche under stage II to achieve the planned phase‑out targets and lay the groundwork for introducing new alternatives. 
Madagascar: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-99
	70,000

	Phase II:
	Jul-04
	60,700

	Phase III:
	Jul-06
	60,700

	Phase IV:
	Nov-09 & Apr-10
	60,700

	Phase V:
	Jul-12
	60,700

	Phase VI:
	Nov-14
	60,700

	Phase VII:
	Dec-16
	85,000

	Phase VIII:
	Dec-18
	85,000

	Phase IX:
	Jul-21
	85,000

		Total:
	628,500

	Amount requested for renewal (phase X) (US $):
	180,000

	Amount recommended for approval for phase X (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	1999

	Date of approval of HCFC phase-out management plan:
	2010

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	16.6

	(c)	Annex E (methyl bromide) (average 1995-1998)
	2.6

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	1,719,334

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	9.35

	(c)	Annex E, (methyl bromide)
	0.00

		Total:
	9.35

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7 
	1,560,674

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	2,625,252

	Amount disbursed (as at December 2022) (US $):
	2,266,972

	ODS to be phased out (as at June 2023) (ODP tonnes):
	56.0

	ODS phased out (as at December 2022) (ODP tonnes):
	38.2



58. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	568,436

	(b)	Institutional strengthening:
	628,500

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	1,428,316

		Total:
	2,625,252

	(d)	HFC activities funded from additional voluntary contributions
	150,000



Progress report
59. Madagascar's NOU successfully implemented phase IX of the IS project, fully achieving two and partially achieving five out of seven performance objectives. The NOU collected ODS import data and submitted country programme and Article 7 data to the Fund and Ozone Secretariats, respectively; held annual meetings with stakeholders, including the National Ozone Committee, for effective coordination; established a national legislative and regulatory framework to prepare for the ratification of the Kigali Amendment; oversaw training for 180 RAC technicians and 41 customs officers and 11 Environmental Judicial Police Officers; raised awareness about HCFC alternatives, relevant laws and regulations; and actively observed World Ozone Day and engaged in regional network and thematic meetings.
Plan of action
60. In phase X of the IS project, the NOU will focus on: continuing information dissemination and awareness activities; coordinating the implementation of stage II of the HPMP; promoting and enforcing the licensing and quota system, providing importers with annual quota information; establishing the technician certification programme; sustaining monitoring and evaluation efforts; conducting annual stakeholder workshops to promote low-GWP HCFC alternatives; timely data collection and reporting to the Ozone and Fund Secretariats; national-level communication regarding the country's ratification of the Kigali Amendment; and establishing the HFC licensing and quota systems.
Sustainability and risk assessment
61. The Government is actively regulating HCFC in line with Montreal Protocol targets. Training centres have been equipped for technicians, and customs officers are being trained to monitor HCFC and HFC imports and potential illegal trade of these substances. These actions are expected to mitigate risks of project implementation experienced in the past. UNEP as implementing agency continues to support Madagascar in timely project implementation. Despite all challenges, online meetings and training have been effective. The government plans to ban certain HCFC and HFC imports, contributing to a sustainable phase-out. 
Mauritius: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jun-93
	50,000

	Phase II:
	Apr-05
	60,000

	Phase III:
	Nov-07
	46,504

	Phase IV:
	Nov-14
	60,000

	Phase V:
	Dec-16
	85,000

	Phase VI:
	Dec-19
	85,000

	Phase VII:
	Jul-21
	85,000

		Total: 
	471,504

	Amount requested for renewal (phase VIII) (US $):
	180,000

	Amount recommended for approval for phase VIII (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	1993

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.1

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	8.0

	(c)	Annex E, (methyl bromide) (average 1995-1998)
	0.1

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	665,957

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	1.81

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	1.81

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7
	650,471

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	2,832,776

	Amount disbursed (as at December 2022) (US $):
	2,239,987

	ODS to be phased out (as at June 2023) (ODP tonnes):
	60.8

	ODS phased out (as at December 2022) (ODP tonnes):
	62.9



62. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	1,511,851

	(b)	Institutional strengthening:
	471,504

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	849,421

		Total:
	2,832,776

	(d)	HFC activities funded from additional voluntary contributions
	0



Progress report
63. During phase VII of the IS project for Mauritius, the NOU in consultation with relevant stakeholders ensured that implementation of the HPMP was effectively and properly done. The NOU also coordinated training for RAC technicians and customs officers and reported Article 7 and country programme data to the Ozone and Fund Secretariats, respectively, in a timely manner. The Environment Protection Act was in the process of being amended during the phase to make provisions for regulation specific to the introduction of a quota system for HFCs, which took longer than expected. Mauritius fully achieved five of the seven IS indicators, and partially achieved two.
Plan of action
64. The NOU under the supervision of the Department of Environment, and in collaboration with stakeholders and partners, will continue the coordination and implementation of the IS project and the HPMP, as well as initiate HFC phase-down activities under the Kigali Amendment. The country will develop and implement its KIP to ensure sustained compliance with Montreal Protocol reduction targets, including consideration of gender issues, following the Multilateral Fund gender policy. Further, the NOU, in collaboration with the Mauritius Institute of Training and Development, will continue implementing training programmes for the RAC technicians; training of newly‑recruited customs officers, and other enforcement agencies to support the implementation and enforcement of regulations including control measures of HCFCs and HFCs; and dialogue with regional network members and participate in the regional network and Montreal Protocol meetings. The NOU will continue its awareness‑raising programme through mass media, NGOs, workshops, and distribution of awareness materials such as flyers, brochures, pamphlets and others to the industry and other stakeholders.
Sustainability and risk assessment
65. The Ministry of Environment, Solid Waste Management, and Climate Change provides in-kind contribution to all projects and activities implemented under the Montreal Protocol, in terms of man-power and other logistics. The projects are also subjected to periodic internal and external audits to ensure adequate risk avoidance and management.  
Micronesia (Federated States of): Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02
	31,239

	Phase II:
	Jul-06 & Jul-09
	41,333

	Phase III:
	Jul-10
	60,000

	Phase IV:
	Jul-12
	60,000

	Phase V:
	May-14
	55,000

	Phase VI:
	Dec-16
	84,031

	Phase VII:
	Dec-19
	85,000

	Phase VIII:
	Nov-21
	85,000

		Total:
	501,603

	Amount requested for renewal (phase IX) (US $):
	180,000

	Amount recommended for approval for phase IX (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	2002

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.2

	(c)	Annex E, (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	13,600

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.0

	(b)	Annex C, Group I (HCFCs)
	0.07

	(c)	Annex E (methyl bromide)
	0.0

		Total:
	0.07

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7
	15,017

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	942,986

	Amount disbursed (as at December 2022) (US $):
	665,770

	ODS to be phased out (as at June 2023) (ODP tonnes):
	1.2

	ODS phased out (as at December 2022) (ODP tonnes):
	0.0



66.  Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	0

	(b)	Institutional strengthening:
	501,603

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	441,383

		Total:
	942,986

	(d)	HFC activities funded from additional voluntary contributions
	50,000



Progress report
67. During phase VIII, the Federated States of Micronesia (FSM) demonstrated a high level of national organisation that the Government has achieved through the NOU and the IS project. The combined efforts of the NOU, Senior Management, College of Micronesia, and the four RAC associations all contributed to the sustained efforts in meeting the country’s obligations to the Montreal Protocol and expediting the implementation of phase VIII. During the phase, the country fulfilled its data reporting obligations to the Ozone and Fund Secretariats in a timely manner and sustained compliance with the HCFC reduction targets. Compliance was sustained through a holistic approach comprised of legislative measures, HCFC/HFC licensing system, HCFC quota system, transitioning to an e-licensing system and monitoring of ODS import, capacity building, involvement of the National Ozone Committee and the RAC association as well as public sector awareness‑raising activities. The Federated States of Micronesia successfully achieved all seven of the IS performance objectives.  
Plan of action
68. Phase IX will include: implementation of the e-licensing system for HCFC and HFC; adoption of the Pacific Harmonized Commodity Description and Coding System 2022 (PACHS22) to have individual HS code for HFCs and blends; timely submission of Article 7 and country programme data; active engagement of the National Ozone Committee and RAC Association in the implementation of Montreal Protocol; coordination with stakeholders for the implementation of the HPMP; organisation of the World Ozone Day celebration and development of awareness materials; and participation in regional and international meetings. Gender mainstreaming will be integrated into implementation of the upcoming phase and other Multilateral Fund-supported projects in the country. 
Sustainability and risk assessment
69. The IS project can be successfully implemented in FSM under conditions of stable funding. Stakeholders, relevant associations, and ministries and agencies actively participate in the development of recommendations and amendments to laws and regulations, as well as public awareness and promotional activities. The NOU is continuously guided by the National Ozone Committee which is comprised of key inline ministries, the RAC sector and other relevant agencies. Since FSM has yet to adopt and put the WCO HS 2022 into effect, there are risks that HFC imports will not be accurately identified and recorded in the Customs system. There will be some difficulties with inaccurate customs declarations due to the different types of HFCs as opposed to one type of HCFC that is currently under the NOU’s and Customs' surveillance. Therefore, it is crucial that the NOU strengthens cooperation with Customs in monitoring HFCs through targeted awareness for importers and customs brokers on identifying HFCs being imported with their proper HS codes. 
Paraguay: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Feb-97
	66,300

	Phase II:
	Dec-00
	44,200

	Phase III:
	Apr-03
	57,460

	Phase IV:
	Nov-07
	60,000

	Phase V:
	Jul-10
	60,000

	Phase VI:
	Apr-12
	60,000

	Phase VII:
	May-14
	60,000

	Phase VIII:
	Dec-16
	80,062

	Phase IX:
	Dec-18
	78,260

	Phase X:
	Nov-21
	85,000

		Total:
	651,282

	Amount requested for renewal (phase XI) (US $):
	180,000

	Amount recommended for approval for phase XI (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XI to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	1997

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	18.0

	(c)	Annex E (methyl bromide)
	0.9

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	1,684,582

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	9.79

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	9.79

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7
	1,563,023

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	4,104,893

	Amount disbursed (as at December 2022) (US $):
	3,684,569

	ODS to be phased out (as at June 2023) (ODP tonnes):
	345.1

	ODS phased out (as at December 2022) (ODP tonnes):
	340.4



70. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	1,441,005

	(b)	Institutional strengthening:
	651,282

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	2,012,606

		Total:
	4,104,893

	(d)	HFC activities funded from additional voluntary contributions
	150,000


Progress report
71. The implementation of Montreal Protocol activities in Paraguay continued with good progress under phase X of the IS project. The NOU worked to achieve broad consensus on revised national SDG legislation; an operational ODS import/export licensing and HCFC quota system is in place; legislation has been updated to comply with obligations under the Kigali Amendment and include HFC substances within the licensing system; and Article 7 and country programme data were submitted to the Ozone and Fund Secretariats, respectively, accurately and in a timely manner. The enabling activities project for HFC phase‑down was completed in June 2022 and NOU staff coordinated activities under the final tranches of stage I of the HPMP as well as the first tranche of stage II. The labor competency standard has been validated for the management of flammable refrigerants and the NOU hosted the committee on good refrigeration practices. Companies were encouraged to adopt good refrigeration practices and an awareness raising campaign was implemented for the public. The country encouraged the continued participation of stakeholders in the implementation of the Montreal Protocol at the national level, and it organized the World Ozone Day celebrations, as well as participated in regional network events. 
Plan of action
72. With the support of the IS project, the NOU will continue activities such as implementation of the HCFC/HFC license and quota system, the development of a work plan with customs to control illegal traffic by updating risk profiles, while ensuring gender mainstreaming and facilitating access to and use of new alternative substances and technologies in the country. The NOU will continue the coordination with customs to ensure an effective surveillance of international trade of all Montreal Protocol controlled substances, facilitating the involvement of main country stakeholders (importers, exporters, suppliers, technicians, and end-users) in the implementation of the HPMP and ultimately in the reduction of the national HCFC/HFC demand. The NOU will also continue with trainings of main actors, continue the participation via the committee on good refrigeration practices and support the implementation of the Kigali Amendment roadmap to comply with the phase-out and phase-down targets of Paraguay. Public awareness campaigns through social media, the RAC association and end-users will continue especially in cooperation with the education sector; and celebrations of World Refrigeration Day and World Ozone Day as well as during national events will include a focus on gender. 
Sustainability and risk assessment
73.  The NOU works together with Customs agency to ensure the sustainability of the activities to control the substances controlled by Montreal Protocol. The country has successfully trained refrigeration technicians on good refrigeration practices and safe handling of alternative substances, gained stakeholder support, and it is committed to the formulation of norms/standards for the safe handling of alternative refrigerants. In addition, it has carried out consultation meetings and raised public awareness on ozone layer protection. UNEP as implementing agency will continue to support Paraguay to implement the HPMP, and IS project and as well as the KIP to meet the HCFC phase-out and HFC phase-down targets, ensuring gender mainstreaming in implementation of the projects, and seek the necessary means to guarantee sustainability and reducing risks. 
Saint Lucia: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Feb-97
	36,580

	Phase II:
	Mar-00
	24,400

	Phase III:
	Jul-02
	31,200

	Phase IV:
	Jul-04
	30,800

	Phase V:
	Jul-06
	60,000

	Phase VI:
	Jul-08
	60,000

	Phase VII:
	Dec-10
	60,000

	Phase VIII:
	Dec-12
	60,000

	Phase IX:
	Nov-14
	60,000

	Phase X:
	Nov-17
	85,000

	Phase XI:
	Dec-20
	85,000

		Total:
	592,980

	Amount requested for renewal (phase XII) (US $):
	180,000

	Amount recommended for approval for phase XII (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XII to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	1995

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.00

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	1.09

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.00

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	83,735

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	0.27

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	0.27

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7
	120,179

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	1,870,260

	Amount disbursed (as at December 2022) (US $):
	1,383,833

	ODS to be phased out (as at June 2023) (ODP tonnes):
	11.9

	ODS phased out (as at December 2022) (ODP tonnes):
	11.5



74. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	409,225

	(b)	Institutional strengthening:
	592,980

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	868,055

		Total:
	1,870,260

	(d)	HFC activities funded from additional voluntary contributions
	95,000



Progress report
75. Under phase XI of the IS project for Saint Lucia, the country experienced some delays in its implementation owing to the lingering effects of the COVID-19 pandemic and administrative challenges within the NOU and Government. However, with the support of UNEP, the NOU engaged with technical and political intergovernmental focal points towards the implementation of the Montreal Protocol project portfolios resulting in implementation of activities and the achievement of the objectives. Saint Lucia maintained compliance with the Montreal Protocol and sustained the 35 per cent reduction in HCFCs met by 1 January 2020, as stipulated by the Montreal Protocol phase out schedule. The NOU continued implementation of ODS legislation and regulation to control and monitor ODS consumption and took measures towards controlling HFCs; data collection, analysis, and submission; consultations and coordination with national agencies/stakeholders; coordination of HPMP implementation activities as scheduled; awareness raising and information exchange; and regional cooperation and participation in Montreal Protocol meetings. During the phase, Saint Lucia fully achieved six of the seven IS performance objectives, and partially achieved one.
Plan of action
76. During phase XII, the Government will continue to support activities to phase out HCFCs and promote related issues. As one of the lessons learned during the COVID-19 pandemic, the NOU will continue to increase the use of various virtual tools to broaden its outreach and visibility including radio and television. The NOU also plans to strengthen its public education and awareness activities to ensure all stakeholders understand their roles in the HCFC phase‑out and HFC phase-down processes. Additionally, climate protection and energy efficiency will continue to be considered when making decisions regarding alternative technologies. The NOU will continue to sensitize Saint Lucians about ozone layer linkages to climate change and energy efficiency and the importance of exploring alternatives that result in climate and energy benefits in line with and maintaining compliance with the Kigali Amendment. The following actions will be undertaken during the new phase: continue to strengthen coordination between the NOU and other national stakeholders; continue to implement the licensing and quota system for HCFCs and begin the implementation of a licensing system for HFCs; continue to coordinate and monitor programme activities under stage II of the HPMP and projects related to HFC phase-down; work closely with stakeholders in the refrigeration servicing sector, including on training and capacity development; and implement public awareness campaigns through virtual and print media. During the next phase, the NOU will maintain its timely country programme and Article 7 data reporting and will maintain active participation in the meetings related to the Montreal Protocol and the promotion of women's participation in the refrigeration servicing sector. 
Sustainability and risk assessment
77. The NOU functions under the Sustainable Development and Environment Division of the Department of Sustainable Development with oversight from the office of the Permanent Secretary and is monitored quarterly by various monitoring arms of the Government including the Customs and Excise Department, the Import Monitoring Unit of the Department of Commerce and the National Air‑conditioning and Refrigeration Association (NARA). The work programme of the NOU is incorporated within these departments, ministries and organizations and is bolstered with in-kind support from the Government of Saint Lucia. In addition, the NOU has established a Montreal Protocol Technical Working Group (MP‑TWG) comprising the full range of stakeholders from the public and private sectors and non‑governmental organisations involved in matters related to environmental protection in general, and ozone layer protection in particular. This multi-level integration contributes to the sustainability of the IS project and HPMP and the framework to assess risks ahead of time and plan for suitable interventions in advance. Additionally, UNEP as implementing agency requires interim reports as part of the SSFA with the country. These reports allow the country to identify in advance, any issues that it is experiencing or where the activities are not progressing as planned, providing an early indication where UNEP may support, assess, and intervene where necessary. 
Solomon Islands: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02
	20,250

	Phase II:
	Jul-06 & Nov-07
	36,833

	Phase III:
	Nov-09 & Apr-10
	60,000

	Phase IV:
	Jul-11
	60,000

	Phase V:
	Jul-13
	60,000

	Phase VI:
	May-15
	60,000

	Phase VII:
	Nov-17
	85,000

	Phase VIII:
	May-19
	85,000

	Phae IX:
	Nov-21
	85,000

		Total:
	552,083

	Amount requested for renewal (phase X) (US $):
	180,000

	Amount recommended for approval for phase X (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	2002

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	2.0

	(c)	Annex E, (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	69,516

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	0.09

	(c)	Annex E, (methyl bromide)
	0.00

		Total:
	0.09

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7
	29,625

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	1,260,407

	Amount disbursed (as at December 2022) (US $):
	917,389

	ODS to be phased out (as at June 2023) (ODP tonnes):
	3.5

	ODS phased out (as at December 2022) (ODP tonnes):
	0.0



78. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	0

	(b)	Institutional strengthening:
	552,083

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	708,324

		Total:
	1,260,407

	(d)	HFC activities funded from additional voluntary contributions
	95,000



Progress report
79. Phase IX of the IS project for Solomon Islands demonstrated the high level of national organization that the Government has achieved through the NOU. The NOU under the Energy and Rural Electrification Division of the Ministry of Mines, Energy and Rural Electrification (MMERE) established working mechanisms with the public and private sector stakeholders; an e‑licensing system was in the testing stage during this phase and is anticipated to be launched by the end of November 2023. The country fulfilled its data reporting obligations to the Ozone and Fund Secretariats in a timely manner. Solomon Islands sustained compliance with its HCFC reduction targets. Compliance was sustained through a holistic approach comprising of legislative measures, HCFC licensing and quota system, monitoring of ODS import, capacity building, involvement of the National Ozone Committee, Solomon Islands National University and the Refrigeration and Air-conditioning Association as well as public sector awareness‑raising activities. All seven IS performance objectives were achieved during this phase.  
Plan of action
80. Phase X will include: implementing the new e-licensing system for HCFCs and HFCs; implementation of the Pacific Harmonized Commodity Description and Coding System 2022; timely submission of Article 7 and country programme data; active engagement of the National Ozone Committee and RAC association in the implementation of the Montreal Protocol; coordination with stakeholders for the implementation of the HPMP; organisation of the World Ozone Day and development of information materials; and participation in regional and international meetings. Gender mainstreaming will be integrated into the implementation of the project. 
Sustainability and risk assessment
81. The IS project can be successfully implemented in Solomon Islands under conditions of stable funding. Stakeholders, relevant associations, ministries and agencies actively participate in the development of recommendations and amendments to laws and regulations, as well as public awareness and promotional activities. The NOU is continuously guided by the National Ozone Steering Committee which is comprised of key inline ministries, the RAC sector and other relevant agencies. Given that Solomon Islands has adopted the PACHS2022, there will be risks of misclassification of HS Codes with ODS and HFC imports. Therefore, it is crucial that the NOU continue to work in collaboration with Customs including quarterly reconciliation of import statistics in monitoring HCFCs and HFCs through targeted awareness for importers and customs brokers on identifying HCFC/HFCs being imported with their proper HS codes. 
Somalia: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02 and Dec-04 and Nov-09 and Apr-10
	111,995

	Phase II:
	Dec-12
	60,000

	Phase III
	Dec-16
	84,470

	Phase IV:
	May-19
	85,000

	Phase V:
	Jul-21
	85,000

	Total:
	426,465

	Amount requested for renewal (phase VI) (US $):
	180,000

	Amount recommended for approval for phase VI (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VI to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	2009

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	45.1

	(c)	Annex E, (methyl bromide) (average 1995-1998)
	0.5

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	1,276,672

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	10.18

	(c)	Annex E, (methyl bromide)
	0.00

		Total:
	10.18

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7
	348,650

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	1,302,750

	Amount disbursed (as at December 2022) (US $):
	994,146

	ODS to be phased out (as at June 2023) (ODP tonnes):
	1.8

	ODS phased out (as at December 2022) (ODP tonnes):
	1.8





82. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	311,665

	(b)	Institutional strengthening:
	426,465

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	564,620

		Total:
	1,302,750

	(d)	HFC activities funded from additional voluntary contributions
	150,000



Progress report
83. Phase VI of the IS project for Somalia has been implemented according to the plan and has fully achieved six out of seven performance objectives. During the reporting period, the NOU implemented the required activities including enforcement of the ODS regulations through the implementation of a licensing and quota system. The NOU further embarked on an awareness raising programme, trained Customs officers, clearing agents, Border Control Police, and refrigeration technicians. Additionally, the ODS regulations were under review to include HFCs.
Plan of action
84. The NOU is the responsible authority for coordination of the implementation of the IS, HPMP and HFC phase-down. The country will endeavor to implement its action plan to ensure sustained compliance with the Montreal Protocol. The NOU will ensure collaboration with stakeholders (customs, local technical institutions) and implementing agencies to control ODS consumption in the country; continue with the training programme for the technicians in the refrigeration sector; organize the training of newly‑recruited and remaining Customs officers to support the implementation and enforcement of ODS regulations, including control measures of HCFCs. The NOU will also continue with the awareness-raising programme through mass media, NGOs, and workshops; continue the training of RAC technicians and customs officers; and implement the licensing and quota system for HCFCs to meet and sustain the 67.5 per cent reduction in 2025.
Sustainability and risk assessment
85. Two employees of the Government of Somalia are tasked with the responsibility of monitoring the project and report on any issues that may affect the continued operation of the project. This is over and above the role of the National Ozone Steering Committee. The project is subjected to periodic internal and external audits to ensure adequate risk avoidance and management.
Timor-Leste: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-08
	40,000

	Phase II:
	Jul-10 & Jul-11
	60,000

	Phase III:
	Apr-13
	60,000

	Phase IV:
	May-16
	85,000

	Phase V:
	Dec-19
	85,000

	Phase VI:
	Nov-21
	85,000

		Total:
	415,000

	Amount requested for renewal (phase VII) (US $):
	180,000

	Amount recommended for approval for phase VII (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VII to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	2009

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.1

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.5

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.2

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	Not available

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.00

	(b)	Annex C, Group I (HCFCs)
	0.12

	(c)	Annex E (methyl bromide)
	0.00

		Total:
	0.12

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7
	Not available

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	1,118,799

	Amount disbursed (as at December 2022) (US $):
	874,081

	ODS to be phased out (as at June 2023) (ODP tonnes):
	0.2

	ODS phased out (as at December 2022) (ODP tonnes):
	0



86. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	199,270

	(b)	Institutional strengthening:
	415,000

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	504,529

		Total:
	1,118,799

	(d)	HFC activities funded from additional voluntary contributions
	0



Progress report
87. Phase VI of the IS project for Timor‑Leste demonstrated the high level of national organization that the Government has achieved through the NOU. The NOU continued to enforce the licensing and quota system in accordance with the Decree-Law No. No. 36/2012 and strengthened collaboration with the Directorate General for Customs to enforce the regulation, in particular the National Single Window System and inspection of all imported refrigerants during import clearance, strengthening the use of accurate HS code and developing the risk profiling for ODS and ODS‑based equipment control. The country fulfilled its data reporting obligations to the Ozone and Fund Secretariats in a timely manner and has sustained compliance with the HCFC reduction targets. Compliance was sustained through a holistic approach comprising of legislative measures, HCFC licensing and quota system, monitoring of ODS import, capacity building, involvement of the National Ozone Committee and the RAC sector, as well as public sector awareness raising activities. The NOU continued to take the lead role in the ratification of the Kigali Amendment which is still in process. Timor‑Leste fully achieved four of the IS performance objectives and partially met three.  
Plan of action
88. The plan of action for phase VII includes: implementation of the licensing system for HCFCs and HFCs; implementation of activities as obligated under the Kigali Amendment; timely submission of Article 7 and country programme data; active engagement of National Ozone Committee and the RAC association in the implementation of Montreal Protocol; coordination with stakeholders for the implementation of the HPMP; organisation of the World Ozone Day celebrations and development of awareness materials; and participation in regional and international meetings. Gender mainstreaming will be integrated into the implementation of the project. 
Sustainability and risk assessment
89. The IS project can be successfully implemented in Timor-Leste under conditions of stable funding. Stakeholders, relevant associations, and ministries and agencies actively participate in the development of recommendations and amendments to laws and regulations, as well as public awareness and promotional activities. The NOU is continuously guided by the National Ozone Committee which is comprised of key inline Ministries, the RAC sector and other relevant agencies. Since Timor‑Leste has yet to ratify the Kigali Amendment, there is a risk of the country becoming non-compliant. Therefore, the NOU will need to work in close collaboration with key stakeholders to ensure timely preparation, finalization and ratification of the Kigali Amendment. 
Togo: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-97
	70,000

	Phase II:
	Jul-02
	60,667

	Phase III:
	Dec-04
	60,667

	Phase IV:
	Nov-06
	60,666

	Phase V
	Nov-08
	60,666

	Phase VI
	Dec-10
	60,666

	Phase VII:
	Dec-12
	60,448

	Phase VIII:
	Nov-14
	60,632

	Phase IX:
	Dec-16
	85,000

	Phase X:
	Dec-18
	85,000

	Phase XI:
	Jul-21
	85,000

		Total:
	749,412

	Amount requested for renewal (phase XII) (US $):
	180,000

	Amount recommended for approval for phase XII (US $): 
	180,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XII to the Multilateral Fund (US $):
	180,000

	Date of approval of country programme:
	1995

	Date of approval of HCFC phase-out management plan:
	2010

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(b)	Annex C, Group I (HCFCs) (average 2009-2010)
	20.0

	(c)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	(d)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	1,124,896

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex B, Group III (methyl chloroform)
	0.0

	(b)	Annex C, Group I (HCFCs)
	6.71

	(c)	Annex E (methyl bromide)
	0.0

		Total:
	6.71

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7
	852,133

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	3,029,487

	Amount disbursed (as at December 2022) (US $):
	2,488,621

	ODS to be phased out (as at June 2023) (ODP tonnes):
	53.2

	ODS phased out (as at December 2022) (ODP tonnes):
	44.5



90. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	706,028

	(b)	Institutional strengthening:
	749,412

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	1,574,047

		Total
	3,029,487

	(d)	HFC activities funded from additional voluntary contributions
	150,000



Progress report
91. Togo's NOU excelled in implementing phase XI of the IS project, fully achieving all seven of the performance objectives. The NOU collected ODS and HFC import data and submitted country programme and Article 7 data to the Fund and Ozone Secretariats, respectively; held annual meetings with stakeholders, including the National Ozone Committee, for effective coordination; and oversaw training for 673 RAC technicians and 372 customs officers under the HPMP. Ongoing activities included raising awareness about HCFC alternatives, relevant laws and regulations. Togo actively observed World Ozone Day and engaged in Montreal Protocol-related meetings. 
Plan of action
92. In Phase XII of the IS project, the NOU will focus on: continuing information dissemination and awareness activities; coordinating the implementation of stage II of the HPMP; promoting and enforcing the licensing and quota system, providing importers with annual quota information; establishing the technician certification programme; sustaining monitoring and evaluation efforts; conducting annual stakeholder workshops to promote low-GWP HCFC alternatives; timely data collection and reporting to the Ozone and Fund Secretariats; and preparation and submission of the overarching strategy for the KIP.
Sustainability and risk assessment
93. The IS project can be successfully implemented in Togo under conditions of stable funding. Stakeholders, relevant associations, ministries and agencies actively participate in the development of recommendations and amendments to laws and regulations, as well as public awareness and promotional activities. The NOU is continuously guided by the National Ozone Steering Committee which is comprised of key line Ministries, RAC sector and other relevant agencies.  
Yemen: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-98
	120,000

	Phase II:
	Dec-01
	118,000

	Phase III:
	Dec-03
	103,609

	Phase IV:
	Nov-05 & Apr-06
	170,000

	Phase V
	Nov-07
	169,608

	Phase VI
	Nov-09
	169,999

	Phase VII:
	Dec-12
	110,251

	Phase VIII:
	Nov-14
	169,999

		Total:
	1,131,466

	Amount requested for renewal (phase IX) (US $):
	450,429

	Amount recommended for approval for phase IX (US $): 
	450,429

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	450,429

	Date of approval of country programme:
	1998

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes for ODS/CO2-eq tonnes for HFCs):
	

	(a)	Annex A, Group I (CFCs) (average 1995-1997)
	1,796.1

	(b)	Annex A, Group II (halons) (average 1995-1997)
	140.0

	(c)	Annex B, Group II (carbon tetrachloride) (average 1998-2000)
	0.0

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.9

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	158.2

	(f)	Annex E (methyl bromide) (average 1995-1998)
	54.5

	(g)	Annex F (HFCs) (average 2020-2022 plus 65% of HCFC baseline)
	Not available

	Latest reported ODS consumption (2022) (ODP tonnes) as per Article 7:
	

	(a)	Annex A, Group I (CFCs)
	0.00

	(b)	Annex A, Group II (halons)
	0.00

	(c)	Annex B, Group II (carbon tetrachloride)
	0.00

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	93.07

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	93.07

	Latest reported Annex F (HFCs) consumption (2022) (CO2-eq tonnes) as per Article 7
	Not available

	Year of reported country programme implementation data:
	2022

	Amount approved for projects (as at June 2023) (US $):
	6,694,665

	Amount disbursed (as at December 2022) (US $):
	6,524,666

	ODS to be phased out (as at June 2023) (ODP tonnes):
	1,105.6

	ODS phased out (as at December 2022) (ODP tonnes):
	493.9



94. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)	Investment projects:
	2,612,856

	(b)	Institutional strengthening:
	1,131,466

	(c)	Project preparation, technical assistance, training and other non-investment projects:
	2,950,343

		Total:
	6,694,665

	(d)	HFC activities funded from additional voluntary contributions
	0



Progress report
95. Although phase VIII of the IS project for Yemen was approved at the end of 2014 to be implemented in 2015-2016, the country was unable to implement it due to civil war and the cessation of NOU activities until 2020. In 2021, the new Government was established and arrangements for reinstating the NOU functions started. Despite the warfare complications on the ground, Yemen in collaboration with UNEP as implementing agency, successfully implemented phase VIII of the IS project during 2022 and 2023. Adopting an on-site focal points enabled the NOU to overcome security and movement difficulties on the ground, and monitor and control imports, uses and illegal trade of ODSs and facilitate the Article 7 and country programme data reporting, which were mostly done in a timely manner for 2020-2021.  
Plan of action
96. Despite political tensions, the NOU, as per its roles, will design a coordination framework during phase IX to continue and expand its collaborations with relevant stakeholders in Government and private sectors. The NOU will intensify and facilitate discussions on the Kigali Amendment among relevant ministries, government agencies and institutions and relevant HFC sectors, to press toward ratification of the Kigali Amendment, as well as to set up procedures for HFC monitoring and control and reporting voluntarily. The NOU will continue producing awareness materials and programmes for the public and industry and preparing Montreal Protocol reports. 
Sustainability and risk assessment
97. The NOU will enhance support to the focal points in the regions by building their capacities to overcome the risk of non-compliance toward the 2025 Montreal Protocol target for reductions in HCFC imports, on one hand. On the other hand, the NOU will speed up the actions toward setting up and enforcing provisions of a ban on the import of HCFC-based equipment.  
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المرفق الثاني
مسودة الآراء التي أعربت عنها اللجنة التنفيذية المعنية بتجديد مشروعات التعزيز المؤسسي 
المقدمة إلى الاجتماع الثالث والتسعين
أنتيغوا وبربودا
1. [bookmark: _Hlk151837048][bookmark: _Hlk151837474]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لأنتيغوا وبربودا (المرحلة الخامسة) وأشارت مع التقدير إلى أن حكومة أنتيغوا وبربودا قد أبلغت أمانتي الصندوق والأوزون، على التوالي، ببيانات البرنامج القطري وبيانات المادة 7، مما يشير إلى أن البلد ممتثل لبروتوكول مونتريال. ولاحظت اللجنة أيضا أن الحكومة قامت برصد تنفيذ نظام التراخيص والحصص ومراقبة حدودها للحماية من التجارة غير المشروعة. ورحبت اللجنة بقيام الحكومة بإنشاء لجنة استشارية مستقلة للرقابة والتي من المتوقع أن تقوم بدور أكبر في توجيه ودعم وحدة الأوزون الوطنية في تنفيذ الأنشطة. وتأمل اللجنة أن تواصل حكومة أنتيغوا وبربودا تنفيذ مشروع التعزيز المؤسسي بنجاح وتحافظ على ما قامت به من إنجازات في مجال التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية.
بنن 
2. [bookmark: _Hlk151837587]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لبنن وأثنت على البلد لتقديمه بيانات المادة 7 وبيانات البرنامج القطري لعامي 2021 و2022 إلى أمانتي الأوزون والصندوق، على التوالي، مشيرة إلى أن البلد ممتثل لبروتوكول مونتريال. وأقرت اللجنة أيضا بالخطوات الكبيرة التي قطعتها بنن في التخلص التدريجي من استهلاك المواد المستنفدة للأوزون أثناء فترة المشروع من خلال إنفاذ ضوابط على واردات المواد المستنفدة للأوزون من خلال نظام التراخيص والحصص وتوفير التدريب لموظفي الجمارك وفنيي التبريد. وتعرب اللجنة عن تقديرها لجهود بنن المبذولة في الحد من استهلاك المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية، وتتطلع إلى استمرار البلد في التنفيذ الناجح لخطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية ومشروع التعزيز المؤسسي، بهدف خفض استهلاك المواد الهيدروكلوروفلوروكربونية بنسبة 67.5 في المئة بحلول 1 يناير/كانون الثاني 2025، على النحو المنصوص عليه في بروتوكول مونتريال. 
بوليفيا (دولة - المتعددة القوميات)
3. [bookmark: _Hlk151837997][bookmark: _Hlk151838533][bookmark: _Hlk151838206]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لبوليفيا (دولة - المتعددة القوميات) (المرحلة الثانية عشرة) وأشارت مع التقدير إلى أن حكومة بوليفيا (دولة - المتعددة القوميات) قد أبلغت عن بيانات البرنامج القطري والمادة 7 بيانات إلى أمانتي الصندوق والأوزون، على التوالي، مشيرة إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. ولاحظت اللجنة كذلك أن البلد قد اتخذ خطوات للتخلص التدريجي من استهلاك المواد المستنفدة للأوزون، بما في ذلك تنفيذ ضوابط على واردات المواد الهيدروكلوروفلوروكربونية من خلال نظام التراخيص والحصص، وتدريب موظفي الجمارك وفنيي التبريد. كما أشارت اللجنة مع التقدير إلى الأنشطة التي بدأت لتسهيل تنفيذ تعديل كيغالي. وأقرت اللجنة بالجهود المطلوبة والتحديات التي تواجهها حكومة بوليفيا (دولة - المتعددة القوميات)، ولذلك تأمل أن تواصل الحكومة خلال السنوات الثلاث القادمة تنفيذ المرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية، ومشروع التعزيز المؤسسي، والتقدم المحرز في إعداد خطة كيغالي لتنفيذ المواد الهيدروفلوروكربونية بطريقة فعالة لتحقيق تخفيض بنسبة 65 في المئة في استهلاك المواد الهيدروكلوروفلوروكربونية بحلول 1 يناير/ كانون الثاني 2025 ووضع الأساس للتخفيض التدريجي من المواد الهيدروفلوروكربونية بموجب تعديل كيغالي.
بوركينا فاسو
4. [bookmark: _Hlk151839120][bookmark: _Hlk151839092]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لبوركينا فاسو (المرحلة الخامسة عشرة) وأشارت مع التقدير إلى أن الحكومة قد أبلغت أمانتي الصندوق والأوزون، على التوالي، بيانات البرامج القطرية وبيانات المادة 7 إلى أمانتي الصندوق والأوزون، مما يشير إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. وأقرت اللجنة أيضاً بالخطوات الكبيرة التي قطعتها بوركينا فاسو في التخلص التدريجي من استهلاك المواد المستنفدة للأوزون خلال فترة المشروع من خلال إنفاذ ضوابط على واردات المواد المستنفدة للأوزون من خلال نظام التراخيص والحصص وتوفير التدريب لموظفي الجمارك وفنيي التبريد. وتعرب اللجنة عن تقديرها لجهود بوركينا فاسو المبذولة في خفض استهلاك المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية، وتتطلع إلى استمرار البلد في التنفيذ الناجح لخطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية ومشروع التعزيز المؤسسي، لتحقيق التخفيض بنسبة 67.5 في المئة في استهلاك المواد الهيدروكلوروفلوروكربونية بحلول 1 يناير/ كانون الثاني 2025.
جزر كوك
5. [bookmark: _Hlk151839157][bookmark: _Hlk151839218][bookmark: _Hlk151839648]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لجزر كوك (المرحلة السابعة) وأشارت مع التقدير إلى أن حكومة جزر كوك قد أبلغت أمانتي الصندوق والأوزون، على التوالي، ببيانات البرنامج القطري وبيانات المادة 7، مشيرة إلى أن البلاد ممتثلة لبروتوكول مونتريال. ولاحظت اللجنة أن الحكومة نفذت التوصيات الصادرة عن التحقق من استهلاك المواد الهيدروكلوروفلوروكربونية لزيادة تعزيز الرقابة على تجارة المواد الهيدروفلوروكربونية والامتثال المستمر لالتزامات التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية بموجب بروتوكول مونتريال والحد الأقصى للاستهلاك المسموح به على النحو المتفق عليه مع اللجنة. وتأمل اللجنة أن تواصل حكومة جزر كوك تنفيذ مشروع التعزيز المؤسسي بنجاح وتحافظ على إنجازات التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية وتبدأ في التخفيض التدريجي للمواد الهيدروفلوروكربونية على النحو المنصوص عليه في تعديل كيغالي.
دومينيكا
6. [bookmark: _Hlk151839742]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لدومينيكا (المرحلة السابعة) وأعربت عن تقديرها لحكومة دومينيكا لإبلاغها بيانات البرامج القطرية وبيانات المادة 7 إلى أمانتي الصندوق والأوزون، على التوالي، مما يشير إلى أن البلاد ممتثلة لبروتوكول مونتريال. وأقرت اللجنة بالتحديات والصعوبات التي واجهتها البلاد في تنفيذها بسبب الآثار المتبقية لإعصار ماريا والتي تفاقمت بسبب جائحة كوفيد-19 والتحديات الإدارية داخل وحدة الأوزون الوطنية والحكومة. وأعربت اللجنة عن تقديرها لتفاني موظف الأوزون الجديد ووحدة الأوزون الوطنية المعاد تنظيمها وكذلك للعمل الذي تم إنجازه لمعالجة التأخيرات. وشجعت اللجنة الحكومة على الاستفادة من التدابير المتخذة لضمان احتفاظ البلاد بالزخم في سعيه للبقاء ممتثلا لبروتوكول مونتريال وتنفيذ الأنشطة في إطار المرحلة الأولى من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية وأنشطة التعزيز المؤسسي القادمة.


غابون
7. [bookmark: _Hlk151840030][bookmark: _Hlk151840684]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لغابون (المرحلة الثانية عشرة) وأشارت مع التقدير إلى أن الحكومة أبلغت بيانات البرامج القطرية وبيانات المادة 7 إلى أمانتي الصندوق والأوزون، على التوالي، مشيرة إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. واعترفت اللجنة أيضاً بالخطوات الكبيرة التي قطعتها غابون في التخلص التدريجي من استهلاك المواد المستنفدة للأوزون خلال فترة المشروع، بما في ذلك عن طريق إنفاذ ضوابط على واردات المواد المستنفدة للأوزون من خلال نظام التراخيص والحصص وتوفير التدريب لموظفي الجمارك. وأعربت اللجنة عن تقديرها لجهود غابون المبذولة في خفض استهلاك المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية، وتتطلع قدما إلى استمرار البلد في التنفيذ الناجح لخطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية ومشروع التعزيز المؤسسي لديه، لتحقيق التخفيض بنسبة 67.5 في المئة في استهلاك المواد الهيدروكلوروفلوروكربونية بحلول 1 يناير/ كانون الثاني2025، على النحو المطلوب بموجب بروتوكول مونتريال.
غيانا
8. [bookmark: _Hlk151840798]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لغيانا (المرحلة التاسعة) وأعربت عن تقديرها لحكومة غيانا لإبلاغها بيانات البرامج القطرية وبيانات المادة 7 إلى أمانتي الصندوق والأوزون، على التوالي. مشيرة إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. وأقرت اللجنة بالتحديات والصعوبات التي واجهتها البلاد في تنفيذها بسبب الآثار المتبقية لجائحة كوفيد-19 والتحديات الإدارية داخل وحدة الأوزون الوطنية والحكومة. وأعربت اللجنة عن تقديرها لتفاني موظف الأوزون ومساعد الأوزون والعمل الذي تم إنجازه لتحقيق نتائج ناجحة. وشجعت اللجنة الحكومة على الاستفادة من التدابير المتخذة لضمان احتفاظ البلاد بالزخم في سعيه للبقاء ممتثلا لبروتوكول مونتريال وتنفيذ الأنشطة في إطار المرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية وأنشطة التعزيز المؤسسي القادمة.
العراق
9. [bookmark: _Hlk151841457]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي للعراق (المرحلة السادسة) وأشارت مع التقدير إلى أن البلد قد أبلغ بيانات المادة 7 وبيانات البرامج القطرية لعام 2022 إلى أمانتي الأوزون والصندوق، على التوالي، مشيرة إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. ولاحظت اللجنة أنه ينبغي تعزيز التنسيق المستمر مع أصحاب المصلحة والقطاعين الحكومي والخاص لضمان مشاركتهم الكاملة في تنفيذ المشروعات الجارية التي يدعمها الصندوق المتعدد الأطراف، بما في ذلك تنفيذ المرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية لتحقيق هدف التخفيض لعام 2025 وفقًا لبروتوكول مونتريال. وأعربت اللجنة عن تقديرها للجهود التي بذلتها حكومة العراق لتسهيل التصديق على تعديل كيغالي. ولاحظت اللجنة أيضاً أن العراق واصل التشغيل الفعال لنظام الحصص والتراخيص للمواد الهيدروكلوروفلوروكربونية وقام بتشغيل النظام المحدث الذي يتضمن المواد الهيدروفلوروكربونية كما هو مطلوب بموجب تعديل كيغالي لضمان استدامة التخلص التدريجي الذي تم تحقيقه والامتثال لأهداف التخفيض المستقبلية. ولذلك، تأمل اللجنة أن يواصل العراق، خلال السنوات الثلاث المقبلة، تنفيذ خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية وأنشطة مشروع التعزيز المؤسسي بنجاح لإعداد البلد لمزيد من التخفيض في استهلاك المواد الهيدروكلوروفلوروكربونية بموجب بروتوكول مونتريال والبدء في الأنشطة المطلوبة بموجب تعديل كيغالي.
مدغشقر
10. [bookmark: _Hlk151841733]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لمدغشقر (المرحلة العاشرة) وأشارت مع التقدير إلى أن الحكومة قد أبلغت بيانات البرامج القطرية وبيانات المادة 7 إلى أمانتي الصندوق والأوزون، على التوالي، مما يشير إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. وأقرت اللجنة بالخطوات الكبيرة التي اتخذتها مدغشقر في التخلص التدريجي من استهلاك المواد المستنفدة للأوزون خلال فترة المشروع من خلال إنفاذ ضوابط على واردات المواد المستنفدة للأوزون من خلال نظام التراخيص والحصص وتوفير التدريب لموظفي الجمارك وفنيي التبريد. وأعربت اللجنة عن تقديرها للجهود التي تبذلها مدغشقر في خفض استهلاك المواد الهيدروكلوروفلوروكربونية وتتطلع إلى استمرار البلد في التنفيذ الناجح لخطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية ومشروع التعزيز المؤسسي، لتحقيق تخفيض بنسبة 67.5 في المئة في استهلاك المواد الهيدروكلوروفلوروكربونية بحلول 1 يناير/ كانون الثاني 2025، وفقا للتكليف الصادر عن بروتوكول مونتريال.
موريشيوس
11. [bookmark: _Hlk151842094][bookmark: _Hlk151842834]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لموريشيوس (المرحلة الثامنة) وأشارت مع التقدير إلى أن حكومة موريشيوس قد أبلغت بيانات البرامج القطرية وبيانات المادة 7 إلى أمانتي الصندوق والأوزون، على التوالي، مشيرة إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. ولاحظت اللجنة كذلك أن موريشيوس قد اتخذت خطوات للتخلص التدريجي من استهلاك المواد الهيدروكلوروفلوروكربونية بما في ذلك تنفيذ ضوابط على واردات المواد الهيدروكلوروفلوروكربونية من خلال نظام التراخيص والحصص؛ والحفاظ على التعاون الوثيق مع مكتب الجمارك؛ وتدريب فنيي التبريد. وأقرت اللجنة بالجهود التي بذلتها البلاد في إنشاء نظام تراخيص للمواد الهيدروفلوروكربونية، وبالتالي فهي واثقة من أن حكومة موريشيوس ستواصل، خلال السنوات الثلاث المقبلة، تنفيذ أنشطة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية ومشروع التعزيز المؤسسي وستقدم خطة كيغالي لتنفيذ المواد الهيدروفلوروكربونية لتمكين البلاد من الامتثال للالتزامات بموجب بروتوكول مونتريال وتعديل كيغالي.
ميكرونيزيا (ولايات - الموحدة)
12. استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لميكرونيزيا (ولايات - الموحدة) (المرحلة التاسعة) وأشارت مع التقدير إلى أن حكومة ميكرونيزيا (ولايات - الموحدة) قد أبلغت عن بيانات البرامج القطرية وبيانات المادة 7 إلى أمانتي الصندوق والأوزون، على التوالي، مشيرة إلى أن البلاد ممتثلة لبروتوكول مونتريال. ولاحظت اللجنة أن البلد يواصل تنفيذ نظام تراخيص للمواد الهيدروكلوروفلوروكربونية ويقوم بتنفيذ خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية، وإجراء أنشطة للوصول إلى المعلومات وزيادة التوعية والمشاركة في اجتماعات الشبكات الإقليمية. وتأمل اللجنة أن تواصل حكومة ميكرونيزيا (ولايات - الموحدة) تنفيذ مشروع التعزيز المؤسسي بنجاح للحفاظ على زخم التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية والوفاء بتدابير الرقابة المستقبلية لبروتوكول مونتريال وتعديل كيغالي.
باراغواي
13. استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لباراغواي (المرحلة الثانية عشرة) وأشارت مع التقدير إلى أن حكومة باراغواي قد أبلغت بيانات البرامج القطرية وبيانات المادة 7 إلى أمانتي الصندوق والأوزون، على التوالي. مشيرة إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. ويسر اللجنة أن البلد قد نجح في تدريب فنيي التبريد على ممارسات التبريد الجيدة والتعامل الآمن مع المواد البديلة، وحصل على دعم أصحاب المصلحة من خلال اللجنة التوجيهية، والتزم بصياغة قواعد ومعايير للتعامل الآمن مع غازات التبريد البديلة. كما لاحظت اللجنة مع التقدير الأنشطة التي بدأت لتسهيل تنفيذ تعديل كيغالي. وأقرت اللجنة بالجهود المطلوبة والتحديات التي تواجهها حكومة باراغواي، ولذلك تأمل أن تواصل الحكومة، خلال السنوات الثلاث القادمة، تنفيذ خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية وأنشطة مشروع التعزيز المؤسسي، وستُعد خطة كيغالي لتنفيذ المواد الهيدروفلوروكربونية لتحقيق تخفيض بنسبة 67.5 في المئة في استهلاك المواد الهيدروكلوروفلوروكربونية بحلول 1 يناير/ كانون الثاني 2025 ووضع الأساس للتخفيض التدريجي للمواد الهيدروفلوروكربونية بموجب تعديل كيغالي.
سانت لوسيا
14. [bookmark: _Hlk151844237][bookmark: _Hlk151844212]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لسانت لوسيا (المرحلة الثانية عشرة) وأعربت عن تقديرها لحكومة سانت لوسيا لإبلاغها بيانات البرنامج القطري وبيانات المادة 7 إلى أمانتي الصندوق الأوزون، على التوالي، مما يشير إلى أن البلاد ممتثلة لبروتوكول مونتريال. وأقرت اللجنة بالتقدم المحرز في المرحلة السابقة على الرغم من جائحة كوفيد-19. وأعربت اللجنة عن تقديرها لتفاني موظف الأوزون الوطني ووحدة الأوزون الوطنية والعمل الذي تم إنجازه للحفاظ على الامتثال. وأثنت اللجنة على الحكومة لتدابيرها المتواصلة والحاسمة التي اتخذتها لضمان احتفاظ البلاد بالزخم في تنفيذ أنشطة بروتوكول مونتريال بما في ذلك في إطار المرحلة الثانية من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية والأنشطة المقبلة للتخفيض التدريجي للمواد الهيدروفلوروكربونية.
جزر سليمان
15. [bookmark: _Hlk151844185]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لجزر سليمان (المرحلة العاشرة) وأشارت مع التقدير إلى أن حكومة جزر سليمان قد أبلغت بيانات البرنامج القطري وبيانات المادة 7 إلى أمانة الصندوق وأمان الأوزون، على التوالي، مما يشير إلى أن البلاد ممتثلة لبروتوكول مونتريال. ولاحظت اللجنة أن البلد يواصل تنفيذ نظام ترخيص المواد الهيدروكلوروفلوروكربونية ويقوم بتنفيذ خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية، وإجراء أنشطة توعية وإرشاد إعلامي والمشاركة في اجتماعات الشبكات الإقليمية. وتأمل اللجنة أن تواصل حكومة جزر سليمان تنفيذ مشروع التعزيز المؤسسي بنجاح للحفاظ على زخم التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية والوفاء بتدابير الرقابة المستقبلية لبروتوكول مونتريال وتعديل كيغالي.
الصومال
16. [bookmark: _Hlk151844337]استعرضت اللجنة التنفيذية طلب تجديد مشروع التعزيز المؤسسي للصومال (المرحلة السادسة) وأشارت مع التقدير إلى أن حكومة الصومال قد أبلغت بيانات البرامج القطرية وبيانات المادة 7 إلى أمانتي الصندوق والأوزون، على التوالي، مشيرة إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. ولاحظت اللجنة أيضا أن الصومال قد اتخذت خطوات نحو استكمال عملية استعراض لوائح المواد المستنفدة للأوزون لتشمل القضايا المتعلقة بتعديل كيغالي. وأقرت اللجنة بجهود حكومة الصومال، وبالتالي فهي واثقة من أن البلد سيواصل خفضه التدريجي لاستهلاك المواد الهيدروكلوروفلوروكربونية فلورية لتحقيق نسبة 67.5 في المئة المطلوبة بموجب بروتوكول مونتريال بحلول 1 يناير/ كانون الثاني 2025 وإتمام التخلص التدريجي بحلول 1 يناير/كانون الثاني 2030. وبالإضافة إلى ذلك، تأمل اللجنة أن يقدم الصومال خطة كيغالي لتنفيذ المواد الهيدروفلوروكربونية وأن يبدأ في التخفيض التدريجي للمواد الهيدروفلوروكربونية وفقا لتعديل كيغالي.
تيمور - ليشتي
17. [bookmark: _Hlk151845007]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لتيمور - ليشتي (المرحلة السابعة) وأشارت مع التقدير إلى أن حكومة تيمور - ليشتي قد أبلغت بيانات البرنامج القطري وبيانات المادة 7 إلى أمانتي الصندوق والأوزون، على التوالي، مما يشير إلى أن البلد في حالة امتثال لبروتوكول مونتريال. ولاحظت اللجنة أن البلد يقوم بتنفيذ خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية، وقد أحرز تقدما في المشاورات الوطنية للتصديق على تعديل كيغالي، وأجرى أنشطة توعية وإرشاد إعلامي، وشارك في اجتماعات الشبكات الإقليمية. وتأمل اللجنة أن تواصل حكومة تيمور - ليشتي تنفيذ مشروع التعزيز المؤسسي بنجاح للحفاظ على زخم التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية، وتسهيل التصديق على تعديل كيغالي، والوفاء بتدابير الرقابة المستقبلية لبروتوكول مونتريال وتعديل كيغالي.
توغو
18. [bookmark: _Hlk151844356][bookmark: _Hlk151845304][bookmark: _Hlk151845594]استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لتوغو (المرحلة الثانية عشرة) وأشارت مع التقدير إلى أن حكومة توغو قد أبلغت بيانات البرامج القطرية وبيانات المادة 7 إلى أمانتي الصندوق والأوزون، على التوالي. مشيرة إلى أن البلاد في حال امتثال لبروتوكول مونتريال. وأقرت اللجنة أيضا بالخطوات الكبيرة التي اتخذتها توغو في التخلص التدريجي من استهلاك المواد المستنفدة للأوزون والمواد الهيدروفلوروكربونية خلال فترة المشروع من خلال إنفاذ ضوابط على واردات المواد المستنفدة للأوزون والمواد الهيدروفلوروكربونية من خلال نظام التراخيص والحصص وتوفير التدريب لموظفي الجمارك وفنيي التبريد. ولاحظت اللجنة مع التقدير جهود توغو في خفض استهلاك المواد الهيدروكلوروفلوروكربونية والمواد الهيدروفلوروكربونية، وتتطلع إلى استمرار البلد في تنفيذ المرحلة الثانية بنجاح من خطة إدارة التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية ومشروع التعزيز المؤسسي لتحقيق التخفيض بنسبة 67.5 في المئة في استهلاك المواد الهيدروكلوروفلوروكربونية بحلول 1 يناير/ كانون الثاني 2025، وفقا لما ينص عليه بروتوكول مونتريال والتحضير للتخفيض التدريجي للمواد الهيدروفلوروكربونية وفقا لتعديل كيغالي.
اليمن
19. استعرضت اللجنة التنفيذية التقرير المقدم مع طلب تجديد مشروع التعزيز المؤسسي لليمن (المرحلة التاسعة) وأشارت مع التقدير إلى أن حكومة اليمن استأنفت أنشطتها وقدمت بيانات البرنامج القطري وبيانات المادة 7 إلى أمانتي الصندوق والأوزون، على التوالي، مما يشير إلى أن البلاد في حالة امتثال لبروتوكول مونتريال. ولاحظت اللجنة أنه من خلال اعتماد جهات اتصال في الموقع، تمكنت وحدة الأوزون الوطنية من التغلب على الصعوبات الأمنية والمتعلقة بالتنقل على أرض الواقع، وأن وحدة الأوزون الوطنية تقوم برصد ومراقبة الواردات والاستخدام والاتجار غير المشروع في المواد المستنفدة للأوزون. وتأمل اللجنة أن تواصل حكومة اليمن تنفيذ مشروع التعزيز المؤسسي بنجاح والحفاظ على إنجازات التخلص التدريجي من المواد الهيدروكلوروفلوروكربونية، وتشجيع التصديق على تعديل كيغالي بين الوكالات والمؤسسات الحكومية والقطاعات ذات الصلة، فضلا عن وضع إجراءات لرصد المواد الهيدروفلوروكربونية والرقابة عليها والإبلاغ الطوعية عنها.
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