| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/97/15 7 November 2025 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-seventh Meeting

Montreal, 1-5 December 2025

Item 7(a)(v) of the provisional agenda

PROGRESS REPORT OF UNIDO as at 31 december 2024

Introduction

# This document presents the progress report of UNIDO as at 31 December 2024.

# The progress report of UNIDO includes the status of implementation of projects, including HFC-related projects that have been funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2024, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in metric tonnes (mt) and CO2-eq tonnes.

# This document presents a summary of progress in implementation of projects for 2024 and cumulative since 1993 addressing all controlled substances, including Annex F substances (HFCs), under the Montreal Protocol for all projects approved under regular funding and additional voluntary contributions. It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee. As all projects approved under the additional voluntary contributions have been completed and the remaining balances will be returned to the Secretariat, the Secretariat will no longer report on these projects separately.

Progress in implementation of projects for 2024 and cumulative since 1991

# As of 31 December 2024, the Executive Committee had approved US $1.1 billion in projects for UNIDO, consisting of US $975.15 million for the implementation of investment and non-investment projects, and US $129.06 million for agency support costs, as shown in table 1.

# Table 1. Approved funding by sector for UNIDO as at 31 December 2024

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 34,397,921 |
| Destruction | 5,845,540 |
| Energy efficiency | 3,922,688 |
| Foam | 88,540,224 |
| Halon | 1,780,369 |
| HFC phase-down plan | 25,910,369 |
| Fumigants | 78,028,741 |
| Multiple sectors | 139,440 |
| Other | 11,317,246 |
| Phase-out plan | 428,605,072 |
| Process agent | 6,337,359 |
| Production | 50,638,105 |
| Refrigeration | 185,836,795 |
| Several | 30,598,719 |
| Solvents | 23,247,443 |
| Sub-total | 975,146,030 |
| Agency support costs | 129,056,352 |
| Total | 1,104,202,382 |

# In 2024, 91 new projects and activities were approved. This level of funding is expected to result in the phase-out of 85,915 ODP tonnes of consumption and production of ODS and 4,408 mt (9,208,505 CO2-eq tonnes) of consumption of HFCs. Annex I shows the status of project implementation per country in 2024.

# Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2024. Annex II presents analytical information per year since 1993.

Table 2. Status of project implementation by type as at 31 December 2024

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 11 | 11 | 100 | 722,669 | 722,669 | 0 | 100 |
| Demonstration | 51 | 43 | 84 | 25,250,447 | 23,170,260 | 2,080,187 | 92 |
| Institutional strengthening (IS) | 115 | 96 | 83 | 22,179,518 | 17,151,813 | 5,027,705 | 77 |
| Investment | 1,101 | 929 | 84 | 865,056,885 | 771,256,435 | 93,800,450 | 89 |
| Project preparation | 650 | 584 | 90 | 31,060,679 | 27,324,653 | 3,736,026 | 88 |
| Technical assistance | 262 | 237 | 90 | 29,679,296 | 27,309,179 | 2,370,118 | 92 |
| Training | 23 | 23 | 100 | 1,196,535 | 1,196,535 | 0 | 100 |
| Total | 2,213 | 1,923 | 87 | 975,146,030 | 868,131,544 | 107,014,486 | 89 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

# Implementation of projects and activities by UNIDO for 2024 and cumulative since 1993 up to 31 December 2024, is summarized as follows:

## Phase-out: In 2024, 669.8 ODP tonnes of consumption of ODS and 89.8 mt (172,709 CO2-eq tonnes) of consumption of HFCs were phased out and an additional 1,431.5 ODP tonnes of consumption of ODS and 2,199.5 mt (4,781,066 CO2-eq tonnes) of consumption of HFCs were approved for phase-out. Since 1993, 65,813 ODP tonnes of consumption of ODS and 17,381 ODP tonnes of production of ODS had been phased out, of an expected total of 85,915 ODP tonnes of consumption and production of ODS and 375.8 mt (681,295 CO2-eq tonnes) of consumption of HFCs had been phased out, of an expected total of 4,408 mt (9,208,505 CO2-eq tonnes) of consumption of HFCs from projects approved (excluding cancelled and transferred projects). In addition, in 2024, 109.9 mt (1,627,017 CO2-eq tonnes) of HFC-23 by-product were destroyed. Since 2022, 314.1 mt (4,648,938 CO2-eq tonnes) had been destroyed of an expected total of 1,274.3 mt (18,858,948 CO2-eq tonnes) of HFC-23 by-product from approved projects;

## Disbursements/approvals: In 2024, US $22.11 million was disbursed and US $19.95 million was planned for disbursement based on the 2023 progress report, representing a rate of disbursement of 111 per cent of that planned. Cumulatively, US $868.13 million had been disbursed out of the total US $975.15 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 89 per cent. In 2024, US $45.91 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1993, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $11.37/kg and for all production sector activities (CFC and methyl bromide (MB)) was US $2.90/kg. The average cost-effectiveness of investment projects per ODP tonne was US $9.09/kg for completed projects and US $14.88/kg for ongoing projects;

## Number of projects completed: In 2024, 62 projects were completed. Since 1993, 1,923 projects of the 2,213 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 87 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2024 were completed on average 45 months after their approval. Since 1993, the average time for completion of investment projects has been 41 months after their approval. First disbursements under these projects occurred, on average, nine months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2024 were completed on average 51 months after their approval. Since 1993, the average time for completion of non-investment projects has been 37 months after their approval. First disbursements under these projects occurred, on average, nine months after they had been approved;

## Project preparation: Of the 650 project preparation activities approved by the end of 2024, 584 have been completed, leaving 66 ongoing activities. In 2024, 29 project preparation activities were completed;

## Implementation delays: A total of 290 projects were under implementation at the end of 2024, experiencing, on average, a delay of 13 months. Twenty-one of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation, and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2024, two MYAs for the control and phase-out of HFC-23 emissions, 77 MYAs for HCFC phase-out management plans (HPMPs), 31 Kigali HFC implementation plans (KIPs) and one ODS phase-out plan were under implementation. Since 1993, 253 MYAs have been approved and 142 MYAs have been completed, representing a completion rate of 56 per cent.

# Table 3 summarizes progress made by UNIDO since 1993.

## Table 3: Progress made by UNIDO since 1993

| Phase out achieved |  | HFC-23 by-product destroyed | Disburse- ment (US $) | Average CE (US$/kg) |  |  | Number of projects |  | Speed of delivery for completion (months) |  | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes* | CO2-eq tonnes** | CO2-eq tonnes *** |  | Consump- tion | Produc- tion | HFC-23 emissions | Approved | Compl- eted | Invest- ment | Non- investment |  | Appro-ved | Compl- eted |
| 83,194 | 681,295 | 4,648,938 | 868,131,544 | 11.37 | 2.90 | 0.66 | 2,213 | 1,923 | 41 | 37 | 13 | 253 | 142 |

*Consumption and production of ODS.

** HFC-related projects.

*** HFC-23 by-product destroyed as reported in the project proposal documents.

HFC-related projects

# As of 31 December 2024, the Executive Committee had approved 157 HFC-related projects (including seven demonstration projects, 52 investment projects, 64 preparation activities and 34 technical assistance projects) amounting to US $41,513,129 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9.

Table 4. HFC-related projects approved

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Demonstration | 7 | 0 | 0 | 2,022,620 | 106,156 | 1,916,464 | 5 |
| Investment** | 52 | 6 | 12 | 29,280,084 | 8,197,039 | 21,083,045 | 28 |
| Project preparation | 64 | 35 | 55 | 5,579,172 | 4,322,958 | 1,256,214 | 77 |
| Technical assistance | 34 | 31 | 91 | 4,631,252 | 4,129,332 | 501,921 | 89 |
| Total | 157 | 72 | 46 | 41,513,129 | 16,755,485 | 24,757,644 | 40 |

* Excludes agency support costs.

** 4,408 mt (9,208,505 CO2-eq tonnes) of HFCs was approved for phase-out.

# As of the end of 2024, of the 157 projects, six investment projects, 35 preparation activities and 31 technical assistance projects have been completed, leaving 85 ongoing. The ongoing projects are at various stages of implementation.

# Of the total cumulative funding approved of US $41,513,129 (excluding agency support costs), US $16,755,485 had been disbursed, representing a disbursement rate of 40 per cent.

Issues identified in project implementation in 2024

# Further to the review process, several issues were discussed and satisfactorily addressed, except for issues on 21 projects classified as projects with implementation delays (including 20 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); and one investment project). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 98th meeting.

# Details of progress in implementation of projects associated with the HPMPs for Argentina, Brunei Darussalam, Cameroon, Chad, China (room air-conditioning manufacturing and heat pump water heaters, and extruded polystyrene foam sectors), Egypt, Montenegro, Oman, Senegal, Serbia, South Africa, and Tunisia, with the KIPs for Mexico, the Niger, and Turkmenistan, and reports on projects with specific reporting requirements associated with Armenia, Iraq, Nicaragua, Pakistan and Qatar (HPMPs), have been submitted to the 97th meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. Outstanding issues for the remaining ongoing projects not included in annex III to the present document, and requests for extension of dates of completion and possible cancellation are addressed below.

# Of the 205 ongoing projects, excluding IS and project preparation, 99 projects have revised planned dates of completion since the 2023 progress report.

# In line with paragraph 95/12(b), UNIDO reported that the IS projects for Serbia and the Syrian Arab Republic were delayed due to the political and security situation in the respective countries; the renewal requests for the two countries are expected to be submitted to the 98th meeting.

# In line with decision 82/11(b), UNIDO has requested the extension of the duration of 22 projects, as shown in tables 5 and 6.

Table 5. Projects for which an extension of the completion dates has been requested

| Country/ project code | Disburse-ment (%) | Activities requiring additional time | Original date of completion | Date of completion requested |
| --- | --- | --- | --- | --- |
| Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) |  |  |  |  |
| Afghanistan AFG/DES/94/PRP/32 | 0 | Completion of survey and report preparation based on legal advice received for continuing project implementation | Jun-26 | Dec-27 |
| Benin BEN/DES/93/PRP/49 | 53 | Completion of survey and data analysis, and report preparation | Dec-25 | Jun-26 |
| Bolivia (Plurinational State of) BOL/DES/93/PRP/58 | 38 | Validation of collected data and cross-checking with multiple stakeholders across sectors to enable the preparation of the action plan for the handling and disposal of banks of controlled substances | Dec-25 | Jun-26 |
| Botswana BOT/DES/94/PRP/32 | 10 | Finalization of the plan of action for the handling and disposal of banks of controlled substances following consultations with relevant national stakeholders | Jun-26 | Jun-27 |
| Burkina Faso BKF/DES/93/PRP/50 | 15 | Completion of survey and data analysis, and report preparation | Dec-25 | Dec-26 |
| Burundi BDI/DES/93/PRP/46 | 0 | Completion of survey and data analysis, and report preparation | Dec-25 | Jun-26 |
| Cameroon CMR/DES/93/PRP/51 | 11 | Recruitment of international consultant, completion of survey and data analysis, and report preparation | Dec-25 | Jun-26 |
| Ecuador ECU/DES/93/PRP/83 | 3 | Comprehensive consolidation of results from the survey, including review, editing, and finalization of deliverables with the strategic objectives | Dec-25 | Jun-26 |
| Guatemala GUA/DES/93/PRP/65 | 22 | Completion of data collection, engagement of stakeholders, and finalization of the project component in alignment with the project objectives | Dec-25 | Jun-26 |
| Honduras HON/DES/93/PRP/62 | 34 | Establishment of data-sharing mechanisms and alignment of efforts across sectors for preparation of the plan | Dec-25 | Jun-26 |
| Iran (Islamic Republic of) IRA/DES/94/PRP/274 | 4 | Recruitment of consultant and finalization of the plan of action for the handling and disposal of banks of controlled substances | Jun-26 | Mar-27 |
| Libya LIB/DES/94/PRP/49 | 0 | Completion of field survey, and data collection and analysis | Jun-26 | Mar-27 |
| Montenegro MOG/DES/93/PRP/20 | 0 | Completion of field survey, and data collection and analysis | Dec-25 | Jun-26 |
| Niger (the) NER/DES/94/PRP/52 | 5 | Recruitment of international consultant and finalization of the plan of action for the handling and disposal of banks of controlled substances | Jun-26 | Dec-26 |
| Togo TOG/DES/93/PRP/44 | 4 | Completion of field survey, and data collection and analysis | Dec-25 | Jun-26 |
| Türkiye TUR/DES/94/PRP/116 | 0 | Completion of field survey, and data collection and analysis | Jun-26 | May-27 |
| Venezuela (Bolivarian Republic of) VEN/DES/93/PRP/141 | 20 | Finalization of the plan of action for the handling and disposal of banks of controlled substances | Dec-25 | Jun-26 |

Table 6. HCFC phase-out management plans for which an extension of the completion dates has been requested

| Country/ project code | Disburse-ment (%) | Reason for delays | Activities requiring additional time | Original date of completion | Date of completion requested |
| --- | --- | --- | --- | --- | --- |
| Algeria (Stage I, first tranche) (activities in the refrigeration servicing sector including phase-out of HCFC-141b used for flushing, and project monitoring) ALG/PHA/66/INV/77 | 67 | The supply of refrigerant identifiers was significantly disrupted due to the supplier’s inability to meet the demand. This situation is expected to be resolved shortly, with the manufacturer expected to resume supply. | Procurement and delivery of refrigerant identifiers | Jul-25 | Dec-26 |
| Jordan (Stage II, third tranche) JOR/PHA/91/INV/114 | 39 | The supply of refrigerant identifiers was significantly disrupted due to the supplier’s inability to meet the demand. This situation is expected to be resolved shortly, with the manufacturer expected to resume supply. | Procurement and delivery of refrigerant identifiers | Dec-24 | Dec-26 |
| Niger (the) (Stage I, second tranche) NER/PHA/84/INV/39 | 85 | Due to the prevailing political situation in the country, equipment delivery has been delayed. The projects were initially classified as completed, as all other activities, including issuance of purchase order, had concluded. However, as this component remains outstanding, the projects are now being reclassified as ongoing. | Procurement and delivery of tools and equipment required for service sector training | Dec-25 | Dec-26 |
| Niger (the) (Stage I, third tranche) NER/PHA/88/INV/41 | 95 |  |  |  |  |
| Sudan (the) (Stage II, first tranche) (foam sector) SUD/PHA/75/INV/38 | 37 | Political situation. The Government submitted a letter in August 2025 confirming that the project would be implemented. | Completion of equipment installation and commissioning at Mina Factory and Target Steel | Dec-25 | Dec-26 |

# The Secretariat noted that no progress was reported for the following projects for Afghanistan for two consecutive meetings, i.e., the 96th and 97th meetings: HPMP (stage I, third tranche) (AFG/PHA/79/INV/22), (stage I, fourth tranche) (AFG/PHA/85/INV/28) and (stage II, first tranche) (AFG/PHA/85/INV/30). Therefore, in line with decision 84/45(c)(ii)a. and in consultation with the agency, it was agreed that a notice of possible cancellation would be sent to Afghanistan and UNIDO. The Executive Committee may with to request the Secretariat to send a letter to Afghanistan and UNIDO regarding possible cancellation of these projects.

# Gender mainstreaming

# In 2024, UNIDO was implementing the Multilateral Fund’s operational policy on gender mainstreaming in 79 countries as part of projects approved from the 85th meeting onwards. UNIDO implements the policy throughout the project preparation and implementation process and continued capacity-building of stakeholders on ensuring equal opportunities are provided to men and women. The performance of the projects on these parameters is carefully monitored. In many countries, the technical workforce in the refrigeration and air-conditioning (RAC) sector is predominantly male. UNIDO is actively engaged in identifying potential female technicians and engineers who could pursue careers in this sector, offering tailored training programmes. The success of these initiatives varies from country to country.

# For example, in Albania, through various active measures taken by the NOU to encourage women’s participation, inclusion of women at sectoral workshops and meetings has increased. In North Macedonia, female consultants were engaged in KIP and IS project activities and this resulted in greater involvement of women in decision-support roles and technical areas during project implementation. In Morocco, women actively participate in the national certification system development. Furthermore, in an awareness event held for World Refrigeration Day, the programme featured a session highlighting the role of female professionals in the RAC sector. In Nigeria, scholarships for female engineers within the RAC manufacturing sector are provided, and this initiative is anticipated to offer further opportunities for female engineers to engage in practical industry-driven activities.

Recommendation

# The Executive Committee may wish:

## To note the progress report of UNIDO as at 31 December 2024 contained in document UNEP/OzL.Pro/ExCom/97/15;

## To approve the extension of the completion dates of the preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) for the countries listed below to allow completion of the remaining ongoing activities, as reflected in table 5 of document UNEP/OzL.Pro/ExCom/97/15:

### To June 2026, for Benin (BEN/DES/93/PRP/49); the Plurinational State of Bolivia (BOL/DES/93/PRP/58); Burundi (BDI/DES/93/PRP/46); Cameroon (CMR/DES/93/PRP/51); Ecuador (ECU/DES/93/PRP/83); Guatemala (GUA/DES/93/PRP/65); Honduras (HON/DES/93/PRP/62); Montenegro (MOG/DES/93/PRP/20); Togo (TOG/DES/93/PRP/44); and the Bolivarian Republic of Venezuela (VEN/DES/93/PRP/141);

### To December 2026, for Burkina Faso (BKF/DES/93/PRP/50); and the Niger (NER/DES/94/PRP/52);

### To March 2027, for the Islamic Republic of Iran (IRA/DES/94/PRP/274); and Libya (LIB/DES/94/PRP/49);

### To May 2027, for Türkiye (TUR/DES/94/PRP/116);

### To June 2027, for Botswana (BOT/DES/94/PRP/32); and

### To December 2027, for Afghanistan (AFG/DES/94/PRP/32);

## Also to approve the extension, to December 2026, of the completion dates of the projects related to HCFC phase-out management plans (HPMPs) listed below to allow completion of the remaining ongoing activities, as reflected in table 6 of document UNEP/OzL.Pro/ExCom/97/15:

### HPMP (stage I, first tranche) (activities in the refrigeration servicing sector including phase-out of HCFC-141b used for flushing, and project monitoring) (ALG/PHA/66/INV/77) for Algeria;

### HPMP (stage II, third tranche) (JOR/PHA/91/INV/114) for Jordan;

### HPMP (stage I, second tranche) (NER/PHA/84/INV/39) and HPMP (stage I, third tranche) (NER/PHA/88/INV/41) for the Niger; and

### HPMP (stage II, first tranche) (foam sector) (SUD/PHA/75/INV/38) for the Sudan;

## To request the Secretariat to send a letter to Afghanistan and UNIDO as the lead implementing agency regarding possible cancellation of the HPMP (stage I, third tranche) (AFG/PHA/79/INV/22), (stage I, fourth tranche) (AFG/PHA/85/INV/28), and (stage II, first tranche) (AFG/PHA/85/INV/30); and

## To approve the recommendations related to ongoing projects with specific issues contained in annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNIDO

PER COUNTRY FOR 2024

# Table 1 of annex I presents the status of project implementation by country for 2024 in achieved phase-out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation by UNIDO for 2024

| Country | Phased out in 2024 (ODP tonnes)* | Phased out in 2024 (CO2-eq tonnes)* | Estimated funds disbursed in 2024 (US$) | Funds disbursed in 2024 (US$) | Percentage of funds disbursed over estimation in 2024 | Percentage of planned projects completed in 2024** |
| --- | --- | --- | --- | --- | --- | --- |
| Afghanistan | 0.0 | 0 | 20,003 | 12,556 | 63 |  |
| Albania | 0.0 | 0 | 150,101 | 141,457 | 94 | 100 |
| Algeria | 0.0 | 0 | 123,001 | 31,577 | 26 | 60 |
| Argentina | 50.5 | 0 | 1,510,001 | 1,747,305 | 116 | 0 |
| Armenia | 0.0 | 0 | 40,000 | 92,024 | 230 |  |
| Bahamas (the) | 0.0 | 0 | 20,000 | 2,224 | 11 |  |
| Bahrain | 16.0 | 0 | 190,000 | 193,476 | 102 | 100 |
| Benin | 0.0 | 0 | 80,000 | 113,695 | 142 | 100 |
| Bolivia (Plurinational State of) | 4.9 | 10,000 | 186,500 | 187,334 | 100 | 100 |
| Bosnia and Herzegovina | 0.0 | 0 | 130,003 | 230,064 | 177 | 0 |
| Botswana | 0.0 | 0 | 50,002 | 68,183 | 136 | 0 |
| Brazil | 8.1 | 0 | 453,000 | 506,726 | 112 | 100 |
| Brunei Darussalam | 0.0 | 0 | 4,000 | 0 | 0 |  |
| Burkina Faso | 0.0 | 0 | 50,700 | 29,745 | 59 |  |
| Burundi | 0.0 | 0 | 30,001 | 27,306 | 91 |  |
| Cameroon | 3.2 | 5,666 | 207,000 | 264,453 | 128 |  |
| Chad | 0.0 | 0 | 35,000 | 38,222 | 109 | 0 |
| Chile | 0.0 | 0 | 93,002 | 113,865 | 122 | 0 |
| China | 318.8 | 0 | 3,540,001 | 4,324,667 | 122 | 0 |
| Congo (the) | 0.0 | 0 | 30,000 | 17,364 | 58 | 100 |
| Cote d’Ivoire | 0.0 | 0 | 155,500 | 167,563 | 108 | 50 |
| Democratic People’s Republic of Korea (the) | 0.0 | 0 | 3 | 1 | 18 |  |
| Dominican Republic (the) | 0.7 | 1,200 | 15,000 | 4,485 | 30 |  |
| Ecuador | 29.6 | 54,901 | 531,003 | 611,429 | 115 | 100 |
| Egypt | 19.1 | 0 | 2,544,933 | 3,992,867 | 157 | 50 |
| Eritrea | 0.1 | 0 | 55,000 | 54,015 | 98 |  |
| Ethiopia | 0.0 | 0 | 23,000 | 8,167 | 36 |  |
| Gabon | 0.0 | 0 | 61,800 | 18,700 | 30 | 100 |
| Gambia (the) | 0.0 | 0 | 88,000 | 83,636 | 95 | 100 |
| Grenada | 0.0 | 0 | 30,000 | 1,148 | 4 | 0 |
| Guatemala | 40.6 | 80,000 | 103,501 | 82,073 | 79 |  |
| Guinea | 0.0 | 0 | 25,301 | 14,538 | 57 | 0 |
| Guinea-Bissau | 0.0 | 0 | 2,500 | 6,371 | 255 | 0 |
| Honduras | 0.0 | 0 | 159,301 | 148,811 | 93 | 100 |
| Iran (Islamic Republic of) | 0.0 | 0 | 112,000 | 60,995 | 54 | 0 |
| Iraq | 0.0 | 0 | 170,002 | 17 | 0 |  |
| Jordan | 0.0 | 0 | 367,154 | 195,597 | 53 | 75 |
| Kuwait | 0.0 | 0 | 272,002 | 265,322 | 98 |  |
| Lebanon | 0.0 | 0 | 1 | 5,111 | 511,068 |  |
| Lesotho | 0.0 | 0 | 10,000 | 16,483 | 165 | 0 |
| Liberia | 0.0 | 0 | 20,000 | 3,205 | 16 |  |
| Libya | 9.8 | 0 | 307,951 | 479,468 | 156 |  |
| Madagascar | 3.4 | 0 | 30,001 | 25,623 | 85 |  |
| Malawi | 0.0 | 0 | 83,000 | 69,465 | 84 | 100 |
| Mauritania | 0.0 | 0 | 50,000 | 24,886 | 50 | 0 |
| Mexico | 24.0 | 0 | 2,302,071 | 2,462,623 | 107 | 100 |
| Mongolia | 0.0 | 0 | 20,000 | 56,424 | 282 |  |
| Montenegro | 0.0 | 0 | 149,000 | 78,173 | 52 | 100 |
| Morocco | 0.0 | 0 | 315,001 | 305,174 | 97 | 0 |
| Mozambique | 0.0 | 0 | 2,001 | 50,847 | 2,541 |  |
| Myanmar | 0.0 | 0 | 2 | 0 | 0 | 100 |
| Namibia | 0.0 | 0 | 3,000 | 0 | 0 | 0 |
| Nicaragua | 0.0 | 0 | 176,801 | 109,744 | 62 |  |
| Niger (the) | 9.4 | 16,995 | 55,901 | 44,784 | 80 |  |
| Nigeria | 8.9 | 0 | 580,001 | 743,086 | 128 | 100 |
| North Macedonia | 13.4 | 3,947 | 293,002 | 241,323 | 82 | 0 |
| Oman | 2.5 | 0 | 120,800 | 43,243 | 36 | 0 |
| Pakistan | 0.0 | 0 | 705,000 | 563,300 | 80 | 100 |
| Philippines (the) | 0.0 | 0 | 132,000 | 151,681 | 115 |  |
| Qatar | 0.0 | 0 | 55,000 | 21,766 | 40 | 0 |
| Rwanda | 0.3 | 0 | 84,000 | 73,981 | 88 | 100 |
| Saint Lucia | 0.0 | 0 | 55,000 | 40,095 | 73 | 0 |
| Saint Vincent and the Grenadines | 0.0 | 0 | 15,000 | 0 | 0 |  |
| Saudi Arabia | 0.0 | 0 | 16,000 | 67,096 | 419 | 100 |
| Senegal | 0.0 | 0 | 40,401 | 61,437 | 152 | 50 |
| Serbia | 0.0 | 0 | 130,000 | 52,660 | 41 | 50 |
| Sierra Leone | 0.3 | 0 | 110,000 | 103,973 | 95 | 100 |
| Somalia | 0.0 | 0 | 55,002 | 84,583 | 154 | 100 |
| South Africa | 0.0 | 0 | 870,003 | 655,905 | 75 | 0 |
| Sudan (the) | 0.0 | 0 | 40,001 | 44,130 | 110 | 0 |
| Suriname | 0.0 | 0 | 21,000 | 0 | 0 | 100 |
| Syrian Arab Republic (the) | 0.0 | 0 | 262,002 | 138,516 | 53 | 0 |
| Togo | 0.0 | 0 | 40,000 | 42,845 | 107 | 100 |
| Tunisia | 13.6 | 0 | 271,001 | 328,715 | 121 | 75 |
| Türkiye | 179.9 | 0 | 290,000 | 383,669 | 132 | 25 |
| Turkmenistan | 2.2 | 0 | 175,002 | 127,927 | 73 | 100 |
| Uganda | 0.0 | 0 | 7,500 | 8,170 | 109 | 100 |
| United Republic of Tanzania (the) | 0.0 | 0 | 45,000 | 28,764 | 64 | 0 |
| Uruguay | 0.0 | 0 | 38,000 | 41,855 | 110 |  |
| Venezuela (Bolivarian Republic of) | 0.0 | 0 | 304,000 | 454,626 | 150 | 50 |
| Zambia | 0.3 | 0 | 12,001 | 18,455 | 154 | 100 |
| Global | 0.0 | 0 | 1 | 0 | -4 | 100 |
| Grand total | 759.6 | 172,709 | 19,949,762 | 22,111,786 | 111 | 56 |

* 89.8 mt (172,709 CO2-eq tonnes) in 2024 for HFC-related projects. In addition, in 2024, 109.9 mt (1,627,017 CO2-eq tonnes) of HFC-23 by-product were destroyed.

** For projects that were planned to be completed in 2024.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNIDO

PER YEAR AS AT 31 DECEMBER 2024

# Table 1 of annex II presents an overview of the status of project implementation by year. All projects and activities approved between 1993 and 2008, 2010, 2011 and 2013, have now been completed.

Table 1. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1993 | 22 | 22 | 100 | 11,815,540 | 11,815,540 | 0 | 100 |
| 1994 | 52 | 52 | 100 | 30,645,899 | 30,645,899 | 0 | 100 |
| 1995 | 59 | 59 | 100 | 25,662,092 | 25,662,092 | -1 | 100 |
| 1996 | 46 | 46 | 100 | 19,820,493 | 19,820,493 | 0 | 100 |
| 1997 | 130 | 130 | 100 | 42,083,037 | 42,083,038 | -1 | 100 |
| 1998 | 88 | 88 | 100 | 23,638,291 | 23,638,291 | 0 | 100 |
| 1999 | 123 | 123 | 100 | 34,140,324 | 34,140,324 | 0 | 100 |
| 2000 | 96 | 96 | 100 | 30,180,752 | 30,180,752 | 0 | 100 |
| 2001 | 119 | 119 | 100 | 24,700,254 | 24,700,255 | -1 | 100 |
| 2002 | 76 | 76 | 100 | 35,992,041 | 35,992,041 | 0 | 100 |
| 2003 | 49 | 49 | 100 | 29,997,305 | 29,997,305 | 0 | 100 |
| 2004 | 44 | 44 | 100 | 33,105,459 | 33,105,460 | -1 | 100 |
| 2005 | 74 | 74 | 100 | 52,035,808 | 52,035,806 | 2 | 100 |
| 2006 | 44 | 44 | 100 | 20,760,312 | 20,760,312 | 0 | 100 |
| 2007 | 42 | 42 | 100 | 24,186,740 | 24,186,740 | 0 | 100 |
| 2008 | 77 | 77 | 100 | 33,386,108 | 33,386,111 | -3 | 100 |
| 2009 | 70 | 68 | 97 | 15,345,924 | 15,054,995 | 290,928 | 98 |
| 2010 | 69 | 69 | 100 | 45,563,485 | 45,558,787 | 4,699 | 100 |
| 2011 | 71 | 71 | 100 | 76,542,377 | 76,542,380 | -2 | 100 |
| 2012 | 52 | 50 | 96 | 32,652,296 | 32,079,961 | 572,334 | 98 |
| 2013 | 37 | 37 | 100 | 31,089,943 | 31,089,943 | 0 | 100 |
| 2014 | 55 | 54 | 98 | 27,148,003 | 27,104,162 | 43,840 | 100 |
| 2015 | 83 | 79 | 95 | 34,771,618 | 32,520,345 | 2,251,272 | 94 |
| 2016 | 58 | 56 | 97 | 34,936,135 | 33,232,180 | 1,703,955 | 95 |
| 2017 | 49 | 46 | 94 | 18,491,629 | 17,847,033 | 644,596 | 97 |
| 2018 | 75 | 72 | 96 | 32,150,658 | 23,349,034 | 8,801,624 | 73 |
| 2019 | 67 | 57 | 85 | 19,117,627 | 15,069,168 | 4,048,459 | 79 |
| 2020 | 58 | 50 | 86 | 15,226,461 | 14,564,894 | 661,567 | 96 |
| 2021 | 73 | 46 | 63 | 22,964,640 | 16,113,506 | 6,851,134 | 70 |
| 2022 | 66 | 18 | 27 | 20,317,479 | 9,732,069 | 10,585,410 | 48 |
| 2023 | 98 | 8 | 8 | 30,768,554 | 5,697,818 | 25,070,736 | 19 |
| 2024 | 91 | 1 | 1 | 45,908,747 | 424,809 | 45,483,938 | 1 |
| Total | 2,213 | 1,923 | 87 | 975,146,030 | 868,131,544 | 107,014,486 | 89 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNIDO

| Country/project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Afghanistan AFG/PHA/79/INV/22 | HCFC phase-out management plan (stage I, third tranche) | 14 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Afghanistan AFG/PHA/85/INV/28 | HCFC phase-out management plan (stage I, fourth tranche) | 0 | 12 and 18 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Afghanistan AFG/PHA/85/INV/30 | HCFC phase-out management plan (stage II, first tranche) | 37 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Albania ALB/PHA/91/INV/47 | HCFC phase-out management plan (stage II, second tranche) | 38 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Algeria ALG/PHA/66/INV/77 | HCFC phase-out management plan (stage I, first tranche) (activities in the refrigeration servicing sector including phase-out of HCFC-141b used for flushing, and project monitoring) | 67 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Bosnia and Herzegovina BHE/PHA/87/INV/39 | HCFC phase-out management plan (stage II, first tranche) | 75 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Ethiopia ETH/PHA/88/INV/34 | HCFC phase-out management plan (stage II, first tranche) | 12 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Iraq IRQ/PHA/58/INV/09 | National phase-out plan (first tranche) | 93 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Iraq IRQ/PHA/74/INV/23 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | 29 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Iraq IRQ/PHA/87/INV/31 | HCFC phase-out management plan (stage II, first tranche) | 4 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Iraq IRQ/REF/57/INV/07 | Replacement of refrigerant CFC-12 with isobutane and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigerators and chest freezers at Light Industries Company | 100 | 12 months delays | Noting decision 77/8(j), to request UNIDO to report to the 98th meeting on this project with implementation delays |
| Jordan JOR/PHA/91/INV/114 | HCFC phase-out management plan (stage II, third tranche) | 39 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Morocco MOR/PHA/88/INV/76 | HCFC phase-out management plan (stage II, first tranche) | 62 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Morocco MOR/PHA/91/INV/78 | HCFC phase-out management plan (stage II): Umbrella project to phase-out HCFC-141b contained in imported pre-blended polyols in the polyurethane foam sector | 19 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Qatar QAT/PHA/88/INV/26 | HCFC phase-out management plan (stage II, first tranche) | 35 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Saint Lucia STL/PHA/87/INV/35 | HCFC phase-out management plan (stage II, first tranche) | 34 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Sudan SUD/PHA/88/INV/48 | HCFC phase-out management plan (stage III, first tranche) | 3 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Syrian Arab Republic (the) SYR/PHA/86/INV/107 | HCFC phase-out management plan (stage I, first tranche) | 23 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Syrian Arab Republic (the) SYR/PHA/91/INV/112 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector) | 0 | 18 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| Türkiye TUR/PHA/75/INV/107 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring) | 97 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |
| United Republic of Tanzania (the) URT/PHA/87/INV/42 | HCFC phase-out management plan (stage II, first tranche) | 47 | 12 months delays | To request UNIDO to report to the 98th meeting on this project with implementation delays |

UNEP/OzL.Pro/ExCom/97/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database, which is provided on the 97th meeting portal on the Multilateral Fund’s website, in the spreadsheet programme, Microsoft Excel.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 97th meeting.

UNIDO became an implementing agency in 1993.

Ongoing projects are all projects that were under implementation as at 31 December 2024. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

Phase-out of ODS is expressed in ODP tonnes and of HFCs in mt and CO2-eq tonnes.

Including 4,408 mt of HFC-related projects. Cost-effectiveness in CO2-eq. is not included due to the limited number of projects approved.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/97/36

UNEP/OzL.Pro/ExCom/97/40

UNEP/OzL.Pro/ExCom/97/42

UNEP/OzL.Pro/ExCom/97/43

UNEP/OzL.Pro/ExCom/97/44

UNEP/OzL.Pro/ExCom/97/49

UNEP/OzL.Pro/ExCom/97/62

UNEP/OzL.Pro/ExCom/97/67

UNEP/OzL.Pro/ExCom/97/73

UNEP/OzL.Pro/ExCom/97/74

UNEP/OzL.Pro/ExCom/97/77

UNEP/OzL.Pro/ExCom/97/80

UNEP/OzL.Pro/ExCom/97/60

UNEP/OzL.Pro/ExCom/97/65

UNEP/OzL.Pro/ExCom/97/81

UNEP/OzL.Pro/ExCom/97/17 or UNEP/OzL.Pro/ExCom/97/18

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The Executive Committee requested bilateral and implementing agencies to provide a brief report on key gender mainstreaming results achieved as part of their annual progress reports, as of 2023, on the basis of the information available to them (decision 90/48(d)).

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.