| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/95/28 10 November 2024 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-fifth Meeting

Montreal, 4-8 December 2024

Item 8(d)(iii) of the provisional agenda

UNEP BUSINESS PLAN FOR 2025–2027

# Introduction

# This document presents UNEP business plan for 2025–2027 and includes the planned activities for the reduction of controlled substances and other activities under the Montreal Protocol during the period 2025–2027. The narrative of UNEP’s business plan for 2025–2027 is attached to the present document.

# This document consists of the following sections:

- Planned activities during the period 2025–2027

- Secretariat’s comments

- Proposed adjustments by the Secretariat

- Performance indicators

- Recommendation

I.	Planned activities during the period 2025–2027

# Table 1 sets out, by year, the value of activities included in UNEP’s business plan.

Table 1. Resource allocation in the UNEP business plan for 2025–2027 (US $)* – as submitted

| Description | 2025 | 2026 | 2027 | Total (2025–2027) | Total after 2027 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 5,494,983 | 9,111,649 | 4,284,545 | 18,891,177 | 7,732,999 |
| HPMP stage II – project preparation (PRP) | 73,450 | 0 | 0 | 73,450 | 0 |
| HPMP stage II | 1,152,725 | 784,868 | 443,484 | 2,381,077 | 3,235,929 |
| HPMP stage III – PRP | 151,420 | 0 | 0 | 151,420 | 0 |
| HPMP stage III | 1,214,307 | 901,377 | 45,200 | 2,160,884 | 2,476,706 |
| HPMP – energy efficiency (decision 89/6) | 2,431,760 | 483,640 | 0 | 2,915,400 | 0 |
| HCFC activities subtotal | 10,518,645 | 11,281,534 | 4,773,229 | 26,573,408 | 13,445,634 |
| HFC activities |  |  |  |  |  |
| Approved Kigali HFC implementation plans (KIPs) | 295,587 | 1,195,611 | 838,844 | 2,330,042 | 526,079 |
| Enabling activities for HFC phase-down | 428,000 | 0 | 0 | 428,000 | 0 |
| KIP stage I – PRP | 1,829,551 | 379,680 | 0 | 2,209,231 | 0 |
| KIP stage I | 4,498,780 | 598,384 | 1,961,797 | 7,058,960 | 5,702,575 |
| HFC – technical assistance | 678,000 | 0 | 0 | 678,000 | 0 |
| HFC activities subtotal | 7,729,917 | 2,173,675 | 2,800,641 | 12,704,233 | 6,228,654 |
| Other activities |  |  |  |  |  |
| Pilot project for energy efficiency – investment (decision 91/65) | 1,096,100 | 0 | 0 | 1,096,100 | 0 |
| National inventories of banks of waste-controlled substances – PRP (decision 91/66) | 2,828,767 | 0 | 0 | 2,828,767 | 0 |
| Other activities subtotal | 3,924,867 | 0 | 0 | 3,924,867 | 0 |
| Standard activities |  |  |  |  |  |
| Institutional strengthening (IS) | 3,090,855 | 9,858,469 | 10,433,603 | 23,382,927 | 0 |
| Compliance Assistance Programme (CAP) | 12,113,777 | 12,310,330 | 12,679,640 | 37,103,747 | 0 |
| Standard activities subtotal | 15,204,632 | 22,168,799 | 23,113,243 | 60,486,674 | 0 |
| Total | 37,378,061 | 35,624,008 | 30,687,113 | 103,689,182 | 19,674,288 |

* Including agency support costs where applicable.

# II.	Secretariat’s comments

II.1	HCFC activities

Stage II of HPMPs

# The total level of funding for stage II of HPMPs for 13 low-volume-consuming (LVC) countries to meet the 100 per cent reduction of the HCFC baseline amounts to US $3.04 million (including US $1.19 million for 2025–2027 and US $1.85 million for the period after 2027).

# The total level of funding for stage II of HPMPs for three non-LVC countries amounts to US $2.58 million (including US $1.19 million for 2025–2027 and US $1.39 million for the period after 2027).

# A total of US $73,450 is included in the business plan for project preparation for stage II of HPMPs for three countries for 2025.

# Stage III of HPMPs

# The total level of funding for stage III of HPMPs for four LVC countries to meet the 100 per cent reduction of the HCFC baseline amounts to US $413,550 (including US $258,164 for 2025–2027 and US $155,386 for the period after 2027).

# The total level of funding for stage III of HPMPs for five non-LVC countries amounts to US $4.22 million (including US $1.9 million for 2025–2027 and US $2.32 million for the period after 2027).

# A total of US $151,420 is included in the business plan for project preparation for stage III of HPMPs for four countries for 2025.

# Energy efficiency for LVC countries (decision 89/6)

# A total of US $2.92 million is included in the business plan for energy efficiency activities for 30 LVC countries for 2025–2027.

II.2	HFC-related activities

# Enabling activities

# HFC activities include enabling activities amounting to US $428,000 in 2025 for two countries (the Central African Republic and Yemen). Both countries have submitted the required letter from their respective Government indicating their intent to make best efforts to ratify the Kigali Amendment as early as possible, in line with decision 79/46(d)(i).

# KIP project preparation

# A total of US $2.21 million is included in the business plan for KIP project preparation activities for 19 countries in 2025–2027.

# Sixteen of the 19 countries for which KIP project preparation activities have been included have not yet ratified the Kigali Amendment but have submitted the required letter from their respective Government indicating their intent to make best efforts to ratify the Kigali Amendment in line with decision 84/46(f).

# Stage I of KIPs

# A total of US $12.76 million is included in the business plan for stage I of KIPs for 55 countries (including US $7.06 million for 2025–2027 and US $5.7 million for the period after 2027). All these countries have ratified the Kigali Amendment.

# HFC technical assistance

# UNEP has included one global HFC technical assistance project, twinning of ozone officers and national energy policymakers to support Kigali Amendment objectives, in the amount of US $678,000 in 2025. Phase I of this project was approved at the 91st meeting.

II.3	Other activities

Pilot projects for energy efficiency (decision 91/65)

# A total of US $1.1 million is included in the business plan under the funding window for pilot projects for energy efficiency for 2025 for three countries.

National inventories of banks of waste-controlled substances project preparation (decision 91/66)

# A total of US $2.83 million is included in the business plan for the preparation of national inventories of banks of waste-controlled substances for 2025 for 31 countries.

II.4	CAP

# The cost for CAP is expected to increase at an annual rate of 3 per cent as agreed by the Executive Committee, and includes additional funding of US $150,000 in 2025 for 2026, pursuant to decision 93/95(d). The total level of funding for CAP is US $37.1 million for 2025–2027. The CAP budget for 2025 has been submitted to the 95th meeting.

III.	Proposed adjustments by the Secretariat

# The adjustments to the UNEP business plan for 2025–2027 were based on relevant decisions of the Executive Committee. In reviewing the revised UNEP business plan for 2025–2027, the Secretariat noted that the following adjustments were not included:

Table 2. Adjustments to the UNEP business plan for 2025–2027 (US $)* – as proposed by the Secretariat

| Adjustment | 2025–2027 | After 2027 |
| --- | --- | --- |
| MYA values to reflect the actual amounts approved under the Agreements that have been submitted to the 95th meeting | 398,048 | 0 |
| Energy efficiency for LVC countries pursuant to decision 89/6 or submitted to the 95th meeting | (152) | 0 |
| KIP stage I values to reflect the draft Agreements submitted to the 95th meeting | (74,015) | 0 |
| Servicing sector for stage I of KIPs pursuant to decision 92/37 | (87,906) | (94,144) |
| Preparation for national inventories of banks of waste-controlled substances submitted to the 95th meeting | (203,400) | 0 |

* Including agency support costs where applicable.

# Table 3 presents the results of the Secretariat’s proposed adjustments to the UNEP business plan for 2025–2027, which are also addressed in the context of the consolidated business plan of the Multilateral Fund for 2025–2027.

Table 3. Resource allocation in UNEP’s adjusted business plan for 2025–2027 (US $)*

| Description | 2025 | 2026 | 2027 | Total (2025–2027) | Total after 2027 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HPMPs | 5,893,031 | 9,111,649 | 4,284,545 | 19,289,225 | 7,732,999 |
| HPMP stage II – PRP | 73,450 | 0 | 0 | 73,450 | 0 |
| HPMP stage II | 1,152,725 | 784,868 | 443,484 | 2,381,077 | 3,235,929 |
| HPMP stage III – PRP | 151,420 | 0 | 0 | 151,420 | 0 |
| HPMP stage III | 1,214,307 | 901,377 | 45,200 | 2,160,884 | 2,476,706 |
| HPMP – energy efficiency (decision 89/6) | 2,431,608 | 483,640 | 0 | 2,915,248 | 0 |
| HCFC activities subtotal | 10,916,541 | 11,281,534 | 4,773,229 | 26,971,304 | 13,445,634 |
| HFC activities |  |  |  |  |  |
| Approved KIPs | 295,587 | 1,195,611 | 838,844 | 2,330,042 | 526,079 |
| Enabling activities for HFC phase-down | 428,000 | 0 | 0 | 428,000 | 0 |
| KIP stage I – PRP | 1,829,551 | 379,680 | 0 | 2,209,231 | 0 |
| KIP stage I | 4,413,515 | 522,934 | 1,960,589 | 6,897,039 | 5,608,431 |
| HFC – technical assistance | 678,000 | 0 | 0 | 678,000 | 0 |
| HFC activities subtotal | 7,644,653 | 2,098,225 | 2,799,433 | 12,542,312 | 6,134,510 |
| Other activities |  |  |  |  |  |
| Pilot project for energy efficiency – investment (decision 91/65) | 1,096,100 | 0 | 0 | 1,096,100 | 0 |
| National inventories of banks of waste-controlled substances – PRP (decision 91/66) | 2,625,367 | 0 | 0 | 2,625,367 | 0 |
| Other activities subtotal | 3,721,467 | 0 | 0 | 3,721,467 | 0 |
| Standard activities |  |  |  |  |  |
| IS | 3,270,855 | 9,858,469 | 10,253,603 | 23,382,927 | 0 |
| CAP | 12,113,777 | 12,310,330 | 12,679,640 | 37,103,747 | 0 |
| Standard activities subtotal | 15,384,632 | 22,168,799 | 22,933,243 | 60,486,674 | 0 |
| Total | 37,667,293 | 35,548,558 | 30,505,906 | 103,721,757 | 19,580,144 |

* Including agency support costs where applicable.

IV.	Performance indicators

# UNEP submitted performance indicators pursuant to decision 93/8(d) in its business plan narrative. The Secretariat informed UNEP of the targets shown in table 4.

Table 4. Performance indicators for UNEP for 2025

| Type of indicator | Short title | Calculation | 2025 target |
| --- | --- | --- | --- |
| Planning-Approval | Tranches approved | Number of tranches approved vs. those planned* | 77 |
| Planning-Approval | Individual projects/ activities approved | Number of projects/activities approved vs. those planned (including project preparation activities) | 96 |
| Implementation | Funds disbursed | Based on estimated disbursement in progress reports | 23,701,624 |
| Implementation | ODS phase-out for HCFC-related projects | ODS phase-out for HCFC-related projects in ODP tonnes vs. those planned per progress reports | 107.9 ODP tonnes |
| Implementation | HFC phase-down for HFC-related projects | HFC phase-down for HFC-related projects in CO2-eq tonnes vs. those planned per progress reports | zero CO2-eq tonnes |
| Implementation | Project operational completion | Project operational completion vs. planned in progress reports for all activities (excluding project preparation)** | 58 |
| Implementation | Gender mainstreaming | Operational policy on gender mainstreaming applied to all approved projects | 100% |
| Administrative | Speed of financial completion | The extent to which projects are financially completed within 12 months after project operational completion | 12 months after operational completion |
| Administrative | Timely submission of project completion reports | Timely submission of project completion reports based on the progress report | 3 |
| Administrative | Timely submission of progress reports and business plans | Timely submission of progress reports and business plans and responses unless otherwise agreed | On time |

- * The targets of an agency will be reduced if it cannot submit a tranche owing to another cooperating agency or lead agency or if the HCFC phase-out management plan or Kigali HFC implementation plan submitted for consideration by the Executive Committee is not approved as a result of factors beyond the control of the national ozone unit and agency.

- ** The targets of an agency will be reduced if an extension of the completion date has been approved by the Executive Committee.

V.	Recommendation

# The Executive Committee may wish:

## To note the UNEP business plan for 2025–2027 contained in document UNEP/OzL.Pro/ExCom/95/28; and

## To approve the performance indicators for UNEP set out in table 4 of document UNEP/OzL.Pro/ExCom/95/28.

UNEP/OzL.Pro/ExCom/95/1

Decision 89/6 allowed bilateral and implementing agencies, when submitting existing and future stages of HPMPs for LVC countries, to include the funding associated with the need for the introduction of alternatives to HCFCs with low- or zero-global-warming potential and for maintaining energy efficiency in the refrigeration servicing sector.

The Executive Committee established a funding window and criteria for pilot projects to maintain and/or enhance energy efficiency of replacement technologies and equipment in the context of HFC phase-down.

The Executive Committee established a funding window and criteria for the preparations of national inventories of banks of used or unwanted controlled substances and a plan for the collection, transport, and disposal of such substances.

The Executive Committee approved the increase in the CAP budget for the years 2024, 2025 and 2026 by US $200,000, US $150,000 and US $150,000, respectively, for providing technical and policy assistance to LVC countries to support KIP implementation.

UNEP/OzL.Pro/ExCom/95/83

UNEP/OzL.Pro/ExCom/95/25

Decision 93/8(d) does not include performance indicators for UNEP’s CAP.