| NACIONES UNIDAS |  | EP |
| --- | --- | --- |
|  | Programa de las Naciones Unidas para el Medio Ambiente | Distr. GENERAL UNEP/OzL.Pro/ExCom/93/4 20 noviembre 2023 ESPAÑOL ORIGINAL: INGLÉS |

COMITÉ EJECUTIVO DEL FONDO MULTILATERAL
 PARA LA APLICACIÓN DEL
 PROTOCOLO DE MONTREAL
Nonagésima tercera reunión

Montreal, 15 – 19 de diciembre de 2023

Cuestión 4 b) del orden del día provisional

# INFORME SOBRE SALDOS Y DISPONIBILIDAD DE RECURSOS

# Introducción

# Este documento presenta una síntesis de los ajustes financieros indicados por los organismos de ejecución y bilaterales conforme a lo acordado por la Secretaría. Incluye datos estadísticos de todos los proyectos con saldos que se han retenido durante más de 12 meses después de la terminación del proyecto, de conformidad con lo estipulado en las decisiones 28/7 y 56/2 c). Se ocupa de los saldos que habrán de devolverse de los proyectos como seguimiento a las decisiones pertinentes (mencionados como proyectos "por decisión" en el presente documento). Indica también el nivel de recursos de que dispone el Comité Ejecutivo en efectivo según lo registrado en el documento sobre la situación de las contribuciones y los desembolsos, como se estipula en la decisión 41/92 b), y presenta una recomendación. Las cantidades que los organismos de ejecución mantienen para los proyectos terminados y para los proyectos de contribuciones voluntarias adicionales se indican en el anexo I y el anexo II. En el anexo III se presentan los fondos devueltos por los organismos bilaterales y de ejecución de proyectos terminados, por decisión y de contribuciones voluntarias adicionales.

Fondos que se han de devolver a la 93ª reunión

# Los fondos totales que han de devolverse ascienden a 4.286.636 $EUA (50.850 $EUA por los organismos bilaterales y 4.235.786 $EUA por los organismos de ejecución) provenientes de proyectos terminados, por decisión y de contribuciones voluntarias adicionales.

Fondos que han de devolver los organismos de ejecución

# Los fondos totales que han de devolver los organismos de ejecución ascienden a 4.235.786 $EUA, tal como indica el cuadro 1.

# Cuadro 1. Fondos que han de devolver los organismos de ejecución a la 93ª reunión ($EUA)

| Organismo | Costo del proyecto | Gastos de apoyo al organismo | Costo total |
| --- | --- | --- | --- |
| PNUD | 562.920 | 39.505 | 602.425 |
| PNUMA | 2.245.847 | 175.064 | 2.420.911 |
| ONUDI | 551.323 | 38.603 | 589.926 |
| Banco Mundial | 320.000 | 302.524 | 622.524 |
| Total | 3.680.090 | 555.696 | 4.235.786 |

Fondos en poder de los organismos de ejecución

# En el cuadro 2 se presenta información sobre los saldos de proyectos terminados y proyectos financiados con contribuciones voluntarias adicionales que aún están en poder de los organismos de ejecución.

Cuadro 2. Saldos de proyectos terminados y proyectos financiados con contribuciones voluntarias adicionales en poder de los organismos de ejecución (incluidos gastos de apoyo a los organismos)

| Año de terminación | PNUD |  | ONUDI |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Número | ($EUA) | Número | ($EUA) | Número | ($EUA) |
| Proyectos terminados hace más de dos años |  |  |  |  |  |  |
| 2019 | 1 | 6.306 |  |  | 1 | 6.306 |
| 2020 | 1 | 40.434 |  |  | 1 | 40.434 |
| 1 ene a 31 oct 2021 | 5 | 63.190 | 2 | 1.828.437 | 7 | 1.891.627 |
| Subtotal | 7 | 109.930 | 2 | 1.828.437 | 9 | 1.938.367 |
| Proyectos terminados hace menos de dos años |  |  |  |  |  |  |
| 1 nov a 31 dic 2021 | 5 | 37.308 | 4 | 39.841 | 9 | 77.149 |
| 2022 | 20 | 277.877 | 25 | 558.563 | 45 | 836.440 |
| Subtotal | 25 | 315.185 | 29 | 598.404 | 54 | 913.589 |
| Total | 32 | 425.115 | 31 | 2.426.841 | 63 | 2.851.956 |
| Proyectos financiados con contribuciones voluntarias adicionales |  |  |  |  |  |  |
|  | 2 | 7.953 | 5 | 122.134 | 7 | 130.087 |
| Total general | 34 | 433.068 | 36 | 2.548.975 | 70 | 2.982.043 |

Fondos que los organismos bilaterales han de devolver a la 93ª reunión

5.	Los fondos totales que ha de devolver un organismo bilateral ascienden a 50.850 $EUA de proyectos terminados, como se indica en el cuadro 3.

| Organismo | Costo del proyecto | Gastos de apoyo al organismo | Total |
| --- | --- | --- | --- |
| Francia | 45.000 | 5.850 | 50.850 |

Cuadro 3. Fondos que ha de devolver un organismo bilateral ($EUA)

Disponibilidad de recursos

# El documento sobre la situación de las contribuciones y los desembolsos indica un saldo disponible de 523.322.098 $EUA al 8 de noviembre de 2023. El saldo total devuelto por los organismos bilaterales y de ejecución a la 93ª reunión asciende a 4.286.636 $EUA. Por lo tanto, excluyendo la cantidad de 246 millones de $EUA por concepto de saldos del trienio 2018-2020 y que se utilizará después de 2023, el nivel total de los recursos disponibles para aprobaciones en la 93ª reunión asciende a 281.608.734 $EUA.

# Comentarios de la Secretaría

# La Secretaría recordó a los organismos de ejecución que los saldos de los proyectos "por decisión", los proyectos terminados con un año de anterioridad o más y los proyectos financiados con contribuciones voluntarias adicionales deberían devolverse al Fondo Multilateral tan pronto como fuera posible.

# Teniendo en cuenta que el nivel total de fondos para proyectos y actividades presentados a la 93ª reunión al 22 de octubre de 2023 asciende a 122.704.590 $EUA, hay suficientes recursos disponibles para las aprobaciones previstas para la 93ª reunión.

Recomendación

# El Comité Ejecutivo puede estimar oportuno:

  - Tomar nota de:

- El informe sobre saldos y disponibilidad de recursos que recoge el documento UNEP/OzL.Pro/ExCom/93/4;

- Que el nivel neto de fondos que los organismos de ejecución reintegran a la 93ª reunión asciende a un total de 4.235.786 $EUA, cifra consistente en 562.920 $EUA más gastos de apoyo al organismo de 39.505 $EUA que reintegra el PNUD; 2.245.847 $EUA más gastos de apoyo al organismo de 175.064 $EUA que reintegra el PNUMA; 551.323 $EUA más gastos de apoyo al organismo de 38.603 $EUA que reintegra la ONUDI; y 320.000 $EUA más gastos de apoyo al organismo de 302.524 $EUA que reintegra el Banco Mundial;

- Que el PNUD mantenía a su haber saldos de 109.930 $EUA, incluyendo gastos de apoyo al organismo, por concepto de siete proyectos terminados hace más de dos años, y de 7.953 $EUA, incluyendo gastos de apoyo al organismo, por concepto de dos proyectos terminados financiados con las contribuciones voluntarias adicionales hechas por un grupo de países donantes para financiar actividades de apoyo inmediato para la reducción de HFC;

- Que la ONUDI mantenía a su haber saldos de 1.828.437 $EUA, incluyendo gastos de apoyo al organismo, por concepto de dos proyectos financiados terminados hace más de dos años, y de 122.134 $EUA, incluyendo gastos de apoyo al organismo, por concepto de cinco proyectos terminados financiados con las contribuciones voluntarias adicionales hechas por un grupo de países donantes para financiar actividades de apoyo inmediato para la reducción de HFC; y

- Que el nivel de fondos devueltos en la 93ª reunión por el Gobierno de Francia es de 50.850 $EUA, que comprenden 45.000 $EUA, más gastos de apoyo al organismo de 5.850 $EUA.

## Solicitar:

### Al PNUD y la ONUDI:

Proceder al desembolso o la cancelación de los fondos comprometidos y no comprometidos que no fueron necesarios para los proyectos terminados, y devolver los saldos conexos en la 94ª reunión;

Proceder al desembolso o la cancelación de los compromisos de los proyectos terminados hace más de dos años, y devolver los saldos respectivos a la 94ª reunión; y

Proceder al desembolso o la devolución a la 94ª reunión de los saldos de los proyectos terminados financiados con las contribuciones voluntarias adicionales;

### A la Tesorería, verificar con el Gobierno de Francia el reintegro en efectivo de la suma de 50.850 $EUA mencionada en el subpárrafo a) v) anterior.

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR COMPLETED PROJECTS

| Code | Project title | Date completed (Actual) | Approved funding plus adjustments as of 31 Dec 2022 (US $) | Funds disbursed as of 93rd meeting (US $) | Balances committed as per 93rd meeting (US $) | Balances not-committed as per 93rd meeting (US $) | Support cost on balances committed and not committed as per 93rd meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| ANG/PHA/84/TAS/22 | Verification report on the implementation of the HCFC phase-out management plan | Dec-21 | 30,000 | 22,149 | 7,851 |  | 707 |  |  |  |
| ARG/SEV/82/INS/188 | Extension for institutional strengthening project (phase X: 1/2019-12/2020) | Dec-22 | 398,806 | 384,407 | 14,399 |  | 1,008 |  |  |  |
| BGD/SEV/81/TAS/52 | Enabling activities for HFC phase-down | Jun-22 | 14,000 | 3,249 | 10,751 |  | 753 |  |  |  |
| BRA/DES/72/DEM/305 | Pilot demonstration project on ODS waste management and disposal | Dec-22 | 1,490,600 | 1,488,205 | 2,395 |  | 168 |  |  |  |
| BRU/PHA/85/INV/26 | HCFC phase-out management plan (stage I, fourth tranche) | Dec-22 | 6,600 | 149 | 6,451 |  | 581 |  |  |  |
| BZE/SEV/85/TAS/37 | Enabling activities for HFC phase-down | Oct-22 | 55,000 | 49,576 | 5,424 |  | 380 |  |  |  |
| CHI/PHA/81/INV/197 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | Dec-22 | 1,290,468 | 1,203,966 | 86,502 |  | 6,055 |  |  |  |
| COL/PHA/84/TAS/108 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector, project management and monitoring) | Dec-22 | 635,749 | 623,148 | 12,601 |  | 882 |  |  |  |
| CUB/PHA/82/PRP/61 | Preparation of a HCFC phase-out management plan (stage II) | Oct-21 | 60,000 | 38,281 | 21,719 |  | 1,520 |  |  |  |
| CUB/SEV/83/INS/62 | Extension of institutional strengthening project (phase XI: 7/2019-6/2021) | Dec-22 | 190,804 | 190,442 | 362 |  | 25 |  |  |  |
| DOM/PHA/83/PRP/68 | Preparation of a HCFC phase-out management plan (stage III) | Jun-21 | 60,000 | 47,408 | 12,592 |  | 881 |  |  |  |
| DRC/PHA/79/PRP/42 | Preparation of a HCFC phase-out management plan (stage II) | Dec-21 | 17,143 | 16,296 | 847 |  | 59 |  |  |  |
| EGY/PHA/79/INV/135 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | Jul-22 | 967,352 | 933,070 | 34,282 |  | 2,400 |  |  |  |
| FIJ/PHA/77/INV/31 | HCFC phase-out management plan (stage I, third tranche) | Dec-19 | 59,850 | 54,065 | 5,785 |  | 521 |  |  |  |
| FIJ/PHA/82/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | Dec-21 | 30,000 | 26,442 | 3,558 |  | 249 |  |  |  |
| FIJ/PHA/86/INV/38 | HCFC phase-out management plan (stage I, fourth tranche) | Dec-22 | 19,950 | 0 | 19,950 |  | 1,795 |  |  |  |
| GEO/PHA/85/INV/42 | HCFC phase-out management plan (stage I, fourth tranche) | Dec-22 | 31,500 | 25,577 | 5,923 |  | 444 |  |  |  |
| GHA/SEV/86/INS/49 | Extension of the institutional strengthening project (phase XIV: 1/2021-12/2022) | Dec-22 | 178,048 | 177,873 | 175 |  | 12 |  |  |  |
| HAI/SEV/84/TAS/23 | Enabling activities for HFC phase-down | Dec-21 | 95,000 | 90,311 | 4,689 |  | 328 |  |  |  |
| JAM/PHA/81/PRP/38 | Preparation of a HCFC phase-out management plan (stage II) | Jul-21 | 40,000 | 33,501 | 6,499 |  | 455 |  |  |  |
| MOL/PHA/86/INV/43 | HCFC phase-out management plan (stage II, third tranche) | Dec-21 | 17,450 | 0 | 17,450 |  | 1,570 |  |  |  |
| MOL/PHA/86/TAS/42 | Verification report for implementation of stage II of the HCFC phase-out management plan | Dec-22 | 30,000 | 21,459 | 8,541 |  | 769 |  |  |  |
| MOL/SEV/85/TAS/41 | Enabling activities for HFC phase-down | Dec-22 | 50,000 | 38,716 | 11,284 |  | 790 |  |  |  |
| NEP/PHA/86/INV/44 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 8,400 | 0 | 8,400 |  | 756 |  |  |  |
| NIR/PHA/83/PRP/154 | Preparation of a HCFC phase-out management plan (stage III) | Dec-22 | 22,500 | 11,717 | 10,783 |  | 755 |  |  |  |
| PAN/PHA/83/PRP/49 | Preparation of a HCFC phase-out management plan (stage III) | Jun-21 | 60,000 | 42,695 | 17,305 |  | 1,211 |  |  |  |
| SRL/SEV/86/INS/57 | Extension of the institutional strengthening project (phase XIII: 1/2021-12/2022) | Dec-22 | 171,592 | 171,357 | 235 |  | 16 |  |  |  |
| SWA/PHA/83/PRP/27 | Preparation of a HCFC phase-out management plan (stage II) | Jun-21 | 10,000 | 9,059 | 941 |  | 66 |  |  |  |
| URU/PHA/77/INV/67 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Dec-20 | 100,000 | 62,211 | 37,789 |  | 2,645 |  |  |  |
| URU/PHA/85/INV/75 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector and implementation and monitoring) | Dec-22 | 111,268 | 104,570 | 6,698 |  | 469 |  |  |  |
| URU/SEV/84/INS/74 | Extension of institutional strengthening project (phase XIII: 1/2020-12/2021) | Apr-22 | 193,024 | 181,625 | 11,399 |  | 798 |  |  |  |
| VEN/SEV/82/INS/136 | Renewal of institutional strengthening project (phase XIV: 1/2019-12/2020) | Dec-22 | 365,414 | 363,110 | 2,305 |  | 162 |  |  |  |
| TOTAL UNDP |  |  |  |  | 395,885 |  | 29,230 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| AFG/PHA/77/INV/20 | HCFC phase-out management plan (stage I, second tranche) | Sep-21 | 131,938 | 131,427 | 511 |  | 46 | 2 | 94 |  |
| ALG/SEV/84/TAS/83 | Enabling activities for HFC phase-down | Jun-22 | 150,000 | 145,808 | 4,192 |  | 293 | 2 | 94 |  |
| ARG/PHA/79/INV/180 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Jun-22 | 645,746 | 642,391 | 3,355 |  | 235 | 2 | 94 |  |
| BDI/PHA/85/PRP/40 | Preparation of a HCFC phase-out management plan (stage II) | Dec-22 | 10,000 | 9,815 | 185 |  | 13 | 3 | 94 |  |
| BHE/PHA/72/INV/29 | HCFC phase-out management plan (stage I, second tranche) (activities in the refrigeration servicing sector including policy actions) | Dec-22 | 128,979 | 128,879 | 100 |  | 7 | 2 | 94 |  |
| BHE/PHA/76/INV/33 | HCFC phase-out management plan (stage I, third tranche) (activities in the refrigeration servicing sector including policy actions) | Dec-22 | 117,692 | 117,416 | 276 |  | 19 | 2 | 94 |  |
| BHE/PHA/82/INV/36 | HCFC phase-out management plan (stage I, fourth tranche) (activities in the refrigeration servicing sector including policy actions) | Dec-22 | 31,000 | 30,339 | 661 |  | 46 | 2 | 94 |  |
| BOT/PHA/75/INV/18 | HCFC phase-out management plan (stage I, first tranche) | Dec-22 | 140,000 | 132,272 | 7,728 |  | 541 | 3 | 94 |  |
| GAB/PHA/79/INV/34 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 119,900 | 108,729 | 11,171 |  | 1,005 | 2 | 94 |  |
| GLO/REF/80/DEM/344 | Global chiller replacement project (Argentina) | Dec-22 | 808,438 | 554,732 | 253,706 |  | 19,028 | 2 | 94 | 82/21(d), 86/17(h) and 88/15(b)(ii) |
| GUI/PHA/85/INV/34 | HCFC phase-out management plan (stage I, third tranche) | Jul-22 | 125,000 | 120,432 | 4,568 |  | 320 | 2 | 94 |  |
| IRQ/PHA/58/INV/09 | National phase-out plan (first tranche) | Jun-21 | 4,353,530 | 2,653,177 | 1,700,353 |  | 127,527 | 2 | 94 | 71/11(b), 73/8(c), 75/10(b)(i) and 79/7(c) |
| IRQ/PHA/74/INV/23 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Dec-21 | 230,000 | 229,936 | 64 |  | 5 | 2 | 94 |  |
| IRQ/PHA/84/INV/29 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | Dec-21 | 210,000 | 177,225 | 32,775 |  | 2,458 | 2 | 94 |  |
| IVC/PHA/84/INV/45 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 460,000 | 451,891 | 8,109 |  | 568 | 2 | 94 | 90/32(a) |
| JOR/PHA/77/INV/100 | HCFC phase-out management plan (stage II, first tranche) (polyurethane spray foam sector) | Dec-22 | 164,485 | 164,374 | 111 |  | 8 | 3 | 94 |  |
| JOR/PHA/84/INV/106 | HCFC phase-out management plan (stage II, second tranche) (polyurethane spray foam sector) | Dec-22 | 246,727 | 239,272 | 7,455 |  | 522 | 3 | 94 |  |
| KUW/PHA/66/INV/21 | HCFC phase-out management plan (stage I, first tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company) | Jun-22 | 3,510,450 | 3,506,188 | 4,262 |  | 320 | 2 | 94 |  |
| KUW/PHA/74/INV/24 | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector phase-out: Kuwait polyurethane Industry Co.; Kirby Building Systems, technical assistance to spray foam users and other small users) | Jun-22 | 643,382 | 637,195 | 6,187 |  | 433 | 2 | 94 |  |
| KUW/PHA/74/INV/25 | HCFC phase-out management plan (stage I, second tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company) | Jun-22 | 2,706,000 | 2,703,464 | 2,536 |  | 177 | 2 | 94 |  |
| KUW/PHA/83/TAS/37 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | Jun-22 | 218,000 | 28,335 | 189,665 |  | 13,277 | 2 | 94 |  |
| KUW/PHA/88/INV/45 | HCFC phase-out management plan (stage I, fourth tranche) (extruded polystyrene foam sector phase-out) | Jun-22 | 877,675 | 876,444 | 1,231 |  | 86 | 2 | 94 |  |
| KUW/PHA/88/INV/46 | HCFC phase-out management plan (stage I, fourth tranche) (polyurethane foam sector phase-out) | Jun-22 | 42,325 | 42,289 | 36 |  | 3 | 2 | 94 |  |
| MAG/PHA/84/PRP/33 | Preparation of a HCFC phase-out management plan (stage II) | Dec-22 | 20,000 | 19,232 | 768 |  | 54 | 3 | 94 |  |
| MOZ/PHA/66/INV/23 | HCFC phase-out management plan (stage I, first tranche) | Dec-22 | 75,000 | 74,225 | 775 |  | 70 | 3 | 94 |  |
| MYA/PHA/80/INV/19 | HCFC phase-out management plan (stage I, second tranche) | Dec-22 | 60,000 | 53,880 | 6,120 |  | 551 | 3 | 94 |  |
| NER/KIP/87/PRP/40 | Preparation of Kigali HFC implementation plan | Dec-22 | 170,000 | 169,632 | 368 |  | 26 | 3 | 94 |  |
| SEN/PHA/85/INV/41 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 50,000 | 48,582 | 1,418 |  | 106 | 2 | 94 |  |
| SEN/PHA/85/PRP/43 | Preparation of a HCFC phase-out management plan (stage II) | Jun-22 | 20,000 | 13,145 | 6,855 |  | 480 | 2 | 94 |  |
| SOM/PHA/77/INV/12 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Dec-22 | 141,500 | 141,442 | 58 |  | 4 | 3 | 94 | 88/40(a) |
| SYR/REF/62/INV/103 | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group | Dec-21 | 1,465,361 | 1,462,556 | 2,805 |  | 210 | 2 | 94 |  |
| TOTAL UNIDO |  |  |  |  | 2,258,404 |  | 168,437 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS

| CODE | Project title | Approved funding plus adjustments as of 31 December 2022 (US $) | Funds disbursed as of 93rd meeting (US $) | Balances committed as per 93rd meeting (US $) | Balances not- committed as per 93rd meeting (US $) | Support cost on balances committed and not-committed as per 93rd meeting (US $) | Why any balances could not be returned? | When they could be returned? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |
| CHI/SEV/80/TAS/03+ | Enabling activities for HFC phase-down | 33,000 | 27,058 | 5,942 |  | 416 |  |  |
| URU/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 100,000 | 98,509 | 1,491 |  | 104 |  |  |
| TOTAL UNDP |  |  |  | 7,433 |  | 520 |  |  |
| UNIDO |  |  |  |  |  |  |  |  |
| ARG/REF/81/INV/01+ | Conversion project for replacement of HFC-134a with isobutane (R-600a)/propane (R-290)-based refrigerant in the manufacture of domestic and commercial refrigeration equipment at Briket, Bambi and Mabe-Kronen | 1,840,755 | 1,835,494 | 5,261 |  | 368 | 1 | 94 |
| ARG/SEV/81/TAS/02+ | Enabling activities for HFC phase-down | 250,000 | 199,189 | 50,811 |  | 3,557 | 1 | 94 |
| EGY/SEV/81/TAS/02+ | Enabling activities for HFC phase-down | 105,000 | 101,318 | 3,682 |  | 258 | 1 | 94 |
| MOR/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 150,000 | 95,809 | 54,191 |  | 3,793 | 1 | 94 |
| VEN/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 250,000 | 249,800 | 200 |  | 14 | 1 | 94 |
| TOTAL UNIDO |  |  |  | 114,144 |  | 7,990 |  |  |

Annex III

DETAILS ON COMPLETED, BY DECISIONS AND ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES

| Code | Project title | Project costs returned (US $) | Agency support costs (US $) | Total (US $) |
| --- | --- | --- | --- | --- |
| BGD/SEV/83/INS/55 | Renewal of the institutional strengthening project (phase IX: 7/2019-6/2021) | 18 | 1 | 19 |
| BZE/PHA/50/PRP/17 | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | 1 | 0 | 1 |
| BZE/PHA/82/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | 1,250 | 87 | 1,338 |
| CHI/SEV/83/INS/198 | Extension of the institutional strengthening project (phase XIII: 7/2019-6/2021) | 169 | 12 | 181 |
| COL/PHA/81/INV/102 | HCFC phase-out management plan (stage II, second tranche) (foam sector) | 542,962 | 38,007 | 580,969 |
| COL/SEV/79/INS/101 | Extension of institutional strengthening project (phase XI: 11/2017-10/2019) | 773 | 54 | 827 |
| COL/SEV/83/INS/106 | Extension of institutional strengthening project (phase XII: 11/2019-10/2021) | 2,624 | 184 | 2,808 |
| COS/SEV/84/INS/62 | Extension of institutional strengthening project (phase XIII: 1/2020-12/2021) | 362 | 25 | 387 |
| ELS/PHA/79/TAS/36 | Verification report for stage I of HCFC phase-out management plan | 835 | 75 | 910 |
| GUY/PHA/75/INV/28 | HCFC phase-out management plan (stage II, first tranche) | 1,893 | 133 | 2,026 |
| IDS/SEV/84/INS/215 | Extension of institutional strengthening project (phase XII: 1/2020-12/2021) | 2,244 | 157 | 2,401 |
| IND/SEV/84/INS/478 | Extension of institutional strengthening project (phase XII: 12/2019-11/2021) | 1,547 | 108 | 1,655 |
| IRA/SEV/82/INS/231 | Extension of the institutional strengthening project (phase XII: 4/2019-3/2021) | 474 | 33 | 507 |
| JAM/PHA/84/TAS/39 | Verification report on the implementation of the HCFC phase-out management plan | 3,421 | 308 | 3,729 |
| JAM/PHA/85/INV/41 | HCFC phase-out management plan (stage I, fourth tranche) | 3,102 | 233 | 3,335 |
| MAL/SEV/84/INS/188 | Extension of institutional strengthening project (phase XIII: 1/2020-12/2021) | 438 | 31 | 469 |
| PAN/SEV/80/INS/45 | Extension of institutional strengthening project (phase VIII: 12/2017-11/2019) | 1 | 0 | 1 |
| TOG/PHA/48/PRP/13 | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | 1 | 0 | 1 |
| TRI/PHA/82/PRP/36 | Preparation of a HCFC phase-out management plan (stage II) | 806 | 56 | 862 |
| Total completed projects |  | 562,920 | 39,505 | 602,425 |
| TOTAL UNDP |  | 562,920 | 39,505 | 602,425 |
| AFG/SEV/83/INS/26 | Extension of institutional strengthening project (phase IX: 1/2020-12/2021) | 38,119 | 0 | 38,119 |
| ALB/SEV/84/INS/38 | Renewal of institutional strengthening project (phase IX: 7/2020-6/2022) | 1,109 | 0 | 1,109 |
| BDI/SEV/85/TAS/39 | Enabling activities for HFC phase-down | 50,000 | 3,500 | 53,500 |
| BEN/PHA/84/PRP/37 | Preparation of a HCFC phase-out management plan (stage II) | 9,800 | 1,274 | 11,074 |
| BGD/SEV/81/TAS/54 | Enabling activities for HFC phase-down | 3,582 | 251 | 3,833 |
| BHA/PHA/84/PRP/30 | Preparation of a HCFC phase-out management plan (stage II) | 4,850 | 631 | 5,481 |
| BHU/PHA/76/TAS/25 | HCFC phase-out management plan (third tranche) | 10 | 1 | 11 |
| BHU/SEV/83/INS/28 | Extension of institutional strengthening project (phase VIII: 12/2019-11/2021) | 2,407 | 0 | 2,407 |
| BOT/PHA/82/TAS/22 | HCFC phase-out management plan (stage I, second tranche) | 9,481 | 1,232 | 10,713 |
| BOT/PHA/83/PRP/23 | Preparation of a HCFC phase-out management plan (stage II) | 3,255 | 423 | 3,678 |
| BOT/PHA/86/TAS/25 | HCFC phase-out management plan (stage I, third tranche) | 47,627 | 6,192 | 53,819 |
| BOT/SEV/76/INS/19 | Extension of institutional strengthening project (phase V: 6/2016-7/2018) | 65,956 | 0 | 65,956 |
| BRU/PHA/82/TAS/24 | HCFC phase-out management plan (stage I, third tranche) | 5,977 | 777 | 6,754 |
| CKI/PHA/74/TAS/11 | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Cook Islands) | 3,169 | 412 | 3,581 |
| CKI/PHA/85/TAS/16 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | 2,500 | 325 | 2,825 |
| CKI/SEV/84/INS/15 | Extension of the institutional strengthening project (phase VII: 7/2020-6/2022) | 5,000 | 0 | 5,000 |
| DJI/PHA/88/TAS/28 | HCFC phase-out management plan (stage I, fourth tranche) | 95 | 12 | 107 |
| DRC/SEV/87/INS/47 | Extension of the institutional strengthening project (phase X: 7/2021-6/2023) | 200 | 0 | 200 |
| ELS/PHA/86/TAS/40 | HCFC phase-out management plan (stage I, fourth tranche) | 32 | 1 | 33 |
| EQG/PHA/86/TAS/17 | Verification report on the implementation of the HCFC phase-out management plan | 240 | 31 | 271 |
| FSM/PHA/85/TAS/15 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | 142 | 18 | 161 |
| FSM/SEV/84/INS/13 | Renewal of institutional strengthening project (phase VII: 7/2020-6/2022) | 1,987 | 0 | 1,987 |
| GAB/PHA/87/TAS/41 | HCFC phase-out management plan (stage I, fifth tranche) | 200 | 26 | 226 |
| GLO/SEV/84/TAS/350 | Compliance Assistance Programme: 2020 budget | 79,692 | 6,375 | 86,067 |
| GLO/SEV/86/TAS/356 | Compliance Assistance Programme: 2021 budget | 212,006 | 16,960 | 228,967 |
| GLO/SEV/88/TAS/357 | Compliance Assistance Programme: 2022 budget | 599,922 | 47,994 | 647,915 |
| GRN/PHA/82/PRP/25 | Preparation of a HCFC phase-out management plan (stage II) | 9,800 | 1,274 | 11,074 |
| GRN/PHA/82/TAS/26 | Verification report on the implementation of the HCFC phase-out management plan | 18,890 | 2,456 | 21,346 |
| GUI/SEV/85/TAS/36 | Enabling activities for HFC phase-down | 50,000 | 3,500 | 53,500 |
| HAI/SEV/75/INS/20 | Extension of the institutional strengthening project (phase IV: 11/2015-10/2017) | 73,671 | 0 | 73,671 |
| HON/PHA/86/TAS/51 | HCFC phase-out management plan (stage I, fifth tranche) | 255 | 33 | 288 |
| IND/PHA/77/TAS/470 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector plan) | 144 | 17 | 161 |
| IND/PHA/87/PRP/490 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | 2,000 | 260 | 2,260 |
| IRA/SEV/82/TAS/233 | Enabling activities for HFC phase-down | 30,333 | 2,123 | 32,457 |
| IVC/PHA/90/TAS/48 | HCFC phase-out management plan (stage I, fifth tranche) | 380 | 46 | 426 |
| KAM/PHA/84/TAS/38 | Verification report on the implementation of the HCFC phase-out management plan | 4,900 | 637 | 5,537 |
| KUW/PHA/66/TAS/19 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector and monitoring and verification) | 50,071 | 5,988 | 56,059 |
| KUW/PHA/74/TAS/23 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector and monitoring and verification) | 113,335 | 13,553 | 126,888 |
| KUW/PHA/88/TAS/44 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing sector) | 24,000 | 2,870 | 26,870 |
| LAO/PHA/85/TAS/34 | HCFC phase-out management plan (stage I, third tranche) | 5,055 | 657 | 5,712 |
| MAG/PHA/84/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | 14,900 | 1,937 | 16,837 |
| MAS/PHA/74/TAS/11 | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Marshall Islands) | 3,370 | 438 | 3,809 |
| MAS/PHA/85/TAS/16 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | 2,900 | 377 | 3,277 |
| MAU/PHA/80/TAS/24 | HCFC phase-out management plan (stage I, first tranche) | 155 | 20 | 175 |
| MLI/PHA/83/TAS/40 | HCFC phase-out management plan (stage I, fourth tranche) | 200 | 26 | 226 |
| MLI/PHA/86/TAS/43 | Verification report on the implementation of the HCFC phase-out management plan | 205 | 27 | 232 |
| MLW/PHA/85/TAS/47 | HCFC phase-out management plan (stage II, first tranche) | 510 | 66 | 576 |
| MOZ/PHA/86/TAS/35 | Verification report on the implementation of the HCFC phase-out management plan | 26 | 3 | 30 |
| NAU/PHA/74/TAS/10 | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Nauru) | 5,776 | 751 | 6,527 |
| NAU/PHA/85/TAS/13 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | 4,370 | 568 | 4,938 |
| NEP/PHA/75/TAS/34 | HCFC phase-out management plan (stage I, second tranche) | 10,575 | 1,375 | 11,950 |
| NEP/PHA/86/TAS/42 | HCFC phase-out management plan (stage I, third tranche) | 6,487 | 843 | 7,330 |
| NIU/PHA/85/TAS/15 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | 3,051 | 397 | 3,448 |
| PAK/PHA/76/TAS/93 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 2,525 | 328 | 2,853 |
| PAK/PHA/85/PRP/104 | Preparation of a HCFC phase-out management plan (stage III) | 4,583 | 596 | 5,179 |
| PAR/PHA/86/TAS/40 | HCFC phase-out management plan (stage I, third tranche) | 44 | 6 | 50 |
| PAR/SEV/82/INS/38 | Extension of institutional strengthening project (phase IX: 1/2019-12/2020) | 3,805 | 0 | 3,805 |
| PER/PHA/80/TAS/54 | HCFC phase-out management plan (stage II, first tranche) | 48 | 6 | 54 |
| SAU/PHA/68/TAS/16 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | 3,375 | 418 | 3,793 |
| SAU/PHA/77/TAS/32 | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring) | 4,125 | 511 | 4,636 |
| SEN/PHA/85/PRP/42 | Preparation of a HCFC phase-out management plan (stage II) | 42 | 5 | 47 |
| SIL/PHA/84/PRP/35 | Preparation of a HCFC phase-out management plan (stage II) | 4,658 | 606 | 5,264 |
| SOI/PHA/74/TAS/11 | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Solomon Islands) | 3,234 | 420 | 3,654 |
| SOI/PHA/85/TAS/17 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | 13 | 2 | 14 |
| SSD/PHA/84/TAS/05 | Verification report on the implementation of the HCFC phase-out management plan | 42 | 6 | 48 |
| SUD/SEV/81/INS/43 | Extension of institutional strengthening (phase IX: 7/2018-6/2020) | 18 | 0 | 18 |
| SUR/PHA/86/TAS/31 | Verification report on the implementation of the HCFC phase-out management plan | 4,750 | 618 | 5,368 |
| SWA/PHA/86/TAS/30 | Verification report on the implementation of the HCFC phase-out management plan | 42 | 6 | 48 |
| TLS/SEV/82/TAS/19 | Enabling activities for HFC phase-down | 3,331 | 233 | 3,565 |
| TLS/SEV/84/INS/20 | Extension of institutional strengthening (phase V: 7/2020-6/2022) | 2,746 | 0 | 2,746 |
| TOG/PHA/83/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | 9,800 | 1,274 | 11,074 |
| TOG/PHA/87/TAS/36 | HCFC phase-out management plan (stage I, fifth tranche) | 120 | 16 | 136 |
| TON/PHA/74/TAS/10 | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Tonga) | 1,891 | 246 | 2,137 |
| TUV/PHA/74/TAS/11 | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Tuvalu) | 1,981 | 257 | 2,238 |
| TUV/PHA/85/TAS/16 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | 2,000 | 260 | 2,260 |
| VAN/PHA/85/TAS/17 | HCFC phase-out management plan for PIC countries through regional approach (stage I, third tranche) | 3,750 | 487 | 4,237 |
| VAN/SEV/84/INS/15 | Extension of institutional strengthening project (phase VII: 7/2020-6/2022) | 5,000 | 0 | 5,000 |
| Total completed projects |  | 1,644,641 | 132,980 | 1,777,621 |
| AFG/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 13,112 | 918 | 14,030 |
| BEN/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 21,115 | 1,478 | 22,593 |
| BOT/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 53,352 | 3,735 | 57,087 |
| CBI/SEV/82/TAS/01+ | Enabling activities for HFC phase-down | 15,962 | 1,117 | 17,079 |
| CHD/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 19,800 | 1,386 | 21,186 |
| CKI/SEV/82/TAS/01+ | Enabling activities for HFC phase-down | 2,290 | 160 | 2,450 |
| COI/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 4,758 | 333 | 5,091 |
| DJI/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 27,578 | 1,930 | 29,508 |
| DRC/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 17,766 | 1,244 | 19,010 |
| EQG/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 36,846 | 2,579 | 39,425 |
| GAB/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 15,798 | 1,106 | 16,904 |
| GBS/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 24,197 | 1,694 | 25,891 |
| GUY/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 40,000 | 2,800 | 42,800 |
| IVC/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 14,395 | 1,008 | 15,403 |
| KEN/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 652 | 46 | 698 |
| KIR/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 17,102 | 1,197 | 18,299 |
| LAO/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 40,918 | 2,864 | 43,782 |
| MAG/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 34,446 | 2,411 | 36,857 |
| MAS/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 12,418 | 869 | 13,287 |
| MAU/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 47,662 | 3,336 | 50,998 |
| MDV/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 199 | 14 | 213 |
| MLI/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 1,931 | 135 | 2,066 |
| MYA/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 41,377 | 2,896 | 44,273 |
| NEP/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 7,835 | 548 | 8,383 |
| PAR/SEV/81/TAS/02+ | Enabling activities for HFC phase-down | 4,343 | 304 | 4,647 |
| SOI/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 6,345 | 444 | 6,789 |
| SRL/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 977 | 68 | 1,045 |
| STP/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 11,085 | 776 | 11,861 |
| SUD/SEV/80/TAS/02+ | Enabling activities for HFC phase-down | 5,833 | 408 | 6,241 |
| SUR/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 29,350 | 2,055 | 31,405 |
| SYR/SEV/83/TAS/01+ | Enabling activities for HFC phase-down | 31,765 | 2,224 | 33,989 |
| Total “additional voluntary contributions” projects |  | 601,206 | 42,084 | 643,290 |
| TOTAL UNEP |  | 2,245,847 | 175,064 | 2,420,911 |
| BAH/FOA/84/PRP/35 | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | 687 | 48 | 735 |
| BHE/PHA/87/INV/40 | HCFC phase-out management plan (stage I, fifth tranche) | 6,105 | 427 | 6,532 |
| BHE/SEV/80/INS/34 | Extension of the institutional strengthening project (phase VI: 3/2018-2/2020) | 32 | 3 | 35 |
| CHD/PHA/82/PRP/33 | Preparation of a HCFC phase-out management plan (stage II) | 857 | 60 | 917 |
| CPR/PHA/75/INV/564 | HCFC phase-out management plan (stage I, fifth tranche) (room air conditioner manufacturing sector plan) | 22,180 | 1,553 | 23,733 |
| EQG/PHA/84/PRP/15 | Preparation of a HCFC phase-out management plan (stage II) | 1,602 | 112 | 1,715 |
| GAM/PHA/82/PRP/37 | Preparation of a HCFC phase-out management plan (stage II) | 770 | 54 | 824 |
| GBS/PHA/81/PRP/23 | Preparation of a HCFC phase-out management plan (stage II) | 89 | 6 | 95 |
| KUW/PHA/83/INV/36 | HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector phase-out) | 17,780 | 1,245 | 19,024 |
| MOR/FOA/73/PRP/71 | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | 11,672 | 817 | 12,489 |
| MOR/PHA/73/PRP/70 | Preparation of a HCFC phase-out management plan (stage II) | 23,633 | 1,654 | 25,287 |
| NIR/PHA/81/INV/146 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector and project management unit) | 90 | 8 | 98 |
| PAK/PHA/85/PRP/105 | Preparation of a HCFC phase-out management plan (stage III) (foam sector) | 7,363 | 515 | 7,878 |
| PRC/PHA/81/PRP/34 | Preparation of a HCFC phase-out management plan (stage II) | 481 | 34 | 514 |
| SAU/PHA/72/INV/20 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring) | 25,449 | 1,782 | 27,231 |
| SAU/PHA/75/INV/24 | HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan) | 200,387 | 14,027 | 214,414 |
| SUD/PHA/82/INV/44 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 2,170 | 152 | 2,322 |
| TOG/PHA/79/INV/30 | HCFC phase-out management plan (stage I, third tranche) | 1,951 | 146 | 2,097 |
| VEN/PHA/76/TAS/132 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 166 | 12 | 177 |
| Total completed projects |  | 323,465 | 22,654 | 346,119 |
| SAU/REF/76/DEM/28 | Demonstration project on promoting HFO-based low-global warming potential refrigerants for air-conditioning sector in high ambient temperatures. | 114,237 | 7,997 | 122,234 |
| Total “by-decision” projects |  | 114,237 | 7,997 | 122,234 |
| LIB/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 2,492 | 174 | 2,667 |
| MEX/REF/81/INV/04+ | Conversion of commercial refrigeration manufacturing in two facilities from the use of HFC-134a and R-404A as the refrigerants to propane (R-290) and isobutane (R-600a) at Imbera | 92,426 | 6,469 | 98,895 |
| PHI/SEV/83/TAS/02+ | Enabling activities for HFC phase-down | 18,703 | 1,309 | 20,012 |
| Total “additional voluntary contributions” projects |  | 113,621 | 7,952 | 121,573 |
| TOTAL UNIDO |  | 551,323 | 38,603 | 589,926 |
| GLO/SEV/88/TAS/358 | Core unit budget (2022) | 0 | 280,124 | 280,124 |
| JOR/PHA/88/PRP/112 | Preparation of HCFC phase-out management plan (stage III) (commercial refrigeration manufacturing) | 30,000 | 2,100 | 32,100 |
| MAL/KIP/91/PRP/194 | Preparation of HFC investment projects in fire fighting sector | 150,000 | 10,500 | 160,500 |
| VIE/KIP/92/PRP/85 | Preparation of a KIP investment project in the commercial refrigeration sector for Sanaky | 30,000 | 2,100 | 32,100 |
| VIE/KIP/92/PRP/86 | Preparation of a KIP investment project in the domestic refrigeration sector for Aqua Electrical Appliances, Darling Electronics, and Hoa Phat Refrigeration Engineering | 80,000 | 5,600 | 85,600 |
| VIE/KIP/92/PRP/88 | Conversion of refrigerator manufacture from CFC-11 to cyclopentane foam blowing agent and CFC-12 to R-134a refrigerant at Domestic Appliances Ltd. (DAL) | 30,000 | 2,100 | 32,100 |
| Total completed projects |  | 320,000 | 302,524 | 622,524 |
| TOTAL WORLD BANK |  | 320,000 | 302,524 | 622,524 |
| LAO/PHA/74/INV/28 | HCFC phase-out management plan (stage I, second tranche) | 40,500 | 5,265 | 45,765 |
| LAO/PHA/85/TAS/35 | HCFC phase-out management plan (stage I, third tranche) | 4,500 | 585 | 5,085 |
| TOTAL FRANCE |  | 45,000 | 5,850 | 50,850 |

UNEP/OzL.Pro/ExCom/93/1

Los datos presentados se basan en el formato de presentación de informes que se ha elaborado en respuesta a la decisión 31/2.

UNEP/OzL.Pro/ExCom/93/3

1: Funds returned in previous meetings; no action needed. 2: Financial closure-initiated funds not returned due to ongoing unpaid obligations. 3: Since funds can be returned up to one year after operational completion, funds will be returned in 94th meeting.

1: Financial closure-initiated fund not returned due to ongoing unpaid obligations.