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关于有具体报告要求项目的报告：没有未决问题的报告

 
概述
 
1. 本文件包括了数个项目报告，涉及含氢氯氟烃淘汰管理计划相关项目[footnoteRef:2],[footnoteRef:3],[footnoteRef:4]，基加利修正案氢氟碳化合物执行计划协议，维持制冷维修行业能源效率的额外活动（第89/6号决定），一个机构变更申请及多个项目撤销申请。表1列出了提交第九十七次会议审议的有特定报告要求项目的报告，经秘书处审查后确认这些报告均无未解决事项，无需执行委员会逐项审议。 [2:  根据第96/8(b)和第95/19(b)号决定，阿根廷提交了一份报告，旨在更新泡沫行业低全球升温潜能值HCFC-141b替代品的本地市场供应情况，以及高全球升温潜能值替代品的过渡使用进展。该报告详见阿根廷项目提案文件（UNEP/OzL.Pro/ExCom/97/36）。]  [3:  根据第94/32号决定，孟加拉国向第九十七次会议提交了关于最终付款工作计划的实施报告，涵盖项目完成情况和直到第九十七次会议第三阶段批准时的核查报告。该报告详见孟加拉国项目提案文件（UNEP/OzL.Pro/ExCom/97/37）。]  [4:  根据第94/34(c)和(d)号决定，中国提交了一份评估方法报告，用于测算多边基金资助企业为满足含氢氯氟烃淘汰管理计划家用空调及热泵热水器制造行业中，由于需要将使用含氢氯氟烃的生产线转为R-290生产线所产生的需求，而可能逐步采用的氢氟碳化合物吨数。该报告详见中国项目提案文件（UNEP/OzL.Pro/ExCom/97/44）。] 

表1.	关于有具体报告要求且没有未决问题项目的报告
	国家
	项目名称
	段落

	A. 与含氢氯氟烃淘汰管理计划（HPMPs）有关的报告

	巴林
	含氢氯氟烃淘汰管理计划（第二阶段–关于第三次即最后一次付款相关工作计划执行情况的进度报告）
	2-15

	伊拉克
	含氢氯氟烃淘汰管理计划（第二阶段–第一阶段完成情况、国家淘汰计划，以及轻工业中家用制冷制造行业使用异丁烷替代CFC-12、环戊烷替代CFC-11的项目）
	16-22

	黎巴嫩
	含氢氯氟烃淘汰管理计划（第二阶段–关于第四次即最后一次付款相关工作计划执行情况的进度报告）
	23-33

	莱索托王国
	含氢氯氟烃淘汰管理计划（第二阶段–依据第87/41(b)号决定要求上交的关于可燃制冷剂安全标准采用情况与技术员强制认证体系建设进度的报告
	34-41

	巴基斯坦
	含氢氯氟烃淘汰管理计划（第三阶段–关于聚氨酯泡沫行业酷点（Cool Point）企业生产线转换的行动计划）
	42-52

	B. 与基加利氢氟碳化合物执行计划（KIP）协议相关的报告

	多国
	根据基加利氢氟碳化合物执行计划第一阶段要求制定的氢氟碳化合物消费量削减协议
	53-57

	C. [bookmark: _Hlk182927302][bookmark: _Hlk182927260]关于维持制冷维修行业能源效率的额外活动的报告（第89/6号决定） 

	吉尔吉斯斯坦
	根据第89/6(b)号决定开展的维持制冷维修行业能源效率的额外活动（最终进度报告）
	58-63

	D. 请求变更执行机构 

	亚美尼亚
	含氢氯氟烃淘汰管理计划（第三阶段）及基加利氢氟碳化合物执行计划（第一阶段）（变更执行机构）
	64-76

	E. 请求取消多个项目

	尼加拉瓜
	该政府提出的取消正在执行项目的申请
	77-84



A. 含氢氯氟烃淘汰管理计划相关报告
[bookmark: OLE_LINK1][bookmark: OLE_LINK281]巴林：含氢氯氟烃淘汰管理计划（第二阶段–关于第三次即最后一次付款相关工作计划执行情况的进度报告）（环境规划署和工发组织）
背景

2. 执行委员会在批准巴林含氢氯氟烃淘汰管理计划（HPMP）第二阶段第三次即最后一次付款时，曾要求巴林政府、环境规划署和工发组织按年度提交最后一次付款相关工作计划执行进度报告（直至项目完成）和直至第三阶段批准前的核查报告，并在2027年执行委员会第二次会议提交项目完工报告（PCR）（第95/34号决定）。
3. 根据第95/34号决定，环境规划署作为牵头机构，已代表巴林政府向本次会议提交了关于最后一次付款相关工作计划执行情况的进度报告。
进度报告

含氢氯氟烃消费量与核查情况
4. 巴林政府报告2024年含氢氯氟烃消费量为28.57 ODP吨，较该国含氢氯氟烃基准量低45%，符合当年最大允许消费量规定。2024年度消费量核查报告尚未提交。


法律框架
5. [bookmark: _Hlk180145135]巴林政府于2024年7月批准了基加利修正案。自2025年1月1日起，已实施对预混多元醇中含HCFC-141b的进口和使用禁令，以及基于HCFC-22的空调设备的进口和生产禁令。
制造行业
6. 淘汰泡沫行业进口预混多元醇中所含135.93公吨HCFC-141b的行业整体淘汰项目已经完成。已经禁止进口预混多元醇中所含HCFC-141b。 
7. 巴林自2025年1月起已禁止HCFC-22空调设备的进口与制造。因此该国唯一生产此类设备的阿瓦尔（Awal）海湾制造公司 (AGM)已停止生产此类设备。此举确保了该禁令在制造行业得到全面落实。
制冷维修行业
8. 第三次付款计划的所有维修行业活动均已完成：
(a) [bookmark: _Hlk126934425][bookmark: _Hlk126663552]作为专项宣传活动的一部分，为政府部门及相关利益攸关方举办了一场包含互动讨论的研讨会，旨在提升对蒙特利尔议定书的认识，推广并实施海湾合作委员会（GCC）最新法规。共有66名参与者出席，其中18名为女性；
(b) 举办了四期培训课程，对40名新入职海关官员进行了包括风险分析在内的关于蒙特利尔议定书及含氢氯氟烃管控的培训；
(c) 与当地机构合作举办了两期培训课程，对来自25家企业的40名技术人员进行了制冷与空调（RAC）良好维护实践的培训及认证；以及
(d) 向培训中心分发了培训工具及设备[footnoteRef:5]； [5:  包括制冷剂储存罐、各类气体储存罐、铜管及回收机。] 

项目执行与监督
9. 项目管理办公室负责活动实施、进展监控及成果汇报。在第三次付款中获批的10,000美元项目管理办公室经费，已支付8,000美元，具体构成为：人员及顾问费用5,600美元，会议及研讨会开支2,400美元。
资金发放情况
10. 截至2025年10月，第二阶段批准资金总额662,999美元中已发放654,559美元（其中环境规划署375,677美元，工发组织278,882美元），具体见表2。剩余8,440美元将于2025年12月31日前发放。
表2.	巴林含氢氯氟烃淘汰管理计划第二阶段财务报告（美元）
	付款批次
	环境规划署
	工发组织
	共计
	发放率（%）

	第一次
	批准资金额
	249,500
	203,999
	453,499
	100

	
	发放资金额
	249,500
	203,999
	453,499
	

	第二次
	批准资金额
	79,500
	54,000
	133,500
	98.9

	
	发放资金额
	78,177
	53,903
	132,080
	

	第三次
	批准资金额
	55,000
	21,000
	76,000
	90.8

	
	发放资金额
	48,000
	20,980
	68,980
	

	共计
	批准资金额
	384,000
	278,999
	662,999
	98.7

	
	发放资金额
	375,677
	278,882
	654,559
	

	
	余额
	8,323
	117
	8,440
	


秘书处的评论
进度报告
法律框架 
11. 巴林政府已核发2025及2026年度含氢氯氟烃进口配额，均为13.75 ODP吨，该配额既符合蒙特利尔议定书管控目标，也达到了与执行委员会签订协议中设定的减排目标。 
制造行业 
12. 制造行业含氢氯氟烃淘汰工作已完成，共淘汰16.50 ODP吨。已颁布禁令，禁止预混多元醇中HCFC-141b进口，和基于HCFC-22的空调设备进口和制造，这将持续巩固制造业的淘汰成果，并强化已实现的减排量。
制冷维修行业
13. 维修行业所有计划活动均已顺利完成。环境规划署确认将于2026年第二次会议提交项目完成报告。
结论
14. 巴林已成功实现与执行委员会所签协议及蒙特利尔议定书规定的含氢氯氟烃管控目标，消费量持续下降。该国通过有效实施许可证与配额制度，对含氢氯氟烃及相关设备的进口实行严格管控。制造业的淘汰成果通过以下禁令得以持续巩固：禁止进口和使用预混多元醇中的HCFC-141b，以及禁止进口和制造采用HCFC-22的设备。在制冷空调维修行业，已提供相关设备和工具以支持强制性的技术人员培训与认证计划；回收制冷剂数量的持续增长有效减少了维修领域对新制冷剂的需求。所有第二阶段活动均已完成，项目完成报告将提交至2026年第二次会议。当前资金发放率已达99%。
建议
15. 执行委员会可以：
(a) 注意到环境规划署提交的、载于文件UNEP/OzL.Pro/ExCom/97/17的巴林含氢氯氟烃淘汰管理计划第二阶段第三次即最后一次付款相关工作计划执行进度报告；以及
(b) 请环境规划署向第九十八次会议提交2024年度消费量核查报告。
伊拉克：含氢氯氟烃淘汰管理计划（第二阶段–第一阶段完成情况，国家淘汰计划，以及轻工业公司家用制冷制造行业使用异丁烷替代CFC-12、环戊烷替代CFC-11的项目）（环境规划署与工发组织）
背景
16. 执行委员会第八十七次会议批准了伊拉克含氢氯氟烃淘汰管理计划第二阶段，并明确指出其第二次付款的审议前提是必须完成以下项目：含氢氯氟烃淘汰管理计划第一阶段（IRQ/PHA/74/INV/23），国家淘汰计划（IRQ/PHA/58/INV/09），以及轻工业公司家用冰箱和冷冻柜制造中采用异丁烷替代制冷剂CFC-12、环戊烷替代发泡剂CFC-11的项目（IRQ/REF/57/INV/07）（第87/40(c)号决定）。在第二次付款申请提交到第九十五次会议时，工发组织尚未完成上述项目；因此那次付款仅批准环境规划署执行活动的资金，同时明确在条件满足前不再考虑向工发组织提供进一步资金。此外，作为特例，将含氢氯氟烃淘汰管理计划第一阶段及项目IRQ/REF/57/INV/07和IRQ/PHA/58/INV/09的完成期限延长至2025年12月31日，前提是工发组织须在其2024年度进度报告和财务进度报告中将后两个项目的实施状态更正为“进行中”（ONG），并向第九十六次会议提交所有三个项目的执行进度报告（第95/52号决定）。
17. 在第九十六次会议上，工发组织提交的进度报告表明：在含氢氯氟烃淘汰管理计划项下，原计划采购40台制冷剂识别仪的剩余资金已被重新分配用于采购技术人员所需的其它必要工具；在国家淘汰计划项下，纳塞尔（Nassr）国营公司已开始设备调试、安装和测试工作，而伊拉克钢铁公司和轻工业公司均预计在2025年4月底前完成设备安装与调试的合同授予。执行委员会注意到了该报告，并请工发组织向第九十七次会议提交关于这些项目完成情况的进度报告（第96/9号决定）。
进度报告
18. 工发组织代表伊拉克政府提交了以下项目的进度报告：

(a) 含氢氯氟烃淘汰管理计划（第一阶段第二次付款）（维修行业技术援助）：如第九十六次会议所报告，原计划采购40台制冷剂识别仪的专项资金已调整用于为100名技术人员采购其它必要工具[footnoteRef:6]；根据批准的延期安排，所有活动（包括向受益方分发工具）将于2025年12月前完成; [6:  包括检测多种制冷剂的电子检漏仪、注油泵、便携式氮气吹扫设备、扭矩扳手工具组、洛克环压钳、装配夹具及不同直径的连接件。] 

(b) 国家淘汰计划（两家聚氨酯泡沫生产企业完成从CFC-11向环戊烷的技术转换）：纳塞尔国营公司已完成设备调试，正在等待后续工作（核查、安全检测及启动商业化生产）。根据批准的延期安排，该项目预计于2025年12月底前完成。伊拉克钢铁公司已通知工发组织将退出该项目，并承诺利用自有资源独立完成设备安装，同时保证在泡沫生产过程中不使用含氢氯氟烃或氢氟碳化合物。为此，工发组织建议取消该项目并退回全部剩余预算；以及
(c) 轻工业公司家用制冷设备制造中以异丁烷替代CFC-12、以环戊烷替代CFC-11的项目：该企业目前正在进行设备安装的场地准备工作；若此项工作能按时完成，技术转换预计将于2025年12月前全面完成。
资金发放情况报告
19. 截至2025年9月，含氢氯氟烃淘汰管理计划第一阶段第二次付款的资金支付率为29.1%，国家淘汰计划的资金支付率为93.7%；而轻工业公司技术转换项目获批总额2,161,581美元已全部支付完毕（详见表3）。剩余款项将于2025年12月前完成支付。
表3.	截至2025年9月伊拉克待完成项目财务报告（美元）
	项目
	批准资金额
	发放资金额
	发放率（%）
	资金余额

	含氢氯氟烃淘汰管理计划（第一阶段，第二次付款）
	230,000
	66,856
	29.1
	*163,144

	国家淘汰计划（纳塞尔国营公司和伊拉克钢铁公司）
	4,353,530
	4,080,068
	93.7
	**273,462

	轻工业公司的技术转换
	2,161,581
	2,161,581
	100
	0


*包含为技术人员采购工具和设备而预留的155,080美元。
**包含为正在进行的企业转换活动而预留的180,503美元。
秘书处的评论
20. 秘书处注意到，根据执行委员会批准的延期安排，含氢氯氟烃淘汰管理计划第一阶段及纳塞尔公司的生产线转换将于2025年12月前完成。关于另外两家企业的转换进度，工发组织报告如下：
(a) 伊拉克钢铁公司因配套设施升级工程无法在年内完成，导致新设备安装不能按时完成。该企业决定利用自有资源独立完成生产线转换。工发组织确认该公司目前未使用含氢氯氟烃或氢氟碳化合物，从而建议在获得企业书面承诺将自费完成生产线转换，且不使用含氢氯氟烃或氢氟碳化合物后，于2025年12月前完成设备所有权移交。国家臭氧机构（NOU）将负责监督该协议的履行情况。该项目将于2025年12月31日完成，届时所有剩余资金将退还多边基金；以及
(b) 工发组织将继续协助轻工业公司完成三条生产线的技术转换直至2025年12月。鉴于项目延期批准时已明确不得再次申请延期，工发组织将在2025年12月31日前通过移交三条生产线设备所有权的方式完成项目实施，前提是轻工业公司承诺，若转换工作超期将自行负责完成后续工作。国家臭氧机构将监督该协议的履行。工发组织还与国家臭氧机构及轻工业公司达成共识，在2025年12月项目完成后将继续提供技术援助以确保转换质量。由于该项目无剩余资金，故无需退款。项目将于2025年底完成实施，2026年6月完成财务结算。
21. 鉴于这些项目已严重推迟，秘书处认为工发组织为伊拉克钢铁公司和轻工业公司提出的解决方案合理。工发组织进一步说明，将不会向这些企业核发任何含氢氯氟烃或氢氟碳化合物配额，且国家臭氧机构将持续监督其协议履行情况并据此提交报告。基于当前情况，秘书处建议工发组织向第九十八次会议汇报这些项目完成情况的最新进展。
建议
22. 执行委员会可以考虑：
(a) 注意到工发组织提交的、载于文件UNEP/OzL.Pro/ExCom/97/17的关于伊拉克含氢氯氟烃淘汰管理计划第一阶段、国家淘汰计划（第一次付款）（IRQ/PHA/58/INV/09）以及轻工业公司家用冰箱和冷冻柜制造中以异丁烷替代制冷剂CFC-12、以环戊烷替代发泡剂CFC-11的项目（IRQ/REF/57/INV/07）完成情况的进度报告；及
(b) 请工发组织向第九十八次会议提交上文（a）分段所述项目的完成进度报告。
黎巴嫩：含氢氯氟烃淘汰管理计划（第二阶段–关于第四次即最后一次付款相关工作计划执行情况的进度报告）（开发计划署）

背景
23. 在其第九十二次会议上，执行委员会在批准黎巴嫩含氢氯氟烃淘汰管理计划第二阶段第四次即最后一次付款时，要求黎巴嫩政府和开发计划署每年提交以下材料：最后一次付款相关工作计划执行进度报告直至项目完成、核查报告直至第三阶段获批，并将项目完工报告提交至2026年执行委员会首次会议（第92/24号决定）[footnoteRef:7]。 [7: 一揽子批准决定] 

24. 黎巴嫩政府报告称，2024年HCFC-22消费量为18.32 ODP吨，较该国含氢氯氟烃履约基准量下降75.1%。2020年至2024年含氢氯氟烃消费量如下表所示。
表4.	黎巴嫩含氢氯氟烃消费量（2020年至2024年，第7条数据）
	含氢氯氟烃
	2020年
	2021年
	2022年
	2023年
	2024年
	基准量

	公吨（mt）

	HCFC-22
	526.18
	474.28
	465.99
	447.79
	333.10
	653.55

	HCFC-123
	0.00
	0.00
	0.00
	0.00
	0.00
	2.50

	HCFC-141b
	56.03
	0.00
	0.00
	0.00
	0.00
	341.18

	共计（mt）
	582.21
	474.28
	465.99
	447.79
	333.10
	997.23

	ODP吨

	HCFC-22
	28.94
	26.09
	25.63
	24.63
	18.32
	35.95

	HCFC-123
	0.00
	0.00
	0.00
	0.00
	0.00
	0.05

	HCFC-141b
	6.16
	0.00
	0.00
	0.00
	0.00
	37.53

	共计（ODP吨）
	35.10
	26.09
	25.63
	24.63
	18.32
	73.53

	最大允许消费量
	36.78
	36.78
	27.58
	27.58
	18.39
	不适用



25. 黎巴嫩政府根据2024年国家方案（CP）执行报告提交的含氢氯氟烃行业消费量数据，与按蒙特利尔议定书第7条规定申报的数据一致。
进度报告
26. 开发计划署代表黎巴嫩政府提交了一份关于第二阶段剩余活动执行进度的报告，现摘要如下：
(a) 2025年含氢氯氟烃进口配额发放量为17.6 ODP吨，低于该国在协议中设定的17.84 ODP吨目标。政府将继续执行配额管理制度，以确保在未来各年实现含氢氯氟烃淘汰管理计划的目标；
(b) 2025年国内局势稳定后，国家臭氧机构恢复了维修行业培训计划的实施。截至目前，已有330名技术人员接受了良好维修实践及替代技术安全使用方面的培训。按照计划，已向培训中心提供设备支持，协助维修技术人员的培训工作；
(c) 国家臭氧机构开展了执法方面的能力建设活动：就第3277号法令和配额制度的执行举办了三次全国研讨会，共有130名人员参加；和
(d) 在批准的用于项目执行和监测的33,964美元中，实际发放金额为33,908美元，具体用于顾问费（2,000美元）、差旅费（2,276美元）、研讨会及会议（4,132美元）以及监测与报告（25,500美元）。
27. 截至2025年9月，第二阶段批准的4,203,826美元中，已发放4,157,626美元。剩余46,200美元将于2025年12月前发放。
28. 根据第89/42(d)号和第90/48(c)号决定，多边基金将性别平等主流化的业务政策纳入含氢氯氟烃淘汰管理计划第二阶段执行的各项活动中。开展的关键活动包括：通过培训与宣传提升工作人员落实性别主流化的能力与意识；在组织含氢氯氟烃淘汰管理计划相关活动时营造性别包容环境（例如让女性参与筹备活动并担任负责人、鼓励女性参与培训活动）；并分享黎巴嫩及其他地区女性参与含氢氯氟烃淘汰管理计划活动的成功经验。
秘书处的评论

29. 如协议第14段规定，开发计划署确认，含氢氯氟烃淘汰管理计划第二阶段将于2025年12月31日前完成。
30. 截至2025年1月1日，黎巴嫩禁止制造使用含氢氯氟烃制冷空调设备；含氢氯氟烃的剩余消费量仅限用于维修业。
31. 开发计划署表示，2023年至2025年含氢氯氟烃消费量核查报告将与含氢氯氟烃淘汰管理计划第三阶段第二次付款申请一并提交至2026年第二次会议审议。
32. 关于在黎巴嫩各类制冷空调应用中采用HFC-32及碳氢制冷剂技术的情况，开发计划署指出当地市场正逐步向采用较低/低全球变暖潜能值制冷剂的过渡。已设计并使用维修行业的培训课程，内容涵盖可燃制冷剂的安全操作与充注，制冷剂泄漏预防和探测及回收，良好维护实践，以及制冷剂再利用。开发计划署进一步说明，在培训推广活动项目规划及实施的不同阶段，将结合本国正在启动的基加利氢氟碳化合物执行计划相关活动，采取统筹协调的工作方法。
建议

33. 执行委员会可以关注由开发计划署提交、载于UNEP/OzL.Pro/ExCom/97/17号文件的关于黎巴嫩含氢氯氟烃淘汰管理计划第二阶段第四次即最后一次付款相关工作计划执行情况的最终进度报告。
[bookmark: OLE_LINK283][bookmark: OLE_LINK284]莱索托：含氢氯氟烃淘汰管理计划（第二阶段–关于可燃制冷剂安全标准采用状况及根据第87/41(b)号决定建立技术人员强制认证体系的报告）（德国政府提交)

背景

34. 在其第九十四次会议上批准莱索托含氢氯氟烃淘汰管理计划第二阶段第二次付款时，执行委员会请德国政府根据第87/41(b)号决定，从2025年开始在每年第一次会议上提交关于可燃制冷剂安全标准采用状况及技术人员强制认证体系建设进度的报告，直至提交含氢氯氟烃淘汰管理计划第二阶段第三次付款申请为止（第94/20号决定）[footnoteRef:8]。 [8:  一揽子批准决定] 

现状报告

35. 回应该决定，德国政府已提交以下现状报告。
易燃制冷剂安全标准的采用

36. 国家臭氧机构就安全标准的制定和采用与莱索托标准研究所（LSI）保持了定期沟通。这包括2025年2月和3月举行的两次线上会议，以及2025年9月进行的会面磋商。该安全标准将与ISO-5149保持一致，预计于2026年第一季度正式采用。
建立技术人员强制性认证机制

37. 莱索托教育部所辖的技术与职业培训部门（TVD）负责全国职业培训监管，目前正着手制定正式的制冷与空调（RAC）技术人员资格认证的课程体系。2024年，该部门派遣五名代表赴南非和纳米比亚多家制冷与空调技术培训机构考察交流，深入了解该地区国家技术人员资格认证项目是如何实施的。
38. 此次考察结束后，莱索托教育部技术与职业培训部门制定了制冷与空调行业资格认证及证书的综合教学课程，预计于2026年1月正式设立相关课程。同时，作为在岗技术人员“预先学习认可”（RPL）计划的组成部分，职业能力测试正在计划中。目前正在最终确定一种用于制冷剂安全处理的“预先学习认可”评估方式。一项试点评估将于2025年11月底前进行，届时将邀请10名通过正规教育或实践培训获得技能的技术人员参与。
秘书处的评论

39. 德国政府告知秘书处，由于莱索托标准研究所人员配置相关的行政问题，易燃制冷剂安全标准的制定工作已被推迟。这些标准将由莱索托标准研究所完成，并通过环境部在2026年第一季度前颁布实施。
40. 此外，德国政府表示，已推迟强制执行技术人员资格认证，预计将在2026年底前执行。
建议

41. 执行委员会注意德国政府提交的关于莱索托含氢氯氟烃淘汰管理计划第二阶段中有关易燃制冷剂安全标准采用情况，以及依照第87/41(b)号决定对技术人员进行强制认证的报告，该报告载于UNEP/OzL.Pro/ExCom/97/17号文件。
巴基斯坦：含氢氯氟烃淘汰管理计划（第三阶段–聚氨酯泡沫行业酷点企业技术转换的行动计划）（工发组织）

背景

42. 在其第九十六次会议上，执行委员会请工发组织代表巴基斯坦政府向第九十七次会议提交一份关于含氢氯氟烃淘汰管理计划第三阶段聚氨酯（PU）泡沫行业酷点企业技术转换的详细行动计划（第96/12(b)号决定）。
行动计划

43. 根据该决定，巴基斯坦政府已委托工发组织提交了行动计划，概要如下。
44. 在含氢氯氟烃淘汰管理计划第三阶段项下核准的用于聚氨酯泡沫酷点企业的技术转换项目的107,993美元中，已发放16,000美元用于支付国内外专家提供的咨询服务，以及国家臭氧机构官员进行的项目现场考察。
45. [bookmark: _Hlk213856293]在剩余的91,993美元中，工发组织提议向生产聚氨酯泡沫管道保温材料的受益企业伊斯兰丁（Islam ud Din）追加资金20,000美元，用于采购配套工具（如小型混合喷头、计量仪表），以解决环戊烷技术在生产小尺寸产品中的工艺难题。该企业在含氢氯氟烃淘汰管理计划第三阶段曾获得初始资金160,000美元资助，此次资金调整将增加企业的整体效益成本，使淘汰HCFC-141b的成本从每公斤9.58美元增加到每公斤10.78美元[footnoteRef:9]。 [9: 根据第74/50号决定，对于年消费量低于20吨且采用低全球变暖潜能值技术的泡沫企业，每公斤淘汰的HCFC-141b的成本效益门槛为10.96美元。] 

46. 提议将剩余的71,993美元用于以下旨在持续淘汰HCFC-141b的活动：
1. 通过为泡沫行业关键利益相关方（包括终端用户、制造商、进口商、进口代理商和海关当局）举办五次研讨会及宣传会议，开展信息推广活动，重点聚焦HCFC-141b法规（22,000美元）；在不同泡沫应用领域采用低全球变暖潜能值替代品的实践经验与技术分享（25,000美元）；以及项目协调与报告工作（9,993美元）；和
(f) 对不同泡沫应用领域切实可行的低全球升温潜能值替代技术的评估与更新，包括可获得性、技术经济考量及环境效益（15,000美元）。
秘书处的评论

47. 工发组织确认，酷点企业已停止生产运营，将不再进一步寻求援助。
48. 关于受益企业伊斯兰丁所需的额外支持，工发组织报告称，该项目计划的设备安装和移交工作已于2025年完成。然而，后续评估显示，最小管道保温部分仍需进一步优化。拟议的资金重新分配旨在通过提供额外资金支持HCFC-141b的转换。
49. [bookmark: _Hlk213926345]秘书处要求澄清第46段所述计划中提议的额外活动的必要性。工发组织回应解释，巴基斯坦政府已实施法规，从2025年1月31日起禁止进口HCFC-141b（包括纯品及进口预混多元醇中所含成分）。目前剩余的HCFC-141b库存正由那些正在转向替代技术的企业使用。
50. [bookmark: _Hlk214284800]工发组织进一步解释说，为确保更有效地落实这些法规，巴基斯坦政府已认识到需要开展更多宣传活动，推动行业以系统且迅速的方式采用替代品。此外，该行业还需要不同应用领域（如喷涂泡沫、聚氨酯泡沫及保温器皿用泡沫）的低全球升温潜能值替代技术的额外技术指导与市场信息。为满足这些需求，计划编制一份关于低全球升温潜能值泡沫替代技术的最新评估报告，其中将包含适用于巴基斯坦不同泡沫应用领域的替代技术信息。该报告主要将在本地顾问以及通过远程提供技术支持的国际专家协助下完成。此举不仅将推动工业企业淘汰HCFC-141b，还能促进当前或潜在使用氢氟碳化合物作为发泡剂的行业进行信息共享与替代技术应用。
51. 秘书处认为，此项资金重新分配将有助于巴基斯坦政府系统性地在泡沫行业淘汰HCFC-141b，包括加强相关进口和使用法规的执行力度，同时推动在各泡沫应用领域采用低全球升温潜能值的替代品。
建议

52. [bookmark: _Hlk213937530]执行委员会可以：
1. 注意到由工发组织提交并载于UNEP/OzL.Pro/ExCom/97/17号文件的巴基斯坦聚氨酯泡沫酷点企业技术转换的详细行动计划，该计划在含氢氯氟烃淘汰管理计划第三阶段下执行；
(h) 进一步注意到，酷点企业已停止其生产业务，剩余资金余额为91,993美元；以及
(i) 批准将上文（b）项所述余额中的20,000美元重新分配给受益企业伊斯兰丁以提供额外支持；并将71,993美元用于执行UNEP/OzL.Pro/ExCom/97/17号文件第46段所述活动，以推动泡沫行业从使用HCFC-141b（包括纯HCFC-141b及预混多元醇中含有的HCFC-141b）全面转向替代技术。
B. 与基加利氢氟碳化合物执行计划（KIP）协议相关的报告
根据基加利氢氟碳化合物执行计划第一阶段减少氢氟碳化合物消费量的协议

背景

53. 在第九十五次会议上，执行委员会就基加利氢氟碳化合物执行计划（KIP）第一阶段的协议模板达成共识（第95/90号决定及UNEP/OzL.Pro/ExCom/95/94号文件附件57）。该协议模板将统一适用于第九十二次至第九十五次会议期间已获批的所有基加利氟碳化合物执行计划。在第九十六次会议上，执行委员会还就氢氟碳化合物供资指南达成共识（第96/50号决定），其中对起始点的明确规定将对协议草案产生重要影响。
秘书处的评论

54. 为确保各国政府与执行委员会之间协议草案的一致性与准确性，秘书处依据已商定的模板、以及在第九十二次至第九十五次会议期间获批的基加利氢氟碳化合物执行计划中所规定的氢氟碳化物逐步削减承诺与资金核准计划，起草了这些协议，并在必要时作出了调整，以：
(a) 根据第96/50(e)号决定，对仅涉及维修行业的低消费量（LVC）国家不设起始点，对于非低消费量国家，起始点将把所有氢氟碳化合物放在一起，统一调整第二段内容；
(b) 根据仅涉及维修行业的低消费量国家、兼有维修与制造行业的低消费量国家以及非低消费量国家的不同情况，相应修订附录1-A和2-A；并且
(c) 对于非低消费量国家及兼有制造行业的低消费量国家，在附录1-A和附录2-A第4行中暂标注“待确定”，待关于消费总量削减起始点及相应的剩余可供资消费量的讨论完成后最终确定。
55. [bookmark: _Hlk214542379]在机构协调会议上[footnoteRef:10]讨论了协议草案的修订事宜。在第九十二次至第九十五次会议期间批准的54个基加利氢氟碳化合物执行计划中，有三个被纳入在本次会议申请资金付款的项目提案，一个被排除在外。已有23份协议草案发送至各牵头机构以征询意见并进行审查，特别要求对附录5-A监测机构与职责提供详细可靠的进度监测方案，明确负责各项活动的组织机构，并确保通过协议达成的消费量削减目标具有可持续性。在发送给牵头机构的23份协议草案中，14份已提交本次会议审议批准，9份尚在最终定稿阶段。另有27份协议草案仍需秘书处审核后发送至牵头机构。秘书处赞赏地注意到所有执行机构为协议审查与验证工作付出的努力。 [10: 2025年9月9日至11日，蒙特利尔] 

56. 秘书处现提交14份基加利氢氟碳化合物执行计划协议草案，提请执行委员会在本届会议上批准。秘书处将继续完成剩余协议草案的定稿工作，并提交执行委员会在第九十八次会议上审议。表5列示了协议草案的定稿状态。
表5：	第九十二次至第九十五次会议批准的基加利氢氟碳化合物执行计划第一阶段协议草案定稿状态
	现状
	国家

	提交执行委员会批准的共14项
	阿尔巴尼亚（本文件附件一）；亚美尼亚*（附件二）；多民族玻利维亚国（附件三）；布基纳法索（附件四）；喀麦隆（附件五）；智利（附件六）；哥伦比亚（附件七）；刚果（附件八）；哥斯达黎加（附件九）；古巴（附件十）；多米尼加共和国（附件十一）；厄瓜多尔（附件十二）；危地马拉（附件十三）；洪都拉斯（附件十四）

	已发送至各机构并待最终定稿（9项）
	贝宁、柬埔寨、乍得、冈比亚、毛里求斯、莫桑比克、卢旺达、圣卢西亚、塞拉利昂

	秘书处待发送至各机构（27项）**
	萨尔瓦多、埃斯瓦蒂尼王国、加纳、格林纳达、约旦、吉尔吉斯斯坦、老挝人民民主共和国、莱索托、利比里亚、马拉维、马来西亚、黑山、尼日利亚、北马其顿、太平洋岛国、巴拿马、巴拉圭、秘鲁、塞内加尔、塞舌尔、多哥、特立尼达和多巴哥、突尼斯、土耳其、乌拉圭、越南和津巴布韦


*此次更新亦反映了从环境规划署向工发组织的移交的活动（见本文件第64-76段）。
**不包括尼加拉瓜，因为多边基金支持的项目已取消（见本文件第77-84段）；墨西哥（见文件UNEP/OzL.Pro/ExCom/97/60）；尼日尔（见文件UNEP/OzL.Pro/ExCom/97/65）以及土库曼斯坦（见文件UNEP/OzL.Pro/ExCom/97/81）。
建议

57. 执行委员会可以批准下列文件：
(a) 根据基加利氢氟碳化合物执行计划第一阶段规定编制的阿尔巴尼亚政府与执行委员会关于的氢氟碳化合物消费量削减协议草案，载于本报告附件一；
(b) 根据基加利氢氟碳化合物执行计划第一阶段规定编制的亚美尼亚政府与执行委员会之间关于氢氟碳化合物消费量削减协议草案，载于本报告附件二；
(c) 根据基加利氢氟碳化合物执行计划第一阶段规定编制的多民族玻利维亚国政府与执行委员会关于氢氟碳化合物消费量削减协议草案，载于本报告附件三；
(d) 根据基加利氢氟碳化合物执行计划第一阶段规定编制的布基纳法索政府与执行委员会关于氢氟碳化合物消费量削减协议草案，载于本报告附件四；
(e) 根据基加利氢氟碳化合物执行计划第一阶段规定编制的喀麦隆政府与执行委员会关于氢氟碳化合物消费量削减协议草案，载于本报告附件五；
(f) 根据基加利氢氟碳化合物执行计划第一阶段规定编制的关于智利政府与执行委员会氢氟碳化合物消费量削减协议草案，载于本报告附件六；
(g) 根据基加利氢氟碳化合物执行计划第一阶段规定编制的哥伦比亚政府与执行委员会关于氢氟碳化合物消费量削减协议草案，载于本报告附件七；
(h) 根据基加利氢氟碳化合物执行计划第一阶段规定编制的刚果政府与执行委员会关于氢氟碳化合物消费量削减协议草案，载于本报告附件八；
(i) 根据基加利氢氟碳化合物执行计划第一阶段规定编制的哥斯达黎加政府与执行委员会关于氢氟碳化合物消费量削减协议草案，载于本报告附件九；
(j) 根据基加利氢氟碳化合物执行计划第一阶段规定编制的古巴政府与执行委员会关于氢氟碳化合物消费量削减协议草案，载于本报告附件十；
(k) 根据基加利氢氟碳化合物执行计划第一阶段规定编制的多米尼加共和国政府与执行委员会关于氢氟碳化合物消费量削减协议草案，载于本报告附件十一；
(l) 根据基加利氢氟碳化合物执行计划第一阶段规定编制的厄瓜多尔政府与执行委员会关于氢氟碳化合物消费量削减协议草案，载于本报告附件十二；
(m) 根据基加利氢氟碳化合物执行计划第一阶段规定编制的危地马拉政府与执行委员会关于氢氟碳化合物消费量削减协议草案，载于本报告附件十三；及
(n) 根据基加利氢氟碳化物执行计划第一阶段规定编制的洪都拉斯政府与执行委员会关于氢氟碳化物消费量削减协议草案，载于本报告附件十四。
C. 关于维持制冷维修行业能源效率的额外活动的报告（第89/6号决定）
吉尔吉斯斯坦：根据第89/6 (b)号决定开展的维持制冷维修行业能源效率额外活动（最终进度报告）（环境规划署）

背景

58. 在第九十六次会议上，执行委员会特例批准将吉尔吉斯斯坦引入低全球升温潜能值或零全球升温潜能值的含氢氯氟烃替代品及维持制冷维修行业能源效率的额外活动项目的完成期限延长至2025年6月30日，前提是不再进一步延期，且环境规划署需代表吉尔吉斯斯坦政府向第九十七次会议提交项目实施的最终进度报告（第96/13号决定）。
59. 环境规划署报告确认所有活动均已完成，资金已发放，并将向第九十七次会议提交该项目的最终进度报告。该最终报告将包含关于项目成果的更多细节，例如研究考察的经验教训与建议、受培训技术人员和海关官员的最终人数，以及研究成果及影响评估[footnoteRef:11]。 [11: UNEP/OzL.Pro/ExCom/96/11] 

60. 根据第96/13(c)号决定，环境规划署已代表吉尔吉斯斯坦政府向本次会议提交了最终进度报告。


进度报告

61. 本次提交的最终进度报告按要求提供了有关项目成果、活动及经验教训的信息，具体内容如下：
(a) 项目已达成以下主要目标：加强利益相关方之间的协调与合作，以促进制冷和空调设备领域的能源效率及低全球变暖潜能值制冷剂的使用；通过举办以能源效率和低全球变暖潜能值制冷剂为主题的信息会议，提升利益相关方的能力；并提高了关键利益相关方和公众的认识水平;
(b) 该试点项目旨在为3千瓦以下的制冷设备（包括农产品冷藏库、牛奶与肉类冷藏柜及冷藏运输设备）制定最低能效标准（MEPS）并建立能效标识体系。据报告，针对3千瓦以下制冷设备的技术法规草案已制定完成，将于2028年1月1日在欧亚经济联盟境内正式生效，其中包含相关认证与标识要求。所有活动均符合欧亚经济联盟[footnoteRef:12]法规和标准，并有助于欧亚经济联盟技术法规048/2019的监督与执行[footnoteRef:13]。 [12:  欧亚经济联盟]  [13:  欧亚经济联盟技术法规048/2019，题目为“关于用能设备能效要求”。] 

(c) 通过对贸易主管部门开展培训，制定了达标机制行动计划，内容涵盖达标评估、市场检查、报告及产品注册体系。项目期间共培训技术人员352名（其中82名女性）、海关官员193名（其中50名女性）。
(d) 项目取得的主要经验包括：由于第5条国家缺乏认证实验室，导致达标评估工作面临挑战，具体执行存在困难。然而，技术法规可借助现有法律框架制定，并可采纳国际标准以加速推进。即使在技术能力尚不完善的情况下，仍可达到能效标准。吉尔吉斯斯坦已颁布建筑规范41-04:2022，以对高效制冷空调设备的进口进行监管，并出台相关决议[footnoteRef:14]为环保产品提供税收和关税优惠。在吉尔吉斯斯坦设立能源效率部门的努力仍面临体制阻力，相关提案尚在审议中；以及 [14:  吉尔吉斯斯坦共和国第246/2025号决议，题目为“关于批准试点国家分类方法–绿色分类方案”。] 

(e) 通过到白俄罗斯进行考察学习，获得了以下经验：设立单一主管机构负责能效管理可有效减少职能重叠，建立标准、认证与检测一体的中心能发挥关键作用。该国广泛采用国际标准[footnoteRef:15]确保技术要求可预期。通过行业协会开展行业自律与技师培训有助于弥补技能缺口。标识系统标准化与向消费者提供信息能提升市场透明度。能源审计与管理体系可改善项目质量与监测效果。通过详细计算方法与性能标准支持建筑能效。供热与计量标准为实现精准监管及制定关税政策创造条件。针对家用及气候设备设定明确指标与检测方法，为实施激励政策与政府采购提供依据。燃气及热力设备标准保障安全与能效。冷链物流领域通过采用国际规程与无接触配送模式获益。存在的风险包括规范体系负荷过重及实验室容量有限，建议采取优先排序策略，并行推进基础设施与技能建设。吉尔吉斯斯坦可复制的措施包括：建立单一窗口协调机制，启动自愿认证与技师培训计划，采用标识验证与标准清单，无接触冷链流程试点，并根据本国国情调整行业自律机制与标准体系。 [15:  GOST（国家联合标准）；STB（白俄罗斯标准）；EN（欧洲标准）；IEC（国际电工委员会标准）；及ISO（国际标准化组织标准）。] 

秘书处评论

62. 秘书处注意到，该最终报告提供了所需信息，且项目已于2025年6月30日前完成，资金发放率达100%。
建议

63. 执行委员会可以注意到关于吉尔吉斯斯坦引进低全球升温潜能值或零全球升温潜能值的含氢氯氟烃替代品及维持制冷维修行业能源效率的额外活动项目的最终进度报告，该报告由环境规划署提交，并载于文件UNEP/OzL.Pro/ExCom/97/17。
D. 多个项目的相关报告

亚美尼亚：含氢氯氟烃淘汰管理计划（第三阶段）与基加利氢氟碳化合物执行计划（第一阶段）（执行机构变更）（工发组织与环境规划署）
背景

64. 工发组织和环境规划署作为牵头与协作执行机构，代表亚美尼亚政府提交了将含氢氯氟烃淘汰管理计划（HPMP）第三阶段和基加利氢氟碳化合物执行计划（KIP）第一阶段的协作机构执行活动部分从环境规划署移交至工发组织的请求，由此工发组织将担任指定执行机构[footnoteRef:16]。随后，工发组织和环境规划署联合提交了关于上述项目执行情况的进度报告，内容包括资金发放情况及尚未完成的剩余活动。 [16:  根据亚美尼亚国家臭氧机构于2025年9月10日致秘书处的信函。] 

65. 在第九十六次会议上，执行委员会原则上批准了亚美尼亚2025–2030年含氢氯氟烃淘汰管理计划第三阶段，总额为635,106美元，其中工发组织执行部分432,400美元加上机构支助费用30,268美元，环境规划署执行部分152,600美元加上机构支助费用19,838美元；同时批准了第一次付款及对应的执行计划，金额为257,623美元，含工发组织执行部分179,200美元加上机构支助费用12,544美元，环境规划署执行部分58,300美元加上机构支助费用7,579美元[footnoteRef:17]。环境规划署在第三阶段计划下负责实施的活动包括加强法律法规框架、开展海关及执法官员能力建设、进行制冷空调行业技术人员能力培养等[footnoteRef:18]。 [17:  第96/33号决定。]  [18:  文件UNEP/OzL.Pro/ExCom/96/25号第31段。] 

66. 在第九十四次会议上，执行委员会原则上批准了亚美尼亚2024–2029年基加利氢氟碳化合物执行计划第一阶段，旨在到2029年将该国氢氟碳化合物消费量在基准量水平上削减10%，批准总额为203,400美元，其中工发组织执行部分114,000美元加上机构支助费用14,820美元，环境规划署执行部分66,000美元加上机构支助费用8,580美元；同时批准了第一次付款及对应的执行计划，金额为186,535美元，含工发组织执行部分99,075美元加上机构支助费用12,880美元，环境规划署执行部分66,000美元加上机构支助费用8,580美元[footnoteRef:19]。环境规划署在第一阶段计划下负责实施的活动包括开展海关与执法官员能力建设以及制冷空调技术人员培训[footnoteRef:20]。 [19: 第94/39号决定。]  [20: 文件UNEP/OzL.Pro/ExCom/94/21 第33段。] 

进度报告
含氢氯氟烃淘汰管理计划第三阶段第一次付款执行进度报告
67. 工发组织报告称，已聘请一名国家顾问开展关于维修站在制冷剂回收、再循环和再生（RRR）方面的技术能力与认知度的调查。在采购方面，用于回收、再循环和再生制冷剂的附加工具和设备的技术规格已准备就绪，招标工作将于2025年底前启动。此外，关于建立再生中心和制冷剂充注基础设施的初步方案已拟定，目前正在讨论中。为职业院校采购的工具和设备的技术规格将于2025年底前制定完成，随后将启动招标程序。
68. 环境规划署报告称，含氢氯氟烃淘汰管理计划第三阶段的第一次付款计划的执行尚未签署任何协议。
基加利氢氟碳化合物执行计划第一阶段第一次付款执行进度报告
69. 工发组织报告，已聘请国家顾问负责起草进口禁令法规、协调利益相关方并提交相关计划。目前正在开展两项研究：一是关于低全球变暖潜能值技术安全使用规范的研究，二是针对气雾剂、溶剂、消防及泡沫行业氢氟碳化合物消费量的行业调研。培训中心工具与设备的采购订单已签署，预计设备将于2025年11月送达。此外，已开展多项宣传活动，包括组织行业专家参观埃里啤酒厂（Yerevan Beer），实地考察采用氨制冷剂的制冷系统优势与应用实践。
70. 环境规划署报告称，已与亚美尼亚政府签署基加利氢氟碳化合物执行计划第一次付款的小额资助协议，资金已发放至开发计划署亚美尼亚办事处。但是国家臭氧机构确认相关活动尚未启动。鉴于机构转移请求，环境规划署现已终止该小额资助协议，已发放资金将退还环境规划署。
资金发放情况
71. 截至2025年11月，在含氢氯氟烃淘汰管理计划第三阶段第一次付款批准的237,500美元资金中（工发组织179,200美元，环境规划署58,300美元），工发组织已发放3,746美元，环境规划署尚未发放任何资金；在基加利氢氟碳化合物执行计划第一阶段第一次付款批准的165,075美元资金中（工发组织99,075美元，环境规划署66,000美元），工发组织已发放38,454美元，环境规划署未发放任何资金。
秘书处的评论
72. 秘书处注意到，将环境规划署负责的含氢氯氟烃淘汰管理计划第三阶段和基加利氢氟碳化合物执行计划第一阶段的实施工作移交工发组织的请求，是经相关各方协商并达成一致后提出的。工发组织已确认，除机构变更外，这两个项目将分别按照第九十六次会议和第九十四次会议批准的内容继续实施。
73. 待移交资金的具体数额详见表6。原批给环境规划署用于第一次付款项目执行的资金尚未发放。因此，环境规划署将把这部分资金返还多边基金，以便后续移交给工发组织。此事宜已在资金余额及可用资源报告[footnoteRef:21]中予以说明。 [21:  UNEP/OzL.Pro/ExCom/97/4] 

表6.	需移交工发组织的含氢氯氟烃淘汰管理计划第三阶段及基加利氢氟碳化合物执行计划第一阶段资金（美元）
	项目说明
	商定供资额
	支助费用
	商定供资总额

	含氢氯氟烃淘汰管理计划第三阶段

	已批准供资额（第一次付款）（ARM/PHA/96/TAS/34）
	58,300
	4,081
	62,381

	原则上商定的供资额（第二及第三次付款）
	94,300
	6,601
	100,901

	共计
	152,600
	10,682
	163,282

	基加利氢氟碳化合物执行计划第一阶段

	已批准供资额（第一次付款）（ARM/KIP/94/TAS/32）*
	66,000
	8,580
	74,580

	共计
	66,000
	8,580
	74,580


* 基加利氢氟碳化合物执行计划第一阶段只在第一次付款中包含了环境规划署的资金。
74. 考虑到执行机构的调整及资金的重新分配，已对亚美尼亚政府与执行委员会签署的含氢氯氟烃淘汰管理计划第三阶段协议进行更新，具体包括：修订了附录2-A，并新增第17款，说明更新后的协议将取代第九十六次会议达成的协议（第96/33号决定），该更新文本载于本文件附件十五。完整的更新版协议将作为第九十七次会议最终报告的附件。相关变更详见表7。
表7：亚美尼亚含氢氯氟烃淘汰管理计划第三阶段付款资金重新分配方案（美元）
	行
	详情
	2023年*
	2025年
	2026年
	2027年
	2028-2029年
	2030年
	共计

	在九十六次会议上核准

	2.1
	牵头执行机构（工发组织）商定的供资额（美元）
	0
	179,200
	0
	210,700
	0
	42,500
	432,400

	2.2
	牵头执行机构支助费用（美元）
	0
	12,544
	0
	14,749
	0
	2,975
	30,268

	2.3
	合作执行机构（环境规划署）商定的供资额（美元）
	100,000
	58,300
	0
	78,300
	0
	16,000
	252,600

	2.4
	合作执行机构支助费用（美元）
	13,000
	7,579
	0
	10,179
	0
	2,080
	32,838

	3.1
	商定供资总额（美元）
	100,000
	237,500
	0
	289,000
	0
	58,500
	685,000

	3.2
	支助费用总额（美元）
	13,000
	20,123
	0
	24,928
	0
	5,055
	63,106

	3.3
	商定费用总额（美元）
	113,000
	257,623
	0
	313,928
	0
	63,555
	748,106

	在第九十七次会议上修订

	2.1
	牵头执行机构（工发组织）商定的供资额（美元）
	0
	237,500
	0
	289,000
	0
	58,500
	585,000

	2.2
	牵头执行机构支助费用（美元）
	0
	16,625
	0
	20,230
	0
	4,095
	40,950

	2.3
	合作执行机构（环境规划署）商定的供资额（美元）
	100,000
	0
	0
	0
	0
	0
	100,000

	2.4
	合作执行机构支助费用（美元）
	13,000
	0
	0
	0
	0
	0
	13,000

	3.1
	商定供资总额（美元）
	100,000
	237,500
	0
	289,000
	0
	58,500
	685,000

	3.2
	支助费用总额（美元）
	13,000
	16,625
	0
	20,230
	0
	4,095
	53,950

	3.3
	商定费用总额（美元）
	113,000
	254,125
	0
	309,230
	0
	62,595
	738,950


* 根据第89/6(b)号决定，第九十三次会议批准了关于引入低或零全球升温潜能值的含氢氯氟烃替代品及维持制冷维修行业能源效率的额外活动资金。
75. 根据本文件第53至57段的规定，秘书处还将基加利氢氟碳化合物执行计划第一阶段的执行机构调整和资金重新分配情况纳入了拟提交第九十七次会议批准的协议草案中。相关变更如下列表8所示。

表8：亚美尼亚基加利氢氟碳化合物执行计划第一阶段分期付款资金重新分配方案（美元）
	行
	详情
	2023年
	2025年
	2026年
	2027年
	2028-2029年
	2030年
	共计

	在九十四次会议上核准

	2.1
	牵头执行机构（工发组织）商定的供资额（美元）
	99,075
	0
	0
	14,925
	0
	0
	114,000

	2.2
	牵头执行机构支助费用（美元）
	12,880
	0
	0
	1,940
	0
	0
	14,820

	2.3
	合作执行机构（环境规划署）商定的供资额（美元）
	66,000
	0
	0
	0
	0
	0
	66,000

	2.4
	合作执行机构支助费用（美元）
	8,580
	0
	0
	0
	0
	0
	8,580

	3.1
	商定供资总额（美元）
	165,075
	0
	0
	14,925
	0
	0
	180,000

	3.2
	支助费用总额（美元）
	21,460
	0
	0
	1,940
	0
	0
	23,400

	3.3
	商定费用总额（美元）
	186,535
	0
	0
	16,865
	0
	0
	203,400

	在九十七次会议上修订

	2.1
	牵头执行机构（工发组织）商定的供资额（美元）
	165,075
	0
	0
	14,925
	0
	0
	180,000

	2.2
	牵头执行机构支助费用（美元）
	21,460
	0
	0
	1,940
	0
	0
	23,400

	3.1
	商定供资总额（美元）
	165,075
	0
	0
	14,925
	0
	0
	180,000

	3.2
	支助费用总额（美元）
	21,460
	0
	0
	1,940
	0
	0
	23,400

	3.3
	商定费用总额（美元）
	186,535
	0
	0
	16,865
	0
	0
	203,400



建议
76. 执行委员会可以：
(a) 注意到亚美尼亚政府请求，将原定由环境规划署负责执行的含氢氯氟烃淘汰管理计划（HPMP）第三阶段及基加利氢氟碳化合物执行计划（KIP）第一阶段的全部活动移交工发组织；
(b) 关于含氢氯氟烃淘汰管理计划第三阶段：
(i) 注意到关于环境规划署返还其第一次付款执行余额的第九十七/--号决定；
(ii) 批准：
a) 将58,300美元资金及4,081美元机构支助费用移交工发组织，纳入其正在执行的第一次付款中；
b) 将原则上核准的第二次和第三次付款中，原分配给环境规划署的资金94,300美元及机构支助费用6,601美元移交工发组织；
(iii) 进一步注意到基金秘书处已根据环境规划署活动向工发组织的移交申请，更新了亚美尼亚政府与执行委员会关于含氢氯氟烃淘汰管理计划第三阶段的协议，载于本文件附件十五，具体更新内容包括附录2-A，以及新增的第17段注明更新后的协议将取代第九十六次会议达成的协议（第96/33号决定）；
(c) 关于基加利氢氟碳化合物执行计划第一阶段：
(i) 注意到关于环境规划署返还其第一次付款余额的第九十七/--号决定；
(ii) 批准将66,000美元资金及8,580美元机构支助费用移交工发组织，纳入其正在执行的第一次付款中；
(iii) 基金秘书处已更新亚美尼亚基加利氢氟碳化合物执行计划的氢氟碳化合物减排承诺与付款安排（第94/39号决定），并将更新后的付款安排纳入亚美尼亚政府与执行委员会关于基加利氢氟碳化合物执行计划第一阶段的协议草案中，载于UNEP/OzL.Pro/ExCom/97/17号文件附件二。
E. 关于请求取消多个项目的报告
尼加拉瓜: 该政府提出的取消正在执行项目的申请（工发组织）
背景
77. 2025年2月18日，工发组织与环境规划署收到尼加拉瓜环境与自然资源部关于完成下列项目的请求：
(a) 体制建设（第十一期）；
(b) 含氢氯氟烃淘汰管理计划（第二阶段，第二次付款）以及核查报告；
(c) 基加利氢氟碳化合物执行计划(第一阶段，第一次付款)；
(d) 关于在氢氟碳化合物淘汰过程中维持及/或提升替代技术和设备能效的试点项目；和
(e) 编制受控物质废物国家库存清单并制定这些物质的管理计划。
78. 在第九十六次会议上，执行委员会注意到尼加拉瓜政府的请求以及环境规划署就以下项目退还资金的情况：NIC/EEF/92/TAS/50、NIC/SEV/92/INS/51、NIC/DES/93/PRP/52、NIC/EEF/93/DEM/54、NIC/KIP/93/TAS/55和NIC/PHA/94/TAS/58。执行委员会还请工发组织在第九十七次会议上说明由其执行的尼加拉瓜项目现状；并请秘书处就多边基金资助项目的相关事宜与尼加拉瓜政府进行跟进（第96/15号决定）。
取消由工发组织执行的项目
79. 2025年8月1日，根据尼加拉瓜政府的通知，工发组织明确表示，工发组织正在执行的所有项目均将取消，并向秘书处提交了以下项目的工发组织部分的项目取消请求：
(a) 含氢氯氟烃淘汰管理计划第二阶段，第二次付款；
(b) 含氢氯氟烃淘汰管理计划第二阶段，第二次付款—为提升能效开展的额外活动；
(c) 基加利氢氟碳化合物执行计划第一阶段，第一次付款；
(d) 在氢氟碳化合物淘汰过程中，维持和/或提升替代技术与设备能效的试点项目；和
(e) 编制受控物质废物国家清单并制定这些物质的管理计划。
80. 关于未用资金余额的相关返还情况载于文件UNEP/OzL.Pro/ExCom/97/4。
秘书处的评论
81. 秘书处注意到，取消由工发组织实施的所有项目标志着结束多边基金在尼加拉瓜资助的所有项目。秘书处还注意到，尼加拉瓜政府提交了2024年的国家方案执行报告和第7条数据，其报告的含氢氯氟烃消费量低于蒙特利尔议定书的淘汰目标和该国与执行委员会签订的含氢氯氟烃淘汰管理计划协议所规定的最大允许消费量。秘书处认为，若无含氢氯氟烃淘汰管理计划协议，该国将遵循蒙特利尔议定书的控制目标。
82. 秘书处与尼加拉瓜政府进行了沟通，以确认取消工发组织项目的进程正在进行。在沟通中，秘书处指出尼加拉瓜已批准蒙特利尔议定书及其所有修正案，并且是首批批准基加利修正案的国家之一。多边基金提供的资金有助于各国履行蒙特利尔议定书的规定，并提供机构建设支持，这对遵守议定书和国家项目的执行都有帮助。在执行委员会在第九十七次和第九十八次会议上审议取消尼加拉瓜的最后一批项目之前，秘书处表示愿意提供任何所需的协助或澄清有关多边基金支持的项目的情况。
83. 尽管在本文件发布时尚未收到回复，但在第三十七次缔约方会议期间，秘书处与尼加拉瓜国家臭氧官员进行了会外交流。该官员口头重申该国对蒙特利尔议定书的承诺，并表示正在准备正式答复。


建议
84. 执行委员会可以：
(a) 注意到：
(i) 尼加拉瓜政府已确认取消由工发组织执行的下列正在执行的项目：NIC/PHA/92/INV/48、NIC/EEF/92/TAS/49、NIC/DES/93/PRP/53、NIC/EEF/93/DEM/56和NIC/KIP/93/INV/57；
(ii) [bookmark: _Hlk211080274]项目NIC/DES/93/PRP/53、NIC/EEF/93/DEM/56和NIC/KIP/93/INV/57的资金已由工发组织在第九十七次会议上退回，详见第UNEP/OzL.Pro/ExCom/97/4号文件（资金余额与可用资源报告）附件三所列；
(iii) 在第九十八次会议上，工发组织将退还项目NIC/PHA/92/INV/48和NIC/EEF/92/TAS/49的资金；并
(b) 要求秘书处就与多边基金资助项目有关的事宜与尼加拉瓜政府进行跟进。
UNEP/OzL.Pro/ExCom/97/17


UNEP/OzL.Pro/ExCom/97/17



执行蒙特利尔议定书多边基金执行委员会的会前文件不妨碍文件印发后执行委员会可能作出的任何决定。
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Annex I
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF ALBANIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023-2030)
Purpose
1. [bookmark: _Hlk146706470][bookmark: _Hlk128135089][bookmark: _Hlk130660551]This Agreement represents the understanding of the Government of Albania (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 795,464 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
[bookmark: _Hlk130659199]The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex  F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
[bookmark: _Hlk128740135]The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
[bookmark: _Hlk130666479]Flexibility in the reallocation of funds
[bookmark: _Hlk130666540]The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) and UNEP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the monitoring and evaluation work programmes of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
[bookmark: _Hlk131268859]Non-compliance with the Targets in the Agreement
[bookmark: _Hlk131270712]Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
[bookmark: _Hlk130668684]The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	[bookmark: _Hlk131268561]Substances
	Starting point for aggregate reductions in consumption

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	883,849
	883,849
	883,849
	883,849
	883,849
	795,464
	795,464
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	883,849
	883,849
	883,849
	883,849
	883,849
	795,464
	795,464
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	129,390
	0
	0
	94,610
	0
	0
	0
	36,000
	260,000

	2.2
	Support costs for Lead IA (US $)
	16,821
	0
	0
	12,299
	0
	0
	0
	4,680
	33,800

	2.3
	Cooperating IA (UNEP) agreed funding (US $)
	50,000
	0
	0
	50,000
	0
	0
	0
	0
	100,000

	2.4
	Support costs for Cooperating IA (US $)
	6,500
	0
	0
	6,500
	0
	0
	0
	0
	13,000

	3.1
	Total agreed funding (US $)
	179,390
	0
	0
	144,610
	0
	0
	0
	36,000
	360,000

	3.2
	Total support costs (US $)
	23,321
	0
	0
	18,799
	0
	0
	0
	4,680
	46,800

	3.3
	Total agreed costs (US $)
	202,711
	0
	0
	163,409
	0
	0
	0
	40,680
	406,800


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
[bookmark: _Hlk130669478]APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), under the Ministry of Tourism and Environment in the Country is responsible for monitoring the progress of implementation of activities in the Plan. 
The monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of trainings and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA.  
The Ministry of Tourism and Environment will be responsible for the sustainability of consumption reduction targets achieved through the agreement. 
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
Providing assistance for policy development when required;
Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently‑, confiscated, destroyed, exported, or returned to the country of origin.
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Annex II
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF ARMENIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024-2029)
Purpose
1. This Agreement represents the understanding of the Government of Armenia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 427,729 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the monitoring and evaluation work programmes of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6‑A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	475,254
	475,254
	475,254
	475,254
	475,254
	427,729
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	475,254
	475,254
	475,254
	475,254
	475,254
	427,729
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	165,075
	0
	0
	14,925
	0
	0
	180,000

	2.2
	Support costs for Lead IA (US $)
	21,460
	0
	0
	1,940
	0
	0
	23,400

	3.1
	Total agreed funding (US $)
	165,075
	0
	0
	14,925
	0
	0
	180,000

	3.2
	Total support costs (US $)
	21,460
	0
	0
	1,940
	0
	0
	23,400

	3.3
	Total agreed costs (US $)
	186,535
	0
	0
	16,865
	0
	0
	203,400


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit, under the Ministry of Environment in the Country, is responsible for monitoring the progress of implementation of activities in the Plan.
The monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of trainings and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA.
The Ministry of Environment will be responsible for the sustainability of consumption reduction targets achieved through the Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently‑, confiscated, destroyed, exported, or returned to the country of origin.
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Annex III
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF THE PLURINATIONAL STATE OF BOLIVIA AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023-2030)
Purpose
1. This Agreement represents the understanding of the Government of the Plurinational State of Bolivia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 576,201 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex  F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) and UNEP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the monitoring and evaluation work programmes of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	677,884
	677,884
	677,884
	677,884
	677,884
	610,096
	610,096
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	15.0
	15.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	677,884
	677,884
	677,884
	677,884
	677,884
	576,201
	576,201
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	153,500
	0
	0
	0
	78,500
	0
	0
	25,000
	257,000

	2.2
	Support costs for Lead IA (US $)
	19,955
	0
	0
	0
	10,205
	0
	0
	3,250
	33,410

	2.3
	Cooperating IA (UNEP) agreed funding (US $)
	40,500
	0
	0
	0
	20,000
	0
	0
	7,500
	68,000

	2.4
	Support costs for Cooperating IA (US $)
	5,265
	0
	0
	0
	2,600
	0
	0
	975
	8,840

	3.1
	Total agreed funding (US $)
	194,000
	0
	0
	0
	98,500
	0
	0
	32,500
	325,000

	3.2
	Total support costs (US $)
	25,220
	0
	0
	0
	12,805
	0
	0
	4,225
	42,250

	3.3
	Total agreed costs (US $)
	219,220
	0
	0
	0
	111,305
	0
	0
	36,725
	367,250


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The Ministry of Environment and Water (Ministerio de Medio Ambiente y Agua, MMAyA) is the national focal point for the implementation of the Montreal Protocol in the Country.
The activities related to the implementation of the Plan will be carried out under the Vice Ministry of Environment, Biodiversity, Climate Change, and Forest Management and Development, through the Governmental Ozone Commission (Comisión Gubernamental del Ozono, CGO).
All activities under the Plan are included in the annual work plan of the MMAyA. Regular monitoring is conducted by MMAyA and the Lead IA and Cooperating IA, covering the following aspects:
Management and coordination of the Plan implementation;
Development and implementation of policies to enable the Government to fulfill its mandates and ensure that industry complies with HFC consumption reduction obligations;
Continuous monitoring of the private sector in relation to the use of HFCs and potential alternatives;
Organization and execution of training, awareness-raising, and capacity-building activities to ensure strong commitment to the Plan’s goals and obligations;
Preparation of annual implementation plans, including the sequencing of beneficiary participation in activities;
Establishment and operation of a reporting system for users of HFCs and their alternatives;
Design and application of corrective measures when necessary;
Provision of ongoing technical assistance to project beneficiaries; and
Establishment and operation of a decentralized monitoring and evaluation mechanism, including on the sustainability of the consumption reduction targets, in collaboration with local environmental regulatory authorities, to ensure sustainability of results.
The Country agrees to participate in evaluations carried out under the monitoring and evaluation work programmes of the Multilateral Fund or by any of the implementing agencies involved in the implementation of the Plan.
The Government will establish strategic alliances with other governmental institutions, industry associations, and academic bodies to strengthen its strategy and broaden the scope of its activities. These alliances may involve:
Collaboration with training institutions that host refrigerant phase-out programmes and provide support to the servicing sector; and
Coordination with the National Customs Office (Aduana Nacional de Bolivia, ANB), which develops, guides, and implements regulations, including those related to Montreal Protocol-controlled substances.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
Providing assistance for policy development when required;
Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently, confiscated, destroyed, exported, or returned to the country of origin.
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Annex IV
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF BURKINA FASO
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Burkina Faso (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 735,075 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex  F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. The Government of Germany has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the monitoring and evaluation work programmes of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025-2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	1,049,523
	1,049,523
	1,049,523
	1,049,523
	944,571
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	22.2
	22.2
	22.2
	22.2
	30.0
	n/a

	
	
	CO2‑eq tonnes
	816,746
	816,746
	816,746
	816,746
	735,075
	n/a

	2.1
	Lead IA (Germany) agreed funding (US $)
	162,500
	0
	162,500
	0
	0
	325,000

	2.2
	Support costs for Lead IA (US $)
	21,125
	0
	21,125
	0
	0
	42,250

	3.1
	Total agreed funding (US $)
	162,500
	0
	162,500
	0
	0
	325,000

	3.2
	Total support costs (US $)
	21,125
	0
	21,125
	0
	0
	42,250

	3.3
	Total agreed costs (US $)
	183,625
	0
	183,625
	0
	0
	367,250


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU), under the Ministry of Environment, Water and Sanitation in the Country is responsible for monitoring the progress of implementation of activities in the Plan. 
1. The monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of trainings and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA. 
1. The Ministry of Environment, Water and Sanitation will be responsible for the sustainability of consumption reduction targets achieved through the agreement
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. [bookmark: _Hlk131269422]In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently, confiscated, destroyed, exported, or returned to the country of origin.
APPENDIX 8-A: SECTOR-SPECIFIC ARRANGEMENTS
1. During the implementation of the Plan, the Government of Burkina Faso would be allowed, on an exceptional basis, to submit a project for the commercial refrigeration sector to achieve additional HFC reductions. 
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Annex V

DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF CAMEROON
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023-2030)
Purpose
1. This Agreement represents the understanding of the Government of Cameroon (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 3,335,300 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2030 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex  F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the monitoring and evaluation work programmes of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4-A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption 

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	10
	n/a

	
	
	CO2‑eq 
tonnes
	n/a
	4,760,203
	4,760,203
	4,760,203
	4,760,203
	4,760,203
	4,284,183
	4,284,183
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	21.1
	21.7
	24.5
	25.0
	28.9
	29.4
	30.0
	n/a

	
	
	CO2‑eq 
tonnes
	3,579,012
	3,753,448
	3,728,532
	3,594,623
	3,568,669
	3,386,415
	3,360,461
	3,335,300
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	355,500
	0
	0
	406,000
	0
	297,000
	0
	153,000
	1,211,500

	2.2
	Support costs for Lead IA (US $)
	24,885
	0
	0
	28,420
	0
	20,790
	0
	10,710
	84,805

	3.1
	Total agreed funding (US $)
	355,500
	0
	0
	406,000
	0
	297,000
	0
	153,000
	1,211,500

	3.2
	Total support costs (US $)
	24,885
	0
	0
	28,420
	0
	20,790
	0
	10,710
	84,805

	3.3
	Total agreed costs (US $)
	380,385
	0
	0
	434,420
	0
	317,790
	0
	163,710
	1,296,305

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	1,424,903

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The National Ozone Unit (NOU), under the Ministry of Environment, Protection of Nature and Sustainable Development in the Country, is responsible for monitoring the progress of implementation of the activities and sustainability of achieved results. 
The monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of trainings and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA. 
The Ministry of Environment, Protection of Nature and Sustainable Development will be responsible for the sustainability of consumption reduction targets achieved through the agreement.
The Lead IA will support the Country in the monitoring of HFC imports. An independent consultant will be recruited by the Lead IA if required for the verification of the achievement. Annual report will be prepared by the NOU under the assistance of the Lead IA. 
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
(k) Ensuring that disbursements made to the Country are based on the use of the indicators;
(l) Providing assistance with the policy, management and technical support when required; and
(m) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
2. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $1.70 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2‑A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non‑compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently, confiscated, destroyed, exported, or returned to the country of origin.
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Annex VI 
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF CHILE
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023-2029)
Purpose
1. This Agreement represents the understanding of the Government of Chile (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 6,028,296 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex  F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) and UNEP has agreed to be the cooperating implementing agency/agencies (the “Cooperating IA[s]”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the monitoring and evaluation work programmes of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	n/a
	6,698,107
	6,698,107
	6,698,107
	6,698,107
	6,698,107
	6,028,296
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	n/a
	6,698,107
	6,698,107
	6,698,107
	6,698,107
	6,698,107
	6,028,296
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	752,607
	0
	0
	566,133
	0
	0
	158,971
	1,477,711

	2.2
	Support costs for Lead IA (US $)
	52,683
	0
	0
	39,629
	0
	0
	11,128
	103,440

	2.3
	Cooperating IA (UNEP) agreed funding (US $)
	123,900
	0
	0
	115,900
	0
	0
	14,200
	254,000

	2.4
	Support costs for Cooperating IA (US $)
	16,107
	0
	0
	15,067
	0
	0
	1,846
	33,020

	3.1
	Total agreed funding (US $)
	876,507
	0
	0
	682,033
	0
	0
	173,171
	1,731,711

	3.2
	Total support costs (US $)
	68,790
	0
	0
	54,696
	0
	0
	12,974
	136,460

	3.3
	Total agreed costs (US $)
	945,297
	0
	0
	736,729
	0
	0
	186,145
	1,868,171

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	847,086

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phasedown pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The national ozone unit (NOU) of the Ministry of Environment shall be responsible for coordinating and monitoring the actions associated with each strategic line of the Plan through collaborating with various areas of the Ministry such as Air Quality and Climate Change Division, Legal Division, Studies and Environmental Economics Division, and Communications Division, among others; as well as with other Government agencies such as National Customs Service and Ministry of Health, among others.
1. The monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of trainings and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA. 
1. To support the implementation of projects in different sectors, national and/or international consultants will be hired, if necessary, to implement the various activities and offer support to the NOU in coordination with key actors, including other Ministries, Agencies and the private sector.
1. The NOU will have the full support of the Government. The Ministry of Environment has ensured the adoption of the laws and the implementation of necessary national regulations to guarantee the country’s compliance with the Montreal Protocol agreements. The Ministry of Environment in the government of Chile will be responsible for the sustainability of consumption reduction targets achieved through the agreement. 
1. For the implementation of these projects, it is essential to continue to have the active participation of relevant public sector counterparts, such as the National Customs Service, which actively participates in the definition and implementation of import and export control processes of HCFC.
1. The Government of Chile has appointed UNDP to be the Lead IA to spearhead the implementation of HPMP, and has appointed UNEP as Cooperating IA. The Lead IA shall also have the overall responsibility of reporting to the Executive Committee, and of supporting the Country in the implementation of non-investment components that are not implemented by Cooperating IA.
1. Before each Executive Committee meeting is held to discuss a tranche to receive funding, the NOU will prepare a report on the status of activities and progress together with the Lead IA and with the help of the Cooperating IA, including the milestones and other key performance indicators, as well as any other information of interest for the implementation of KIP. This report will be reviewed and verified by the Lead IA and will then be sent to the Executive Committee through the Secretariat of the Multilateral Fund.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
Coordinating the activities of the Cooperating IA[s] and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and the Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
Providing assistance for policy development when required;
Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $4.09 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently, confiscated, destroyed, exported, or returned to the country of origin.
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Annex VII
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF COLOMBIA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Colombia (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 7,068,258 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) and the Government of Germany and UNEP have agreed to be the cooperating implementing agencies (the “Cooperating IAs”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the monitoring and evaluation work programmes of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IAs taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IAs will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IAs are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IAs with the fees set out in rows 2.2, 2.4, and 2.6 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IAs to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IAs with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	8,652,982
	8,652,982
	8,652,982
	8,652,982
	8,652,982
	7,787,684
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	18.3
	n/a

	
	
	CO2‑eq tonnes
	8,652,982
	8,652,982
	8,652,982
	8,652,982
	8,652,982
	7,068,258
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	2,554,986
	0
	0
	1,715,974
	0
	0
	4,270,960

	2.2
	Support costs for Lead IA (US $)
	178,849
	0
	0
	120,118
	0
	0
	298,967

	2.3
	Cooperating IA (Germany) agreed funding (US $)
	258,825
	0
	0
	109,900
	0
	0
	368,725

	2.4
	Support costs for Cooperating IA (US $)
	33,647
	0
	0
	14,287
	0
	0
	47,934

	2.5
	Cooperating IA (UNEP) agreed funding (US $)
	0
	0
	0
	50,000
	0
	0
	50,000

	2.6
	Support costs for Cooperating IA (US $)
	0
	0
	0
	6,500
	0
	0
	6,500

	3.1
	Total agreed funding (US $)
	2,813,811
	0
	0
	1,875,874
	0
	0
	4,689,685

	3.2
	Total support costs (US $)
	212,496
	0
	0
	140,905
	0
	0
	353,401

	3.3
	Total agreed costs (US $)
	3,026,307
	0
	0
	2,016,779
	0
	0
	5,043,086

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	1,584,724

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The Ministry of Environment and Sustainable Development (MinAmbiente) is the entity responsible for the coordination and management of programs and activities under stage I of the KIP. This ministry is supported by the Ozone Technical Unit (UTO), which is currently part of the Group of Chemical Substances and Hazardous Waste of the Sectorial, Urban and Environmental Affairs Direction. 
The UTO works as an institution of a public character to coordinate activities of the Plan, supported by MinAmbiente and other government entities and implementing partners. Collaborations with further government entities and private associations also contribute to the development, monitoring, and implementation of the Plan and adherence to the Montreal Protocol. 
Coordination and monitoring of the Plan will be accomplished through the operational monitoring of stage I activities, verification of funding disbursements, and the monitoring and assessment of implemented activities in advanced stages of the Plan. The monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of trainings and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA. 
The Ministry of Environment and Sustainable Development coordinates all activities aimed at achieving and sustaining the commitments to reduce HFC consumption with different entities at the national level, including the National Environmental Licensing Authority (ANLA), the Ministry of Commerce, Industry and Tourism (MinCit), the National Tax and Customs Directorate (DIAN), the Ministry of Health and Social Protection, the Ministry of Mines and Energy, trade associations and the productive sectors.
The Ministry of Environment and Sustainable Development will be responsible for the sustainability of consumption reduction targets achieved through the agreement. 
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IAs;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
Coordinating the activities of the Cooperating IAs and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IAs, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IAs on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IAs will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
Providing assistance for policy development when required;
Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IAs, and referring to the Lead IA to ensure a coordinated sequence of activities;
Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $5.92 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently, confiscated, destroyed, exported, or returned to the country of origin.
APPENDIX 8-A: SECTOR-SPECIFIC ARRANGEMENTS

1. That UNDP will include in progress reports submitted under the KIP the names and consumption of enterprises manufacturing HFC-based stand-alone commercial refrigeration equipment beyond the 27 enterprises assisted under the project, and that consumption will be deducted from the country’s remaining HFC consumption eligible for funding when stage II of the KIP is submitted.

2. That UNDP would report on the quantity of HFCs phased out through carbon dioxide-based equipment manufactured by the enterprise Weston upon completion of the project, and that, if Weston phased out less than 5 metric tonnes of HFCs through the manufacture of carbon dioxide-based stand-alone refrigeration units, the enterprise would return to the Multilateral Fund, through UNDP, US $19.01/kg plus agency support costs for every kilogram not manufactured using carbon dioxide.
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Annex VIII

DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF THE CONGO
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023-2030)
Purpose
1. This Agreement represents the understanding of the Government of the Congo (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 258,932 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex  F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) and UNEP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the monitoring and evaluation work programmes of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IA are contained in Appendix 6-A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4-A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption 

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	10
	n/a

	
	
	CO2‑eq 
tonnes
	n/a
	504,649
	504,649
	504,649
	504,649
	504,649
	454,184
	454,184
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction 
in %
	n/a
	34.4
	36.7
	39.8
	42.3
	44.3
	48.7
	48.7
	n/a

	
	
	CO2‑eq 
tonnes
	304,964
	330,903
	319,196
	303,718
	291,384
	281,270
	258,932
	258,932
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	67,750
	0
	0
	96,500
	0
	0
	0
	12,750
	177,000

	2.2
	Support costs for Lead IA (US $)
	8,808
	0
	0
	12,545
	0
	0
	0
	1,658
	23,010

	2.3
	Cooperating IA (UNEP) agreed funding (US $)
	13,750
	0
	0
	27,500
	0
	0
	0
	9,750
	51,000

	2.4
	Support costs for Cooperating IA (US $)
	1,788
	0
	0
	3,575
	0
	0
	0
	1,267
	6,630

	3.1
	Total agreed funding (US $)
	81,500
	0
	0
	124,000
	0
	0
	0
	22,500
	228,000

	3.2
	Total support costs (US $)
	10,595
	0
	0
	16,120
	0
	0
	0
	2,925
	29,640

	3.3
	Total agreed costs (US $)
	92,095
	0
	0
	140,120
	0
	0
	0
	25,425
	257,640


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
(a) A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
(b) An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
(c) A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
(d) An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The National Ozone Unit (NOU), under the Ministry of the Environment, Sustainable Development and the Congo Basin in the Country, is responsible for monitoring the progress of implementation of the activities and sustainability of achieved results. 
The monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of trainings and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA.  
The Ministry of the Environment, Sustainable Development and the Congo Basin in the government of the Republic of Congo will be responsible for the sustainability of consumption reduction targets achieved through the agreement. 
The Lead IA will support the country in the monitoring of HFC imports. An independent consultant will be recruited by the Lead IA if required for the verification of the achievement. Annual report will be prepared by the NOU under the assistance of the Lead IA. 
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
(a) Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
(b) Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
(c) Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
(d) Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
(e) Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee including the activities implemented by the Cooperating IA;
(f) In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
(g) Ensuring that appropriate independent technical experts carry out the technical reviews;
(h) Carrying out the required supervision missions;
(i) Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
(j) Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
(k) In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
(l) Ensuring that disbursements made to the Country are based on the use of the indicators;
(m) Providing assistance with the policy, management and technical support when required;
(n) Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
(o) Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
2. After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES 
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
(a) Providing assistance for policy development when required;
(b) Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
(c) Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
(d) Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently, confiscated, destroyed, exported, or returned to the country of origin.
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Annex IX
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF COSTA RICA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Costa Rica (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 1,305,719 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex  F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; 
Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the monitoring and evaluation work programmes of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances 
	%
	freeze
	freeze
	freeze 
	freeze
	freeze
	10
	n/a

	
	
	CO2-eq tonnes
	1,450,799
	1,450,799
	1,450,799
	1,450,799
	1,450,799
	1,305,719
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2-eq tonnes
	1,450,799
	1,450,799
	1,450,799
	1,450,799
	1,450,799
	1,305,719
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	370,968
	0
	0
	247,312
	0
	0
	618,280

	2.2
	Support costs for Lead IA (US $)
	46,807
	0
	0
	31,204
	0
	0
	78,011

	3.1
	Total agreed funding (US $)
	370,968
	0
	0
	247,312
	0
	0
	618,280

	3.2
	Total support costs (US $)
	46,807
	0
	0
	31,204
	0
	0
	78,011

	3.3
	Total agreed costs (US $)
	417,775
	0
	0
	278,516
	0
	0
	696,291

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	211,395

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The Ministry of Environment and Energy (MINAE) is the authority responsible for the implementation of national actions related to the preservation of the ozone layer under the Montreal Protocol. The Directorate of Environmental Quality Management (DIGECA) is the focal point of the Montreal Protocol designated by the Ministry of Foreign Affairs and Worship and MINAE. DIGECA coordinates with other public institutions and organizations and with the private sector for the implementation of activities under stage I of the KIP´s. The roles and responsibilities of these institutions are described as follows:
58. DIGECA is responsible for granting import licenses for controlled substances, distributing annual import quotas as established in the reduction schedule, and approving permits for the import and export of controlled substances, ensuring the sustainability of annual reductions and compliance with established commitments. 
58. Ministry of Finance and its customs offices are responsible for regulating international trade of controlled substances, monitoring imports and enforcing quotas together with other governing entities, and is in charge of public procurement; 
Ministry of Health is responsible for issuing the corresponding regulations for the use of controlled substances; 
Training and technical training institutions such as the National Institute of Learning (INA), the Ministry of Public Education (MEP), the Samuel Foundation, Public Universities will support strengthening of the technical capabilities of refrigeration and air‑conditioning technicians and professionals;
DIGECA will collaborate with the industrial chambers and associations (Chamber of Industries, Association of Industrial Technicians, Federated College of Engineers and Architects, Chamber of Commerce, Costa Rican refrigeration, air conditioning and ventilation chamber. (CCRAVE), among others) when dealing with overarching issues for the interest of the industry during the process of complete elimination of HFCs;
DIGECA will also work with other Government departments responsible for the National Quality System, including the technical standards body, for updating and adoption of the technical standards and regulations required for the implementation of the Montreal Protocol; and
The Lead IA will provide administrative, budgetary and financial monitoring necessary for the implementation of project activities.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
[bookmark: _Int_iqryaQfs]Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country the allocation of the reductions to the different budget items and to the funding of the Lead IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $5.85 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently‑, confiscated, destroyed, exported, or returned to the country of origin.
APPENDIX 8-A: SECTOR-SPECIFIC ARRANGEMENTS  
1. During the implementation of stage I of the KIP, the Country is encouraged to initiate the development of a strategic approach for the sustained phase-out of HFC consumption in the local assembly and installation subsector for commercial refrigeration, for possible inclusion within stage II of the KIP, that included consideration of incentives and policy measures to sustain the phase-out achieved and taking into account document UNEP/OzL.Pro/ExCom 95/89 discussed at the 95th meeting. 
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Annex X
DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF CUBA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of Cuba (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 927,596 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex  F substances specified in Appendix 1‑A.
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the monitoring and evaluation work programmes of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption

	HFCs
	n/a


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq 
tonnes
	n/a
	1,030,662
	1,030,662
	1,030,662
	1,030,662
	1,030,662
	927,596
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq 
tonnes
	n/a
	1,030,662
	1,030,662
	1,030,662
	1,030,662
	1,030,662
	927,596
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	160,000
	0
	0
	130,000
	0
	0
	35,000
	325,000

	2.2
	Support costs for Lead IA (US $)
	20,800
	0
	0
	16,900
	0
	0
	4,550
	42,250

	3.1
	Total agreed funding (US $)
	160,000
	0
	0
	130,000
	0
	0
	35,000
	325,000

	3.2
	Total support costs (US $)
	20,800
	0
	0
	16,900
	0
	0
	4,550
	42,250

	3.3
	Total agreed costs (US $)
	180,800
	0
	0
	146,900
	0
	0
	39,550
	367,250


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. [bookmark: _Hlk211248681]Supervision will be provided by the Ministry of Science Technology and Environment, through the Ozone Technical Office (OTOZ), part of Cubaenergía, with assistance from the Lead IA.
Consumption will be monitored and determined from official data, on the import and export of substances registered by the National Customs Directorate (DGA).
OTOZ will compile and report the following data and information each year or before the deadlines:
Annual reports on the consumption of the substances to be submitted to the Ozone Secretariat, and
Annual reports on progress in implementing the Plan will be submitted to the Executive Committee of the Multilateral Fund.
The monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of trainings and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA. 
The Ministry of Science Technology and Environment coordinates all activities aimed at achieving and sustaining the commitments to reduce HFC consumption with different entities at the national level, including the Ministry of Domestic Trade (MINCIN), the Ministry of External Trade (MINCEX), the Ministry of Public Health (MINSAP), the Ministry of Energy and Mines (MINEM), the National Customs Directorate (DGA), Office of Environmental Regulation and Safety (ORSA) and the productive sectors.
The Ministry of Ministry of Science Technology and Environment will be responsible for the sustainability of consumption reduction targets achieved through the agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $7.00 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently, confiscated, destroyed, exported, or returned to the country of origin.
APPENDIX 8-A: SECTOR-SPECIFIC ARRANGEMENTS  
1. During the implementation of stage I of the KIP, the Country will be allowed, on an exceptional basis, to submit investment projects in the refrigeration and air-conditioning sector to achieve additional HFC reductions. 
1. A project to phase out HFCs contained in imported pre-blended polyols in the polyurethane foam sector in the Country will be subject to the decision taken by the Committee on whether it would fund the phase-out of HFCs contained in imported pre-blended polyols.
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Annex XI

DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF THE DOMINICAN REPUBLIC
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2023–2029)
Purpose
1. This Agreement represents the understanding of the Government of the Dominican Republic (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 3,450,680 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex  F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNDP has agreed to be the lead implementing agency (the “Lead IA”) and UNEP and UNIDO have agreed to be the cooperating implementing agencies (the “Cooperating IAs”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the monitoring and evaluation work programmes of the Multilateral Fund or under the evaluation programme of the Lead IA and/or Cooperating IAs taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IAs will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and Cooperating IAs are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IAs with the fees set out in rows 2.2, 2.4, and 2.6 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IAs to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IAs with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING*
	Row
	Particulars
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	3,834,089 
	3,834,089 
	3,834,089 
	3,834,089 
	3,834,089 
	3,450,680 
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	0.0
	0.0
	0.0
	0.0
	0.0
	10.0
	n/a

	
	
	CO2‑eq tonnes
	n/a
	3,834,089 
	3,834,089 
	3,834,089 
	3,834,089 
	3,834,089 
	3,450,680 
	n/a

	2.1
	Lead IA (UNDP) agreed funding (US $)
	365,106
	0
	0
	368,223
	0
	0
	60,839
	794,168

	2.2
	Support costs for Lead IA (US $)
	25,557
	0
	0
	25,776
	0
	0
	4,259
	55,592

	2.3
	Cooperating IA (UNEP) agreed funding (US $)
	120,774
	0
	0
	103,272
	0
	0
	45,903
	269,949

	2.4
	Support costs for Cooperating IA (US $)
	15,701
	0
	0
	13,425
	0
	0
	5,967
	35,093

	2.5
	Cooperating IA (UNIDO) agreed funding (US $)
	50,050
	0
	0
	49,280
	0
	0
	10,670
	110,000

	2.6
	Support costs for Cooperating IA (US $)
	4,505
	0
	0
	4,435
	0
	0
	960
	9,900

	3.1
	Total agreed funding (US $)
	535,930
	0
	0
	520,775
	0
	0
	117,412
	1,174,117

	3.2
	Total support costs (US $)
	45,763
	0
	0
	43,636
	0
	0
	11,186
	100,585

	3.3
	Total agreed costs (US $)
	581,693
	0
	0
	564,411
	0
	0
	128,598
	1,274,702

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	383,409

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes) *
	6,323

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


* Noting that 4.01 mt (5,734.3 CO2-eq tonnes) of HFC-134a and 0.15 mt (588.3 CO2-eq tonnes) of R-404A would be deducted from the starting point for sustained aggregate reduction in HFCs once it has been established (decision 81/57)
APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The National Ozone Programme (PRONAOZ) of the Ministry of Environment and Natural Resources (MARN) shall be responsible for monitoring the progress of implementation of activities in the plan and coordinating the actions associated with each programme and projects through collaborating with various areas of the Ministry; as well as with other government agencies such as the General Customs Directorate of the Ministry of Treasury, between others. 
1. The MARN in the Country will be responsible for the sustainability of consumption reduction targets achieved through the agreement. 
1. To support the implementation of projects in different sectors, national and/or international consultants will be hired, if necessary, to implement the various activities and offer support to the PRONAOZ in coordination with key actors, including other Ministries, Agencies and the private sector. 
PRONAOZ have the full support of the Government. The MARN has ensured the adoption of the laws and the implementation of necessary national regulations to guarantee the country’s compliance with the Montreal Protocol agreements. 
1. For the adequate implementation of these projects, it is essential to continue to have the active participation of relevant public sector counterparts, such as the General Customs Directorate, which actively participates in the definition and implementation of import and export control processes of HCFC. 
1. The monitoring will be conducted during the implementation of the Plan to ensure efficient and effective implementation; overall project coordination; stakeholder engagement and coordination; smooth implementation of activities planned under various tranches; delivery of trainings and other expected outcomes; and facilitation of the HFC consumption verification undertaken by the Lead IA. 
1. The Lead IA shall have the overall responsibility of reporting to the Executive Committee, and of supporting the Country in the implementation of the non-investment components that are not implemented by the Cooperating IA. 
1. Before each Executive Committee meeting is held to discuss a tranche to receive funding, PRONAOZ will prepare a report on the status of activities and progress together with the Lead IA and with the help of the Cooperating IA, including the milestones and other key performance indicators as well as any other information of interest for the implementation of the Plan. This report will be reviewed and verified by the Lead IA and will then be sent to the Executive Committee through the Secretariat of the Multilateral Fund.
1. A project coordinator will be hired with funding from the project monitoring unit, and they will report to the national ozone officer. The project coordinator will coordinate the daily activities in the project and will assure that all activities are in line with the approved work plan.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IAs;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
Coordinating the activities of the Cooperating IAs and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IAs, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IAs on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IAs will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
Providing assistance for policy development when required;
Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IAs, and referring to the Lead IA to ensure a coordinated sequence of activities;
Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $6.69 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently, confiscated, destroyed, exported, or returned to the country of origin.
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Annex XII

DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF ECUADOR
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
	(Period: 2022–2029)	
Purpose
1. This Agreement represents the understanding of the Government of Ecuador (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 2,730,168 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex  F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report;
Any enterprise included in the Plan that would be found to be ineligible under the policies of the Multilateral Fund (i.e., due to foreign ownership or establishment after the applicable cut‑off date) would not receive financial assistance. This information would be reported as part of the Tranche Implementation Plan; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the monitoring and evaluation work programmes of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The role of the Lead IA is contained in Appendix 6-A. The Executive Committee agrees, in principle, to provide the Lead IA with the fees set out in row 2.2 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee and the Lead IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2022*
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	n/a
	n/a
	freeze
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	n/a
	n/a
	3,179,294
	3,179,294
	3,179,294
	3,179,294
	3,179,294
	2,861,365
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	n/a
	n/a
	0.0
	3.0
	5.9
	8.7
	11.5
	14.1
	n/a

	
	
	CO2‑eq tonnes
	n/a
	n/a
	3,179,294
	3,083,915
	2,991,398
	2,901,656
	2,814,606
	2,730,168
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	267,885
	292,600
	0
	0
	364,414
	0
	0
	72,930
	997,829

	2.2
	Support costs for Lead IA (US $)
	18,752
	20,482
	0
	0
	25,509
	0
	0
	5,105
	69,848

	3.1
	Total agreed funding (US $)
	267,885
	292,600
	0
	0
	364,414
	0
	0
	72,930
	997,829

	3.2
	Total support costs (US $)
	18,752
	20,482
	0
	0
	25,509
	0
	0
	5,105
	69,848

	3.3
	Total agreed costs (US $)
	286,637
	313,082
	0
	0
	389,923
	0
	0
	78,035
	1,067,677

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	434,225 

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	14,901

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


* Conversion of one commercial and domestic refrigerator manufacturing line at the enterprise Induglob, approved by decision 91/59 to phase out 14,901 CO2-eq tonnes (10.42 mt) of HFC-134a.
APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The Minister of Production, Foreign Trade, Investment and Fishery (MPCEIP) is the Focal Point of the Montreal Protocol in the Country. The activities corresponding to the implementation of the Protocol are aligned with the strategies and proposals of the National Direction of Environment and Technological Reconversion. This Division coordinates the Plan with the authorities.
The Plan is implemented through the National Ozone Unit established within the MPCEIP, as part of the National Direction of Environment and Technological Reconversion, and its functions are:
To coordinate, as a focal point, all the activities related to the implementation of the country programme for the HFC phase-down in the Country;
To monitor and control the Montreal Protocol controlled substances consumption;
To disseminate data and pertinent information to all the interested parties, and to inform on the requirements of the Montreal Protocol;
To promote awareness of the HFC and HFC alternatives issues;
To report to the Ozone Secretariat, Multilateral Fund Secretariat, and to the implementing agencies about the consumption and phase-out of the HFC consumption in the Country; and
To coordinate and implement projects for the substances controlled by the Montreal Protocol in the Country including HFCs.
The MPCEIP will be responsible for the sustainability of consumption reduction targets achieved through the Agreement, monitoring of the Plan, and the enforcement of the policies and legislation, the procedures to carry out these activities are:
Implementation of all the activities of the components within the Plan, including detailed activity design, audit of the parties involved, identification and selection of the beneficiaries, contracting of goods and services, continuous technical assistance to the project beneficiaries;
Regular monitoring of the trends and attitudes in the local private sector related to HFC use and its possible substitutes;
Design, organization and implementation (annual) of the project monitoring activities, including the design of the data gathering and analysis instruments;
Analysis and report of results of the monitoring, and organization of the corresponding meetings for review and management of the monitoring;
Design and implementation of the corrective measures; and
Regular implementation of activities of technical assistance to the project beneficiaries.
The Plan will be managed by a dedicated team that consists of a coordinator that will be designated by the MPCEIP and has the support of the representatives and experts of the Lead IA and the necessary support infrastructure. The component of support to the management and update of the legal instruments of the Plan will include the following activities:
Management and coordination of the implementation of the Plan;
Establishment of a policy development and application programme to allow the Government to exercise the required mandates and ensure the industry fulfilment with the obligations of the HFC reduction;
Development and implementation of training, awareness and capacity building activities to ensure a high-level commitment to the Plan objectives and obligations; and
Preparation of annual implementation plans including the determination of the sequence of participation of the beneficiaries in the activities.
The Country agrees to evaluations, which might be carried out under the monitoring and evaluation work programmes of the Multilateral Fund or under the evaluation programme of the Lead IA taking part in this Agreement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country, the allocation of the reductions to the different budget items and to the funding of the Lead IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $4.44 per CO2‑eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently, confiscated, destroyed, exported, or returned to the country of origin.
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Annex XIII

DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF GUATEMALA
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Guatemala (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 1,024,695 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex  F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) and UNEP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the monitoring and evaluation work programmes of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025-2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	1,217,998
	1,217,998
	1,217,998
	1,217,998
	1,096,198
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	15.9
	n/a

	
	
	CO2‑eq tonnes
	1,217,998
	1,217,998
	1,217,998
	1,217,998
	1,024,695
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	251,019
	0
	121,019
	0
	31,019
	403,057

	2.2
	Support costs for Lead IA (US $)
	17,571
	0
	8,471
	0
	2,171
	28,213

	2.3
	Cooperating IA (UNEP) agreed funding (US $)
	10,000
	0
	85,573
	0
	30,000
	125,573

	2.4
	Support costs for Cooperating IA (US $)
	1,300
	0
	11,124
	0
	3,900
	16,324

	3.1
	Total agreed funding (US $)
	261,019
	0
	206,592
	0
	61,019
	528,630

	3.2
	Total support costs (US $)
	18,871
	0
	19,595
	0
	6,071
	44,537

	3.3
	Total agreed costs (US $)
	279,890
	0
	226,187
	0
	67,090
	573,167

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	193,303

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the second meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The Ministry of Environment and Natural Resources the Country (MARN), through the National Ozone Unit (NOU), which operates under the Department for the Environmentally Sound Management of Chemicals and Hazardous Waste, will serve as the coordinating authority for the implementation of the Plan at the national level. The NOU will be responsible for coordinating national authorities, key stakeholders, and the implementing and cooperating agencies; overseeing the execution of project activities; and reporting on progress in alignment with the Plan Agreement. The NOU will submit annual progress reports to the Lead IA, outlining the status of implementation, key achievements, constraints, and recommendations for corrective action.
With the support of technical consultants, and in collaboration with the Lead IA and Cooperating IA, the NOU will ensure the effective implementation of the Plan. This includes managing and monitoring the national HFC licensing and quota system, tracking project components, and facilitating coordination with other relevant national initiatives. The NOU will actively engage with competent institutions to secure compliance with relevant national regulations and promote alignment with the Plan objectives. If deemed necessary, independent verification of implementation will be carried out by a consultant designated by the Lead IA.
To ensure the long-term sustainability of the reductions in HFC consumption achieved under the Plan, the following institutions will be involved:
Superintendency of Tax Administration (SAT): Through the Customs Directorate, will continue to enforce the HFC licensing and quota system, monitor imports and exports of HFCs and related equipment, and ensure ongoing capacity-building for customs officials on emerging alternatives and control measures; and
MARN – Environmental Regulation and Control Units: Will contribute to the oversight and enforcement of environmental regulations related to the use and management of HFCs and promote inter-institutional cooperation for policy implementation.
These institutions, in close coordination with the NOU and implementing agencies, will be essential to ensuring that the reductions achieved through the Plan are sustained beyond the duration of the project through regulation, institutional capacity, continued training, and stakeholder engagement.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
Providing assistance for policy development when required;
Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $5.47 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently, confiscated, destroyed, exported, or returned to the country of origin.
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Annex XIV

DRAFT AGREEMENT BETWEEN THE GOVERNMENT OF HONDURAS
AND THE EXECUTIVE COMMITTEE OF THE MULTILATERAL FUND
FOR THE REDUCTION IN CONSUMPTION OF HYDROFLUOROCARBONS
IN ACCORDANCE WITH STAGE I OF THE KIGALI HFC IMPLEMENTATION PLAN
(Period: 2024–2029)
Purpose
1. This Agreement represents the understanding of the Government of Honduras (“the Country”) and the Executive Committee with respect to the reduction of controlled use of Annex F substances set out in Appendix 1‑A (“The Substances”) to a sustained level of 1,223,456 CO2‑equivalent (CO2‑eq) tonnes by 1 January 2029 in compliance with the Montreal Protocol schedule and the terms of this Agreement.
The Country agrees to meet the annual consumption limits of Annex F substances as set out in row 1.2 of Appendix 2‑A (“The Targets, and Funding”) in this Agreement as well as in the Montreal Protocol reduction schedule for Annex F substances mentioned in Appendix 1-A. The Country accepts that, by its acceptance of this Agreement and performance by the Executive Committee of its funding obligations described in paragraph 3, it is precluded from applying for or receiving further funding from the Multilateral Fund in respect to any consumption of Annex F substances that exceeds the level defined in row 1.2 of Appendix 2‑A as the final reduction step under this Agreement for Annex  F substances specified in Appendix 1‑A, and in respect to any consumption of Annex F substances that exceeds the level defined in row 4.1.3 (remaining consumption eligible for funding).
Subject to compliance by the Country with its obligations set out in this Agreement, the Executive Committee agrees, in principle, to provide the funding set out in row 3.1 of Appendix 2-A to the Country. The Executive Committee will, in principle, provide this funding at the Executive Committee meetings specified in Appendix 3-A (“Funding Approval Schedule”).
The Country agrees to implement this Agreement in accordance with stage I of the Kigali HFC implementation plan (“the Plan”) as approved. In accordance with subparagraph 5(b) of this Agreement, the Country will accept independent verification of the achievement of the annual consumption limits of Annex F substances set out in row 1.2 of Appendix 2-A of this Agreement. The aforementioned verification will be commissioned by the relevant bilateral or implementing agency.
Conditions for funding release
The Executive Committee will only provide the Funding, in accordance with the Funding Approval Schedule, when the Country satisfies the following conditions at least 10 weeks in advance of the applicable Executive Committee meeting set out in the Funding Approval Schedule:
That the Country has met the Targets set out in row 1.2 of Appendix 2-A for all relevant years. Relevant years are all years since the year in which this Agreement was approved. Years for which there are no due country programme implementation reports at the date of the Executive Committee meeting at which the funding request is being presented are exempted;
That the meeting of these Targets has been independently verified for all relevant years, unless the Executive Committee decided that such verification would not be required;
That the Country had submitted a Tranche Implementation Report in accordance with Appendix 4‑A (“Format of Tranche Implementation Reports and Plans”) covering each previous calendar year; that it had achieved a significant level of implementation of activities initiated with previously approved tranches; and that the rate of disbursement of funding available from the previously approved tranche was more than 20 per cent; and
That the Country has submitted a Tranche Implementation Plan in accordance with Appendix 4‑A covering each calendar year until and including the year for which the Funding Approval Schedule foresees the submission of the next tranche or, in case of the final tranche, until completion of all activities foreseen.
Monitoring
The Country will ensure that it conducts accurate monitoring of its activities under this Agreement. The institutions set out in Appendix 5-A (“Monitoring Institutions and Roles”) will monitor and report on implementation of the activities in the previous Tranche Implementation Plans in accordance with their roles and responsibilities set out in the same appendix.
Flexibility in the reallocation of funds
The Executive Committee agrees that the Country may have the flexibility to reallocate part or all approved funds, according to the evolving circumstances, to achieve the smoothest reduction of consumption and phase-down of Annex F substances specified in Appendix 1-A, in accordance with the following considerations:
Reallocations categorized as major changes must be documented in advance, either in a Tranche Implementation Plan as foreseen in subparagraph 5(d) above, or as a revision to an existing Tranche Implementation Plan to be submitted 10 weeks prior to any meeting of the Executive Committee, for its approval. Major changes would relate to:
Issues potentially concerning the rules and policies of the Multilateral Fund; 
Changes that would modify any clause of this Agreement; 
Changes in the annual levels of funding allocated to the individual bilateral or implementing agencies for the different tranches;
Provision of funding for activities not included in the current endorsed Tranche Implementation Plan, or removal of an activity in the Tranche Implementation Plan, with a cost greater than 30 per cent of the total cost of the last approved tranche;
Changes in alternative technologies, on the understanding that any submission for such a request would identify the associated incremental costs, the potential impact on the climate, and any differences in CO2-eq tonnes to be phased down if applicable, as well as confirm that the Country agrees that potential savings related to the change of technology would accordingly decrease the overall funding level under this Agreement;
Reallocations not categorized as major changes may be incorporated into the approved Tranche Implementation Plan, under implementation at the time, and reported to the Executive Committee in the subsequent Tranche Implementation Report; and
Any remaining funds held by the bilateral or implementing agencies or the Country under the Plan will be returned to the Multilateral Fund upon completion of the last tranche foreseen under this Agreement.
Specific attention will be paid to the execution of activities in the refrigeration servicing sector included in the Plan, in particular that the Country may use the flexibility available under this Agreement to address specific needs that might arise during project implementation.
Bilateral and implementing agencies
The Country agrees to assume overall responsibility for the management and implementation of this Agreement and of all activities undertaken by it or on its behalf to fulfil the obligations under this Agreement. UNIDO has agreed to be the lead implementing agency (the “Lead IA”) and UNEP has agreed to be the cooperating implementing agency (the “Cooperating IA”) under the lead of the Lead IA in respect of the Country’s activities under this Agreement. The Country agrees to evaluations, which might be carried out under the monitoring and evaluation work programmes of the Multilateral Fund or under the evaluation programme of the Lead IA and/or the Cooperating IA taking part in this Agreement.
The Lead IA will be responsible for ensuring coordinated planning, implementation and reporting of all activities under this Agreement, including but not limited to the independent verification as per subparagraph 5(b). The Cooperating IA will support the Lead IA by implementing the Plan under the overall coordination of the Lead IA. The roles of the Lead IA and the Cooperating IA are contained in Appendix 6‑A and Appendix 6-B, respectively. The Executive Committee agrees, in principle, to provide the Lead IA and the Cooperating IA with the fees set out in rows 2.2 and 2.4 of Appendix 2‑A.
Non-compliance with the Targets in the Agreement
Should the Country, for any reason, not meet the Targets for the elimination of Annex F substances set out in row 1.2 of Appendix 2-A or otherwise does not comply with this Agreement, then the Country agrees that it will not be entitled to the Funding in accordance with the Funding Approval Schedule. At the discretion of the Executive Committee, funding will be reinstated according to a revised Funding Approval Schedule determined by the Executive Committee after the Country has demonstrated that it has satisfied all its obligations that were due to be met prior to receipt of the next tranche of funding under the Funding Approval Schedule. The Country acknowledges that the Executive Committee may reduce the amount of the Funding by the amount set out in Appendix 7-A (“Reductions in Funding for Failure to Comply”) in respect of each CO2‑eq kg of reductions in consumption not achieved in any one year. The Executive Committee will discuss each specific case in which the Country did not comply with this Agreement and take related decisions. Once decisions are taken, the specific case of non-compliance with this Agreement will not be an impediment for the provision of funding for future tranches as per paragraph 5 above.
The Funding of this Agreement will not be modified on the basis of any future Executive Committee decisions that may affect the funding of any other consumption sector projects or any other related activities in the Country.
The Country will comply with any reasonable request of the Executive Committee, the Lead IA and the Cooperating IA to facilitate implementation of this Agreement. In particular, it will provide the Lead IA and the Cooperating IA with access to the information necessary to verify compliance with this Agreement.
Date of completion
The completion of the Plan and the associated Agreement will take place at the end of the year following the last year for which a maximum allowable total consumption level has been specified in Appendix 2‑A. Should at that time there still be activities that are outstanding, and which were foreseen in the last Tranche Implementation Plan and its subsequent revisions as per subparagraph 5(d) and paragraph 7, the completion of the Plan will be delayed until the end of the year following the implementation of the remaining activities. The reporting requirements as per subparagraphs 1(a), 1(b), and 1(d) of Appendix 4‑A will continue until the time of the completion of the Plan unless otherwise specified by the Executive Committee. 
Validity
All conditions set out in this Agreement are undertaken solely within the context of the Montreal Protocol and as specified in this Agreement. All terms used in this Agreement have the meaning ascribed to them in the Montreal Protocol unless otherwise defined herein.
This Agreement may be modified or terminated only by mutual written agreement of the Country and the Executive Committee of the Multilateral Fund.
APPENDICES
APPENDIX 1-A: THE SUBSTANCES
	Substances
	Starting point for aggregate reductions in consumption

	HFCs
	To be determined (TBD)


APPENDIX 2-A: THE TARGETS, AND FUNDING
	Row
	Particulars
	2024
	2025-2026
	2027
	2028
	2029
	Total

	1.1
	Montreal Protocol reduction schedule of Annex F substances
	%
	freeze
	freeze
	freeze
	freeze
	10
	n/a

	
	
	CO2‑eq tonnes
	1,449,723
	1,449,723
	1,449,723
	1,449,723
	1,304,751
	n/a

	1.2
	Maximum allowable total consumption of Annex F substances
	Reduction in %
	0.0
	0.0
	0.0
	0.0
	15.6
	n/a

	
	
	CO2‑eq tonnes
	1,449,723
	1,449,723
	1,449,723
	1,449,723
	[bookmark: _Hlk196292148]1,223,456
	n/a

	2.1
	Lead IA (UNIDO) agreed funding (US $)
	226,918
	0
	178,000
	0
	27,292
	432,210

	2.2
	Support costs for Lead IA (US $)
	15,885
	0
	12,460
	0
	1,910
	30,255

	2.3
	Cooperating IA (UNEP) agreed funding (US $)
	70,000
	0
	65,000
	0
	30,000
	165,000

	2.4
	Support costs for Cooperating IA (US $)
	9,100
	0
	8,450
	0
	3,900
	21,450

	3.1
	Total agreed funding (US $)
	296,918
	0
	243,000
	0
	57,292
	597,210

	3.2
	Total support costs (US $)
	24,985
	0
	20,910
	0
	5,810
	51,705

	3.3
	Total agreed costs (US $)
	321,903
	0
	263,910
	0
	63,102
	648,915

	4.1.1
	Deduction of HFCs under this Agreement (CO2-eq tonnes)
	226,267

	4.1.2
	Deduction of HFCs from previously approved projects (CO2-eq tonnes)
	0

	4.1.3
	Remaining eligible consumption for HFCs (CO2-eq tonnes)
	TBD


APPENDIX 3-A: FUNDING APPROVAL SCHEDULE
1. Funding for the future tranches will be considered for approval at the first meeting of the year specified in Appendix 2-A.
APPENDIX 4-A: FORMAT OF THE TRANCHE IMPLEMENTATION REPORTS AND PLANS
1. The submission of the Tranche Implementation Report and Plans for each tranche request will consist of four parts:
A narrative report, with data provided by tranche, describing the progress achieved since the previous report, reflecting the situation of the Country in regard to phase-down of Annex F substances, how the different activities contribute to it, and how they relate to each other, including, where applicable, activities related to energy efficiency approved in the context of HFC phase‑down pursuant to decision 91/65. The report should include the amount of Annex F substances consumption reduced as a direct result of the implementation of activities, by substance, the alternative technology used and the related phase‑in of alternatives, to allow the Secretariat to inform the Executive Committee on the resulting change in climate‑relevant emissions. The report should also include quantitative information on the activities implemented and further highlight the successes, experiences, and challenges related to the different activities included in the Plan, reflecting any changes in the circumstances in the Country, and providing other relevant information. The report should also include information on and justification for any changes vis-à-vis the previously submitted Tranche Implementation Plan(s), such as delays, use of flexibility for the reallocation of funds during implementation of a tranche as provided for in paragraph 7 of this Agreement, or other changes;
An independent verification report on the Plan’s results and the consumption of Annex F substances, as per subparagraph 5(b) of the Agreement. If not decided otherwise by the Executive Committee, such a verification of consumption data must be provided with each tranche request, covering all relevant years for which a verification report has not yet been acknowledged by the Committee, as specified in subparagraph 5(a) of the Agreement;
A written description of the activities to be undertaken during the period covered by the requested tranche including quantitative information, highlighting implementation milestones, the time of completion and the interdependence of the activities, and taking into account experiences made and progress achieved in the implementation of earlier tranches; the data in the Plan will be provided by calendar year. The description should include a reference to the overall Plan and progress achieved, as well as any possible changes to the overall Plan that are foreseen. The description should also specify and explain in detail such changes to the overall Plan. This description of future activities can be submitted as a part of the same document as the narrative report under subparagraph 1(a) above; and
An Executive Summary of about five paragraphs, summarizing the information contained in subparagraphs 1(a) to 1(c) above.
APPENDIX 5-A: MONITORING INSTITUTIONS AND ROLES
1. The Secretariat of Natural Resources and Environment (SERNA), through the National Ozone Unit (NOU), will be the national coordinating entity responsible for the effective implementation and oversight of the Plan. The NOU will lead the coordination with national authorities, regulatory and enforcement bodies, key sectoral stakeholders (including industry and servicing sector representatives), and the Lead IA and the Cooperating IA. Its responsibilities will include ensuring that project implementation remains aligned with national strategies and obligations under the Kigali Amendment and the Agreement with the Executive Committee. The NOU will submit detailed annual progress reports to the Lead IA, covering technical, regulatory, and institutional achievements, challenges encountered, lessons learned, and proposed corrective actions.
1. To strengthen technical oversight, the NOU will work closely with national and international consultants specialized in project monitoring and implementation. This technical support will assist the NOU in planning, supervising, and validating activities related to HFC phase-down, including:
Administration and enforcement of the national HFC licensing and quota system;
Monitoring and evaluation of the implementation of individual project components;
Collection and analysis of consumption data for reporting and policy planning; and
Coordination with related climate and energy-efficiency initiatives to ensure policy coherence and maximize synergies.
1. In collaboration with the Lead IA and Cooperating IA, the NOU will ensure that implementation follows the approved work plan and adheres to reporting and accountability requirements set by the Multilateral Fund.
1. Furthermore, the NOU will proactively engage with relevant institutions such as the national customs administration, technical regulatory bodies, environmental enforcement agencies, national training institutes, and private sector actors. This engagement is critical to ensure compliance with national regulations, institutionalize best practices, and build long-term technical and administrative capacity for the continued reduction of HFC consumption.
1. The monitoring of HFC consumption levels and verification of sustained reductions will be carried out jointly by SERNA, through the NOU, and the national customs authority. SERNA will be responsible for tracking aggregate national consumption, overseeing licensing and quota compliance, and reporting to the Multilateral Fund. The customs authority will monitor and report on imports and exports of HFCs and related equipment, enforce border controls in accordance with the national licensing system, and ensure that illegal or non-compliant trade is identified and addressed. This dual mechanism will help ensure the accuracy and integrity of consumption data and the long-term enforceability of phase-down measures.
1. If deemed necessary, an independent verification of project implementation—including progress on policy, capacity-building, and sustained reductions in consumption—will be conducted by a third-party consultant designated by the Lead IA, in accordance with the guidelines and reporting frameworks of the Multilateral Fund.
APPENDIX 6-A: ROLE OF THE LEAD IMPLEMENTING AGENCY
1. The Lead IA will be responsible for a range of activities, including at least the following:
Ensuring performance and financial verification in accordance with this Agreement and with its specific internal procedures and requirements as set out in the Country’s Plan;
Assisting the Country in the preparation of the Tranche Implementation Reports and Plans as per Appendix 4‑A;
Providing independent verification to the Executive Committee that the Targets have been met and associated tranche activities have been completed as indicated in the Tranche Implementation Plan, consistent with Appendix 4-A;
Ensuring that the experiences and progress are reflected in the updates to the overall Plan and in the future Tranche Implementation Plans, consistent with subparagraph 1(c) of Appendix 4‑A;
Fulfilling the reporting requirements of the Tranche Implementation Reports and Plans and of the overall Plan as specified in Appendix 4-A for submission to the Executive Committee, including the activities implemented by the Cooperating IA;
In the event that the last funding tranche is requested one or more years prior to the last year for which a consumption target had been established, annual Tranche Implementation Reports and, where applicable, verification reports on the current stage of the Plan should be submitted until all activities foreseen had been completed and HFC consumption targets had been met;
Ensuring that appropriate independent technical experts carry out the technical reviews;
Carrying out the required supervision missions;
Ensuring the presence of an operating mechanism to allow for an effective and transparent implementation of the Tranche Implementation Plan and accurate data reporting;
Coordinating the activities of the Cooperating IA and ensuring the appropriate sequence of activities;
In case of reductions in funding for failure to comply in accordance with paragraph 11 of the Agreement, to determine, in consultation with the Country and the Cooperating IA, the allocation of the reductions to the different budget items and to the funding of the Lead IA and each Cooperating IA;
Ensuring that disbursements made to the Country are based on the use of the indicators;
Providing assistance with the policy, management and technical support when required;
Reaching consensus with the Cooperating IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan; and
Timely releasing funds to the Country/participating enterprises for completing the activities related to the project.
After consultation with the Country and taking into account any views expressed, the Lead IA will select and mandate an independent entity to carry out the verification of the Plan’s results and of the consumption of Annex F substances mentioned in Appendix 1-A, as per subparagraph 5(b) of the Agreement and subparagraph 1(b) of Appendix 4-A.
APPENDIX 6-B: ROLE OF THE COOPERATING IMPLEMENTING AGENCIES
1. The Cooperating IA will be responsible for a range of activities. These activities are specified in the Plan, including at least the following:
Providing assistance for policy development when required;
Assisting the Country in the implementation and assessment of the activities funded by the Cooperating IA, and referring to the Lead IA to ensure a coordinated sequence of activities;
Providing reports to the Lead IA on these activities, for inclusion in the consolidated reports as per Appendix 4-A; and
Reaching consensus with the Lead IA on any planning, coordination and reporting arrangements required to facilitate the implementation of the Plan.
APPENDIX 7-A: REDUCTIONS IN FUNDING FOR FAILURE TO COMPLY WITH THE TARGETS IN THE AGREEMENT
1. In accordance with paragraph 11 of the Agreement, the amount of funding provided may be reduced by US $5.28 per CO2-eq tonne of consumption beyond the level defined in row 1.2 of Appendix 2‑A for each year in which the Target specified in row 1.2 of Appendix 2-A has not been met, on the understanding that the maximum funding reduction would not exceed the funding level of the tranche being requested. Additional measures might be considered in cases where non-compliance extends for two consecutive years. Where the Country has failed to comply with the Agreement due to illegal trade, the reduction in funding would not be applied if the illegally traded controlled substances are seized and subsequently, confiscated, destroyed, exported, or returned to the country of origin.
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附件十五
根据含氢氯氟烃淘汰管理计划第三阶段要求拟纳入亚美尼亚政府
与多边基金执行委员会更新版协议的文本

（为便于参考相关更改已用粗体字标出）
1. 这份更新后的协议取代了在第九十六次执行委员会会议上达成的亚美尼亚政府与执行委员会之间的协议。
附录2-A：目标与供资

	行
	详情
	2023年**
	2025年
	2026年
	2027年
	2028-2029年
	2030年
	共计

	1.1
	蒙特利尔议定书附件C第一类物质削减时间表（ODP吨）
	不适用
	2.28
	2.28
	2.28
	2.28
	0
	不适用

	1.2
	附件C第一类物质的最大允许总消费量（ODP吨）
	不适用
	2.28
	2.28
	2.28
	2.28
	0
	不适用

	2.1
	牵头执行机构（工发组织）商定的供资额（美元）
	0
	237,500
	0
	289,000
	0
	58,500
	585,000

	2.2
	牵头执行机构支助费用（美元）
	0
	16,625
	0
	20,230
	0
	4,095
	40,950

	2.3
	合作执行机构（环境规划署）商定的供资额（美元）
	100,000
	0
	0
	0 
	0
	0
	100,000

	2.4
	合作执行机构支助费用（美元）
	13,000
	0
	0
	0
	0
	0
	13,000

	3.1
	商定供资总额（美元）
	100,000
	237,500
	0
	289,000
	0
	58,500
	685,000

	3.2
	商定费用总额（美元）
	13,000
	16,625
	0
	20,230
	0
	4,095
	53,950

	3.3
	商定费用总额（美元）
	113,000
	254,125
	0
	309,230
	0
	62,595
	738,950

	4.1.1
	根据本协议将实现的HCFC-22淘汰总量（ODP吨）
	2.34

	4.1.2
	根据已批准的项目将实现的HCFC-22淘汰量（ODP吨）
	4.66

	4.1.3
	HCFC-22剩余符合供资条件消费量（ODP吨）
	0

	4.2.1
	根据本协议将实现的进口预混多元醇中HCFC-141b淘汰总量（ODP吨）
	0

	4.2.2
	根据已批准的项目将实现的进口预混多元醇中的HCFC-141b淘汰量（ODP 吨）
	0.83

	4.2.3
	进口预混多元醇中所含HCFC-141b的剩余符合供资条件消费量（ODP吨）
	0


*根据第二阶段协议，第二阶段完成日期：2021年12月31日。
**根据第89/6(b)号决定，第九十三次会议批准开展的为引入全球变暖潜能值较低或为零的含氢氯氟烃替代品，并维持制冷维修业的能效的额外活动。
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