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UPDATE ON THE STATUS OF IMPLEMENTATION OF THE 2024-2026 CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND

Introduction

At its 93rd meeting, the Executive Committee endorsed the 2024–2026 consolidated business plan of the Multilateral Fund. In response to decision 93/28, the Secretariat adjusted the consolidated 2024–2026 business plan, as shown in table 1.
Table 1. Resource allocation of the adjusted 2024–2026 consolidated business plan of the Multilateral Fund (US $)*
	Description 
	2024
	2025
	2026
	Total 

	HCFC activities
	 
	 
	 
	 

	Approved HCFC phase-out management plans (HPMPs)
	48,499,466
	50,384,491
	50,158,180
	149,042,137

	Approved HCFC production phase-out management plans (HPPMPs)
	23,232,000
	0
	0
	23,232,000

	HPMP stage II – preparation 
	134,400
	44,300
	0
	178,700

	HPMP stage II
	4,970,041
	6,870,087
	10,870,876
	22,711,004

	HPMP stage III – preparation 
	522,900
	65,400
	0
	588,300

	HPMP stage III
	15,849,471
	10,765,760
	23,015,282
	49,630,513

	HPMP stage IV – preparation 
	70,000
	0
	0
	70,000

	HPMP stage IV
	0
	0
	3,691,000
	3,691,000

	HPMP verification**
	588,600
	588,600
	588,600
	1,765,800

	HPMP – energy efficiency
	3,726,111
	3,305,040
	111,200
	7,142,351

	HCFC activities subtotal
	97,592,989
	72,023,678
	88,435,138
	258,051,805

	HFC activities
	 
	 
	 
	 

	Approved Kigali HFC implementation plans (KIPs)
	0
	10,127,716
	6,590,654
	16,718,370

	Approved HFC-23 emission control 
	414,238
	626,900
	572,433
	1,613,571

	HFC – enabling activities
	53,500
	160,500
	0
	214,000

	HFC – technical assistance
	678,000
	0
	0
	678,000

	HFC-23 
	8,000,000
	0
	0
	8,000,000

	KIP stage I
	11,458,349
	27,565,521
	6,378,667
	45,402,537

	KIP stage I – investment preparation
	32,100
	0
	0
	32,100

	KIP stage I – investment 
	3,712,616
	0
	0
	3,712,616

	KIP stage I – preparation
	2,891,415
	1,167,771
	211,280
	4,270,466

	HFC activities subtotal
	27,240,219
	39,648,408
	13,753,034
	80,641,660

	Other activities
	 
	 
	 
	 

	Pilot project for energy efficiency – demonstration 
	1,870,000
	1,000,000
	0
	2,870,000

	Pilot project for energy efficiency – investment 
	4,789,988
	248,600
	0
	5,038,588

	Pilot project for energy efficiency – preparation 
	85,600
	0
	0
	85,600

	ODS banks preparation
	1,232,150
	310,300
	0
	1,542,450

	HFC activities subtotal
	7,977,738
	1,558,900
	0
	9,536,638

	Standard activities
	 
	 
	 
	 

	Institutional strengthening (IS)
	22,071,008
	1,830,362
	21,294,756
	45,196,125

	Compliance Assistance Programme (CAP)
	11,765,667
	12,113,777
	12,310,330
	36,189,774

	Core unit
	6,611,529
	6,653,609
	6,095,985
	19,361,122

	Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart
	7,202,023
	6,816,624
	6,964,604
	20,983,251

	Treasurer
	500,000
	500,000
	500,000
	1,500,000

	Standard activities subtotal
	48,150,226
	27,914,372
	47,165,675
	123,230,273

	Grand total
	180,961,172
	141,145,358
	149,353,846
	471,460,376

	By agency
	 
	 
	 
	 

	Australia
	0
	615,610
	0
	615,610

	Austria
	783,667
	0
	0
	783,667

	France
	671,075
	0
	0
	671,075

	Germany
	7,500,449
	2,148,339
	5,834,901
	15,483,689

	UNDP
	44,305,827
	38,729,891
	40,741,817
	123,777,535

	UNEP
	47,977,295
	27,975,506
	35,097,810
	111,050,611

	UNIDO
	40,363,268
	49,551,567
	30,746,018
	120,660,853

	World Bank
	31,068,968
	14,219,221
	28,880,096
	74,168,285

	HPMP verification**
	588,600
	588,600
	588,600
	1,765,800

	Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart
	7,202,023
	6,816,624
	6,964,604
	20,983,251

	Treasurer
	500,000
	500,000
	500,000
	1,500,000


* Including agency support costs where applicable.
** Funding for the preparation of HPMP verification reports for low-volume-consuming countries is approved by the Executive Committee on an annual basis.

Status of implementation of the 2024 business plan

The total business plan values for 2024 amounts to US $180,961,172. Of this amount, US $61,332,446 has been approved at the 94th meeting. In addition, activities amounting to US $124,178,563 would be considered at the 95th meeting; if funding for all project proposals submitted as requested are approved, the 2024 business plan budget would be exceeded by US $4,549,837, as shown in table 2. 
Table 2. 2024 consolidated business plan, approvals at the 94th meeting, project recommended to the 95th meeting, and balance (US $)*
	Budget items
	Total value in business plan
	Approvals at the 94th meeting
	Activities recommended to the 95th meeting
	Balance (above)/below

	Bilateral agencies
	8,955,191
	7,722,115
	4,501,291
	(3,268,215)

	UNDP
	44,305,827
	16,932,440
	22,592,547
	4,780,840

	UNEP
	47,977,295
	12,910,251
	34,033,332
	1,033,712

	UNIDO
	40,363,268
	23,196,140
	27,767,338
	(10,600,210)

	World Bank
	31,068,968
	0
	27,582,032
	3,486,936

	HPMP verification
	588,600
	571,500
	0
	17,100

	Subtotal (agencies)
	173,259,149
	61,332,446
	116,476,540
	(4,549,837)

	Secretariat/Executive Committee/Monitoring and Evaluation (excluding Canadian counterpart)
	7,202,023
	0
	7,202,023
	0

	Treasurer
	500,000
	0
	500,000
	0

	Subtotal (standard costs)
	7,702,023
	0
	7,702,023
	0

	Total
	180,961,172
	61,332,446
	124,178,563
	(4,549,837)


* Including core unit costs.

The value of project proposals recommended to the 95th meeting of US $116,476,540 is US $25,156,871 above its value in the 2024 business plan and includes US $15,899,209 associated with project proposals not included in the 2024 business plan.[footnoteRef:2]  [2:  Stage I of the HPMP for Bhutan (UNDP and UNEP); stage II of the HPMPs for the Cook Islands (UNEP), Kiribati (UNEP), the Marshall Islands (UNEP), Micronesia (Federated States of) (UNEP), Nauru (UNEP), Niue (UNEP), Palau (UNEP), the Pacific Island countries (PIC) region (Australia and UNEP), Samoa (UNEP), Solomon Islands (UNEP), Tonga (UNEP), Tuvalu (UNEP), and Vanuatu (UNEP); stage III of the HPMPs for Chile (UNDP) and Mexico (Germany); one project preparation for stage II of the HPMP for Dominica (UNIDO); three project preparation activities for stage III of the HPMPs for Angola (UNDP) and Bangladesh (UNDP and UNEP); one project preparation for stage IV of the HPMP for Nigeria (Germany); one KIP investment project for Argentina (UNIDO); one project preparation for a KIP investment project for Indonesia (World Bank); four project preparation for stage I of KIPs for the Bahamas (UNEP and UNIDO), Barbados (UNEP) and China (UNDP); stage I of KIPs for Benin (UNEP and UNIDO), Chad (UNEP and UNIDO), Guatemala (UNEP and UNIDO), Mauritius (Germany), PIC region (Australia and UNEP), Senegal (UNEP and UNIDO), and Uruguay (UNDP and UNIDO); 16 energy efficiency projects under decision 89/6 for Bhutan (UNEP), the Cook Islands (UNEP), Kiribati (UNEP), Marshall Islands (UNEP), Micronesia (Federated States of) (UNEP), Nauru (UNEP), Niue (UNEP), Palau (UNEP), PIC region (Australia and UNEP), Saint Vincent and the Grenadines (UNEP), Samoa (UNEP), Solomon Islands (UNEP), Tonga (UNEP), Tuvalu (UNEP), and Vanuatu (UNEP); and 28 project preparation activities for national inventories of banks of waste‑controlled substances under decision 91/66 for the Bahamas (UNEP), Bangladesh (UNIDO), Bhutan (UNEP), Brunei Darussalam (UNEP), the Congo (UNIDO), the Cook Islands (UNEP), Eswatini (UNEP), Fiji (UNEP), the Gambia (UNEP), Indonesia (UNDP), Kiribati (UNEP), Madagascar (UNIDO), Marshall Islands (UNEP), Micronesia (Federated States of) (UNEP), Mongolia (UNEP), Nauru (UNEP), Nepal (UNEP), Niue (UNEP), Palau (UNEP), Samoa (UNEP), Senegal (Germany), Solomon Islands (UNEP), Thailand (World Bank), Timor‑Leste (UNEP), Tonga (UNEP), Tuvalu (UNEP), Uganda (UNEP), and Vanuatu (UNEP).] 

The value of HFC-related activities recommended to the 95th meeting is US $19,833,551 of which US $8,720,978 is associated with project proposals not included in the 2024 business plan. Annex I to the present document lists HFC-related projects submitted by bilateral and implementing agencies to the 95th meeting. 
The value of projects recommended under the funding window for pilot projects for energy efficiency pursuant to decision 91/65 is US $4,642,176. Taking into account approvals at the 92nd, 93rd and 94th meetings of US $5,976,489, and the values recommended to the 95th meeting, the remaining funding available under this funding window is US $9,381,335. Annex II to the present document lists the pilot projects submitted by bilateral and implementing agencies to the 95th meeting pursuant to decision 91/65. 
The value of projects recommended under the funding window for energy efficiency pursuant to decision 94/60 is US $1,170,247 and the remaining funding available under this funding window is US $98,829,753. Annex III to the present document lists the projects submitted by bilateral and implementing agencies to the 95th meeting pursuant to decision 94/60. 
The value of projects recommended under the funding window for the preparation of national inventories of banks of waste-controlled substances pursuant to decision 91/66 is US $2,638,600 including US $2,446,500 that is not included in the 2024 business plan. Annex IV to the present document lists the project preparation activities submitted by bilateral and implementing agencies to the 95th meeting pursuant to decision 91/66.
Forward commitments
The total amount for existing forward commitments for multi-year agreements (MYAs) for the period 2024 to 2031 is US $336.66 million, assuming that the funding requests of MYAs submitted to the 95th meeting will be approved in principle, as shown in table 3.
Table 3. Forward commitments (2024–2031) (US $000)
	Description
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	2031
	Total

	Approved in principle
	99,643
	50,780
	67,400
	22,538
	20,214
	8,176
	15,120
	57
	283,929

	Submitted to the 95th meeting
	22,866
	0
	0
	24,773
	139
	2,367
	2,583
	0
	52,729

	Total 
	122,510
	50,780
	67,400
	47,312
	20,353
	10,543
	17,703
	57
	336,657



Recommendation 

The Executive Committee may wish to note:
The update on the status of implementation of the 2024-2026 consolidated business plan of the Multilateral Fund contained in document UNEP/OzL.Pro/ExCom/95/23; and
That the total value of activities as recommended to the 95th meeting amounts to US $116,476,540 (including US $19,833,551 for HFC‑related activities; US $4,642,176 for pilot projects for energy efficiency pursuant to decision 91/65; US $1,170,247 for energy efficiency projects pursuant to decision 94/60; and US $2,638,600 for the preparation of national inventories of banks of waste-controlled substances pursuant to decision 91/66), of which US $15,899,209 is associated with project proposals not included in the 2024 business plan.
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HFC-RELATED ACTIVITIES SUBMITTED TO THE 95TH MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Argentina
	UNIDO
	INV
	KIP
	Investment project to phase out R‑410A in domestic air conditioner manufacturing sector in Argentina
	5,697,593
	398,832

	Bahamas (the)
	UNEP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	91,000
	11,830

	Bahamas (the)
	UNIDO
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	39,000
	2,730

	Barbados
	UNEP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	130,000
	16,900

	Benin
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	117,500
	15,275

	Benin
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	60,000
	7,800

	Chad
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	141,000
	18,330

	Chad
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	75,000
	9,750

	China
	UNDP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	250,000
	17,500

	Colombia
	Germany
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	258,825
	33,647

	Colombia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	1,066,225
	74,636

	Colombia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (local installation and assembly subsector)
	341,100
	23,877

	Colombia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (manufacturing sector)
	1,023,513
	71,646

	Colombia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	124,148
	8,690

	Cook Islands (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	23,250
	3,023

	Costa Rica
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first trance)
	356,880
	45,029

	Costa Rica
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first trance) (PMU)
	14,088
	1,778

	Guatemala
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	10,000
	1,300

	Guatemala
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	251,019
	17,571

	Indonesia
	IBRD
	PRP
	KIP
	Preparation of a KIP investment project in the domestic and stand-alone commercial refrigerator manufacturing sector
	80,000
	5,600

	Kiribati
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	15,000
	1,950

	Lesotho
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	64,000
	8,320

	Lesotho
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	18,000
	2,340

	Marshall Islands (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	11,750
	1,527

	Mauritius
	Germany
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	103,000
	13,390

	Micronesia (Federated States of)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	63,500
	8,255

	Morocco
	UNIDO
	INV
	KIP
	Conversion of two production lines in one enterprise (MANAR) manufacturing domestic refrigeration equipment from HFC-134a to R-600a
	352,985
	24,709

	Nauru
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	10,500
	1,365

	Nigeria
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	1,902,050
	133,144

	Nigeria
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	130,800
	17,004

	Nigeria
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	705,510
	49,386

	Niue
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	9,250
	1,202

	Oman
	UNEP
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	160,000
	20,800

	Oman
	UNIDO
	PRP
	KIP
	Preparation of a Kigali HFC implementation plan (stage I)
	30,000
	2,100

	Palau
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	57,500
	7,475

	Rwanda
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	48,400
	6,292

	Rwanda
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	27,500
	3,575

	Samoa
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	66,000
	8,580

	Senegal
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	168,000
	21,840

	Senegal
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	127,500
	8,925

	Solomon Islands
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	74,125
	9,637

	Togo
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	117,500
	15,275

	Togo
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	70,000
	9,100

	Tonga
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	60,750
	7,898

	Türkiye
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	845,445
	59,181

	Türkiye
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	1,943,985
	136,079

	Tuvalu
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	12,250
	1,592

	Uruguay
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	126,927
	16,500

	Uruguay
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	49,860
	6,482

	Vanuatu
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	31,625
	4,112

	Zimbabwe
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	90,000
	11,700

	Zimbabwe
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	151,500
	19,695

	Region: ASP
	Australia
	INV
	KIP
	Regional Kigali HFC implementation plan for Pacific Island Countries (stage I, first tranche)
	295,000
	38,350

	Region: ASP
	UNEP
	TAS
	KIP
	Regional Kigali HFC implementation plan for Pacific Island Countries (stage I, first tranche)
	247,500
	32,174
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Annex II

PILOT PROJECTS FOR ENERGY EFFICIENCY (DECISION 91/65) 
SUBMITTED TO THE 95TH MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	China
	UNDP
	INV
	EEF
	Pilot project to enhance the energy efficiency of cooling technologies in data centres through the demonstration of single-phase immersion cooling system in a data centre (decision 91/65)
	1,790,800
	125,356

	Colombia
	UNDP
	TAS
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	506,319
	35,442

	Costa Rica
	UNDP
	INV
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	260,000
	18,200

	Honduras
	UNIDO
	INV
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	278,068
	19,465

	Malaysia
	IBRD
	INV
	EEF
	Pilot project to enhance the energy efficiency of stand-alone commercial refrigeration equipment in Malaysia in the context of the HFC phase-down (investment and non-investment activities) (decisions 91/65)
	500,000
	35,000

	Montenegro
	UNIDO
	TAS
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	120,000
	10,800

	Peru
	UNEP
	TAS
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65)
	115,000
	14,950

	Uganda
	United Kingdom of Great Britain and Northern Ireland
	INV
	EEF
	Demonstration of energy-efficient ultra‑low GWP technology in a supermarket (decision 91/65)
	435,200
	56,576

	Uruguay
	UNDP
	INV
	EEF
	Pilot project to maintain and/or enhance the energy efficiency of technologies in the commercial refrigeration and residential AC sectors in the context of HFC phase-down (non-investment activities) (decision 91/65)
	300,000
	21,000
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Annex III

PROJECTS FOR ENERGY EFFICIENCY PURSUANT TO DECISION 94/60
SUBMITTED TO THE 95TH MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Egypt
	UNIDO
	PRP
	EEF
	Preparation of a pilot project on energy efficiency (decision 94/60)
	210,000
	14,700

	Malaysia
	IBRD
	INV
	EEF
	Pilot project to enhance the energy efficiency of stand-alone commercial refrigeration equipment in Malaysia in the context of the HFC phase-down (investment and non‑investment activities) (decisions 94/60)
	415,689
	29,098

	Nigeria
	UNIDO
	PRP
	EEF
	Preparation of a pilot project on energy efficiency (decision 94/60)
	78,000
	5,460

	Thailand
	IBRD
	PRP
	EEF
	Preparation of a project for enhancing energy efficiency in manufacturing of light commercial air-conditioning (AC) systems in the context of HFC phase-down (decision 94/60)
	150,000
	10,500

	Tunisia
	UNIDO
	PRP
	EEF
	Preparation of a pilot project on energy efficiency (decision 94/60)
	20,000
	1,400

	Türkiye
	UNIDO
	PRP
	EEF
	Preparation of a pilot project on energy efficiency (decision 94/60)
	220,000
	15,400
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PROJECT PREPARATION FOR NATIONAL INVENTORIES OF BANKS 
OF WASTE‑CONTROLLED SUBSTANCES (DECISION 91/66) 
SUBMITTED TO THE 95TH MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Bahamas (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Bangladesh
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Bhutan
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Brunei Darussalam
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Congo (the)
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Cook Islands (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Eswatini
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Fiji
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Gambia (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Indonesia
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Kiribati
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Madagascar
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Maldives
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Marshall Islands (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Micronesia (Federated States of)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Mongolia
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Nauru
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Nepal
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Niue
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Palau
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Samoa
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Senegal
	Germany
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Solomon Islands
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Sri Lanka
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Thailand
	IBRD
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Timor-Leste
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Tonga
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Tuvalu
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Uganda
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100

	Vanuatu
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	9,100
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