| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/95/23 25 November 2024 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-fifth Meeting

Montreal, 4-8 December 2024

Item 8(a) of the provisional agenda

UPDATE ON THE STATUS OF IMPLEMENTATION OF THE 2024-2026 CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND

- Introduction

# At its 93rd meeting, the Executive Committee endorsed the 2024–2026 consolidated business plan of the Multilateral Fund. In response to decision 93/28, the Secretariat adjusted the consolidated 2024–2026 business plan, as shown in table 1.

Table 1. Resource allocation of the adjusted 2024–2026 consolidated business plan of the Multilateral Fund (US $)*

| Description | 2024 | 2025 | 2026 | Total |
| --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 48,499,466 | 50,384,491 | 50,158,180 | 149,042,137 |
| Approved HCFC production phase-out management plans (HPPMPs) | 23,232,000 | 0 | 0 | 23,232,000 |
| HPMP stage II – preparation | 134,400 | 44,300 | 0 | 178,700 |
| HPMP stage II | 4,970,041 | 6,870,087 | 10,870,876 | 22,711,004 |
| HPMP stage III – preparation | 522,900 | 65,400 | 0 | 588,300 |
| HPMP stage III | 15,849,471 | 10,765,760 | 23,015,282 | 49,630,513 |
| HPMP stage IV – preparation | 70,000 | 0 | 0 | 70,000 |
| HPMP stage IV | 0 | 0 | 3,691,000 | 3,691,000 |
| HPMP verification** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| HPMP – energy efficiency | 3,726,111 | 3,305,040 | 111,200 | 7,142,351 |
| HCFC activities subtotal | 97,592,989 | 72,023,678 | 88,435,138 | 258,051,805 |
| HFC activities |  |  |  |  |
| Approved Kigali HFC implementation plans (KIPs) | 0 | 10,127,716 | 6,590,654 | 16,718,370 |
| Approved HFC-23 emission control | 414,238 | 626,900 | 572,433 | 1,613,571 |
| HFC – enabling activities | 53,500 | 160,500 | 0 | 214,000 |
| HFC – technical assistance | 678,000 | 0 | 0 | 678,000 |
| HFC-23 | 8,000,000 | 0 | 0 | 8,000,000 |
| KIP stage I | 11,458,349 | 27,565,521 | 6,378,667 | 45,402,537 |
| KIP stage I – investment preparation | 32,100 | 0 | 0 | 32,100 |
| KIP stage I – investment | 3,712,616 | 0 | 0 | 3,712,616 |
| KIP stage I – preparation | 2,891,415 | 1,167,771 | 211,280 | 4,270,466 |
| HFC activities subtotal | 27,240,219 | 39,648,408 | 13,753,034 | 80,641,660 |
| Other activities |  |  |  |  |
| Pilot project for energy efficiency – demonstration | 1,870,000 | 1,000,000 | 0 | 2,870,000 |
| Pilot project for energy efficiency – investment | 4,789,988 | 248,600 | 0 | 5,038,588 |
| Pilot project for energy efficiency – preparation | 85,600 | 0 | 0 | 85,600 |
| ODS banks preparation | 1,232,150 | 310,300 | 0 | 1,542,450 |
| HFC activities subtotal | 7,977,738 | 1,558,900 | 0 | 9,536,638 |
| Standard activities |  |  |  |  |
| Institutional strengthening (IS) | 22,071,008 | 1,830,362 | 21,294,756 | 45,196,125 |
| Compliance Assistance Programme (CAP) | 11,765,667 | 12,113,777 | 12,310,330 | 36,189,774 |
| Core unit | 6,611,529 | 6,653,609 | 6,095,985 | 19,361,122 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 7,202,023 | 6,816,624 | 6,964,604 | 20,983,251 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |
| Standard activities subtotal | 48,150,226 | 27,914,372 | 47,165,675 | 123,230,273 |
| Grand total | 180,961,172 | 141,145,358 | 149,353,846 | 471,460,376 |
| By agency |  |  |  |  |
| Australia | 0 | 615,610 | 0 | 615,610 |
| Austria | 783,667 | 0 | 0 | 783,667 |
| France | 671,075 | 0 | 0 | 671,075 |
| Germany | 7,500,449 | 2,148,339 | 5,834,901 | 15,483,689 |
| UNDP | 44,305,827 | 38,729,891 | 40,741,817 | 123,777,535 |
| UNEP | 47,977,295 | 27,975,506 | 35,097,810 | 111,050,611 |
| UNIDO | 40,363,268 | 49,551,567 | 30,746,018 | 120,660,853 |
| World Bank | 31,068,968 | 14,219,221 | 28,880,096 | 74,168,285 |
| HPMP verification** | 588,600 | 588,600 | 588,600 | 1,765,800 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 7,202,023 | 6,816,624 | 6,964,604 | 20,983,251 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |

* Including agency support costs where applicable.

** Funding for the preparation of HPMP verification reports for low-volume-consuming countries is approved by the Executive Committee on an annual basis.

Status of implementation of the 2024 business plan

# The total business plan values for 2024 amounts to US $180,961,172. Of this amount, US $61,332,446 has been approved at the 94th meeting. In addition, activities amounting to US $124,178,563 would be considered at the 95th meeting; if funding for all project proposals submitted as requested are approved, the 2024 business plan budget would be exceeded by US $4,549,837, as shown in table 2.

Table 2. 2024 consolidated business plan, approvals at the 94th meeting, project recommended to the 95th meeting, and balance (US $)*

| Budget items | Total value in business plan | Approvals at the 94th meeting | Activities recommended to the 95th meeting | Balance (above)/below |
| --- | --- | --- | --- | --- |
| Bilateral agencies | 8,955,191 | 7,722,115 | 4,501,291 | (3,268,215) |
| UNDP | 44,305,827 | 16,932,440 | 22,592,547 | 4,780,840 |
| UNEP | 47,977,295 | 12,910,251 | 34,033,332 | 1,033,712 |
| UNIDO | 40,363,268 | 23,196,140 | 27,767,338 | (10,600,210) |
| World Bank | 31,068,968 | 0 | 27,582,032 | 3,486,936 |
| HPMP verification | 588,600 | 571,500 | 0 | 17,100 |
| Subtotal (agencies) | 173,259,149 | 61,332,446 | 116,476,540 | (4,549,837) |
| Secretariat/Executive Committee/Monitoring and Evaluation (excluding Canadian counterpart) | 7,202,023 | 0 | 7,202,023 | 0 |
| Treasurer | 500,000 | 0 | 500,000 | 0 |
| Subtotal (standard costs) | 7,702,023 | 0 | 7,702,023 | 0 |
| Total | 180,961,172 | 61,332,446 | 124,178,563 | (4,549,837) |

* Including core unit costs.

# The value of project proposals recommended to the 95th meeting of US $116,476,540 is US $25,156,871 above its value in the 2024 business plan and includes US $15,899,209 associated with project proposals not included in the 2024 business plan.

# The value of HFC-related activities recommended to the 95th meeting is US $19,833,551 of which US $8,720,978 is associated with project proposals not included in the 2024 business plan. Annex I to the present document lists HFC-related projects submitted by bilateral and implementing agencies to the 95th meeting.

# The value of projects recommended under the funding window for pilot projects for energy efficiency pursuant to decision 91/65 is US $4,642,176. Taking into account approvals at the 92nd, 93rd and 94th meetings of US $5,976,489, and the values recommended to the 95th meeting, the remaining funding available under this funding window is US $9,381,335. Annex II to the present document lists the pilot projects submitted by bilateral and implementing agencies to the 95th meeting pursuant to decision 91/65.

# The value of projects recommended under the funding window for energy efficiency pursuant to decision 94/60 is US $1,170,247 and the remaining funding available under this funding window is US $98,829,753. Annex III to the present document lists the projects submitted by bilateral and implementing agencies to the 95th meeting pursuant to decision 94/60.

# The value of projects recommended under the funding window for the preparation of national inventories of banks of waste-controlled substances pursuant to decision 91/66 is US $2,638,600 including US $2,446,500 that is not included in the 2024 business plan. Annex IV to the present document lists the project preparation activities submitted by bilateral and implementing agencies to the 95th meeting pursuant to decision 91/66.

# Forward commitments

# The total amount for existing forward commitments for multi-year agreements (MYAs) for the period 2024 to 2031 is US $336.66 million, assuming that the funding requests of MYAs submitted to the 95th meeting will be approved in principle, as shown in table 3.

Table 3. Forward commitments (2024–2031) (US $000)

| Description | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approved in principle | 99,643 | 50,780 | 67,400 | 22,538 | 20,214 | 8,176 | 15,120 | 57 | 283,929 |
| Submitted to the 95th meeting | 22,866 | 0 | 0 | 24,773 | 139 | 2,367 | 2,583 | 0 | 52,729 |
| Total | 122,510 | 50,780 | 67,400 | 47,312 | 20,353 | 10,543 | 17,703 | 57 | 336,657 |

# Recommendation

# The Executive Committee may wish to note:

## The update on the status of implementation of the 2024-2026 consolidated business plan of the Multilateral Fund contained in document UNEP/OzL.Pro/ExCom/95/23; and

## That the total value of activities as recommended to the 95th meeting amounts to US $116,476,540 (including US $19,833,551 for HFC-related activities; US $4,642,176 for pilot projects for energy efficiency pursuant to decision 91/65; US $1,170,247 for energy efficiency projects pursuant to decision 94/60; and US $2,638,600 for the preparation of national inventories of banks of waste-controlled substances pursuant to decision 91/66), of which US $15,899,209 is associated with project proposals not included in the 2024 business plan.

Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 95TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Argentina | UNIDO | INV | KIP | Investment project to phase out R-410A in domestic air conditioner manufacturing sector in Argentina | 5,697,593 | 398,832 |
| Bahamas (the) | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 91,000 | 11,830 |
| Bahamas (the) | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 39,000 | 2,730 |
| Barbados | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 130,000 | 16,900 |
| Benin | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 117,500 | 15,275 |
| Benin | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 60,000 | 7,800 |
| Chad | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 141,000 | 18,330 |
| Chad | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 75,000 | 9,750 |
| China | UNDP | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 250,000 | 17,500 |
| Colombia | Germany | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 258,825 | 33,647 |
| Colombia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 1,066,225 | 74,636 |
| Colombia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (local installation and assembly subsector) | 341,100 | 23,877 |
| Colombia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (manufacturing sector) | 1,023,513 | 71,646 |
| Colombia | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) (PMU) | 124,148 | 8,690 |
| Cook Islands (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 23,250 | 3,023 |
| Costa Rica | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first trance) | 356,880 | 45,029 |
| Costa Rica | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first trance) (PMU) | 14,088 | 1,778 |
| Guatemala | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 10,000 | 1,300 |
| Guatemala | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 251,019 | 17,571 |
| Indonesia | IBRD | PRP | KIP | Preparation of a KIP investment project in the domestic and stand-alone commercial refrigerator manufacturing sector | 80,000 | 5,600 |
| Kiribati | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 15,000 | 1,950 |
| Lesotho | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 64,000 | 8,320 |
| Lesotho | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 18,000 | 2,340 |
| Marshall Islands (the) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 11,750 | 1,527 |
| Mauritius | Germany | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 103,000 | 13,390 |
| Micronesia (Federated States of) | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 63,500 | 8,255 |
| Morocco | UNIDO | INV | KIP | Conversion of two production lines in one enterprise (MANAR) manufacturing domestic refrigeration equipment from HFC-134a to R-600a | 352,985 | 24,709 |
| Nauru | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 10,500 | 1,365 |
| Nigeria | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 1,902,050 | 133,144 |
| Nigeria | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 130,800 | 17,004 |
| Nigeria | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 705,510 | 49,386 |
| Niue | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 9,250 | 1,202 |
| Oman | UNEP | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 160,000 | 20,800 |
| Oman | UNIDO | PRP | KIP | Preparation of a Kigali HFC implementation plan (stage I) | 30,000 | 2,100 |
| Palau | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 57,500 | 7,475 |
| Rwanda | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 48,400 | 6,292 |
| Rwanda | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 27,500 | 3,575 |
| Samoa | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 66,000 | 8,580 |
| Senegal | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 168,000 | 21,840 |
| Senegal | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 127,500 | 8,925 |
| Solomon Islands | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 74,125 | 9,637 |
| Togo | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 117,500 | 15,275 |
| Togo | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 70,000 | 9,100 |
| Tonga | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 60,750 | 7,898 |
| Türkiye | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 845,445 | 59,181 |
| Türkiye | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 1,943,985 | 136,079 |
| Tuvalu | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 12,250 | 1,592 |
| Uruguay | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 126,927 | 16,500 |
| Uruguay | UNIDO | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 49,860 | 6,482 |
| Vanuatu | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 31,625 | 4,112 |
| Zimbabwe | UNDP | INV | KIP | Kigali HFC implementation plan (stage I, first tranche) | 90,000 | 11,700 |
| Zimbabwe | UNEP | TAS | KIP | Kigali HFC implementation plan (stage I, first tranche) | 151,500 | 19,695 |
| Region: ASP | Australia | INV | KIP | Regional Kigali HFC implementation plan for Pacific Island Countries (stage I, first tranche) | 295,000 | 38,350 |
| Region: ASP | UNEP | TAS | KIP | Regional Kigali HFC implementation plan for Pacific Island Countries (stage I, first tranche) | 247,500 | 32,174 |

Annex II

Pilot projects for energy efficiency (decision 91/65) 
SUBMITTED TO THE 95TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| China | UNDP | INV | EEF | Pilot project to enhance the energy efficiency of cooling technologies in data centres through the demonstration of single-phase immersion cooling system in a data centre (decision 91/65) | 1,790,800 | 125,356 |
| Colombia | UNDP | TAS | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) | 506,319 | 35,442 |
| Costa Rica | UNDP | INV | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) | 260,000 | 18,200 |
| Honduras | UNIDO | INV | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) | 278,068 | 19,465 |
| Malaysia | IBRD | INV | EEF | Pilot project to enhance the energy efficiency of stand-alone commercial refrigeration equipment in Malaysia in the context of the HFC phase-down (investment and non-investment activities) (decisions 91/65) | 500,000 | 35,000 |
| Montenegro | UNIDO | TAS | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) | 120,000 | 10,800 |
| Peru | UNEP | TAS | EEF | Pilot project to maintain and/or enhance the energy efficiency of replacement technologies and equipment in the context of HFC phase-down (non-investment activities) (decision 91/65) | 115,000 | 14,950 |
| Uganda | United Kingdom of Great Britain and Northern Ireland | INV | EEF | Demonstration of energy-efficient ultra-low GWP technology in a supermarket (decision 91/65) | 435,200 | 56,576 |
| Uruguay | UNDP | INV | EEF | Pilot project to maintain and/or enhance the energy efficiency of technologies in the commercial refrigeration and residential AC sectors in the context of HFC phase-down (non-investment activities) (decision 91/65) | 300,000 | 21,000 |

Annex III

projects for energy efficiency PURSUANT TO decision 94/60
SUBMITTED TO THE 95TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Egypt | UNIDO | PRP | EEF | Preparation of a pilot project on energy efficiency (decision 94/60) | 210,000 | 14,700 |
| Malaysia | IBRD | INV | EEF | Pilot project to enhance the energy efficiency of stand-alone commercial refrigeration equipment in Malaysia in the context of the HFC phase-down (investment and non-investment activities) (decisions 94/60) | 415,689 | 29,098 |
| Nigeria | UNIDO | PRP | EEF | Preparation of a pilot project on energy efficiency (decision 94/60) | 78,000 | 5,460 |
| Thailand | IBRD | PRP | EEF | Preparation of a project for enhancing energy efficiency in manufacturing of light commercial air-conditioning (AC) systems in the context of HFC phase-down (decision 94/60) | 150,000 | 10,500 |
| Tunisia | UNIDO | PRP | EEF | Preparation of a pilot project on energy efficiency (decision 94/60) | 20,000 | 1,400 |
| Türkiye | UNIDO | PRP | EEF | Preparation of a pilot project on energy efficiency (decision 94/60) | 220,000 | 15,400 |

Annex IV

Project preparation for national inventories of banks 
of waste-controlled substances (decision 91/66) 
SUBMITTED TO THE 95TH MEETING

| Country | Agency | Type | Sector | Project title | Amount recommended (US $) | Support costs recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Bahamas (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Bangladesh | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Bhutan | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Brunei Darussalam | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Congo (the) | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Cook Islands (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Eswatini | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Fiji | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Gambia (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Indonesia | UNDP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Kiribati | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Madagascar | UNIDO | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 6,300 |
| Maldives | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Marshall Islands (the) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Micronesia (Federated States of) | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Mongolia | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Nauru | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Nepal | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Niue | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Palau | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Samoa | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Senegal | Germany | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Solomon Islands | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 80,000 | 10,400 |
| Sri Lanka | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 90,000 | 11,700 |
| Thailand | IBRD | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 100,000 | 7,000 |
| Timor-Leste | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Tonga | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Tuvalu | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Uganda | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |
| Vanuatu | UNEP | PRP | DES | Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66) | 70,000 | 9,100 |

UNEP/OzL.Pro/ExCom/95/1

Stage I of the HPMP for Bhutan (UNDP and UNEP); stage II of the HPMPs for the Cook Islands (UNEP), Kiribati (UNEP), the Marshall Islands (UNEP), Micronesia (Federated States of) (UNEP), Nauru (UNEP), Niue (UNEP), Palau (UNEP), the Pacific Island countries (PIC) region (Australia and UNEP), Samoa (UNEP), Solomon Islands (UNEP), Tonga (UNEP), Tuvalu (UNEP), and Vanuatu (UNEP); stage III of the HPMPs for Chile (UNDP) and Mexico (Germany); one project preparation for stage II of the HPMP for Dominica (UNIDO); three project preparation activities for stage III of the HPMPs for Angola (UNDP) and Bangladesh (UNDP and UNEP); one project preparation for stage IV of the HPMP for Nigeria (Germany); one KIP investment project for Argentina (UNIDO); one project preparation for a KIP investment project for Indonesia (World Bank); four project preparation for stage I of KIPs for the Bahamas (UNEP and UNIDO), Barbados (UNEP) and China (UNDP); stage I of KIPs for Benin (UNEP and UNIDO), Chad (UNEP and UNIDO), Guatemala (UNEP and UNIDO), Mauritius (Germany), PIC region (Australia and UNEP), Senegal (UNEP and UNIDO), and Uruguay (UNDP and UNIDO); 16 energy efficiency projects under decision 89/6 for Bhutan (UNEP), the Cook Islands (UNEP), Kiribati (UNEP), Marshall Islands (UNEP), Micronesia (Federated States of) (UNEP), Nauru (UNEP), Niue (UNEP), Palau (UNEP), PIC region (Australia and UNEP), Saint Vincent and the Grenadines (UNEP), Samoa (UNEP), Solomon Islands (UNEP), Tonga (UNEP), Tuvalu (UNEP), and Vanuatu (UNEP); and 28 project preparation activities for national inventories of banks of waste-controlled substances under decision 91/66 for the Bahamas (UNEP), Bangladesh (UNIDO), Bhutan (UNEP), Brunei Darussalam (UNEP), the Congo (UNIDO), the Cook Islands (UNEP), Eswatini (UNEP), Fiji (UNEP), the Gambia (UNEP), Indonesia (UNDP), Kiribati (UNEP), Madagascar (UNIDO), Marshall Islands (UNEP), Micronesia (Federated States of) (UNEP), Mongolia (UNEP), Nauru (UNEP), Nepal (UNEP), Niue (UNEP), Palau (UNEP), Samoa (UNEP), Senegal (Germany), Solomon Islands (UNEP), Thailand (World Bank), Timor-Leste (UNEP), Tonga (UNEP), Tuvalu (UNEP), Uganda (UNEP), and Vanuatu (UNEP).