| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/97/25 4 November 2025 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-seventh Meeting

Montreal, 1-5 December 2025

Item 8(c)(v) of the provisional agenda

THE WORLD BANK Business plan for 2026–2028

# Introduction

# This document presents the World Bank business plan for 2026–2028 and includes the planned activities for the reduction of controlled substances and other activities under the Montreal Protocol during the period 2026–2028. The narrative of the World Bank’s business plan for 2026–2028 is attached to the present document.

# This document consists of the following sections:

- Planned activities during the period 2026–2028

- Secretariat’s comments

- Proposed adjustments by the Secretariat

- Performance indicators

- Recommendation

I.	Planned activities during the period 2026–2028

# Table 1 sets out, by year, the value of activities included in the World Bank’s business plan.

Table 1. Resource allocation in the World Bank business plan for 2026–2028 (US $)* – as submitted

| Description | 2026 | 2027 | 2028 | Total (2026–2028) | Total after 2028 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 4,494,000 | 4,932,894 | 0 | 9,426,894 | 1,479,869 |
| HCFC production phase-out management plan (HPPMP) stage III | 0 | 23,540,000 | 0 | 23,540,000 | 23,540,000 |
| HPMP stage III | 4,280,000 | 0 | 10,700,000 | 14,980,000 | 10,700,000 |
| HCFC activities subtotal | 8,774,000 | 28,472,894 | 10,700,000 | 47,946,894 | 35,719,869 |
| HFC activities |  |  |  |  |  |
| Approved Kigali HFC implementation plans (KIPs) | 3,473,530 | 4,119,331 |  | 7,592,861 | 1,253,464 |
| KIP stage I | 2,140,000 | 4,280,000 | 7,490,000 | 13,910,000 | 11,770,000 |
| HFC activities subtotal | 5,613,530 | 8,399,331 | 7,490,000 | 21,502,861 | 13,023,464 |
| Other activities |  |  |  |  |  |
| Energy efficiency (decision 94/60) | 5,350,000 | 0 | 0 | 5,350,000 | 0 |
| Energy efficiency revolving fund (decision 95/87) | 64,200,000 | 0 | 0 | 64,200,000 | 0 |
| Other activities subtotal | 69,550,000 | 0 | 0 | 69,550,000 | 0 |
| Standard activities |  |  |  |  |  |
| Institutional strengthening (IS) | 0 | 0 | 982,829 | 982,829 | 0 |
| Core unit | 1,947,145 | 1,759,375 | 1,771,691 | 5,478,211 | 0 |
| Standard activities subtotal | 1,947,145 | 1,759,375 | 2,754,520 | 6,461,040 | 0 |
| Total | 85,884,675 | 38,631,600 | 20,944,520 | 145,460,795 | 48,743,333 |

* Including agency support costs where applicable.

# II.	Secretariat’s comments

II.1	HCFC activities

Stage III of HPPMP

# A total of US $23.54 million is planned for stage III of the HPPMP for one country in 2027.

# Stage III of HPMPs

# A total of US $25.68 million is planned for stage III of the HPMP for one country, including US $14.98 million for 2026–2028 and US $10.7 million for the period after 2028.

II.2	HFC-related activities

Stage I of KIPs

# A total of US $25.68 million is included in the business plan for stage I of KIPs for two countries (including US $13.91 million for 2026–2028 and US $11.77 million for the period after 2028). All these countries have ratified the Kigali Amendment.

II.3	Other activities

Energy efficiency (decision 94/60)

# A total of US $5.35 million is included in the business plan under the funding window for energy efficiency per decision 94/60 for 2026 for two countries.

Energy efficiency revolving fund for end users (decision 95/87)

# A total of US $64.2 million is included in the business plan under the funding window for energy-efficiency end-user projects using a revolving fund mechanism for 2026 for three countries. Preparation projects for these countries were approved at the 96th meeting. The Executive Committee will select two projects from all those submitted by agencies under this funding window.

# II.4	Core unit costs

# The core unit costs are expected to increase at an annual rate of 0.7 per cent as agreed.

III.	Proposed adjustments by the Secretariat

# The adjustments to the World Bank business plan for 2026–2028 were based on relevant decisions of the Executive Committee. In reviewing the revised World Bank business plan for 2026–2028, the Secretariat noted that the following adjustments were not included:

Table 2. Adjustments to the World Bank business plan for 2026–2028 (US $)* – as proposed by the Secretariat

| Adjustment | 2026–2028 | After 2028 |
| --- | --- | --- |
| MYA values to reflect the actual amounts approved under the Agreements, including MYA tranches that are due but have not been submitted to the 97th meeting | 186,763 | 0 |
| Core unit costs to exclude additional core unit funding in the amount of US $200,000 pursuant to decision 93/95(b) | (200,000) | 0 |

* Including agency support costs where applicable.

# Table 3 presents the results of the Secretariat’s proposed adjustments to the World Bank business plan for 2026–2028, which are also addressed in the context of the consolidated business plan of the Multilateral Fund for 2026–2028.

Table 3. Resource allocation in the World Bank’s adjusted business plan for 2026–2028 (US $)*

| Description | 2026 | 2027 | 2028 | Total (2026–2028) | Total after 2028 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HPMPs | 9,613,657 | 0 | 0 | 9,613,657 | 1,479,869 |
| HPPMP stage III | 0 | 23,540,000 | 0 | 23,540,000 | 23,540,000 |
| HPMP stage III | 4,280,000 | 0 | 10,700,000 | 14,980,000 | 10,700,000 |
| HCFC activities subtotal | 13,893,657 | 23,540,000 | 10,700,000 | 48,133,657 | 35,719,869 |
| HFC activities |  |  |  |  |  |
| Approved KIPs | 5,092,640 | 2,500,221 |  | 7,592,861 | 1,253,464 |
| KIP stage I | 2,140,000 | 4,280,000 | 7,490,000 | 13,910,000 | 11,770,000 |
| HFC activities subtotal | 7,232,640 | 6,780,221 | 7,490,000 | 21,502,861 | 13,023,464 |
| Other activities |  |  |  |  |  |
| Energy efficiency (decision 94/60) | 5,350,000 | 0 | 0 | 5,350,000 | 0 |
| Energy efficiency revolving fund (decision 95/87) | 64,200,000 | 0 |  | 64,200,000 | 0 |
| Other activities subtotal | 69,550,000 | 0 | 0 | 69,550,000 | 0 |
| Standard activities |  |  |  |  |  |
| IS | 0 | 0 | 982,829 | 982,829 | 0 |
| Core unit | 1,747,145 | 1,759,375 | 1,771,691 | 5,278,211 | 0 |
| Standard activities subtotal | 1,747,145 | 1,759,375 | 2,754,520 | 6,261,040 | 0 |
| Total | 92,423,442 | 32,079,596 | 20,944,520 | 145,447,558 | 48,743,333 |

* Including agency support costs where applicable.

IV.	Performance indicators

# The World Bank submitted performance indicators pursuant to decision 93/8(d) in its business plan narrative. The Secretariat informed the World Bank of the targets shown in table 4.

Table 4. Performance indicators for the World Bank for 2026

| Type of indicator | Short title | Calculation | 2026 target |
| --- | --- | --- | --- |
| Planning-Approval | Tranches approved | Number of tranches approved vs. those planned* | 7 |
| Planning-Approval | Individual projects/ activities approved | Number of projects/activities approved vs. those planned (including project preparation activities) | 5 |
| Implementation | Funds disbursed | Based on estimated disbursement in progress reports | 23,145,194 |
| Implementation | ODS phase-out for HCFC-related projects | ODS phase-out for HCFC-related projects in ODP tonnes vs. those planned per progress reports | 4,776.8 ODP tonnes |
| Implementation | HFC phase-down for HFC-related projects | HFC phase-down for HFC-related projects in CO2-eq tonnes vs. those planned per progress reports | 1,388,278 CO2-eq tonnes |
| Implementation | Project operational completion | Project operational completion vs. planned in progress reports for all activities (excluding project preparation)** | 17 |
| Implementation | Gender mainstreaming | Operational policy on gender mainstreaming applied to all approved projects | 100% |
| Administrative | Speed of financial completion | The extent to which projects are financially completed within 12 months after project operational completion | 12 months after operational completion |
| Administrative | Timely submission of project completion reports | Timely submission of project completion reports based on the progress report | 0 |
| Administrative | Timely submission of progress reports and business plans | Timely submission of progress reports and business plans and responses unless otherwise agreed | On time |

- * The targets of an agency will be reduced if it cannot submit a tranche owing to another cooperating agency or lead agency or if the HCFC phase-out management plan or Kigali HFC implementation plan submitted for consideration by the Executive Committee is not approved as a result of factors beyond the control of the national ozone unit and agency.

- ** The targets of an agency will be reduced if an extension of the completion date has been approved by the Executive Committee.

V.	Recommendation

# The Executive Committee may wish:

## To note the World Bank business plan for 2026–2028 contained in document UNEP/OzL.Pro/ExCom/97/25; and

## To approve the performance indicators for the World Bank set out in table 4 of document UNEP/OzL.Pro/ExCom/97/25.

UNEP/OzL.Pro/ExCom/97/1

The Executive Committee established a funding window for projects developed and implemented under the operational framework to support maintaining and/or enhancing energy efficiency while phasing down HFCs.

The Executive Committee established a funding window of US $40 million for two energy-efficiency end-user projects using a revolving fund mechanism developed and supported by implementing agencies, over a duration of eight years, after which funds would be returned to the Multilateral Fund, on the understanding that it would not be operationalized until the Executive Committee had agreed on the modalities for operationalizing the revolving fund (decision 95/87). Subsequently, the modalities were agreed at the 96th meeting (decision 96/51).

The World Bank’s 2026 core unit costs will be considered at the 97th meeting (UNEP/OzL.Pro/ExCom/97/84).

UNEP/OzL.Pro/ExCom/97/20