UNEP/OzL.Pro/ExCom/84/20
   19 November 2019

PROGRESS REPORT OF UNIDO as at 31 december 2018

# This document presents the progress report of UNIDO as at 31 December 2018.

Scope of the document

# This document consists of the following parts:

## Part I:	Projects approved under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2018 and cumulative since 1991 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs); it contains a review on the status of implementation of each ongoing project at the country level; and it identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## Part II:	Projects approved under the additional voluntary contributions for fast start support for HFC phase-down. It provides a status of implementation of HFC phase-down projects funded under the voluntary contributions.

## Recommendation.

# This document also contains the following annexes:

Annex I: 	A summary status and a recommendation for each ongoing project with outstanding issues for consideration by the Executive Committee.

Annex II: 	An analysis of the progress report.

Measurements used in the progress reports

# Prior to agreement on the Kigali Amendment, all controlled substances under the Montreal Protocol were ozone-depleting substances, measured in ODP tonnes. Controlled substances under the Kigali Amendment are not ozone-depleting substances, and their control targets are measured in mt CO2-eq. (i.e., consumption in metric tonnes (mt) multiplied by the global warming-potential (GWP) of the substance). Notwithstanding the two different measurements for reporting controlled substances, the progress report of UNIDO submitted to the 84th meeting is based on ODP tonnes for all controlled substances.

An overview of HFC phase-down activities

# As of 31 December 2018, the Executive Committee has approved 38 projects (including four investment projects, five project preparation and 29 enabling activities) amounting to US $9.83 million, in 32 countries. Approved investment projects will phase down 383.8 mt (720,098 mt CO2-eq.) of HCFs. Regarding enabling activities, extension of the completion dates of 13 of these projects was approved at the 83rd meeting and requests for extension for six others have been submitted to the 84th meeting.

Progress review process by the Secretariat

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2018, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The Secretariat had several discussions with UNIDO, where a number of issues on ongoing projects were raised and subsequently satisfactorily resolved.

Part I: 	Projects approved under the regular contributions to the Multilateral Fund

Summary of progress in implementation of projects for 2018 and cumulative

# Implementation of projects and activities by UNIDO for 2018 and cumulative since 1991 up to 31 December 2018 is summarized as follows:

## Phase-out: In 2018, 16 ODP tonnes of consumption of controlled substances were phased out and an additional 1,034 ODP tonnes of consumption of controlled substances were approved for phase-out. Since 1991, 62,858 ODP tonnes of consumption of controlled substances and 17,381 ODP tonnes of production of controlled substances had been phased out, of an expected total of 82,438 ODP tonnes from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2018, US $25.96 million was disbursed and US $23.57 million was planned for disbursement based on the 2017 progress report, representing a rate of disbursement of 110 per cent of that planned. Cumulatively, US $722.15 million had been disbursed out of the total US $822.33 million approved for disbursement (excluding agency support costs). This represents a rate of disbursement of 88 per cent. In 2018, US $27.94 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $11.71/kg and for all production sector activities (CFC and methyl bromide (MB)) was US $2.91/kg. The average cost-effectiveness of investment projects per ODP tonne was US $7.02/kg for completed projects and US $39.92/kg for ongoing projects;

## Number of projects completed: In 2018, 44 projects were completed. Since 1991, 1,523 projects of the 1,734 projects approved (excluding closed or transferred projects) were completed. This represents a completion rate of 88 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2018 were completed on average 57 months after their approval. Since 1991, the average time for completion of investment projects has been 38 months after their approval. First disbursements under these projects occurred, on average, nine months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2018 were completed on average 38 months after their approval. Since 1991, the average time for completion of non-investment projects has been 36 months after their approval. First disbursements under these projects occurred, on average, ten months after they had been approved;

## Project preparation: Of the 510 project preparation activities approved by the end of 2018, 472 have been completed, leaving 38 ongoing. In 2018, two projects have been completed;

## Implementation delays: There were a total of 132 ongoing investment projects under implementation at the end of 2018. These projects, on average, are experiencing a delay of 26 months. However, there are four projects classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as project preparation, multi-year agreements (MYAs), and institutional strengthening (IS) are not subject to those procedures); and

## MYAs: In 2018, UNIDO was implementing one MYA for ODS phase-out, one MYA for MB production and 75 MYAs for HCFC phase-out management plans (HPMPs). Since 1991, 155 MYAs have been approved and 78 MYAs have been completed.

Project implementation progress in 2018

# Further to the review process, a number of issues were resolved, except for a number of projects or tranches of MYAs for the phase-out of CFCs or HCFCs; projects for ODS waste disposal; and renewal of IS projects, as shown in Annex I to the present document. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Of the 157 ongoing projects, excluding IS and project preparation, 73 projects have revised planned dates of completion since the 2017 progress report.

# Details of progress in implementation of projects associated with the HPMPs for Argentina, Bahrain, China (stage II of XPS foam sector plan), Côte d’Ivoire, Egypt, Iran (Islamic Republic of), Iraq, the Niger, North Macedonia, Pakistan, Tunisia, and Turkey, and reports on projects with specific reporting requirements associated with China (HPMP, CFC phase-out plan, MB phase-out plan, MB production phase-out plan), Libya (HPMP), Mexico (HPMP), Morocco (demonstration project), Qatar (HPMP) and the Eastern Africa and Caribbean regions (low-GWP alternative demonstration project) have been submitted to the 84th meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of these documents. The issues relating to stage I of the HPMPs for Algeria and Saudi Arabia and stage II of the HPMP for Venezuela (Bolivarian Republic of) are addressed in the document on tranche submission delays. Outstanding issues for the remaining ongoing projects not included in Annex I to the present document, and requests for extension of date of completion, are addressed below.

# In line with decision 82/11(c)(ii), the Secretariat noted that renewal of IS projects for Qatar and Syrian Arab Republic have not been submitted for the last two years. UNIDO informed that it is planning to submit those renewal requests in 2020. The main reasons for delays are large balances mainly on account of slow progress in implementation.

# At its 82nd meeting, upon a request by UNIDO the Executive Committee decided to extend the Tunisia component of the demonstration project for the introduction of trans-critical CO2 refrigeration technology for supermarkets (Argentina and Tunisia) (GLO/REF/76/DEM/335) to 31 December 2019 (decision 82/22(d)(ii)). UNIDO reported that as a beneficiary enterprise to undertake the demonstration project could not be identified and noting that the Committee had already extended the completion date to the end of 2019, UNIDO has requested the cancellation of this sub-project component. Therefore, the Executive Committee way wish to cancel the Tunisia component of the demonstration project for the introduction of trans-critical CO2 refrigeration technology for supermarkets, noting that the balances would be returned to the 86th meeting.

# In line with decision 82/11(b), UNIDO has requested the extension of the duration of eight projects relating to HPMPs for four countries, implementation of which is beyond the completion date as per their respective Agreements with the Executive Committee; and one metered-dose inhaler project. The reasons for the requests for extension of completion dates for these projects are shown in Table 1.

Table 1. Projects for which an extension of the completion dates have been requested

| Country/project code | Project title | Disburse-ment (%) | Status/Issues | Original date of completion | Date of completion requested |
| --- | --- | --- | --- | --- | --- |
| Cameroon CMR/PHA/80/INV/44 | HCFC phase-out management plan (refrigeration servicing sector plan) (stage I, fourth tranche) | 0 | Equipment procurement completed and final obligations are being liquidated | 31-12-2018 | 31-12-2019 |
| Democratic People's Republic of Korea (the) DRK/PHA/73/INV/59 | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b in polyurethane foam sector at Pyongyang Sonbong and Puhung Building Materials) | 22 | Implementation subject to United Nations Security Council (UNSC) resolutions | 31-12-2019 | 31-12-2021 |
| Democratic People's Republic of Korea (the) DRK/PHA/73/TAS/60 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | 89 |  |  |  |
| Democratic People's Republic of Korea (the) DRK/PHA/75/INV/62 | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in polyurethane foam sector at Pyongyang Sonbong and Puhung Building Materials) | 2 |  |  |  |
| Democratic People's Republic of Korea (the) DRK/PHA/75/TAS/63 | HCFC phase-out management plan (stage I, second tranche) (policy, refrigeration servicing and monitoring) | 89 |  |  |  |
| Democratic People's Republic of Korea (the) DRK/PHA/77/INV/64 | HCFC phase-out management plan (stage I, third tranche) (policy, refrigeration servicing and monitoring) | 1 |  |  |  |
| Egypt EGY/ARS/50/INV/92 | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | 96 | Completion pending Egyptian Health Authorities for marketing approval of the last product; incremental operating costs to be paid upon marketing approval and completion of project | 31-7-2018 | 31-3-2020 |
| Sudan (the) SUD/PHA/80/INV/42 | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | 39 | Remaining training activities for technicians’ association and Ozone office to be completed by December 2019 | 31-12-2018 | 31-12-2019 |

# The Executive Committee may wish to approve the extension, to the date indicated in the last column, of the projects contained in Table 1 to the present document.

Part II:	Projects approved under the additional voluntary contributions for fast start support for HFC phase-down

# As of 31 December 2018, the Executive Committee had approved 34 HFC-related projects under the additional voluntary contributions amounting to US $7,863,736 (excluding agency support costs). A summary of the status of these projects is presented in Table 2.

# Table 2. HFC-related projects approved in 2018

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 3 | 0 | 0 | 3,912,736 | 785 | 3,911,951 | 0 |
| Project preparation | 4 | 3 | 75 | 120,000 | 78,522 | 41,478 | 65 |
| Technical assistance - Enabling activities | 27 | 0 | 0 | 3,831,000 | 735,541 | 3,095,459 | 19 |
| Total | 34 | 3 | 9 | 7,863,736 | 814,848 | 7,048,888 | 10 |

*Excludes agency support costs.

** Phase out of 265.2 mt (508,586 mt CO2-eq.) of HFCs.

# Of the 34 projects approved by the end of 2018, three preparation activities have been completed, leaving 31 ongoing. Ongoing investment projects that include two refrigeration sector projects in Lebanon and Mexico, were approved at the 81st meeting with disbursement in one project; UNIDO confirmed that these projects will be completed on time in 30 June 2020. The enabling activities are at various stages of implementation. Cumulatively, US $814,848 had been disbursed out of the total US $7,863,736 approved for disbursement (excluding support costs), representing a disbursement rate of 10 per cent.

# Recommendation

# The Executive Committee may wish:

## To note the progress report of UNIDO as at 31 December 2018 contained in document UNEP/OzL.Pro/ExCom/84/20;

## To approve the recommendations related to ongoing projects with specific issues contained in Annex I to the present document;

## To cancel at the 84th meeting the Tunisia component of the demonstration project for the introduction of trans-critical CO2 refrigeration technology for supermarkets (Argentina and Tunisia) (GLO/REF/76/DEM/335), noting that the balances would be returned to the 86th meeting;

## To approve the extension, to 31 December 2019, of the HPMP for Cameroon (stage I, fourth tranche) (CMR/PHA/80/INV/44), noting that final disbursement on procurement and related activities would be completed by December 2019;

## To approve the extension, on an exceptional basis, to 31 December 2021, of the HPMP for the Democratic People's Republic of Korea (stage I, first, second and third tranches) (DRK/PHA/73/INV/59, DRK/PHA/73/TAS/60, DRK/PHA/75/INV/62, DRK/PHA/75/TAS/63 and DRK/PHA/77/INV/64);

## To approve the extension, to 31 March 2020, of the phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) for Egypt (EGY/ARS/50/INV/92) to conclude regulatory approval by health authorities in the country; and

## To approve the extension, to 31 December 2019, of the HPMP for the Sudan, (stage I, third tranche) (SUD/PHA/80/INV/42), noting that activities would be completed by November 2019.

Annex I

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNIDO

| Country/project code | Project title | Disburse-ment (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Afghanistan AFG/PHA/79/INV/22 | HCFC phase-out management plan (stage I, third tranche) | 0 | Low disbursement rate of approved funds; implementation plan finalisation delayed. | To request a status report to the 85th meeting on the level of funds disbursement and progress in implementation |
| China CPR/ARS/56/INV/473 | Sector plan for phase-out of CFCs consumption in MDI sector | 98 | 12 months delays | To request UNIDO to report to the 85th meeting on this project with implementation delays |
| Democratic People's Republic of Korea (the) DRK/PHA/73/INV/59 | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b in polyurethane foam sector at Pyongyang Sonbong and Puhung Building Materials) | 22 | Implementation subject to United Nations Security Council (UNSC) resolutions | To request a status report to the 85th meeting on progress in implementation including updates on the resumption of activities |
| Democratic People's Republic of Korea (the) DRK/PHA/73/TAS/60 | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | 89 |  |  |
| Democratic People's Republic of Korea (the) DRK/PHA/75/INV/62 | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in polyurethane foam sector at Pyongyang Sonbong and Puhung Building Materials) | 2 |  |  |
| Democratic People's Republic of Korea (the) DRK/PHA/75/TAS/63 | HCFC phase-out management plan (stage I, second tranche) (policy, refrigeration servicing and monitoring) | 89 |  |  |
| Democratic People's Republic of Korea (the) DRK/PHA/77/INV/64 | HCFC phase-out management plan (stage I, third tranche) (policy, refrigeration servicing and monitoring) | 1 |  |  |
| Egypt EGY/ARS/50/INV/92 | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | 96 | 12 months delays | To request a report to the 85th meeting on this project with implementation delays |
| Iraq IRQ/REF/57/INV/07 | Replacement of refrigerant CFC-12 with isobutane and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigerators and chest freezers at Light Industries Company | 89 | 12 months delays | To request a report to the 85th meeting on this project with implementation delays, noting the extension to 31 December 2019, of the completion date approved at the 82nd meeting |
| Lebanon LEB/DES/73/DEM/83 | Pilot demonstration project on ODS waste management and disposal | 93 | Final report and project completion report due for submission to the 84th meeting in line with decision 82/15(c) not submitted as UNIDO is still planning to export ODSs for destruction; an extension to 30 June 2019 was approved at the 82nd meeting | To request submission of the final report and the project completion report in line with decision 82/15(c) |
| Libya LIB/FOA/82/PRP/41 | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | 0 | Implementation slow due to political situation in the country | To request a status report to the 85th meeting on progress in stage II preparation |
| Libya LIB/PHA/82/PRP/43 | Preparation of a HCFC phase-out management plan (stage II) | 0 |  |  |
| Qatar QAT/PHA/73/PRP/21 | Preparation of a HCFC phase-out management plan (stage II) | 46 | Progress slow as national ozone unit (NOU) is not fully functional | To request a status report to the 85th meeting on progress in preparation and submission of stage II |
| Qatar QAT/SEV/79/INS/22 | Renewal of institutional strengthening project (phase IV: 8/2017-7/2019) | 13 | Operationalisation of NOU is challenging; discussions on the way forward is underway with NOU | To request a status report to the 85th meeting on operationalisation of NOU |
| Saudi Arabia SAU/FOA/62/INV/13 | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Al-Watania Plastics | 18 | Equipment procured to be auctioned as enterprise no longer will participate in the project; auction process delayed | To request a status report to the 85th meeting on the auction process |
| Somalia SOM/PHA/77/INV/12 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | 61 | Delay due to security situation in the country | To request a status report to the 85th meeting on progress in implementation |
| Somalia SOM/PHA/77/TAS/13 | HCFC phase-out management plan (stage I, second tranche) (additional security) | 71 |  |  |
| Syrian Arab Republic SYR/PHA/55/PRP/97 | Preparation of a HCFC phase-out management plan | 82 | Delay due to security situation in the country | To request a status report to the 85th meeting on project preparation and proposed date for submission |
| Syrian Arab Republic SYR/FOA/61/PRP/102 | Preparation for HCFC phase-out investment activities (foam sector) | 58 |  |  |
| Syrian Arab Republic SYR/REF/62/INV/103 | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group | 28 | 12 months delay; plants were inspected by UNIDO in September 2019 and enterprise is in operation. Project expected to be completed by 31 December 2020 | To request a report to the 85th meeting on this project with implementation delays, noting that the project would be completed by 31 December 2020 |
| Syrian Arab Republic SYR/SEV/73/INS/104 | Extension of institutional strengthening (phase V: 1/2015-12/2016) | 4 | Delay due to security situation in the country | To request a status report to the 85th meeting on progress in implementation and the level of funds disbursement |
| United Republic of Tanzania (the) URT/PHA/76/INV/35 | HCFC phase-out management plan (stage I, second tranche) | 23 | Delay due to operational issues relating to approval of implementation plan by Government | To request a status report to the 85th meeting on progress in implementation |
| Zambia ZAM/PHA/77/INV/33 | HCFC phase-out management plan (stage I, third tranche) | 0 | Low disbursement rate of approved funds; delay due to operational issues | To request a status report to the 85th meeting on progress in implementation and the level of funds disbursement |
| Global GLO/REF/76/DEM/335 | Demonstration project for the introduction of trans-critical CO2 refrigeration technology for supermarkets (Argentina and Tunisia) | 58 | Activities delayed due to inability to identify beneficiary in the Tunisia component; activities relating to Argentina component completed | To request final report to the 85th meeting on the Argentina component, noting that the Tunisia component would be cancelled at the 84th meeting |

Annex II

ANALYSIS OF THE PROGRESS REPORT OF UNIDO AS AT 31 DECEMBER 2018

# This Annex consists of the following two parts:

## Part I:	Projects approved under the regular contributions to the Multilateral Fund.

## Part II:	Projects approved under the additional voluntary contributions for fast start support for HFC phase-down.

Part I: 	Projects approved under the regular contributions to the Multilateral Fund

# As of 31 December 2018, the Executive Committee had approved US $928.88 million consisting of US $822.33 million for the implementation of investment and non-investment projects and US $106.55 million for agency support costs, as shown in Table 1. In 2018, 62 new projects and activities were approved. This level of funding is expected to result in the phase-out of 82,438 ODP tonnes of consumption and production of controlled substances.

# Table 1: Approved funding by sector for UNIDO as at 31 December 2018

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 34,413,701 |
| Destruction | 3,861,804 |
| Foam | 89,036,986 |
| Halon | 1,780,369 |
| Fumigants | 78,092,525 |
| Multiple sectors | 139,440 |
| Other | 11,317,246 |
| Phase-out plan | 324,163,481 |
| Process agent | 6,337,359 |
| Production | 50,590,327 |
| Refrigeration | 182,262,875 |
| Several | 17,085,170 |
| Solvents | 23,247,443 |
| Sub-total | 822,328,725 |
| Agency support costs | 106,551,992 |
| Total | 928,880,717 |

# A summary of the status of projects implemented by category is presented in Table 2.

Table 2: Status of project implementation by category

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 11 | 11 | 100 | 722,669 | 722,669 | 0 | 100 |
| Demonstration | 43 | 35 | 81 | 23,792,166 | 21,348,941 | 2,443,225 | 90 |
| Institutional strengthening (IS) | 82 | 70 | 85 | 12,632,662 | 10,609,346 | 2,023,316 | 84 |
| Investment | 886 | 754 | 85 | 741,229,786 | 650,205,530 | 91,024,256 | 88 |
| Project preparation | 510 | 472 | 93 | 21,838,778 | 20,454,633 | 1,384,144 | 94 |
| Technical assistance | 179 | 158 | 88 | 20,916,130 | 17,615,172 | 3,300,958 | 84 |
| Training | 23 | 23 | 100 | 1,196,535 | 1,196,533 | 2 | 100 |
| Total | 1,734 | 1,523 | 88 | 822,328,725 | 722,152,823 | 100,175,902 | 88 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

# Table 3 presents an overview of the status of project implementation by year. All projects and activities approved between 1993 and the end of 2005, as well as 2007, have now been completed.

Table 3: Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1993 | 22 | 22 | 100 | 11,815,540 | 11,815,540 | 0 | 100 |
| 1994 | 52 | 52 | 100 | 30,645,899 | 30,645,900 | -1 | 100 |
| 1995 | 59 | 59 | 100 | 25,662,092 | 25,662,092 | 0 | 100 |
| 1996 | 46 | 46 | 100 | 19,820,493 | 19,820,493 | 0 | 100 |
| 1997 | 130 | 130 | 100 | 42,083,037 | 42,083,040 | -3 | 100 |
| 1998 | 88 | 88 | 100 | 23,638,291 | 23,638,290 | 1 | 100 |
| 1999 | 123 | 123 | 100 | 34,140,324 | 34,140,324 | 0 | 100 |
| 2000 | 96 | 96 | 100 | 30,180,752 | 30,180,751 | 1 | 100 |
| 2001 | 119 | 119 | 100 | 24,700,254 | 24,700,254 | 1 | 100 |
| 2002 | 76 | 76 | 100 | 35,992,041 | 35,992,040 | 2 | 100 |
| 2003 | 49 | 49 | 100 | 29,997,305 | 29,997,305 | 0 | 100 |
| 2004 | 44 | 44 | 100 | 33,105,459 | 33,105,458 | 1 | 100 |
| 2005 | 74 | 74 | 100 | 52,035,808 | 52,035,808 | -1 | 100 |
| 2006 | 44 | 43 | 98 | 20,760,993 | 20,539,241 | 221,752 | 99 |
| 2007 | 42 | 42 | 100 | 24,186,740 | 24,186,739 | 1 | 100 |
| 2008 | 78 | 75 | 96 | 33,437,482 | 33,066,911 | 370,571 | 99 |
| 2009 | 70 | 68 | 97 | 15,409,470 | 14,669,645 | 739,825 | 95 |
| 2010 | 71 | 65 | 92 | 46,729,483 | 43,977,296 | 2,752,187 | 94 |
| 2011 | 72 | 65 | 90 | 76,775,116 | 70,551,160 | 6,223,956 | 92 |
| 2012 | 53 | 40 | 75 | 32,963,759 | 29,520,448 | 3,443,311 | 90 |
| 2013 | 37 | 34 | 92 | 31,167,516 | 29,924,221 | 1,243,295 | 96 |
| 2014 | 57 | 37 | 65 | 28,010,864 | 24,491,876 | 3,518,988 | 87 |
| 2015 | 84 | 61 | 73 | 37,466,033 | 17,759,958 | 19,706,075 | 47 |
| 2016 | 58 | 12 | 21 | 37,184,191 | 14,409,623 | 22,774,568 | 39 |
| 2017 | 28 | 3 | 11 | 16,476,598 | 5,186,077 | 11,290,521 | 31 |
| 2018 | 62 | 0 | 0 | 27,943,186 | 52,335 | 27,890,851 | 0 |
| Total | 1,734 | 1,523 | 88 | 822,328,725 | 722,152,823 | 100,175,902 | 88 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

# Table 4 presents project implementation by country for 2018.

Table 4. Summary of project implementation by UNIDO for 2018

| Country | Phased out in 2018* | Percentage of planned phase-out achieved in 2018 | Estimated funds disbursed in 2018 (US$) | Funds disbursed in 2018 (US$) | Percentage of funds disbursed over estimation in 2018 | Percentage of planned projects completed in 2018 |
| --- | --- | --- | --- | --- | --- | --- |
| Afghanistan | 0.0 |  | 5,001 | 192 | 4 |  |
| Albania | 0.0 |  | 29,909 | 47,865 | 160 | 100 |
| Algeria | 0.0 |  | 990,000 | 1,009,349 | 102 | 0 |
| Argentina | 0.0 |  | 315,002 | 450,471 | 143 | 100 |
| Armenia | 0.0 |  | 30,001 | 76,941 | 256 |  |
| Bahamas (the) | 0.0 |  | 10,000 | 131 | 1 |  |
| Bahrain | 3.7 |  | 17,001 | 146,991 | 865 |  |
| Benin | 0.0 |  | 67,001 | 67,495 | 101 |  |
| Bolivia (Plurinational State of) | 0.0 |  | 17,000 | 12,958 | 76 | 100 |
| Bosnia and Herzegovina | 0.0 |  | 93,004 | 133,189 | 143 | 100 |
| Botswana | 0.0 |  | 35,000 | 39,450 | 113 |  |
| Brazil | 0.0 |  | 440,000 | 407,626 | 93 |  |
| Burkina Faso | 0.0 |  | 15,000 | 0 | 0 |  |
| Burundi | 0.0 |  | 5,000 | 0 | 0 | 0 |
| Cameroon | 0.0 |  | 149,701 | 46,347 | 31 | 67 |
| Central African Republic (the) | 0.0 |  | 1 | 0 | 0 |  |
| Chad | 0.0 |  | 1 | 1,173 |  |  |
| Chile | 0.0 |  | 50,000 | 154,995 | 310 |  |
| China | 0.0 |  | 9,316,710 | 11,302,296 | 121 | 86 |
| Congo (the) | 0.0 |  | 20,000 | 49,336 | 247 |  |
| Cote d'Ivoire | 0.0 |  | 20,000 | 12,871 | 64 |  |
| Democratic People’s Republic of Korea (the) | 0.0 |  | 12,178 | 19,422 | 159 |  |
| Ecuador | 0.0 |  | 30,200 | 31,904 | 106 |  |
| Egypt | 3.1 | 100 | 508,002 | 521,482 | 103 | 80 |
| Eritrea | 0.0 |  | 26,000 | 44,640 | 172 |  |
| Ethiopia | 0.0 |  | 2,800 | 1,112 | 40 |  |
| Gabon | 0.0 |  | 25,000 | 3,219 | 13 | 0 |
| Gambia (the) | 0.0 |  | 15,000 | 7,105 | 47 |  |
| Georgia | 0.0 |  | 13,000 | 13,094 | 101 |  |
| Grenada | 0.0 |  | 20,000 | 1,926 | 10 |  |
| Guatemala | 0.0 |  | 53,000 | 66,671 | 126 | 100 |
| Guinea-Bissau | 0.0 |  | 15,000 | 26,373 | 176 |  |
| Honduras | 0.0 |  | 33,200 | 35,824 | 108 | 100 |
| Indonesia | 0.0 |  | 1 | 1 | 131 |  |
| Iran (Islamic Republic of) | 0.0 |  | 541,369 | 178,368 | 33 |  |
| Iraq | 0.0 |  | 620,003 | 36,067 | 6 | 33 |
| Jordan | 0.0 |  | 41,600 | 74,491 | 179 |  |
| Kuwait | 0.0 | 0 | 2,550,001 | 2,925,591 | 115 | 50 |
| Lebanon | 0.0 |  | 25,000 | 17,031 | 68 | 0 |
| Libya | 0.0 |  | 764,001 | 751,347 | 98 | 100 |
| Madagascar | 0.0 |  | 27,000 | 24,486 | 91 |  |
| Malawi | 0.0 |  | 25,000 | 53,898 | 216 |  |
| Mexico | 0.0 |  | 622,601 | 668,517 | 107 | 50 |
| Montenegro | 0.0 |  | 25,001 | 48,740 | 195 |  |
| Morocco | 0.0 |  | 205,000 | 114,496 | 56 | 0 |
| Mozambique | 0.0 | 0 | 20,000 | 0 | 0 | 0 |
| Nicaragua | 0.0 |  | 19,000 | 19,944 | 105 | 100 |
| Niger (the) | 0.0 |  | 89,001 | 95,329 | 107 |  |
| Nigeria | 4.1 |  | 709,001 | 690,001 | 97 | 100 |
| North Macedonia | 0.0 |  | 73,001 | 82,524 | 113 | 100 |
| Oman | 0.0 |  | 73,001 | 157,278 | 215 | 100 |
| Pakistan | 0.0 |  | 576,845 | 488,946 | 85 |  |
| Qatar | 0.0 |  | 75,002 | 30,425 | 41 |  |
| Rwanda | 0.0 |  | 20,001 | 0 | 0 |  |
| Saint Lucia | 0.0 |  | 10,000 | 0 | 0 |  |
| Saudi Arabia | 0.0 | 0 | 625,007 | 1,088,454 | 174 | 0 |
| Senegal | 0.0 |  | 71,000 | 90,377 | 127 | 0 |
| Serbia | 0.0 |  | 255,302 | 295,844 | 116 | 100 |
| Sierra Leone | 0.0 |  | 15,001 | 8,065 | 54 |  |
| Somalia | 0.0 |  | 43,000 | 84,182 | 196 |  |
| South Africa | 0.0 |  | 562,000 | 1,390,413 | 247 | 25 |
| Sudan (the) | 4.3 | 108 | 486,501 | 133,721 | 27 | 50 |
| Suriname | 0.0 |  | 10,000 | 0 | 0 | 100 |
| Syria | 0.0 |  | 120,001 | 8,370 | 7 |  |
| Togo | 0.0 |  | 39,000 | 23,620 | 61 | 100 |
| Tunisia | 0.8 | 100 | 330,002 | 242,636 | 74 | 100 |
| Turkey | 0.0 |  | 738,887 | 497,950 | 67 | 67 |
| Turkmenistan | 0.0 |  | 70,002 | 72,455 | 104 |  |
| Uganda | 0.0 |  | 20,001 | 14,967 | 75 |  |
| United Republic of Tanzania (the) | 0.0 |  | 15,000 | 879 | 6 |  |
| Uruguay | 0.0 |  | 25,000 | 22,492 | 90 |  |
| Venezuela (Bolivarian Republic of) | 0.0 |  | 160,801 | 203,104 | 126 | 100 |
| Yemen | 0.0 |  | 5 | 0 | 6 |  |
| Zambia | 0.0 |  | 2 | 3,800 |  |  |
| Global | 0.0 |  | 427,002 | 510,177 | 119 | 50 |
| Region: ASP | 0.0 |  | 30,001 | 42,498 | 142 |  |
| Region: EUR | 0.0 |  | 40,000 | 34,066 | 85 |  |
| Total | 16.0 | 11 | 23,573,656 | 25,957,997 | 110 | 61 |

* No phase-out in 2018 for HFC-related projects.

# Table 5 presents a summary of HFC-related projects approved under regular contributions.

Table 5. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 1 | 0 | 0 | 1,637,610 | 0 | 1,637,610 | 0 |
| Project preparation | 1 | 0 | 0 | 75,000 | 0 | 75,000 | 0 |
| Technical assistance - Enabling activities | 2 | 0 | 0 | 250,000 | 0 | 250,000 | 0 |
| Total | 4 | 0 | 0 | 1,962,610 | 0 | 1,962,610 | 0 |

*Excludes agency support costs.

** 118.7 mt was approved for investment projects with mt CO2-eq. of 211,512.

# There are currently four HFC-related projects (including one investment, one preparation and two enabling activities) approved under regular contributions at a total value of US $1,962,610. Funds have not been disbursed for these projects. The investment project related to the refrigeration sector in Jordan approved in June 2018 is progressing and UNIDO confirmed that it will complete on time. Regarding enabling activities, the projects are progressing and are at various stages of implementation.

# Part II:	Projects approved under the additional voluntary contributions for fast start support for HFC phase-down

# As of 31 December 2018, the Executive Committee had approved 34 HFC-related projects under the additional voluntary contributions amounting to US $7,863,736 (excluding agency support costs). A summary of the status of these projects is presented in Table 6.

# Table 6. HFC-related projects approved in 2018

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 3 | 0 | 0 | 3,912,736 | 785 | 3,911,951 | 0 |
| Project preparation | 4 | 3 | 75 | 120,000 | 78,522 | 41,478 | 65 |
| Technical assistance - Enabling activities | 27 | 0 | 0 | 3,831,000 | 735,541 | 3,095,459 | 19 |
| Total | 34 | 3 | 9 | 7,863,736 | 814,848 | 7,048,888 | 10 |

*Excludes agency support costs.

** Phase-out of 265.2 mt (508,586 mt CO2-eq.) of HFCs.

# Of the 34 projects approved by the end of 2018, three preparation activities have been completed, and three investment projects are under implementation. The enabling activities are at various stages of implementation. Cumulatively, US $814,848 had been disbursed out of the total US $7,863,736 approved for disbursement (excluding support costs), representing a disbursement rate of 10 per cent.

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database that is available upon request.

Ongoing projects are all projects that were under implementation as at 31 December 2018. Key indicators of progress include: percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

The issue of the two different measurements of controlled substances is discussed in the consolidated progress report (UNEP/OzL.Pro/ExCom/84/16).

The phase-out includes approvals for HFC investment projects of 118.7 mt with mt CO2-eq. of 211,512.

Including 118.7 mt of HFC investment projects.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

UNEP/OzL.Pro/ExCom/84/39

UNEP/OzL.Pro/ExCom/84/40

UNEP/OzL.Pro/ExCom/84/42

UNEP/OzL.Pro/ExCom/84/46

UNEP/OzL.Pro/ExCom/84/49

UNEP/OzL.Pro/ExCom/84/51

UNEP/OzL.Pro/ExCom/84/52

UNEP/OzL.Pro/ExCom/84/55

UNEP/OzL.Pro/ExCom/84/56

UNEP/OzL.Pro/ExCom/84/57

UNEP/OzL.Pro/ExCom/84/60

UNEP/OzL.Pro/ExCom/84/61

UNEP/OzL.Pro/ExCom/84/22 and Add.1

UNEP/OzL.Pro/ExCom/84/25

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively-financed projects.