| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/93/17 20 November 2023 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-third Meeting

Montreal, 15-19 December 2023

Item 7(a)(iv) of the provisional agenda

PROGRESS REPORT OF UNEP AS AT 31 DECEMBER 2022

Introduction

# This document presents the progress report of UNEP as at 31 December 2022.

# The progress report of UNEP includes the status of implementation of projects, including 79 HFC-related projects that have been funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2022, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs which are measured in CO2-eq tonnes.

# This document consists of the following sections:

## I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2022 and cumulative since 1991 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs). It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## II.	Projects approved for Annex F substances (HFCs) under the additional voluntary contributions for fast-start support for HFC phase-down.

III.	Recommendation.

I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund

I.1	Progress in implementation of projects for 2022 and cumulative since 1991

# As of 31 December 2022, the Executive Committee had approved US $417.2 million in projects for UNEP, consisting of US $385.4 million for the implementation of investment and non-investment projects, and US $31.8 million for agency support costs, as shown in table 1.

# Table 1. Approved funding by sector for UNEP as at 31 December 2022

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 882,689 |
| Destruction | 190,040 |
| Halon | 767,640 |
| HFC phase-down plan | 5,367,000 |
| Fumigants | 2,614,366 |
| Phase-out plan | 75,583,006 |
| Refrigeration | 13,956,016 |
| Several | 285,842,159 |
| Solvents | 198,860 |
| Sub-total | 385,401,777 |
| Agency support costs | 31,796,964 |
| Total | 417,198,741 |

# In 2022, 101 new projects and activities were approved. This level of funding is expected to result in the phase-out of 2,413.2 ODP tonnes of consumption of controlled substances. Annex I shows the status of project implementation per country in 2022.

# Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2022. Annex II presents analytical information per year since 1991.

Table 2. Status of project implementation by type as at 31 December 2022

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 94 | 94 | 100 | 2,946,574 | 2,946,574 | 0 | 100 |
| Demonstration | 3 | 3 | 100 | 542,845 | 542,845 | 0 | 100 |
| Institutional strengthening (IS) | 972 | 869 | 89 | 81,213,144 | 70,794,136 | 10,419,007 | 87 |
| Investment | 4 | 3 | 75 | 598,500 | 490,500 | 108,000 | 82 |
| Project preparation | 303 | 236 | 78 | 15,538,011 | 10,183,746 | 5,354,265 | 66 |
| Technical assistance | 1,149 | 1,000 | 87 | 270,270,146 | 238,967,028 | 31,303,118 | 88 |
| Training | 196 | 196 | 100 | 14,292,557 | 14,292,557 | 0 | 100 |
| Total | 2,721 | 2,401 | 88 | 385,401,777 | 338,217,387 | 47,184,390 | 88 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

# Implementation of projects and activities by UNEP for 2022 and cumulative since 1991 up to 31 December 2022, is summarized as follows:

## Phase-out: In 2022, zero ODP tonnes of consumption of controlled substances were phased out and an additional 114 ODP tonnes of consumption of controlled substances were approved for phase-out. Since 1991, 1,575 ODP tonnes of consumption of controlled substances had been phased out, of an expected total of 2,413 ODP tonnes from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2022, US $18.4 million was disbursed and US $21.7 million was planned for disbursement based on the 2021 progress report, representing a rate of disbursement of 85 per cent of that planned. Cumulatively, US $338.2 million had been disbursed out of the total US $385.4 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 88 per cent. In 2022, US $24.3 million was approved for implementation;

## Number of projects completed: In 2022, 127 projects were completed. Since 1991, 2,401 projects of the 2,721 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 88 per cent;

## Speed of delivery – non-investment projects: Projects that were completed in 2022 were completed on average 41 months after their approval. Since 1991, the average time for completion of non-investment projects has been 37 months after their approval. First disbursements under these projects occurred, on average, 12 months after they had been approved;

## Project preparation: Of the 303 project preparation activities approved by the end of 2022, 236 have been completed, leaving 67 ongoing activities. In 2022, 14 project preparation activities have been completed;

## Implementation delays: A total of 320 projects were under implementation at the end of 2022, experiencing, on average, a delay of seven months. Twenty-eight of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2022, 98 MYAs for HCFC phase-out management plans (HPMPs) were under implementation. Since 1991, 254 MYAs have been approved and 156 MYAs have been completed, representing a completion rate of 61 per cent.

# Table 3 summarized progress made by UNEP since 1991.

## Table 3. Progress made by UNEP since 1991

| Phase out achieved |  | Disbursement (US $) | Number of projects |  | Speed of delivery for completion for non-investment projects (months) | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes | CO2-eq tonnes |  | Approved | Completed |  |  | Approved | Completed |
| 1,575 | 0 | 338,217,387 | 2,721 | 2,401 | 37 | 7 | 254 | 156 |

HFC-related projects

# As of 31 December 2022, the Executive Committee had approved 66 HFC-related projects (including 50 preparation projects, 14 enabling activities, one Kigali HFC implementation plan (KIP) and one global technical assistance project) under regular contributions amounting to US $8,293,353 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 5 to 9.

Table 4. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Project preparation | 50 | 0 | 0 | 5,347,000 | 318,453 | 5,028,547 | 6 |
| Technical assistance | 16 | 12 | 75 | 2,946,353 | 1,584,737 | 1,361,616 | 54 |
| Total | 66 | 12 | 18 | 8,293,353 | 1,903,190 | 6,390,164 | 23 |

* Excludes agency support costs.

# As of the end of 2022, of the 66 projects, 12 enabling activities have been completed, leaving 54 ongoing. Of the two ongoing enabling activities, extension of the completion date of one was approved. The remaining ongoing activities are at various stages of implementation, noting that the global technical assistance project and stage I of the KIP for the Niger (advance funding) were approved at the 91st meeting and are expected to be completed in 2024 and 2026, respectively.

# Of the total cumulative funding approved of US $8,293,353 (excluding agency support costs), US $1,903,190 had been disbursed, representing a disbursement rate of 23 per cent.

I.2	Issues identified in project implementation in 2022

# Further to the review process, several issues were discussed and satisfactorily addressed, except for issues on 28 projects classified as projects with implementation delays (including 25 projects related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c); and three technical assistance projects). Annex III to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendations requesting the submission of a report to the 94th meeting.

# In addition, issues have been identified regarding projects or tranches of MYAs for the phase-out of HCFCs; renewal of IS projects; preparation of HPMPs and KIPs; and technical assistance for verification report. These issues are also presented in annex III. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Details of progress in implementation of projects associated with the HPMPs for Bahrain, Bolivia (Plurinational State of), Burundi, China (refrigeration servicing sector and national enabling programme), Colombia, the Gambia, Guatemala, Guinea, Mongolia, Mozambique, Oman, Qatar, Saint Kitts and Nevis, Sierra Leone, and Suriname and reports on projects with specific reporting requirements associated with the HPMPs of Cote d’Ivoire and Mauritania, have been submitted to the 93rd meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. The issues relating to the HPMPs for Afghanistan, Botswana, Dominica, Egypt, Iraq, Kuwait, the Lao People’s Democratic Republic, Nepal, Senegal, Sri Lanka, and Timor-Leste, tranches of which were due at the 93rd meeting but were not submitted, and for the Islamic Republic of Iran, the tranche of which was submitted but later withdrawn, are addressed in the document on tranche submission delays. Outstanding issues for the remaining ongoing projects not included in annex III to the present document, and requests for extension of dates of completion, are addressed below.

# Of the 150 ongoing projects, excluding IS and project preparation, 34 projects have revised planned dates of completion since the 2021 progress report.

# In line with decision 82/11(c)(ii), the Secretariat noted that renewal of IS projects had not been submitted for the last two years for 14 Article 5 countries namely, Angola, Burundi, the Central African Republic, the Congo, the Democratic Republic of the Congo, Equatorial Guinea, Grenada, Guinea-Bissau, Morocco, Myanmar, Nauru, Nepal, South Sudan, and Suriname. These projects have large remaining balances due to slow progress in implementation for various reasons including political situation. UNEP informed that it has been providing assistance to those countries and is planning to submit those renewal requests by 2024, except for the case of Myanmar, which will be subject to the political situation and the resumption of activities in the country.

# In line with decision 82/11(b), UNEP has requested the extension of the duration of two projects as shown in table 5.

Table 5. Projects for which an extension of the completion dates has been requested

| Country/ project code | Project title | Disburse-ment (%) | Status/issues | Original date of completion | Date of completion requested |
| --- | --- | --- | --- | --- | --- |
| Dominica DMI/PHA/62/TAS/19 | HCFC phase-out management plan (stage I, first tranche) | 12 | Additional time required for completion of activities, noting that activities are resuming with support from UNEP’s Compliance Assistance Programme (CAP) | Dec-14 | Dec-24 |
| Dominica DMI/PHA/84/TAS/25 | HCFC phase-out management plan (stage I, second tranche) | 0 |  | Dec-21 | Dec-24 |

# Regarding the implementation of HPMPs in Afghanistan and Myanmar, UNEP informed the Secretariat that due to the political situation in the countries, it is unable to communicate with the respective Government authorities and continue implementation of the projects. Further, the Secretariat received a request from the Government of Afghanistan to transfer the projects to UNIDO. In consultation with the agency, it was agreed that:

## The following UNEP components of the HPMP for Afghanistan would be transferred to UNIDO: (stage I, fourth tranche) (AFG/PHA/85/TAS/27) and (stage II, first tranche) (AFG/PHA/85/TAS/29) noting that:

### The final remaining balances would be confirmed by UNEP and returned to the 94th meeting to be transferred to UNIDO for implementation; and

### UNIDO will submit the updated Agreements for stage I and stage II of the HPMP together with the revised implementation plans to the 94thmeeting;

## The following projects for Myanmar would be cancelled and the remaining balances would be returned in line with decision 28/7: HPMP (stage I, first tranche) (MYA/PHA/68/TAS/14), HPMP (stage I, second tranche) (MYA/PHA/80/TAS/18), HPMP (stage I, third tranche) (MYA/PHA/86/TAS/23), HPMP preparation (stage II) (MYA/PHA/83/PRP/21), and HPMP verification report (MYA/PHA/86/TAS/24).

Gender mainstreaming

# UNEP promotes gender equality and empowerment of women through CAP activities in line with UNEP’s policy and strategy for gender equality and the environment and the Multilateral Fund’s operational policy on gender mainstreaming for projects funded by the Multilateral Fund. OzonAction’s Gender core team provides internal guidance to the CAP regional teams, monitors, and reports on gender mainstreaming in projects. OzonAction operationalizes its own internal plan which provides a comprehensive approach to gender mainstreaming, including both institutional (internal) and programmatic (external) actions. As part of the latter, UNEP has included gender considerations in all projects approved since June 2020 as per the Fund’s requirements. In order to help national ozone units implement the gender mainstreaming policy of the Fund, several products and initiatives were delivered under the CAP in 2022, such as the International Network of Women in Cooling (INWIC), Women in Cooling, A Worldwide Survey, and Gender Mainstreaming in the Montreal Protocol: Experiences in Latin America and the Caribbean. They are designed to support and complement gender mainstreaming activities organized as part of CAP regional activities and national project preparation and implementation. UNEP actively participated in the process of refining the gender mainstreaming requirements, activities, and corresponding indicators for MLF-funded projects. Based on the types of projects that are being implemented, UNEP implements relevant activities for gender mainstreaming.

II.	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2022, the Executive Committee had approved 79 HFC-related projects under the additional voluntary contributions amounting to US $8,122,853 (excluding agency support costs). A summary of the status of these projects is presented in table 6.

# Table 6. Status of approved HFC-related projects as of the end of 2022

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Technical assistance – Enabling activities | 79 | 78 | 99 | 8,122,853 | 6,995,029 | 1,127,824 | 86 |

* Excludes agency support costs.

# As of the end of 2022, of the 79 enabling activities approved, 78 had been completed. Extension of the completion date of the remaining ongoing enabling activities project was approved. This activity is expected to be completed in 2023.

# Of the total cumulative funding approved of US $8,122,853, US $6,995,029 had been disbursed, representing a disbursement rate of 86 per cent.

# Further to the review process, the ongoing project for enabling activities is classified as project with implementation delays and is included in annex III to the present document containing the Secretariat’s recommendation requesting the submission of a report to the 94th meeting.

III.	Recommendation

# The Executive Committee may wish:

## To note the progress report of UNEP as at 31 December 2022 contained in document UNEP/OzL.Pro/ExCom/93/17;

## To approve the extension, to 31 December 2024, of the completion date of stage I of the HCFC phase-out management plan (HPMP) for Dominica: first tranche (DMI/PHA/62/TAS/190) and second tranche (DMI/PHA/84/TAS/25), to allow for completion of the remaining ongoing activities as reflected in table 5 of document UNEP/OzL.Pro/ExCom/93/17;

## With regard to the HPMP for Afghanistan, to note:

### The request from the Government of Afghanistan to transfer to UNIDO the following projects: stage I, fourth tranche (AFG/PHA/85/TAS/27) and stage II, first tranche (AFG/PHA/85/TAS/29);

### That, at the 94th meeting, the remaining balances from the projects referred to in subparagraph (c)(i) above will be transferred from UNEP to UNIDO; and

### That UNIDO will submit the updated Agreements for stage I and stage II of the HPMP for Afghanistan together with the revised implementation plans to the 94thmeeting;

## To cancel the following projects of the HPMP for Myanmar and to request UNEP to return the remaining balances in line with decision 28/7: stage I, first tranche (MYA/PHA/68/TAS/14), stage I, second tranche (MYA/PHA/80/TAS/18), stage I, third tranche (MYA/PHA/86/TAS/23), preparation for stage II (MYA/PHA/83/PRP/21) and technical assistance for verification report (MYA/PHA/86/TAS/24); and

## To approve the recommendations related to ongoing projects with specific issues contained in annex III to the present document.

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNEP

PER COUNTRY FOR 2022

# Table 1 of annex I presents the status of project implementation by country for 2022 in planned and achieved disbursements and project completion.

Table 1. Status of project implementation by UNEP for 2022

| Country | Estimated funds disbursed in 2022 (US$) | Funds disbursed in 2022 (US$) | Percentage of funds disbursed over estimation in 2022 | Percentage of planned projects completed in 2022* |
| --- | --- | --- | --- | --- |
| Afghanistan | 305,972 | 134,314 | 44 | 0 |
| Albania | 98,824 | 106,724 | 108 | 100 |
| Angola | 141,016 | 0 | 0 | 0 |
| Antigua and Barbuda | 30,000 | 0 | 0 | 0 |
| Armenia | 42,500 | 102,000 | 240 |  |
| Bahamas (the) | 52,669 | 0 | 0 | 50 |
| Bahrain | 174,255 | 153,760 | 88 | 100 |
| Bangladesh | 193,578 | 24,348 | 13 | 50 |
| Barbados | 51,187 | 9,838 | 19 | 50 |
| Belize | 67,575 | 81,662 | 121 | 100 |
| Benin | 63,650 | 125,000 | 196 | 100 |
| Bhutan | 52,690 | 27,499 | 52 | 100 |
| Bolivia (Plurinational State of) | 56,475 | 0 | 0 |  |
| Botswana | 192,531 | 56,259 | 29 | 25 |
| Brunei Darussalam | 133,018 | 101,890 | 77 | 100 |
| Burkina Faso | 40,671 | 60,000 | 148 |  |
| Burundi | 71,250 | 50,000 | 70 | 100 |
| Cambodia | 104,853 | 181,330 | 173 | 50 |
| Cameroon | 133,718 | 89,068 | 67 |  |
| Cabo Verde | 58,250 | 15,000 | 26 |  |
| Central African Republic (the) | 30,000 | 60,000 | 200 | 100 |
| Chad | 16,250 | 65,000 | 400 | 100 |
| Chile | 129,322 | 62,615 | 48 | 0 |
| China | 1,456,655 | 1,133,245 | 78 | 0 |
| Colombia | 31,250 | 0 | 0 | 0 |
| Comoros (the) | 27,750 | 60,035 | 216 | 100 |
| Congo (the) | 43,750 | 105,130 | 240 | 0 |
| Cook Islands | 129,093 | 46,062 | 36 | 100 |
| Cote d’Ivoire | 20,000 | 100,000 | 500 |  |
| Democratic Republic of the Congo (the) | 66,250 | 94,800 | 143 |  |
| Djibouti | 16,135 | 2,020 | 13 | 100 |
| Dominica | 136,512 | 0 | 0 | 20 |
| Dominican Republic (the) | 107,688 | 133,676 | 124 | 0 |
| Egypt | 120,525 | 111,050 | 92 | 100 |
| El Salvador | 141,874 | 134,793 | 95 | 100 |
| Equatorial Guinea | 37,358 | 3,576 | 10 | 100 |
| Eritrea | 31,250 | 60,000 | 192 | 100 |
| Eswatini | 106,250 | 90,000 | 85 | 100 |
| Ethiopia | 109,250 | 55,000 | 50 | 100 |
| Fiji | 96,200 | 49,265 | 51 | 50 |
| Gabon | 42,250 | 114,515 | 271 | 100 |
| Gambia (the) | 99,750 | 61,000 | 61 |  |
| Ghana | 43,142 | 0 | 0 |  |
| Grenada | 74,160 | 43,601 | 59 | 100 |
| Guatemala | 75,834 | 7,337 | 10 |  |
| Guinea | 46,465 | 5,050 | 11 | 100 |
| Guinea-Bissau | 38,750 | 64,880 | 167 |  |
| Guyana | 76,790 | 11,753 | 15 | 0 |
| Haiti | 78,730 | 44,234 | 56 | 100 |
| Honduras | 51,250 | 77,765 | 152 | 100 |
| India | 369,187 | 449,488 | 122 | 50 |
| Iran (Islamic Republic of) | 228,152 | 107,266 | 47 | 50 |
| Iraq | 160,550 | 251,970 | 157 |  |
| Jamaica | 46,500 | 62,567 | 135 | 100 |
| Kenya | 97,067 | 92,688 | 95 | 100 |
| Kiribati | 171,965 | 53,574 | 31 | 100 |
| Kuwait | 879,751 | 948,300 | 108 | 100 |
| Kyrgyzstan | 50,462 | 95,466 | 189 | 100 |
| Lao People's Democratic Republic (the) | 125,649 | 62,251 | 50 | 50 |
| Lesotho | 22,750 | 0 | 0 |  |
| Liberia | 29,768 | 68,250 | 229 | 100 |
| Madagascar | 33,700 | 95,000 | 282 | 100 |
| Malawi | 82,904 | 119,938 | 145 | 100 |
| Maldives | 48,211 | 51,632 | 107 | 100 |
| Mali | 43,500 | 68,715 | 158 |  |
| Marshall Islands (the) | 73,089 | 13,274 | 18 | 100 |
| Mauritania | 40,000 | 79,845 | 200 | 100 |
| Mauritius | 21,250 | 0 | 0 |  |
| Mexico | 7,500 | 5,050 | 67 |  |
| Micronesia (Federated States of) | 150,794 | 66,872 | 44 | 100 |
| Mongolia | 110,103 | 84,567 | 77 |  |
| Mozambique | 51,187 | 85,375 | 167 | 100 |
| Myanmar | 106,102 | 255 | 0 | 0 |
| Namibia | 77,248 | 52,496 | 68 | 100 |
| Nauru | 85,803 | 10,909 | 13 | 67 |
| Nepal | 127,638 | 21,517 | 17 | 67 |
| Nicaragua | 89,441 | 62,017 | 69 | 0 |
| Niger (the) | 17,500 | 10,000 | 57 | 100 |
| Nigeria | 14,500 | 0 | 0 |  |
| Niue | 67,800 | 65,258 | 96 | 100 |
| Oman | 88,218 | 42,502 | 48 |  |
| Pakistan | 242,339 | 188,729 | 78 | 100 |
| Palau | 164,984 | 108,709 | 66 | 100 |
| Paraguay | 106,263 | 132,030 | 124 | 100 |
| Peru | 90,839 | 102,537 | 113 | 100 |
| Philippines (the) | 92,055 | 96,301 | 105 |  |
| Qatar | 141,735 | 153,920 | 109 | 100 |
| Republic of Moldova (the) | 50,128 | 58,463 | 117 |  |
| Rwanda | 89,000 | 35,000 | 39 |  |
| Saint Kitts and Nevis | 52,693 | 8,818 | 17 | 0 |
| Saint Lucia | 63,714 | 0 | 0 | 67 |
| Saint Vincent and the Grenadines | 127,543 | 45,479 | 36 | 50 |
| Samoa | 123,150 | 64,100 | 52 | 100 |
| Sao Tome and Principe | 76,355 | 59,571 | 78 | 0 |
| Saudi Arabia | 312,690 | 240,800 | 77 | 75 |
| Senegal | 162,465 | 135,679 | 84 |  |
| Serbia | 11,000 | 7,696 | 70 |  |
| Seychelles | 22,500 | 45,000 | 200 | 100 |
| Sierra Leone | 101,241 | 59,824 | 59 | 100 |
| Solomon Islands | 179,166 | 94,159 | 53 | 100 |
| Somalia | 21,250 | 0 | 0 |  |
| South Sudan | 52,500 | 20,000 | 38 | 67 |
| Sri Lanka | 118,708 | 29,769 | 25 |  |
| Sudan (the) | 93,284 | 93,200 | 100 | 100 |
| Suriname | 111,890 | 56,340 | 50 | 25 |
| Syrian Arab Republic | 157,714 | 64,784 | 41 |  |
| Timor-Leste | 88,539 | 82,359 | 93 | 67 |
| Togo | 52,100 | 173,080 | 332 | 100 |
| Tonga | 178,243 | 139,461 | 78 | 100 |
| Turkmenistan | 42,500 | 72,720 | 171 |  |
| Tuvalu | 66,152 | 47,943 | 72 | 100 |
| Uganda | 57,300 | 29,800 | 52 |  |
| United Republic of Tanzania (the) | 81,625 | 72,000 | 88 | 100 |
| Vanuatu | 153,392 | 45,764 | 30 | 100 |
| Viet Nam | 84,895 | 129,580 | 153 |  |
| Yemen | 85,000 | 0 | 0 | 0 |
| Zambia | 94,000 | 80,000 | 85 |  |
| Zimbabwe | 129,938 | 167,750 | 129 |  |
| Region: ASP | 162,500 | 22 | 0 | 100 |
| Global | 8,614,433 | 8,211,652 | 95 | 100 |
| Grand total | 21,719,273 | 18,395,175 | 85 | 67 |

* For projects that were planned to be completed in 2022.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION FOR UNEP

PER YEAR AS AT 31 DECEMBER 2022

# Table 1 of annex II presents an overview of the status of project implementation by year.  All projects and activities approved between 1991 and 2009, and in 2011 and 2013 have now been completed.

Table 1. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 11 | 11 | 100 | 1,372,335 | 1,372,335 | 0 | 100 |
| 1992 | 15 | 15 | 100 | 1,711,000 | 1,711,000 | 0 | 100 |
| 1993 | 49 | 49 | 100 | 4,194,343 | 4,194,343 | 0 | 100 |
| 1994 | 58 | 58 | 100 | 4,231,169 | 4,231,169 | 0 | 100 |
| 1995 | 50 | 50 | 100 | 4,047,683 | 4,047,683 | 0 | 100 |
| 1996 | 47 | 47 | 100 | 3,366,039 | 3,366,039 | 0 | 100 |
| 1997 | 87 | 87 | 100 | 7,962,291 | 7,962,291 | 0 | 100 |
| 1998 | 64 | 64 | 100 | 4,669,124 | 4,669,124 | 0 | 100 |
| 1999 | 87 | 87 | 100 | 6,368,983 | 6,368,983 | 0 | 100 |
| 2000 | 85 | 85 | 100 | 6,300,398 | 6,300,398 | 0 | 100 |
| 2001 | 59 | 59 | 100 | 7,411,159 | 7,411,159 | 0 | 100 |
| 2002 | 72 | 72 | 100 | 9,469,401 | 9,469,401 | 0 | 100 |
| 2003 | 78 | 78 | 100 | 11,165,394 | 11,165,394 | 0 | 100 |
| 2004 | 99 | 99 | 100 | 12,362,652 | 12,362,652 | 0 | 100 |
| 2005 | 72 | 72 | 100 | 12,339,483 | 12,339,483 | 0 | 100 |
| 2006 | 108 | 108 | 100 | 12,731,484 | 12,731,484 | 0 | 100 |
| 2007 | 79 | 79 | 100 | 14,611,111 | 14,611,111 | 0 | 100 |
| 2008 | 132 | 132 | 100 | 17,875,070 | 17,875,070 | 0 | 100 |
| 2009 | 115 | 115 | 100 | 17,250,876 | 17,250,876 | 0 | 100 |
| 2010 | 79 | 78 | 99 | 14,361,124 | 14,288,901 | 72,224 | 99 |
| 2011 | 100 | 100 | 100 | 16,782,433 | 16,782,434 | -2 | 100 |
| 2012 | 80 | 79 | 99 | 16,191,080 | 16,040,886 | 150,194 | 99 |
| 2013 | 90 | 90 | 100 | 14,152,112 | 14,152,112 | 0 | 100 |
| 2014 | 74 | 71 | 96 | 12,348,941 | 12,109,041 | 239,900 | 98 |
| 2015 | 180 | 178 | 99 | 21,386,100 | 21,073,292 | 312,809 | 99 |
| 2016 | 96 | 90 | 94 | 19,724,181 | 19,109,662 | 614,519 | 97 |
| 2017 | 57 | 53 | 93 | 12,588,345 | 12,303,025 | 285,320 | 98 |
| 2018 | 126 | 113 | 90 | 19,862,046 | 18,029,126 | 1,832,920 | 91 |
| 2019 | 110 | 88 | 80 | 15,111,761 | 13,219,948 | 1,891,813 | 87 |
| 2020 | 134 | 76 | 57 | 16,098,976 | 10,394,868 | 5,704,108 | 65 |
| 2021 | 127 | 17 | 13 | 23,088,170 | 11,174,097 | 11,914,073 | 48 |
| 2022 | 101 | 1 | 1 | 24,266,515 | 100,000 | 24,166,515 | 0 |
| Total | 2,721 | 2,401 | 88 | 385,401,777 | 338,217,387 | 47,184,390 | 88 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

Annex III

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNEP

| Country/project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Algeria ALG/SEV/90/INS/87 | Extension of the institutional strengthening project (phase VII: 7/2022-6/2024) | 0 | Slow progress | To request UNEP to report to the 94th meeting on implementation progress |
| Antigua and Barbuda ANT/PHA/73/PRP/17 | Preparation of a HCFC phase-out management plan (stage II) | 100 | Delay in the submission of stage II | Noting decision 77/8(j), to request UNEP to report to the 94th meeting on the status of preparation of stage II |
| Bangladesh BGD/PHA/81/TAS/50 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 0 | 12 and 18 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Barbados BAR/PHA/84/TAS/29 | HCFC phase-out management plan (stage I, third tranche) | 23 | 12 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Botswana BOT/PHA/82/TAS/22 | HCFC phase-out management plan (stage I, second tranche) | 50 | 12 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Botswana BOT/PHA/86/TAS/25 | HCFC phase-out management plan (stage I, third tranche) | 10 | 12 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Botswana BOT/PHA/86/TAS/26 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Brunei Darussalam BRU/SEV/82/TAS/01+ | Enabling activities for HFC phase-down | 41 | 12 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Burundi BDI/PHA/86/TAS/41 | Verification report on the implementation of stage I of the HCFC phase-out management plan | 0 | 18 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Cambodia KAM/PHA/83/TAS/35 | HCFC phase-out management plan (fourth tranche) | 91 | 12 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Chile CHI/PHA/76/TAS/191 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 58 | 12 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Chile CHI/PHA/81/TAS/195 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 44 | 12 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Congo (the) PRC/PHA/76/TAS/30 | HCFC phase-out management plan (stage I, third tranche) | 38 | 12 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Dominica DMI/PHA/62/TAS/19 | HCFC phase-out management plan (stage I, first tranche) | 12 | 12 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Dominica DMI/PHA/84/TAS/25 | HCFC phase-out management plan (stage I, second tranche) | 0 | 12 and 18 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Dominica DMI/PHA/86/TAS/26 | Verification report on the implementation of stage I of the HCFC phase-out management plan | 0 | 18 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Guyana GUY/PHA/83/TAS/31 | HCFC phase-out management plan (stage II, second tranche) | 33 | 12 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| India IND/PHA/91/TAS/502 | HCFC phase-out management plan (stage III, first tranche) (enabling activities) | 0 | 12 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Iran (Islamic Republic of) IRA/PHA/86/TAS/248 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | 0 | 18 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Maldives MDV/KIP/87/PRP/35 | Preparation of Kigali HFC implementation plan | 3 | Delays in the preparation and submission of stage I | To request UNEP to report to the 94th meeting on progress in the preparation of stage I |
| Marshall Islands (the) MAS/PHA/86/TAS/17 | HCFC phase-out management plan for PIC countries through regional approach (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Nauru NAU/PHA/86/TAS/14 | HCFC phase-out management plan for PIC countries through regional approach (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Nepal NEP/SEV/85/INS/40 | Extension of the institutional strengthening project (phase XI: 11/2020-10/2022) | 13 | Slow progress | To request UNEP to report to the 94th meeting on implementation progress |
| Nepal NEP/PHA/86/TAS/43 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Nepal NEP/PHA/88/TAS/45 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 0 | Slow progress | To request UNEP to report to the 94th meeting on progress in the preparation of the verification report |
| Nicaragua NIC/PHA/86/TAS/42 | HCFC phase-out management plan (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Pakistan PAK/SEV/81/TAS/97 | Enabling activities for HFC phase-down | 53 | 12 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Pakistan PAK/PHA/83/TAS/101 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | 47 | 12 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Pakistan PAK/PHA/90/TAS/114 | HCFC phase-out management plan (stage III, first tranche) (refrigeration servicing sector) | 0 | 12 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Saint Vincent and the Grenadines STV/PHA/75/TAS/23 | HCFC phase-out management plan (stage I, second tranche) | 67 | 12 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Saint Vincent and the Grenadines STV/PHA/86/TAS/26 | HCFC phase-out management plan (stage I, third tranche) | 0 | 18 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Sao Tome and Principe STP/PHA/81/PRP/28 | Preparation of a HCFC phase-out management plan (stage II) | 100 | Delay in the submission of stage II | Noting decision 77/8(j), to request UNEP to report to the 94th meeting on progress in the preparation of stage II |
| South Sudan SSD/SEV/76/INS/03 | Institutional strengthening project (phase I: 5/2016-4/2018) | 0 | Delay in project implementation | To request UNEP to report to the 94th meeting on implementation progress |
| Timor-Leste TLS/PHA/80/TAS/16 | HCFC phase-out management plan (stage II, first tranche) | 52 | 12 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Tuvalu TUV/PHA/86/TAS/17 | HCFC phase-out management plan for PIC countries through regional approach (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |
| Region: ASP ASP/PHA/86/TAS/63 | HCFC phase-out management plan for PIC countries through regional approach (stage II, first tranche) | 0 | 18 months delays | To request UNEP to report to the 94th meeting on this project with implementation delays |

*Codes ending with “+” are from the additional contributions.

UNEP/OzL.Pro/ExCom/93/1

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database that is available upon request.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 93rd meeting.

Ongoing projects are all projects that were under implementation as at 31 December 2022. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

In line with decision 84/12(b), a detailed progress report providing an overview of the objectives, status of implementation, key findings and lessons learned, the amounts of HFC phased out where applicable, the level of funds approved and disbursed and potential challenges in completing the projects and activities, is presented in the consolidated progress report (UNEP/OzL.Pro/ExCom/93/14).

All the controlled substances under these projects were ozone-depleting substances.

All the controlled substances under these projects were ozone-depleting substances.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61).

UNEP/OzL.Pro/ExCom/93/41

UNEP/OzL.Pro/ExCom/93/43

UNEP/OzL.Pro/ExCom/93/44

UNEP/OzL.Pro/ExCom/93/47

UNEP/OzL.Pro/ExCom/93/48

UNEP/OzL.Pro/ExCom/93/54

UNEP/OzL.Pro/ExCom/93/57

UNEP/OzL.Pro/ExCom/93/58

UNEP/OzL.Pro/ExCom/93/71

UNEP/OzL.Pro/ExCom/93/73

UNEP/OzL.Pro/ExCom/93/79

UNEP/OzL.Pro/ExCom/93/83

UNEP/OzL.Pro/ExCom/93/84

UNEP/OzL.Pro/ExCom/93/86

UNEP/OzL.Pro/ExCom/93/88

UNEP/OzL.Pro/ExCom/93/20 or UNEP/OzL.Pro/ExCom/93/21

UNEP/OzL.Pro/ExCom/93/24

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of the project completion date, noting that no new commitments were to be made before the extension had been approved.

As per the letter of 9 November 2023 from the National Environmental Protection of Afghanistan to the Secretariat.

The Executive Committee requested bilateral and implementing agencies to provide a brief report on key gender mainstreaming results achieved as part of their annual progress reports, as of 2023, on the basis of the information available to them (decision 90/48(d)).

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.