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اللجنــة التنفيـذيــــة للصنــدوق المــتعــدد الأطـــراف
لتنفيـــذ بروتوكـول مونتريــال 
الاجتمــــــاع الثالث والتسعــــون 
[bookmark: _Hlk128756171]مونتريال، 15 - 19 ديسمبر / كانون الأول 2023
البند 8 (أ) من جدول الأعمال المؤقت[footnoteRef:1] [1:  الوثيقة UNEP/OzL.Pro/ExCom/93/1] 



تحديث لحالة تنفيذ خطة العمل الموحدة للصندوق المتعدد الأطراف
 للفترة 2023-2025


مقدمة

1. تتكون هذه الوثيقة من الأقسام التالية:
أولاً: 	 تحديث لحالة تنفيذ خطة العمل للفترة 2023-2025

ثانيا: 	تخصيص الموارد لفترة الثلاث سنوات 2021-2023

ثالثا: 	التوصية

أولاً: 	تحديث بشأن حالة تنفيذ خطة العمل للفترة 2023-2025

في اجتماعها الحادي والتسعين، أقرت اللجنة التنفيذية خطة العمل الموحدة للصندوق المتعدد الأطراف للفترة 2023-2025. واستجابة للمقرر 91/31، عدلت الأمانة خطة العمل الموحدة للفترة 2023-2025، على النحو المبين في الجدول 1.


الجدول 1- تخصيص الموارد لخطة العمل الموحدة المعدلة للصندوق المتعدد الأطراف للفترة 2023-2025 (بالدولار الأمريكي)*
	الوصف
	2023
	2024
	2025
	المجموع

	أنشطة المواد الهيدروكلوروفلوروكربونية

	خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية 
	60,280,861
	56,111,450
	43,084,350
	159,476,661

	إعداد مشروع خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية - المرحلة الثانية
	200,480
	77,600
	0
	278,080

	المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية
	2,937,082
	5,199,804
	3,462,199
	11,599,085

	المرحلة الثانية من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية – الاستثمارية
	0
	248,532
	0
	248,532

	إعداد مشروع خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية – المرحلة الثالثة
	290,100
	92,750
	0
	382,850

	المرحلة الثالثة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية
	14,794,713
	10,344,520
	20,526,731
	45,665,964

	إعداد مشروع خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية – المرحلة الرابعة
	90,000
	0
	0
	90,000

	المرحلة الرابعة من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية
	0
	0
	2,093,000
	2,093,000

	من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية – كفاءة استخدام الطاقة
	3,258,494
	2,672,980
	3,379,420
	9,310,894

	التحقق من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية**
	588,600
	588,600
	588,600
	1,765,800

	المجموع الفرعي لأنشطة المواد الهيدروكلوروفلوروكربونية
	82,440,330
	75,336,236
	73,134,299
	230,910,865

	أنشطة المواد الهيدروفلوروكربونية

	الأنشطة التمكينية للتخفيض التدريجي للمواد الهيدروفلوروكربونية
	53,500
	160,500
	0
	214,000

	خطط تنفيذ تعديل كيغالي للمواد الهيدروفلوروكربونية – إعداد المشروعات
	3,945,431
	2,567,011
	144,560
	6,657,002

	خطط تنفيذ تعديل كيغالي للمواد الهيدروفلوروكربونية
	27,299,967
	21,437,607
	245,413
	48,982,987

	إعداد مشروعات خطط تنفيذ تعديل كيغالي للمواد الهيدروفلوروكربونية – الاستثمارية
	129,000
	0
	0
	129,000

	إعداد مشروعات خطط تنفيذ تعديل كيغالي للمواد الهيدروفلوروكربونية - الاستثمارية
	321,000
	8,963,616
	0
	9,284,616

	إعداد مشروعات التحكم في انبعاثات الهيدروفلوروكربون-23 
	43,000
	0
	0
	43,000

	التحكم في انبعاثات الهيدروفلوروكربون-23 
	0
	8,000,000
	0
	8,000,000

	الهيدروفلوروكربون – المساعدة الفنية
	0
	678,000
	0
	678,000

	المجموع الفرعي لأنشطة المواد الهيدروفلوروكربونية
	31,791,898
	41,806,734
	389,973
	73,988,605

	مشروع تجريبي لكفاءة استخدام الطاقة

	مشروع تجريبي لكفاءة استخدام الطاقة
	20,000,000
	0
	0
	20,000,000

	المجموع الفرعي للمشروع التجريبي لكفاءة استخدام الطاقة 
	20,000,000
	0
	0
	20,000,000

	الأنشطة القياسية

	التعزيز المؤسسي 
	27,860,444
	16,639,896
	0
	44,500,341

	برنامج المساعدة على الامتثال 
	11,445,002
	11,788,350
	12,142,003
	35,375,355

	الوحدة الأساسية
	5,969,740
	6,011,529
	6,053,610
	18,034,878

	تكاليف السكرتارية واللجنة التنفيذية والرصد والتقييم مطروحًا منها نظيرتها الكندية
	7,237,326
	7,202,023
	6,816,624
	21,255,973

	أمين الخزانة
	500,000
	500,000
	500,000
	1,500,000

	المجموع الفرعي للأنشطة القياسية 
	53,012,512
	42,141,798
	25,512,237
	120,666,547

	المجموع الكلي
	187,244,740
	159,284,767
	99,036,509
	445,566,017

	أستراليا
	0
	0
	152,497
	152,497

	النمسا
	783,667
	0
	0
	783,667

	فرنسا
	671,075
	0
	0
	671,075

	ألمانيا
	1,349,869
	3,705,721
	1,028,250
	6,083,840

	اليابان
	67,800
	0
	0
	67,800

	برنامج الأمم المتحدة الإنمائي
	62,425,117
	54,216,500
	29,064,016
	145,705,634

	برنامج الأمم المتحدة للبيئة
	40,325,066
	36,674,895
	22,071,085
	99,071,046

	اليونيدو
	38,767,526
	29,078,890
	29,553,746
	97,400,162

	البنك الدولي
	14,528,694
	27,318,138
	9,261,691
	51,108,523

	التحقق من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية**
	588,600
	588,600
	588,600
	1,765,800

	مشروع تجريبي لكفاءة استخدام الطاقة
	20,000,000
	0
	0
	20,000,000

	تكاليف السكرتارية واللجنة التنفيذية والرصد والتقييم مطروحًا منها نظيرتها الكندية
	7,237,326
	7,202,023
	6,816,624
	21,255,973

	أمين الخزانة
	500,000
	500,000
	500,000
	1,500,000


* شاملا تكاليف دعم الوكالة حيثما ينطبق ذلك.
** توافق اللجنة التنفيذية على تمويل إعداد تقارير التحقق لخطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية للبلدان ذات حجم الاستهلاك المنخفض على أساس سنوي.
أولا-1- 	حالة تنفيذ خطة العمل لعام 2023

يصل إجمالي قيم خطة العمل لعام 2023 إلى 187,244,740 دولارًا أمريكيًا. ومن هذا المبلغ، تمت اعتماد المبلغ 29,253,988 دولارًا أمريكيًا في الاجتماع الثاني والتسعين. وبالإضافة إلى ذلك، سيتم النظر في الأنشطة التي تصل قيمتها إلى 108,304,705 دولارا أمريكيا في الاجتماع الثالث والتسعين؛ وإذا تمت الموافقة على تمويل جميع مقترحات المشروعات المقدمة على النحو المطلوب، سيتم توفير رصيد قدره 49,686,047 دولارًا أمريكيًا من خطة العمل لعام 2023، على النحو الموضح في الجدول 2.
الجدول 2- خطة العمل الموحدة لعام 2023 والاعتمادات في الاجتماع الثاني والتسعين والمشروع الموصي به في الاجتماع الثالث والتسعين والرصيد (بالدولار الأمريكي) *
	بنود الميزانية
	القيمة الإجمالية في خطة العمل
	الموافقات في الاجتماع الثاني والتسعين
	الأنشطة الموصي بها للاجتماع الثالث والتسعين
	الرصيد 
(أعلى) / أقل

	الوكالات الثنائية
	2,872,411
	687,988
	1,657,265
	527,158

	اليوئنديبي
	62,425,117
	10,211,836
	28,591,500
	23,621,781

	اليونيب
	40,325,066
	6,644,731
	22,767,524
	10,912,811

	اليونيدو
	38,767,526
	8,419,645
	24,134,585
	6,213,296

	بنك عالمي
	14,528,694
	2,681,989
	15,997,224
	(4,150,519)

	التحقق من خطة إدارة إزالة المواد الهيدروكلوروفلوروكربونية
	588,600
	573,900
	0
	14,700

	مشروع تجريبي لكفاءة استخدام الطاقة
	20,000,000
	33,900
	7,419,281
	12,546,819

	المجموع الفرعي (الوكالات)
	179,507,414
	29,253,988
	100,567,379
	49,686,047

	الأمانة / اللجنة التنفيذية/ الرصد والتقييم (باستثناء النظير الكندي)
	7,237,326
	0
	7,237,326
	0

	أمين الخزانة
	500,000
	0
	500,000
	0

	المجموع الفرعي (التكاليف القياسية)
	7,737,326
	0
	7,737,326
	0

	المجموع
	187,244,740
	29,253,988
	108,304,705
	49,686,047


* شاملا تكاليف الوحدة الأساسية.

قيمة مقترحات المشروعات الموصي بها للاجتماع الثالث والتسعين وقدرها 100,567,379 دولارًا أمريكيًا أعلى بحوالي 16,578,316 دولارًا أمريكيًا من قيمتها المذكورة في خطة العمل لعام 2023 وتشمل المبلغ 12,521,905 دولارًا أمريكيًا المرتبط بمقترحات مشروعات غير مدرجة في خطة العمل لعام 2023.[footnoteRef:2]  [2:  المرحلة الثانية من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية لبوليفيا ( دولة - المتعددة القوميات) (اليونيب واليونيدو)، وإكوادور (اليونيدو)، وغواتيمالا (اليونيب واليونيدو)، وموزامبيق (اليوئنديبي)، ومقدونيا الشمالية (اليونيدو)؛ والمرحلة الثالثة من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية لفييت نام (البنك الدولي)؛ وإعداد مشروع واحد للمرحلة الثالثة من خطط إدارة إزالة المواد الهيدروكلوروفلوروكربونية لبيرو (اليوئنديبي)؛ وإعداد مشروع واحد استثماري لإدارة إزالة المواد الهيدروكلوروفلوروكربونية في تايلند (البنك الدولي)؛ وإعداد مشروع واحد توضيحي للهند (اليوئنديبي)؛ وخمسة أعمال إعداد خطة تنفيذ تعديل كيغالي لمشروعات استثمارية في كولومبيا (2) (اليوئنديبي)، ولبنان (اليوئنديبي)، ومنغوليا (اليونيدو)، وسري لانكا (اليوئنديبي)؛ وإعداد ثمانية مشروعات للمرحلة الأولى من خطط تنفيذ تعديل كيغالي للبرازيل (ألمانيا واليوئنديبي واليونيدو)، وكينيا (ألمانيا)، ومالي (اليوئنديبي واليونيب)، وسانت فنسنت وجزر غرينادين (اليونيب واليونيدو)؛ وثلاثة مشروعات استثمارية للمواد الهيدروفلوروكربونية في الهند (اليوئنديبي)؛ و12 مشروعاً لكفاءة استخدام الطاقة بموجب المقرر 89/6 لألبانيا (اليونيدو)، وبنن (اليونيدو)، وبوليفيا (دولة - المتعددة القوميات ) (اليونيب واليونيدو)، وإكوادور (اليونيدو)، وغرينادا (اليونيدو)، وغواتيمالا (اليونيب واليونيدو)، وليسوتو (ألمانيا)، وليبريا (ألمانيا)، وناميبيا (ألمانيا)، وسيشيل (ألمانيا)؛ والمرحلة الأولى من خطط تنفيذ تعديل كيغالي لبوليفيا ( دولة - متعددة القوميات) (اليونيب)، والكونغو (اليونيب واليونيدو)، والجمهورية الدومينيكية (اليونيب واليونيدو)، وقيرغيزستان (اليوئنديبي)، ونيكاراغوا (اليونيب)، والنيجر (اليونيب واليونيدو) وبيرو (اليوئنديبي)؛ ومشروع التعزيز المؤسسي لبوليفيا ( دولة - متعددة القوميات ) (اليونيب)؛ وإعداد 37 مشروعاً لقوائم الجرد الوطنية لبنوك المواد الخاضعة للرقابة بموجب المقرر 91/66 وفقاً للمرفق الثالث.] 

وتبلغ قيمة الأنشطة المتعلقة بالمواد الهيدروفلوروكربونية الموصي بها في الاجتماع الثالث والتسعين 23,789,140 دولارًا أمريكيًا، ومنها المبلغ 3,182,574 دولارًا أمريكيًا المرتبط بمقترحات المشروعات غير المدرجة في خطة العمل لعام 2023. ويدرج المرفق الأول بهذه الوثيقة قائمة بالمشروعات المتعلقة بالمواد الهيدروفلوروكربونية المقدمة من الوكالات الثنائية والوكالات المنفذة إلى الاجتماع الثالث والتسعين.
وتبلغ قيمة المشروعات الموصي بها في إطار نافذة التمويل للمشروعات التجريبية لكفاءة استخدام الطاقة عملاً بالمقرر 91/65 7,419,281 دولارًا أمريكيًا. ومع الأخذ في الاعتبار الاعتمادات في الاجتماع الثاني والتسعين وقدرها 33,900 دولارا أمريكيا والقيم الموصي بها في الاجتماع الثالث والتسعين، يكون التمويل المتبقي المتاح في إطار نافذة التمويل 12,546,819 دولارا أمريكيا. ويتضمن المرفق الثاني بهذه الوثيقة قائمة بالمشروعات التجريبية المقدمة من الوكالات الثنائية والوكالات المنفذة إلى الاجتماع الثالث والتسعين عملاً بالمقرر 91/65.
وتبلغ قيمة المشروعات الموصي بها في إطار نافذة التمويل لإعداد قوائم الجرد الوطنية لبنوك المواد الخاضعة للرقابة بموجب القرار 91/66، 3,222,500 دولارا أمريكيا وهي غير مدرجة في خطة العمل لعام 2023. ويتضمن المرفق الثالث بهذه الوثيقة قائمة بأنشطة إعداد المشروعات المقدمة من الوكالات الثنائية والوكالات المنفذة إلى الاجتماع الثالث والتسعين عملاً بالمقرر 91/66.
بالإضافة إلى ذلك، فيما يتعلق بالمقرر 91/66، تشترط الفقرة (ج)(3) الذي يتطلب تقديم المشروعات في إطار نافذة التمويل المذكورة أعلاه لكي تنظر فيها اللجنة التنفيذية اعتباراً من الاجتماع الثالث والتسعين حتى الاجتماع السابع والتسعين، وتشمله، على أساس أنه سيتم إدراجها في خطط العمل ذات الصلة قبل اعتمادها. وأثناء المناقشات مع الوكالات في اجتماعات الشبكة، أبلغت الوكالات الأمانة بأن بلدان المادة 5 تحتاج إلى مزيد من الوقت لفهم الجوانب المختلفة لإدارة المواد الخاضعة للرقابة غير المرغوب فيها وتحتاج إلى مزيد من المعلومات من الوكالات أثناء اجتماعات الشبكة قبل الموافقة على إدراج هذه الأنشطة في خطط الأعمال الخاصة بكل منهما؛ واستغرق هذا وقتًا أطول من المتوقع. واستنادًا إلى المدخلات والمشاورات الإضافية التي أجريت خلال الأشهر القليلة الماضية بما في ذلك خلال الاجتماع الخامس والثلاثين للأطراف الذي عقد في أكتوبر/ تشرين الأول 2023، أعربت البلدان عن اهتمامها بتقديم المشروعات في إطار نافذة التمويل هذه. ومن أجل تسهيل تقديم المشروعات المتعلقة بإعداد قوائم جرد بنوك المواد الخاضعة للرقابة المستخدمة أو غير المرغوب فيها، قد ترغب اللجنة التنفيذية، استثنائيا، في السماح للوكالات الثنائية والمنفذة بتقديم أنشطة إعداد المشروعات في إطار نافذة التمويل المنشأة عملاً بالقرار 91/66 خلال عام 2024، حتى في الحالات التي لا يتم فيها تضمين هذه الأنشطة في خطط العمل.
تم تقديم مقترحات المشروعات بقيمة 54,097,185 دولارًا أمريكيًا[footnoteRef:3] التي تم تضمينها في خطة العمل لعام 2023، إلى الاجتماع الثالث والتسعين. وأُدرجت هذه المقترحات في خطة العمل الموحدة للصندوق المتعدد الأطراف للفترة 2024-2026.[footnoteRef:4] [3:  تشمل هذه الأنشطة ما يلي: 104 نشاطا متعلقا بالمواد الهيدروكلوروفلوروكربونية لعدد 40 بلدا (32.37 مليون دولارا أمريكي)، و49 نشاطًا متعلقًا بالمواد الهيدروفلوروكربونية لعدد 34 بلدا (12.26 مليون دولارا أمريكيا)، و28 نشاطا للتعزيز المؤسسي (9.47 مليون دولارا أمريكيا).]  [4:  الوثيقة UNEP/OzL.Pro/ExCom/93/25] 

أولا-2- 	الالتزامات الآجلة
قيمة المبلغ الإجمالي للالتزامات الآجلة الحالية للاتفاقات المتعددة السنوات للفترة من 2023 إلى 2031 هي 314.16 مليون دولارا أمريكيا، بافتراض أنه ستتم الموافقة من حيث المبدأ على طلبات تمويل الاتفاقات المتعددة السنوات المقدمة إلى الاجتماع الثالث والتسعين، على النحو المبين في الجدول 3.
الجدول 3- الالتزامات الآجلة (2023-2031) (000 دولارا أمريكيا)
	الوصف
	2023
	2024
	2025
	2026
	2027
	2028
	2029
	2030
	2031
	المجموع

	الموافق عليها من حيث المبدأ
	68,086
	53,334
	51,015
	42,781
	10,187
	5,852
	4,733
	8,163
	57
	244,207

	المقدمة إلى الاجتماع الثالث والتسعين
	27,918
	0
	10,122
	14,050
	10,623
	24
	5,528
	1,683
	0
	69,949

	المجموع
	96,005
	53,334
	61,137
	56,831
	20,811
	5,876
	10,261
	9,846
	57
	314,156


ثانيا: 	تخصيص الموارد لفترة الثلاث سنوات 2021-2023

حتى 8 نوفمبر/ تشرين الثاني 2023، بلغ الرصيد المتاح في الصندوق المتعدد الأطراف 277,322,098 دولارًا أمريكيًا، مع مساهمة مستحقة لم يتم سدادها قدرها 52,864,962 دولارًا أمريكيًا لفترة الثلاث سنوات 2021-2023، ومن غير المتوقع تحصيل 23,281,488 دولارًا أمريكيًا منها.[footnoteRef:5] وبعد 8 نوفمبر/ تشرين الثاني 2023، تقدر الفوائد المحتملة المتراكمة والخسارة المحتملة بسبب آلية سعر الصرف الثابت بقيمة 5,849,812 دولارًا أمريكيًا و753,989 دولارًا أمريكيًا، على التوالي. بالإضافة إلى ذلك، بلغت الأموال المعادة للمشروعات المنجزة والفوائد المعادة إلى الاجتماع الثالث والتسعين 4,669,316 دولارًا أمريكيًا[footnoteRef:6]  و505,720 دولارًا أمريكيًا [footnoteRef:7]، على التوالي. وبناء على ذلك، يكون إجمالي التمويل الذي يمكن أن يكون متاحا للمخصصات الجديدة في الاجتماع الثالث والتسعين317,176,431  دولار أمريكي. [5:  الوثيقة UNEP/OzL.Pro/ExCom/93/3]  [6:  الوثيقتانUNEP/OzL.Pro/ExCom/93/4  و  UNEP/OzL.Pro/ExCom/93/95.]  [7:  الوثيقتان UNEP/OzL.Pro/ExCom/93/6  و  UNEP/OzL.Pro/ExCom/93/47.] 

ونظراً لقيمة التمويل الموصي به للمشروعات المقدمة إلى الاجتماع الثالث والتسعين وقدرها 100,567,379 دولاراً أمريكياً وميزانية الأمانة وقدرها 7,737,326 دولاراً أمريكياً، ستكون الموارد المتاحة في نهاية فترة الثلاث سنوات 2021-2023 قدرها 208,871,726 دولاراً أمريكياً. بالإضافة إلى ذلك، أشار الاجتماع الاستثنائي الخامس للأطراف أيضاً إلى أن المبلغ 246 مليون دولارا أمريكيا من الأموال المتبقية التي كانت مستحقة للصندوق المتعدد الأطراف خلال فترة الثلاث سنوات 2018-2020 سيتم استخدامه بعد عام 2023 لدعم تنفيذ بروتوكول مونتريال (المقررEx.V/1). لذلك، يكون إجمالي الموارد المتاحة لفترة الثلاث سنوات 2024-2026 قدره 454,871,726 دولارًا أمريكيًا، على النحو المبين في الجدول 4.
الجدول 4- تخصيص الموارد لفترة الثلاث سنوات 2021-2023 (بالدولار الأمريكي)
	الوصف
	 
	المبلغ
 )بالدولار الأمريكي(

	التمويل المتاح

	الرصيد متاح حتى 8  نوفمبر/ تشرين الثاني 2023
	(أ)
	277,322,098

	المساهمات المعلقة للقترة من 2021 إلى 2023
	(ب)
	52,864,962

	المساهمات المعلقة التي لا يتوقع تحصيلها
	(ج)
	(23,281,488)

	الفوائد المحتملة المتراكمة بعد8  نوفمبر/ تشرين الثاني 2023
	 (د)
	5,849,812

	الخسارة المحتملة بسبب آلية سعر الصرف الثابت بعد 8  نوفمبر/ تشرين الثاني 2023
	(هـ)
	(753,989)

	الأموال المعادة في الاجتماع 93
	(و)
	4,669,316

	الفائدة المعادة في الاجتماع الثالث والتسعين
	(ز)
	505,720

	إجمالي التمويل المتاح
	(ح  = أ+ب+ج+د+هـ+و+ز) 
	317,176,431

	النفقات

	المشروعات الموصي بها للاجتماع الثالث والتسعين
	(ط)
	100,567,379

	السكرتارية /اللجنة التنفيذية/ الرصد/ أمين الخزانة
	)ي)
	7,737,326

	إجمالي النفقات
	(ك =  ط + ي)
	108,304,705

	الموارد المتاحة في نهاية عام 2023
	(ل =  ح - ك)
	208,871,726

	المبالغ المُرحَّلة من فترة الثلاث سنوات2018-2020  لاستخدامها بعد عام 2023
	(م)
	246,000,000

	إجمالي الموارد المتاحة لفترة الثلاث سنوات 2024-2026
	(ن = ل+م)
	454,871,726





ثالثا: 	التوصية

قد ترغب اللجنة التنفيذية في:
أن تحيط علما بما يلي:
تحديث حالة تنفيذ خطة العمل الموحدة للصندوق المتعدد الأطراف للفترة 2023-2025 على النحو الوارد في الوثيقة UNEP/OzL.Pro/ExCom/93/23؛
تبلغ القيمة الإجمالية للأنشطة على النحو المطلوب في الاجتماع الثالث والتسعين 100,567,379 دولارًا أمريكيًا (تشمل 23,789,140 دولارًا أمريكيًا للأنشطة المتعلقة بالمواد الهيدروفلوروكربونية، و7,419,281 دولارًا أمريكيًا للمشروعات التجريبية لكفاءة استخدام الطاقة و3,222,500 دولارًا أمريكيًا لإعداد قوائم الجرد الوطنية لبنوك نفايات المواد الخاضعة للرقابة)، منها المبلغ 12,521,905 دولارًا أمريكيًا المرتبط بمقترحات المشروعات غير المدرجة في خطة العمل لعام 2023؛
وأن تسمح، استثنائيا، للوكالات الثنائية والمنفذة بتقديم مشروعات، خلال عام 2024، لإعداد قوائم جرد وطنية لبنوك نفايات المواد الخاضعة للرقابة في إطار نافذة التمويل المنشأة عملا بالمقرر 91/66، حتى في حالات المشروعات غير المدرجة في خطط عمل الوكالات.
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إن وثائق ما قبل دورات اللجنة التنفيذية للصندوق المتعدد الأطراف لتنفيذ بروتوكول مونتريال 
قد تصدر دون إخلال بأي قرار تتخذه اللجنة التنفيذية بعد صدورها. 
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Annex I

HFC-RELATED ACTIVITIES SUBMITTED TO THE 93RD MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Albania
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	50,000
	6,500

	Albania
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	129,390
	9,057

	Bolivia (Plurinational State of)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	40,500
	5,265

	Bolivia (Plurinational State of)
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	153,500
	10,745

	Brazil
	Germany
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	40,000
	5,200

	Brazil
	UNDP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	126,500
	8,855

	Brazil
	UNIDO
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	63,500
	4,445

	Cambodia
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	123,810
	11,143

	Cambodia
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	126,300
	16,419

	Chile
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	752,607
	52,683

	Chile
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	123,900
	16,107

	Colombia
	UNDP
	PRP
	KIP
	Preparation of a KIP investment project in the air-conditioning manufacturing sector
	50,000
	3,500

	Colombia
	UNDP
	PRP
	KIP
	Preparation of a KIP investment project in the refrigeration manufacturing sector
	150,000
	10,500

	Congo (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	13,750
	1,788

	Congo (the)
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	67,750
	6,098

	Cuba
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	145,455
	10,182

	Cuba
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	14,545
	1,018

	Dominican Republic (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	120,774
	15,701

	Dominican Republic (the)
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	50,050
	4,505

	Dominican Republic (the)
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	320,935
	22,465

	Dominican Republic (the)
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	44,171
	3,092

	Ecuador
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	292,600
	20,482

	Egypt
	UNDP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	40,000
	2,800

	Egypt
	UNIDO
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	180,000
	12,600

	Eritrea
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	91,000
	11,830

	Eritrea
	UNIDO
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	39,000
	2,730

	Georgia
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	130,000
	16,900

	Ghana
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	125,000
	11,250

	Ghana
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	51,000
	6,630

	Ghana
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	7,500
	675

	Ghana
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	4,500
	585

	Grenada
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	29,670
	2,670

	Grenada
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	42,830
	5,568

	India
	UNDP
	INV
	KIP
	Conversion from R-407C and R-410A to HFC-32 in the manufacturing of light commercial air-conditioning packaged and ducted air-conditioning units at Voltas Limited
	422,561
	29,579

	India
	UNDP
	INV
	KIP
	Conversion of the manufacturing of commercial refrigeration appliances at Rockwell Industries Limited from HFC‑134a to propane (R-290)
	423,765
	29,664

	India
	UNDP
	INV
	KIP
	Demonstration/conversion from R-404A and R-407C to CO2 transcritical heat pump technology in the food processing and cold storage refrigeration equipment manufacturing sector at Mech Air Industries
	322,452
	22,572

	India
	UNDP
	PRP
	KIP
	Preparation of a demonstration project in the manufacture of compressors for mobile air-conditioning manufacturing sector
	30,000
	2,100

	Jordan
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	2,540,680
	177,848

	Kenya
	Germany
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	95,000
	12,350

	Kenya
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	95,000
	12,350

	Kyrgyzstan
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	51,000
	4,590

	Kyrgyzstan
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	30,000
	3,900

	Lebanon
	UNDP
	PRP
	PHA
	Preparation of a KIP investment project in the refrigeration manufacturing sector
	70,000
	4,900

	Malawi
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	39,000
	5,070

	Malawi
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	29,000
	2,610

	Malaysia
	IBRD
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	3,042,912
	213,004

	Mali
	UNDP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	35,000
	2,450

	Mali
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	135,000
	17,550

	Mexico
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring)
	79,905
	5,593

	Mexico
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring)
	12,695
	1,574

	Mexico
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (coordination and monitoring)
	283,418
	19,839

	Mexico
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (foam sector plan)
	888,833
	62,218

	Mexico
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (servicing sector)
	465,000
	32,550

	Mexico
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (servicing sector)
	215,100
	26,669

	Mexico
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (servicing sector)
	4,801,972
	336,138

	Mongolia
	UNIDO
	PRP
	KIP
	Preparation of a KIP investment project in the foam sector
	80,000
	5,600

	Nicaragua
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	40,000
	5,200

	Nicaragua
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	159,000
	14,310

	Niger (the)
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I)
	15,000
	1,950

	Niger (the)
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I)
	35,000
	850

	North Macedonia
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	103,555
	9,320

	Panama
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	331,100
	23,177

	Peru
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	283,140
	19,820

	Republic of Moldova (the)
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	130,000
	16,900

	Saint Vincent and the Grenadines
	UNEP
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	70,000
	9,100

	Saint Vincent and the Grenadines
	UNIDO
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	30,000
	2,100

	Sri Lanka
	UNDP
	PRP
	KIP
	Preparation of a KIP investment project in the refrigeration manufacturing sector
	80,000
	5,600

	Thailand
	IBRD
	PRP
	PHA
	Preparation of a Kigali HFC implementation plan (stage I)
	220,000
	15,400

	Trinidad and Tobago
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	496,973
	34,788

	Trinidad and Tobago
	UNDP
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	46,276
	3,239

	Turkmenistan
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche)
	106,000
	7,420

	Turkmenistan
	UNIDO
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	10,000
	700

	Viet Nam
	IBRD
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (manufacturing sector)
	289,220
	20,245

	Viet Nam
	IBRD
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	119,265
	8,349

	Viet Nam
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (PMU)
	35,533
	4,244

	Viet Nam
	IBRD
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (servicing sector)
	984,000
	68,880

	Viet Nam
	UNEP
	TAS
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (servicing sector)
	426,163
	50,906

	Viet Nam
	IBRD
	INV
	KIP
	Kigali HFC implementation plan (stage I, first tranche) (technical assistance and policy)
	165,307
	11,571
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Annex II

PILOT PROJECTS FOR ENERGY EFFICIENCY (DECISION 91/65) 
SUBMITTED TO THE 93RD MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Bolivia (Plurinational State of)
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	96,000
	8,640

	Chile
	UNDP
	PRP
	EEF
	Preparation of a pilot project for the use of R-744 (carbon dioxide) as an alternative refrigerant in heat pumps in industrial refrigeration (decision 91/65)
	30,000
	2,100

	China
	UNIDO
	DEM
	EEF
	Demonstration project of replacing HFC‑134a with R-744 in the field of electric vehicles (decision 91/65)
	1,371,500
	96,005

	Ecuador
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	190,000
	17,100

	Egypt
	UNIDO
	DEM
	EEF
	Energy efficiency pilot project in the refrigeration and air-conditioning sector (decision 91/65)
	285,000
	19,950

	India
	Germany
	DEM
	EEF
	Design and development of a pilot scale energy-efficient rotary compressor along with microchannel heat exchanger compatible with R-290 technology at Godrej & Boyce Mfg. Ltd., for use in manufacturing of room air conditioners (decision 91/65)
	1,853,795
	213,918

	India
	UNDP
	DEM
	EEF
	Conversion of the manufacturing of commercial refrigeration appliances at Rockwell Industries Limited from HFC‑134a to propane (R-290) (technical assistance to enhance the energy efficiency of the converted equipment) (decision 91/65)
	150,000
	13,500

	Kenya
	Germany
	PRP
	EEF
	Preparation for a pilot project on energy efficiency (decision 91/65)
	30,000
	3,900

	Kyrgyzstan
	UNEP
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	206,000
	26,780

	Malaysia
	IBRD
	PRP
	EEF
	Preparation for a pilot project on energy efficiency in stand-alone commercial refrigeration sector (decision 91/65)
	30,000
	2,100

	Mexico
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	938,620
	65,703

	Nicaragua
	UNEP
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	30,000
	3,900

	Nicaragua
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	66,000
	5,940

	Nigeria
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	145,000
	13,050

	South Africa
	UNIDO
	DEM
	EEF
	Energy efficiency-related activities (decision 91/65)
	1,120,000
	78,400

	Togo
	Germany
	PRP
	EEF
	Project preparation for energy efficiency‑related activities (decision 91/65)
	30,000
	3,900

	Turkmenistan
	UNIDO
	DEM
	EEF
	Pilot project for maintaining and enhancing energy efficiency of replacement technologies and equipment (decision 91/65)
	142,000
	12,780

	Viet Nam
	IBRD
	PRP
	EEF
	Preparation for a pilot project on energy efficiency in the air-conditioning sector (decision 91/65)
	30,000
	2,100

	Global
	UNDP
	PRP
	EEF
	Preparation for a pilot project for digital monitoring and management tools to enhance energy efficiency and reduce emission of greenhouse gases in the space cooling and cold chain sectors in Colombia, Lebanon, Panama, Sri Lanka, and Trinidad and Tobago
	80,000
	5,600
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Annex III

PROJECT PREPARATION FOR NATIONAL INVENTORIES OF BANKS 
OF WASTE‑CONTROLLED SUBSTANCES (DECISION 91/66) 
SUBMITTED TO THE 93RD MEETING

	Country
	Agency
	Type
	Sector
	Project title
	Amount recommended (US $)
	Support costs recommended (US $)

	Albania
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Armenia
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Benin
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Bolivia (Plurinational State of)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	35,000
	4,550

	Bolivia (Plurinational State of)
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	55,000
	3,850

	Burkina Faso
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Burundi
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Cameroon
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Costa Rica
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Cuba
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Dominican Republic (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Ecuador
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Egypt
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	El Salvador
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Guatemala
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	35,000
	4,550

	Guatemala
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	55,000
	3,850

	Honduras
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	35,000
	4,550

	Honduras
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	55,000
	3,850

	Jamaica
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Kenya
	Germany
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Liberia
	Germany
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Mexico
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Montenegro
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	70,000
	4,900

	Namibia
	Germany
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	11,700

	Nicaragua
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	35,000
	4,550

	Nicaragua
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	55,000
	3,850

	North Macedonia
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	5,600

	Peru
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Republic of Moldova (the)
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Seychelles
	Germany
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	80,000
	10,400

	Togo
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Trinidad and Tobago
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Turkmenistan
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Uruguay
	UNDP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	90,000
	6,300

	Venezuela (Bolivarian Republic of)
	UNIDO
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Viet Nam
	IBRD
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	7,000

	Yemen
	UNEP
	PRP
	DES
	Preparation of national inventory of banks of waste-controlled substances and development of a national plan for management of these substances (decision 91/66)
	100,000
	13,000
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