UNEP/OzL.Pro/ExCom/84/24
   2 December 2019

UPDATE ON THE STATUS OF IMPLEMENTATION OF

THE 2019–2021 CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND

- Introduction

# This document consists of:

## Part I:	An update on the status of the implementation of the 2019–2021 business plans

## Part II:	Resource allocation for the 2018–2020 triennium

Recommendation

Annex I: HFC phase-out activities submitted to the 84th meeting

## PART I:	UPDATE ON THE STATUS OF THE IMPLEMENTATION OF THE 2019–2021 BUSINESS PLANS

# At its 82nd meeting, the Executive Committee endorsed the 2019–2021 consolidated business plan of the Multilateral Fund. In response to decision 82/45(b) and (c), the Secretariat adjusted the consolidated 2019–2021 business plan, as shown in Table 1.

Table 1. Resource allocation of the adjusted 2019–2021 consolidated business plans of the Multilateral Fund (US $)

| Item | 2019 | 2020 | 2021 | Total |
| --- | --- | --- | --- | --- |
| Required for compliance |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 96,379,090 | 111,848,069 | 85,792,031 | 294,019,190 |
| HPMP stage I | 0 | 353,978 | 0 | 353,978 |
| HPMP stage I – additional funding | 0 | 645,788 | 0 | 645,788 |
| HPMP project preparation (PRP) – stage II | 1,414,723 | 395,650 | 130,800 | 1,941,173 |
| HPMP stage II | 1,761,439 | 15,034,014 | 5,046,206 | 21,841,660 |
| HCFC production – stage II | 23,496,000 | 23,496,000 | 23,496,000 | 70,488,000 |
| HPMP PRP – stage III | 246,675 | 894,088 | 160,500 | 1,301,263 |
| HPMP stage III | 0 | 1,299,272 | 112,059 | 1,411,331 |
| HPMP verification | 588,600 | 588,600 | 588,600 | 1,765,800 |
| Required for compliance subtotal | 123,886,528 | 154,555,459 | 115,326,196 | 393,768,183 |
| HFC activities |  |  |  |  |
| HFC – enabling activities | 679,450 | 0 | 0 | 679,450 |
| HFC – investment PRP | 62,100 | 0 | 0 | 62,100 |
| HFC – investment | 15,512,484 | 0 | 0 | 15,512,484 |
| HFC activities subtotal | 16,254,034 | 0 | 0 | 16,254,034 |
| Standard activities |  |  |  |  |
| Compliance Assistance Programme (CAP) | 11,300,749 | 11,639,772 | 11,988,965 | 34,929,486 |
| Core unit | 5,931,915 | 5,961,294 | 5,990,878 | 17,884,086 |
| Institutional strengthening (IS) | 10,461,285 | 10,886,318 | 10,546,285 | 31,893,889 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 6,799,233 | 6,954,313 | 7,114,045 | 20,867,591 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |
| Standard activities subtotal | 34,993,182 | 35,941,697 | 36,140,173 | 107,075,052 |
| Grand total | 175,133,744 | 190,497,157 | 151,466,369 | 517,097,269 |
| Indicative budget | 174,600,000 | 171,000,000 | 180,000,000 | 525,600,000 |
| Difference | 533,744 | 19,497,157 | -28,533,631 | -8,502,731 |
| Funding distribution by agency |  |  |  |  |
| France | 78,769 | 692,895 | 0 | 771,664 |
| Germany | 1,628,838 | 2,611,677 | 2,394,232 | 6,634,747 |
| Italy | 565,000 | 264,840 | 0 | 829,840 |
| Japan | 305,529 | 90,400 | 90,400 | 486,329 |
| UNDP | 31,787,842 | 53,743,937 | 32,001,629 | 117,533,408 |
| UNEP | 27,470,794 | 28,440,307 | 25,909,156 | 81,820.258 |
| UNIDO | 59,822,423 | 50,437,927 | 41,319,974 | 151,580,323 |
| World Bank | 45,586,716 | 46,172,260 | 41,548,333 | 133,307,309 |
| HPMP verification* | 588,600 | 588,600 | 588,600 | 1,765,800 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 6,799,233 | 6,954,313 | 7,114,045 | 20,867,591 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |

* Funding for the preparation of HPMP verification reports for low-volume-consuming countries (LVC) is approved by the Executive Committee on an annual basis.

Status of implementation of the 2019 business plans

# The total funding available for 2019 amounts to US $174,600,000. Of this amount, US $9,520,278 has been approved at the 83rd meeting. Funding requests submitted to the 84th meeting amounts to US $130,778,657. If funding requests for all project proposals submitted are approved, a balance of US $34,834,809 would be available from the 2019 business plan, as shown in Table 2.

Table 2. 2019 consolidated business plan, submissions to the 84th meeting, and balance (US $)*

| Budget items | Total value in business plan | Approvals at the 83rd meeting | Submissions 84th meeting** | Total (83rd and 84th) | Balance (above)/below |
| --- | --- | --- | --- | --- | --- |
| Bilateral agencies | 2,578,136 | 0 | 2,822,543 | 2,822,543 | (244,407) |
| UNDP | 31,787,842 | 1,647,767 | 30,536,587 | 32,184,354 | (396,512) |
| UNEP | 27,470,794 | 3,711,600 | 19,194,030 | 22,905,630 | 4,565,164 |
| UNIDO | 59,822,423 | 4,160,911 | 28,312,527 | 32,473,438 | 27,348,985 |
| World Bank | 45,586,716 | 0 | 42,044,637 | 42,044,637 | 3,542,079 |
| HPMP verification | 588,600 | 0 | 569,100 | 569,100 | 19,500 |
| Sub-total (agencies) | 167,834,511 | 9,520,278 | 123,479,424 | 132,999,702 | 34,834,809 |
| Secretariat/Executive Committee/Monitoring and Evaluation (excluding Canadian counterpart) | 6,799,233 |  | 6,799,233 | 6,799,233 | 0 |
| Treasurer | 500,000 |  | 500,000 | 500,000 | 0 |
| Sub-total (standard costs) | 7,299,233 |  | 7,299,233 | 7,299,233 | 0 |
| Total | 175,133,744 | 9,520,278 | 130,778,657 | 140,298,935 | 34,834,809 |

* Including core unit costs.

** As at 2 December 2019

# The value of project proposals submitted to the 84th meeting of US $123,479,424 is US $355,330 above their value in the 2019 business plan, including US $3,580,552 associated with project proposals not included in the 2019 business plan.

# The value of HFC phase-down activities submitted to the 84th meeting is US $2,539,511, of which US $1,101,777 is associated with project proposals not included in the 2019 business plan. Annex I to the present document lists HFC-related projects submitted by the implementing agencies to the 84th meeting.

# Project proposals with a value of US $44,710,417 that were included in the 2019 business plan, were not submitted to the 84th meeting. These proposals have been included in the Consolidated business plan of the Multilateral Fund for 2020–2022.

# Forward commitments

# The total amount for existing forward commitments for multi-year agreements (MYAs) for the period 2019 to 2031 is US $647.24 million, assuming that the funding requests of MYAs submitted to the 84th meeting will be approved in principle, as shown in Table 3.

Table 3. Forward commitments (2019–2031) (US $000)

| Description | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2030 | 2031 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Approved in principle* | 79,440 | 135,145 | 104,089 | 81,455 | 58,556 | 29,137 | 30,319 | 33,237 | 16,078 | 212 | 57 | 567,725 |
| Submitted to 84th meeting | 26,756 | 25,551 | 25,964 | 527 | 0 | 316 | 156 | 0 | 135 | 111 | 0 | 79,516 |
| Total | 106,196 | 160,696 | 130,053 | 81,982 | 58,556 | 29,453 | 30,475 | 33,237 | 16,213 | 323 | 57 | 647,240 |

*Including revised HPMP agreements.

## PART II: RESOURCE ALLOCATION FOR THE 2018-2020 TRIENNIUM

# The resources approved by the Parties to the Montreal Protocol for the 2018–2020 triennium amount to US $540,000,000. Of this amount, US $144,921,792 had been allocated to activities approved in 2018, with US $395,078,208 remaining for 2019 and 2020.

# Taking into account approvals at the 81st, 82nd, 83rd meetings, submissions to the 84th meeting, and the Secretariat’s/Executive Committee’s and the Treasurer’s costs, the remaining resources available for the 2018-2020 triennium would be US $64.28 million, as shown in Table 4.

Table 4: Resource allocation for the current 2018-2020 triennium (US $)

| Description | 2018 | 2019 | 2020 | Total |
| --- | --- | --- | --- | --- |
| Resource allocation |  |  |  |  |
| Initial resource allocation (a) | 194,400,000 | 174,600,000 | 171,000,000 | 540,000,000 |
| Revised resource allocation (b)* | 144,921,792 | 224,078,208 | 171,000,000 | 540,000,000 |
| Approved funding |  |  |  |  |
| Approvals - 81st meeting | 73,930,598 |  |  | 73,930,598 |
| Approvals - 82nd meeting | 64,546,960 |  |  | 64,546,960 |
| Approvals - 83rd meeting |  | 9,520,278 |  | 9,520,278 |
| Submissions to the 84th meeting |  | 123,479,424 |  | 123,479,424 |
| Business plan values |  |  | 183,042,844 | 183,042,844 |
| Secretariat’s/Executive Committee’s cost (excluding Canadian counterpart) | 5,944,234 | 6,799,233** | 6,954,313** | 19,697,780 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 |
| Approved funding total (c) | 144,921,792 | 140,298,935 | 190,497,157 | 475,717,884 |
| Amount available from 2018 resource allocation (a) - (c) | 49,478,208 |  |  |  |
| Remaining resources (b) - (c) | 0 | 83,779,273 | -19,497,157 | 64,282,116 |

* The resource allocation for 2018 was decreased based on actual costs in 2018 by US $49,478,208 and the initial allocation for 2019 was adjusted by this amount.

** Estimated

Possible factors impacting financial planning and cash flow during the 2018-2020 triennium

# The cash flow of the Multilateral Fund for the 2018-2020 triennium is influenced by several factors, inter alia: receipt of agreed 2018-2020 pledged contributions; interest to be accrued; the loss/gain due to the fixed-exchange rate mechanism (FERM); payment of contributions in arrears included in the carry-over; and the balances returned from cancelled or completed projects. The following paragraphs provide forecasted information for the 2018-2020 triennium based on actual data from 2018 and 2019.

Receipt of agreed pledged contributions

# Based on the rate of pledges received in 2017 and 2018 (i.e. 97.4 per cent), of the US $166.67 million annual contribution, US $162.31 million is expected to be received for each year during the 2018-2020 triennium, for a total of US $486.93 million.

Payment of outstanding contributions in arrears included in the carry-over

# Based on updated information up to September 2019, the actual carry-over is US $39,767,556 including US $22,219,910 of outstanding contributions expected to be collected.

Potential interest accrued during the 2018-2020 triennium

# Based on the cash balance in 2018 and 2019 and using the average interest collected for 2018 and up to September of 2019, it might be expected that the interest accrued during the 2018-2020 triennium would amount to US $9.82 million.

# Gains/losses due to the FERM

# The potential impact on resources for the 2018-2020 triennium due to the FERM has been estimated at a gain of US $3.28 million.

# Potential balances returned from cancelled or completed projects

# It is difficult to calculate the potential total funds associated with return of balances from cancelled or completed projects during the 2018-2020 triennium. As reference. the average funds returned for the 2015-2018 period was US $5.5 million per year. Bilateral and implementing agencies are strongly encouraged to immediately return all the balances for those projects which have been operationally completed or cancelled.

# RECOMMENDATION

# The Executive Committee may wish to note:

## The update on the status of implementation of the 2019–2021 consolidated business plan of the Multilateral Fund as contained in document UNEP/OzL.Pro/ExCom/84/24; and

## That US $2,539,511 in HFC phase-down activities were submitted to the 84th meeting, including US $1,101,777 that had not been included in the 2019–2021 business plans.

Annex I

HFC PHASE-DOWN ACTIVITIES SUBMITTED TO THE 84TH MEETING

| Country | Agency | Type | Sector | Project title | Amount reviewed or recommended (US $) | Support costs reviewed or recommended (US $) |
| --- | --- | --- | --- | --- | --- | --- |
| Algeria | UNIDO | TAS | SEV | Enabling activities for HFC phase-down | 150,000 | 10,500 |
| Argentina | UNIDO | INV | PRO | Control and phase-out of HFC-23 emissions in production of HCFC-22 at FIASA | 1,343,677 | 94,057 |
| Cuba | UNDP | INV | REF | Conversion from HFC-134a to HFC-290 (propane) in the manufacture of chillers at Frioclima | 120,000 | 10,800 |
| Egypt | UNDP | PRP | FFI | Preparation for HFC investment project in the fire-fighting equipment assembly sector | 30,000 | 2,100 |
| Haiti | UNDP | TAS | SEV | Enabling activities for HFC phase-down | 95,000 | 6,650 |
| Mexico | UNIDO | INV | PRO | Control and phase-out of HFC-23 emissions in production of HCFC-22 at Quimobasicos | 632,455 | 44,272 |
| Total |  |  |  |  | 2,371,132 | 168,379 |

Resource allocation adopted at the 81st meeting (decision 81/26(b).

Stage I of the HPMP for Serbia (UNEP and UNIDO); stage II of the HPMP for Tunisia (UNIDO); HCFC investment project for Pakistan (UNIDO); project preparation for stage II of the HPMP for Bahrain (UNEP and UNIDO), Equatorial Guinea (UNEP and UNIDO), Georgia (UNDP), Liberia (UNEP and UNIDO), Mali (UNDP), Mozambique (UNDP) and Sierra Leone (UNEP and (UNIDO); project preparation for stage III of the HPMP for Armenia (UNEP and UNIDO) and the Republic of Moldova (UNEP); HFC enabling activities for Algeria (UNIDO) and Haiti (UNDP), HFC investment project preparation for Egypt (UNDP); HFC investment projects for Cuba (UNDP) and Mexico (UNIDO); and IS project for India (UNDP).

These activities include: 77 HCFC activities for 49 countries (US $32.22 million), 13 HFC-related activities for 11 countries (US $6.62 million) and 43 IS activities (US $5.87 million).

UNEP/OzL.Pro/ExCom/84/26

Decision XXIX/1