UNEP/OzL.Pro/ExCom/84/18
   19 November 2019

PROGRESS REPORT OF UNDP AS AT 31 DECEMBER 2018

# This document presents the progress report of UNDP as at 31 December 2018.

Scope of the document

# This document consists of the following parts:

## Part I:	Projects approved under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2018 and cumulative since 1991 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs); it contains a review on the status of implementation of each ongoing project at the country level; and it identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## Part II:	Projects approved under the additional voluntary contributions for fast start support for HFC phase-down. It provides a status of implementation of HFC phase-down projects funded under the voluntary contributions.

Recommendation.

# This document also contains the following annexes:

Annex I: 	A summary status and a recommendation for each ongoing project with outstanding issues for consideration by the Executive Committee.

Annex II: 	An analysis of the progress report.

Measurements used in the progress reports

# Prior to agreement on the Kigali Amendment, all controlled substances under the Montreal Protocol were ozone-depleting substances, measured in ODP tonnes. Controlled substances under the Kigali Amendment are not ozone-depleting substances, and their control targets are measured in mt CO2-eq. (i.e., consumption in metric tonnes (mt) multiplied by the global warming-potential (GWP) of the substance). Notwithstanding the two different measurements for reporting controlled substances, the progress report of UNDP submitted to the 84th meeting are based on ODP tonnes for all controlled substances.

An overview of HFC phase-down activities

# As of 31 December 2018, the Executive Committee has approved 26 projects (including five investment project, five project preparation and 16 enabling activities) amounting to US $9.02 million, in 20 countries. Approved investment projects will phase down 623.4 mt (791,633 mt CO2-eq.) of HCFs. Regarding enabling activities, extension of the completion dates of 10 of these projects was approved at the 83rd meeting and requests for extension for five others have been submitted to the 84th meeting.

Progress review process by the Secretariat

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2018, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The Secretariat had several discussions with UNDP, where a number of issues on ongoing projects were raised and subsequently satisfactorily resolved.

# Part I: 	Projects approved under the regular contributions to the Multilateral Fund

Summary of progress in implementation of projects for 2018 and cumulative

# Implementation of projects and activities by UNDP for 2018 and cumulative since 1991 up to 31 December 2018 is summarized as follows:

## Phase-out: In 2018, 243.6 ODP tonnes of consumption of controlled substances were phased out and an additional 746.6 ODP tonnes of consumption of controlled substances were approved for phase-out. Since 1991, 67,009 ODP tonnes of consumption of controlled substances had been phased out, of an expected total of 68,281 ODP tonnes from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2018, US $41.43 million was disbursed and US $24.92 million was planned for disbursement based on the 2017 progress report, representing a rate of disbursement of 166 per cent of that planned. Cumulatively, US $745.56 million had been disbursed out of the total US $822.21 million approved for disbursement (excluding agency support costs). This represents a rate of disbursement of 91 per cent. In 2018, US $40.27 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $10.58/kg. The average cost-effectiveness of investment projects per ODP tonne was US $8.65/kg for completed projects and US $78.65/kg for ongoing projects;

## Number of projects completed: In 2018, 58 projects were completed. Since 1991, 2,289 projects of the 2,435 projects approved (excluding closed or transferred projects) were completed. This represents a completion rate of 94 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2018 were completed on average 40 months after their approval. Since 1991, the average time for completion of investment projects has been 34 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;

## Speed of delivery – non investment projects: Projects that were completed in 2018 were completed on average 33 months after their approval. Since 1991, the average time for completion of non-investment projects has been 39 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;

## Project preparation: Of the 529 project preparation activities approved by the end of 2018, 517 have been completed, leaving 12 ongoing. In 2018, 12 projects have been completed;

## Implementation delays: There were a total of 73 ongoing investment projects under implementation at the end of 2018. These projects, on average, are experiencing a delay of 13 months. However, there are no projects classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as project preparation, multi-year agreements (MYAs) and institutional strengthening (IS) are not subject to those procedures); and

## MYAs: In 2018, UNDP was implementing 49 MYAs for HCFC phase-out management plans (HPMPs). Since 1991, 133 MYAs have been approved and 84 MYAs have been completed.

Project implementation progress in 2018

# Further to the review process, a number of issues were resolved, except for two projects: one related to an MYA tranche for the phase-out of HCFCs, and the other for a project preparation, as shown in Annex I to the present document. For each ongoing project, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Of the 107 ongoing projects, excluding IS and project preparation, 36 projects have revised planned dates of completion since the 2017 progress report.

# Details of progress in implementation of projects associated with the HPMPs for China (stage II of the industrial and commercial refrigeration and air-conditioning (ICR) and solvent sector plans), Colombia, Costa Rica, Egypt, Ghana, Iran (Islamic Republic of) and Malaysia, and reports on projects with specific reporting requirements associated with Brazil (HPMP and ODS demonstration project), China (CFC solvent), Cuba (HPMP), Egypt (low GWP-alternative demonstration project), India (HPMP), Indonesia (HPMP), Lebanon (HPMP), Trinidad and Tobago (HPMP) and Uruguay (HPMP), have been submitted to the 84th meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of these documents.

# In line with decision 82/11(c)(ii), the Secretariat noted that renewal of the IS project for Brazil has not been submitted for the last two years. UNDP informed that it is planning to submit the renewal request in 2021.

Part II: Projects approved under the additional voluntary contributions for fast start support for HFC phase-down

# As of 31 December 2018, the Executive Committee had approved 18 HFC-related projects under the additional voluntary contributions amounting to US $6,079,610 (excluding agency support costs). A summary of the status of these projects is presented in Table 1.

# Table 1. HFC-related projects approved in 2018

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 2 |  | 0 | 4,406,610 | 1,208,577 | 3,198,033 | 27 |
| Project preparation | 5 | 3 | 60 | 150,000 | 47,178 | 102,822 | 31 |
| Technical assistance - Enabling activities | 11 |  | 0 | 1,523,000 | 220,635 | 1,302,365 | 14 |
| Total | 18 | 3 | 17 | 6,079,610 | 1,476,389 | 4,603,221 | 24 |

* Excludes agency support costs.

** Phase out of 480.6 mt (586,551 mt CO2-eq.) of HFCs.

# Of the 18 projects approved by the end of 2018, three preparation activities have been completed, leaving 15 ongoing. There are two ongoing investment projects approved at the 80th and 82nd meetings, of which funds have been disbursed for one. The enabling activities are at various stages of implementation. Cumulatively, US $1,476,389 had been disbursed out of the total US $6,079,610 approved for disbursement (excluding support costs), representing a disbursement rate of 24 per cent.

Recommendation

# The Executive Committee may wish:

## To note the progress report of UNDP as at 31 December 2018 contained in document UNEP/OzL.Pro/ExCom/84/18; and

## To approve the recommendations related to ongoing projects with specific issues contained in Annex I to the present document.

Annex I

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNDP

| Country/project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Haiti HAI/PHA/76/INV/22 | HCFC phase-out management plan (stage I, second tranche) | 0 | No disbursement; slow progress in implementation | To request a status report to the 85th meeting on progress in implementation and the level of funds disbursement |
| Democratic Republic of the Congo (the) DRC/PHA/79/PRP/42 | Preparation of a HCFC phase-out management plan (stage II) | 0 | No disbursement due to delays in implementation and Ebola outbreak resulting in difficulties in field activities; submission of stage II delayed | To request a status report to the 85th meeting on the level of funds disbursement and the status of submission of stage II |

Annex II

ANALYSIS OF THE PROGRESS REPORT OF UNDP AS AT 31 DECEMBER 2018

# This Annex consists of the following two parts:

## Part I:	Projects approved under the regular contributions to the Multilateral Fund.

## Part II:	Projects approved under the additional voluntary contributions for fast start support for HFC phase-down.

Part I: 	Projects approved under the regular contributions to the Multilateral Fund

# As of 31 December 2018, the Executive Committee had approved US $932.88 million consisting of US $822.21 million for the implementation of investment and non-investment projects and US $110.66 million for agency support costs, as shown in Table 1. In 2018, 60 new projects and activities were approved. This level of funding is expected to result in the phase-out of 68,281 ODP tonnes of consumption of controlled substances.

# Table 1: Approved funding by sector for UNDP as at 31 December 2018

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 26,054,838 |
| Destruction | 3,606,279 |
| Fire fighting | 50,000 |
| Foam | 173,366,807 |
| Halon | 4,996,975 |
| Fumigants | 20,081,243 |
| Phase-out plan | 326,512,742 |
| Process agent | 1,286,923 |
| Production | 1,056,000 |
| Refrigeration | 139,929,636 |
| Several | 61,151,282 |
| Solvents | 63,699,996 |
| Sterilant | 417,628 |
| Sub-total | 822,210,347 |
| Agency support costs | 110,664,988 |
| Total | 932,875,335 |

# A summary of the status of projects implemented by category is presented in Table 2.

Table 2: Status of project implementation by category

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 22 | 22 | 100 | 1,628,797 | 1,628,797 | 0 | 100 |
| Demonstration | 43 | 38 | 88 | 22,204,392 | 20,764,309 | 1,440,084 | 94 |
| Institutional strengthening (IS) | 238 | 211 | 89 | 50,971,615 | 45,142,687 | 5,828,928 | 89 |
| Investment | 1,265 | 1,192 | 94 | 677,423,733 | 617,060,549 | 60,363,183 | 91 |
| Project preparation | 529 | 517 | 98 | 22,207,434 | 21,547,273 | 660,162 | 97 |
| Technical assistance | 310 | 281 | 91 | 46,183,886 | 37,823,467 | 8,360,419 | 82 |
| Training | 28 | 28 | 100 | 1,590,489 | 1,590,489 | 0 | 100 |
| Total | 2,435 | 2,289 | 94 | 822,210,347 | 745,557,571 | 76,652,776 | 91 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

# Table 3 presents an overview of the status of project implementation by year. All projects and activities approved between 1991 and 2008, have now been completed.

Table 3: Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 15 | 15 | 100 | 1,149,032 | 1,149,032 | 0 | 100 |
| 1992 | 67 | 67 | 100 | 8,619,002 | 8,619,002 | 0 | 100 |
| 1993 | 57 | 57 | 100 | 13,204,712 | 13,204,712 | 0 | 100 |
| 1994 | 148 | 148 | 100 | 49,481,580 | 49,481,581 | -1 | 100 |
| 1995 | 117 | 117 | 100 | 29,599,445 | 29,599,446 | -1 | 100 |
| 1996 | 83 | 83 | 100 | 27,838,805 | 27,838,805 | 0 | 100 |
| 1997 | 188 | 188 | 100 | 44,056,257 | 44,056,257 | 0 | 100 |
| 1998 | 172 | 172 | 100 | 31,305,010 | 31,305,010 | 0 | 100 |
| 1999 | 204 | 204 | 100 | 35,896,883 | 35,896,884 | -1 | 100 |
| 2000 | 149 | 149 | 100 | 31,268,362 | 31,268,361 | 1 | 100 |
| 2001 | 179 | 179 | 100 | 35,292,272 | 35,292,271 | 1 | 100 |
| 2002 | 117 | 117 | 100 | 44,316,424 | 44,316,422 | 2 | 100 |
| 2003 | 64 | 64 | 100 | 36,336,530 | 36,336,530 | 0 | 100 |
| 2004 | 69 | 69 | 100 | 24,802,715 | 24,802,714 | 1 | 100 |
| 2005 | 53 | 53 | 100 | 29,125,258 | 29,124,834 | 425 | 100 |
| 2006 | 62 | 62 | 100 | 15,753,458 | 15,753,461 | -3 | 100 |
| 2007 | 54 | 54 | 100 | 12,142,488 | 12,142,486 | 2 | 100 |
| 2008 | 84 | 84 | 100 | 22,873,866 | 22,873,865 | 0 | 100 |
| 2009 | 92 | 91 | 99 | 13,226,899 | 13,188,578 | 38,321 | 100 |
| 2010 | 43 | 42 | 98 | 19,567,971 | 19,545,191 | 22,779 | 100 |
| 2011 | 63 | 60 | 95 | 57,453,704 | 56,972,603 | 481,101 | 99 |
| 2012 | 29 | 26 | 90 | 33,889,851 | 32,376,384 | 1,513,466 | 96 |
| 2013 | 43 | 39 | 91 | 34,573,366 | 33,590,429 | 982,938 | 97 |
| 2014 | 67 | 64 | 96 | 22,958,186 | 21,963,919 | 994,268 | 96 |
| 2015 | 75 | 62 | 83 | 33,666,689 | 27,262,490 | 6,404,199 | 81 |
| 2016 | 53 | 17 | 32 | 42,802,250 | 26,924,872 | 15,877,378 | 63 |
| 2017 | 28 | 6 | 21 | 30,734,847 | 20,418,385 | 10,316,462 | 66 |
| 2018 | 60 | 0 | 0 | 40,274,486 | 253,048 | 40,021,438 | 1 |
| Total | 2,435 | 2,289 | 94 | 822,210,347 | 745,557,571 | 76,652,776 | 91 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

# Table 4 presents project implementation by country for 2018.

Table 4. Summary of project implementation by UNDP for 2018

| Country | Phased out in 2018* | Percentage of planned phase-out achieved in 2018 | Estimated funds disbursed in 2018 (US$) | Funds disbursed in 2018 (US$) | Percentage of funds disbursed over estimation in 2018 | Percentage of planned projects completed in 2018 |
| --- | --- | --- | --- | --- | --- | --- |
| Angola | 0.0 |  | 151,639 | 88,817 | 59 |  |
| Argentina | 0.0 |  | 91,423 | 135,453 | 148 |  |
| Armenia | 0.0 |  | 62,309 | 70,387 | 113 |  |
| Bangladesh | 0.0 |  | 116,495 | 77,116 | 66 | 67 |
| Barbados | 0.0 |  | 44,162 | 55,791 | 126 |  |
| Belize | 0.0 |  | 4,550 | 0 | 0 |  |
| Bhutan | 0.0 |  | 10,754 | 19,528 | 182 |  |
| Brazil | 45.2 |  | 3,068,058 | 4,422,753 | 144 |  |
| Brunei Darussalam | 0.0 |  | 7,380 | 0 | 0 | 0 |
| Cambodia | 0.0 |  | 15,000 | 0 | 0 |  |
| Chile | 6.0 | 100 | 395,812 | 895,921 | 226 | 100 |
| China | 88.8 |  | 8,384,723 | 23,003,574 | 274 | 50 |
| Colombia | 16.0 | 100 | 810,427 | 1,288,525 | 159 | 100 |
| Costa Rica | 0.0 |  | 185,918 | 175,042 | 94 | 100 |
| Cuba | 0.0 |  | 205,499 | 141,381 | 69 |  |
| Democratic Republic of the Congo (the) | 0.0 |  | 24,351 | 23,536 | 97 | 50 |
| Dominican Republic (the) | 0.0 |  | 76,662 | 196,701 | 257 |  |
| Egypt | 0.6 | 14 | 1,023,783 | 588,656 | 57 | 50 |
| El Salvador | 2.0 |  | 46,000 | 68,663 | 149 |  |
| Fiji | 0.2 |  | 18,997 | 12,294 | 65 |  |
| Georgia | 0.0 |  | 17,777 | 17,499 | 98 |  |
| Ghana | 0.0 |  | 56,407 | 140,053 | 248 | 100 |
| Guyana | 0.0 |  | 37,671 | 74,358 | 197 |  |
| Haiti | 0.0 |  | 29,136 | 0 | 0 |  |
| India | 10.0 |  | 4,056,125 | 3,460,223 | 85 | 83 |
| Indonesia | 9.0 | 100 | 1,317,271 | 421,109 | 32 | 0 |
| Iran (Islamic Republic of) | 0.0 |  | 506,468 | 252,313 | 50 | 100 |
| Jamaica | 0.0 |  | 32,787 | 26,221 | 80 |  |
| Kuwait | 0.0 |  | 107,900 | 0 | 0 |  |
| Kyrgyzstan | 1.3 | 100 | 21,162 | 70,400 | 333 | 100 |
| Lebanon | 29.8 |  | 258,781 | 841,562 | 325 | 100 |
| Malaysia | 14.0 | 100 | 1,441,111 | 2,092,991 | 145 | 100 |
| Maldives | 0.0 |  | 88,445 | 130,151 | 147 |  |
| Mali | 2.6 |  | 32,082 | 84,296 | 263 |  |
| Mauritania | 0.0 |  | 31,500 | 0 | 0 |  |
| Mexico | 0.0 | 0 | 716,710 | 597,950 | 83 | 0 |
| Nepal | 0.1 |  | 17,280 | 30,916 | 179 | 100 |
| Nigeria | 18.0 | 38 | 282,423 | 612,897 | 217 | 100 |
| Pakistan | 0.0 |  | 97,766 | 140,564 | 144 | 100 |
| Panama | 0.0 |  | 199,675 | 218,217 | 109 | 100 |
| Paraguay | 0.0 |  | 32,212 | 38,626 | 120 |  |
| Peru | 0.0 |  | 166,297 | 75,513 | 45 |  |
| Republic of Moldova (the) | 0.0 |  | 38,970 | 1,901 | 5 |  |
| Saint Kitts and Nevis | 0.0 |  | 12,000 | 0 | 0 |  |
| Sri Lanka | 0.0 |  | 65,689 | 199,265 | 303 | 100 |
| Timor-Leste | 0.0 |  | 35,204 | 55,600 | 158 | 100 |
| Trinidad and Tobago | 0.0 |  | 122,408 | 158,178 | 129 |  |
| Uruguay | 0.0 |  | 162,504 | 289,835 | 178 |  |
| Venezuela (Bolivarian Republic of) | 0.0 |  | 192,849 | 139,748 | 72 |  |
| Total | 243.6 | 44 | 24,920,548 | 41,434,526 | 166 | 81 |

* No phase-out in 2018 for HFC-related projects.

# Table 5 presents a summary of HFC-related projects approved under regular contributions.

Table 5. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 3 | 0 | 0 | 2,491,791 | 0 | 2,491,791 | 0 |
| Technical assistance - Enabling activities | 5 | 0 | 0 | 444,000 | 4,334 | 439,666 | 1 |
| Total | 8 | 0 | 0 | 2,935,791 | 4,334 | 2,931,457 | 0.1 |

*Excludes agency support costs.

** 142.8 mt was approved for investment projects with mt CO2-eq. of 204,332.

# There are currently eight HFC-related projects (including three investment and five enabling activities) approved under regular contributions at a total value of US $2,935,791, with US $4,334 of the funds already disbursed. These projects are progressing at various stages of implementation and the investment projects are expected to be completed on time in 2020.

# Part II: Projects approved under the additional voluntary contributions for fast start support for HFC phase-down

# As of 31 December 2018, the Executive Committee had approved 18 HFC-related projects under the additional voluntary contributions amounting to US $6,079,610 (excluding agency support costs). A summary of the status of these projects is presented in Table 6.

# Table 6. HFC-related projects approved in 2018

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 2 |  | 0 | 4,406,610 | 1,208,577 | 3,198,033 | 27 |
| Project preparation | 5 | 3 | 60 | 150,000 | 47,178 | 102,822 | 31 |
| Technical assistance - Enabling activities | 11 |  | 0 | 1,523,000 | 220,635 | 1,302,365 | 14 |
| Total | 18 | 3 | 17 | 6,079,610 | 1,476,389 | 4,603,221 | 24 |

* Excludes agency support costs.

** 480.6 mt (587,301 mt CO2-eq.) of HFCs to be phased out.

# Of the 18 projects approved by the end of 2018, three preparation activities have been completed and two investment projects are under current implementation. The enabling activities are at various stages of implementation. Cumulatively, US $1,476,389 had been disbursed out of the total US $6,079,610 approved for disbursement (excluding support costs), representing a disbursement rate of 24 per cent.

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database that is available upon request.

Ongoing projects are all projects that were under implementation as at 31 December 2018. Key indicators of progress include: percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

The issue of the two different measurements of controlled substances is discussed in the consolidated progress report (UNEP/OzL.Pro/ExCom/84/16).

The phase-out includes approvals for HFC investment projects of 142.8 mt with mt CO2-eq. of 204,332.

Including 142.8 mt of HFC investment projects.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

UNEP/OzL.Pro/ExCom/84/42

UNEP/OzL.Pro/ExCom/84/43

UNEP/OzL.Pro/ExCom/84/45

UNEP/OzL.Pro/ExCom/84/49

UNEP/OzL.Pro/ExCom/84/50

UNEP/OzL.Pro/ExCom/84/51

UNEP/OzL.Pro/ExCom/84/54

UNEP/OzL.Pro/ExCom/84/22 and Add.1

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively-financed projects.