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UPDATE ON THE STATUS OF IMPLEMENTATION OF THE 2016-2018 CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND

At the 75th meeting, the Executive Committee endorsed the consolidated business plan of the Multilateral Fund for 2016-2018. In response to decision 75/22(b) and (c), the Secretariat adjusted the consolidated 2016-2018 business plan[footnoteRef:1], which was further adjusted pursuant to decision 76/3(c), as shown in Table 1.  [1:  The adjusted consolidated 2016-2018 business plan was sent to bilateral and implementing agencies on 8 December 2015.] 

Table 1. Resource allocation of the 2016-2018 consolidated business plan of the Multilateral Fund (US $)
	Description
	2016
	2017
	2018
	Total
	Approved MYAs after 2018

	Required for compliance

	Approved multi-year agreements (MYAs)
	22,267,577
	11,922,133
	16,645,965
	50,835,675
	13,365,125

	HCFC production phase-out management plan (HPPMP) preparation – stage I
	107,000
	0
	0
	107,000
	 

	HPPMP – stage I
	0
	0
	532,500
	532,500
	 

	HPPMP – stage II
	0
	21,874,286
	21,874,286
	43,748,571
	 

	HCFC phase-out management plan (HPMP) preparation – stage II
	1,814,755
	408,336
	3,611,279
	5,834,369
	 

	HPMP preparation – stage III
	0 
	0
	22,600
	22,600
	 

	HPMPs and HPMP investment projects – stage I
	564,098
	2,453,989
	330,800
	3,348,887
	 

	HPMPs and HPMP investment projects – stage II
	114,913,217
	109,823,665
	158,190,630
	382,927,512
	 

	HPMP verification
	588,600
	588,600
	588,600
	1,765,800
	 

	Low global-warming potential (GWP) alternative demonstration projects
	7,674,500
	0
	0
	7,674,500
	 

	Sub-total
	147,929,746
	147,071,009
	201,796,660
	496,797,415
	13,365,125

	Standard costs

	UNEP compliance assistance programme (CAP)
	10,837,857
	11,162,993
	11,497,882
	33,498,732
	 

	Core unit (UNDP, UNIDO, World Bank)
	5,835,000
	5,875,845
	5,916,976
	17,627,821
	 

	Institutional strengthening (IS)
	11,303,609
	9,918,458
	11,210,431
	32,432,498
	 

	Secretariat/Executive Committee/Monitoring and Evaluation  costs (excluding Canadian counterpart funding)
	5,629,692
	5,759,245
	5,892,686
	17,281,623
	 

	Treasurer 
	500,000
	500,000
	500,000
	1,500,000
	 

	Sub-total
	34,106,158
	33,216,541
	35,017,975
	102,340,673
	 

	Grand total
	182,035,904
	180,287,550
	236,814,634
	599,138,088
	13,365,125

	BY AGENCY

	Bilateral
	2,349,314
	2,501,711
	6,945,256
	11,796,281
	 

	UNDP
	45,514,953
	29,260,832
	58,554,541
	133,330,325
	 

	UNEP
	26,011,401
	21,415,427
	27,822,360
	75,249,188
	 

	UNIDO
	64,633,448
	59,338,893
	73,389,231
	197,361,572
	 

	World Bank
	36,808,496
	60,922,843
	63,121,960
	160,853,299
	 

	HPMP verification reports*
	588,600
	588,600
	588,600
	1,765,800
	 

	Secretariat/Executive Committee/Monitoring and Evaluation  costs (excluding Canadian counterpart funding)
	5,629,692
	5,759,245
	5,892,686
	17,281,623
	 

	Treasurer
	500,000
	500,000
	500,000
	1,500,000
	 


* Funding for the preparation of HPMP verification reports for low-volume-consuming countries is approved by the Executive Committee on an annual basis.

Status of implementation of the 2016 business plans
Table 2 sets out the approvals at the 76th meeting (amounting to US $30,160,016), the submissions by agency to the 77th meeting (as at 21 October 2016), and the balance of funds from projects in the 2016 business plans. 
Table 2. 2016 consolidated business plan, approvals of the 76th, and submissions to the 77th meetings, and balance by agency (US $)*
	Budget items
	Total value in business plan
	76th meeting approvals
	77th meeting submissions**
	Balance (above)/below business plan levels

	Bilateral agencies
	2,349,314
	1,233,353
	5,802,857
	-4,686,896

	UNDP
	45,514,953
	9,986,962
	74,498,925
	-38,970,934

	UNEP
	26,011,401
	3,796,796
	19,093,788
	3,120,817

	UNIDO
	64,633,448
	10,427,960
	46,811,956
	7,393,532

	World Bank
	36,808,496
	4,714,945
	16,089,392
	16,004,159

	HPMP verification reports
	588,600
	0
	268,800
	319,800

	Sub-total (agencies)
	175,906,212
	30,160,016
	162,565,718
	-16,819,522

	Secretariat/Executive Committee/Monitoring and Evaluation costs (excluding Canadian counterpart)
	5,629,692
	 
	5,629,692
***
	0

	Treasurer
	500,000
	 
	500,000
	0

	Sub-total (standard costs)
	6,129,692
	0
	6,129,692
	0

	Total
	182,035,904
	30,160,016
	168,695,410
	-16,819,522


* Including core unit costs.
** As at 21 October 2016. Funding requests associated with new stages I and II of HPMPs were still under discussion between the Secretariat and the relevant bilateral and implementing agencies. 
*** Estimated. See Approved 2015, 2016 and 2017 and proposed 2018 budgets of the Fund Secretariat (UNEP/OzL.Pro/ExCom/75/82).

The total funding submitted by bilateral and implementing agencies to the 77th meeting (as at 21 October 2016) amounts to US $162,565,718, which is US $33,655,989 above the value for these activities in the consolidated 2016 business plan. This amount includes US $11,179,108 associated with the following activities which were not in the 2016 business plan: 
Tranches of stage I of HPMPs for Grenada (UNIDO), Paraguay (UNDP) Saudi Arabia (UNEP), Senegal (UNEP and UNIDO) and South Sudan (UNDP)[footnoteRef:2]; and [2:  All HPMPs had been included in the business plan for 2017 except Paraguay where additional stage I funding submitted for the foam sector for polyols, but subsequently withdrawn.] 

Tranches of stage II of HPMPs for China (Germany, Japan, UNDP (overarching strategy)), Jordan (World Bank and UNIDO), Malaysia (UNDP), Mexico (Spain) and Uruguay (UNDP (foam and monitoring))[footnoteRef:3]. [3:  All stage II of HPMPs had been included in the business plan for 2017 except for China (Japan) and overarching strategy (UNDP) and Mexico (Spain), and Uruguay (foam sector) that was not included at all in the business plans.] 

Table 3 presents the value for activities[footnoteRef:4] included in the consolidated 2016 business plan but not submitted to the 77th meeting. The list of these activities is contained in Annex I to the present report. [4:  These activities include: 86 HCFC activities for 42 countries (US $17.54 million) and 16 IS activities (US $2.38 million).] 

 Table 3. Activities in the consolidated 2016 business plan not yet submitted 
	Agency 
	Value (US $)

	Bilateral 
	400,000

	UNDP
	2,613,384

	UNEP
	4,580,665

	UNIDO
	10,055,389

	World Bank
	2,268,676

	Total
	19,918,114



Resource allocation for 2015-2017 triennium
The resources approved by the Parties to the Montreal Protocol for the 2015-2017 triennium[footnoteRef:5] total US $507,500,000. Of this amount, US $191,476,898 had been allocated to activities approved in 2015, with US $316,023,102 remaining for 2016 and 2017.  [5:  Decision XXVI/10. ] 

The value of the activities approved at the 76th meeting, submitted to the 77th meeting, planned in the 2017 adjusted business plans, and the operation of Secretariat/Executive Committee/Monitoring and evaluation and Treasurer for 2016 and 2017, amounts to US $366,830,932, exceeding the resources available by US $50,807,830 as shown in Table 4. The deficit could be further increased if the value of the interest to be accrued and the contributions to be paid are less than that indicated in the replenishment (i.e. US $491.5 million[footnoteRef:6]).  [6:  New contributions for the 2015-2017 replenishment amount to US $437.5 million; however, the US $64 million carryover includes US $48 million in contributions from triennia prior to 2015. With the US $6 million of interest, the expected income amounts to US $491.5 million. ] 

Table 4: Resource allocation for 2016 and 2017 (US$)
	Description
	2016
	2017
	Total

	Revised resource allocation (a)*
	162,223,102
	153,800,000
	316,023,102

	Project costs
	 
	 
	 

	Approvals at the 76th meeting
	30,160,016
	 
	30,160,016

	Submissions to the 77th meeting
	162,565,718
	 
	162,565,718

	Business plans values
	 
	161,716,261
	161,716,261

	Subtotal project costs (b)
	192,725,734
	161,716,261
	354,441,995

	Recurrent costs
	 
	 
	 

	Secretariat/Executive Committee/Monitoring and evaluation
	5,629,692
	5,759,245
	11,388,937

	Treasurer
	500,000
	500,000
	1,000,000

	Subtotal recurrent costs (c)
	6,129,692
	6,259,245
	12,388,937

	Total costs (d) = (b) + (c)
	198,855,426
	167,975,506
	366,830,932

	Balance (e) = (a) – (d)
	-36,632,324
	-14,175,506
	-50,807,830


(*) Resources available from the 2015-2017 replenishment approved by the Parties.

An addendum to the present document will be issued prior to the 77th meeting to address, inter alia, the resource allocation for 2016 and 2017 based on recommendations provided in documents submitted to the 77th meeting.
Forward commitments 
The addendum will also assess more accurately forward commitments associated with new stages I and II of HPMPs submitted to the 77th meeting. 
RECOMMENDATIONS

The Executive Committee may wish to note: 
The update on the status of implementation of the 2016-2018 consolidated business plan of the Multilateral Fund contained in document UNEP/OzL.Pro/ExCom/77/5; and
That an addendum will be issued to address resource allocation for 2016 and 2017 based on recommendations provided in documents submitted to the 77th meeting and forward commitments associated with new stages I and II of HCFC phase-out management plans.
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Annex I

REMAINING ACTIVITIES REQUIRED FOR COMPLIANCE (2016)

	Country
	Agency
	Type
	Chemical
	Sector and Subsector
	Value ($000) 2016
	ODP 2016 

	Albania
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	26
	0.2

	Algeria
	UNEP
	INS
	SEV
	Institutional Strengthening
	329
	 

	Algeria
	UNIDO
	PHA
	HCFC
	REF-Servicing - HPMP - Stage I
	155
	1.0

	Algeria
	UNIDO
	PRP
	HCFC
	FOA-Rigid PU foam - Preparation of Stage II HPMP 
	54
	0.0

	Algeria
	UNIDO
	PRP
	HCFC
	REF-Manufacturing - Preparation of Stage II HPMP 
	54
	0.0

	Algeria
	UNIDO
	PRP
	HCFC
	REF-Servicing - Preparation of Stage II HPMP 
	64
	0.0

	Antigua and Barbuda
	UNEP
	PHA
	HCFC
	Stage 2 - HCFC Phase-out Management Plan (implementation)
	45
	 

	Argentina
	World Bank
	PHA
	HCFC
	FOA - Rigid PU foam - HPMP Stage II
	1,202
	17.7

	Bahamas (the)
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	66
	0.3

	Bahamas (the)
	UNIDO
	PHA
	HCFC
	REF-Servicing - HPMP - Stage I
	39
	0.2

	Bahrain
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	141
	1.0

	Bangladesh
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	20
	0.2

	Bangladesh
	UNEP
	PRP
	HCFC
	Stage 2 - HCFC Phase-out Management Plan (preparation) 
	34
	 

	Barbados
	UNDP
	PHA
	HCFC
	Stage I HPMP
	41
	0.2

	Barbados
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	54
	0.2

	Belize
	UNDP
	PHA
	HCFC
	Stage I HPMP
	7
	0.0

	Belize
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	108
	0.4

	Burundi
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	40
	0.3

	Burundi
	UNIDO
	PHA
	HCFC
	REF-Servicing - HPMP - Stage I
	87
	0.6

	Cameroon
	UNIDO
	PHA
	HCFC
	REF-Assembly and charging of refrigeration equipment - HPMP Stage II
	755
	8.1

	Cameroon
	UNIDO
	PHA
	HCFC
	REF-Servicing - HPMP Stage II
	374
	4.0

	Central African Republic (the)
	UNEP
	INS
	SEV
	Institutional Strengthening
	85
	 

	Central African Republic (the)
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	62
	0.4

	Cote d'Ivoire
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	168
	1.8

	Cote d'Ivoire
	UNIDO
	PHA
	HCFC
	REF-Servicing - HPMP - Stage I
	495
	5.6

	Democratic People’s Republic of Korea (the)
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	102
	2.0

	Democratic People’s Republic of Korea (the)
	UNIDO
	PRP
	PRO HCFC
	PRO - Stage I
	107
	0.0

	Democratic People’s Republic of Korea (the)
	UNIDO
	PRP
	HCFC
	REF-Manufacturing - Preparation of Stage II HPMP 
	30
	0.0

	Democratic People’s Republic of Korea (the)
	UNIDO
	PRP
	HCFC
	REF-Servicing - Preparation of Stage II HPMP 
	45
	0.0

	Democratic Republic of the Congo (the)
	UNDP
	PHA
	HCFC
	Stage I HPMP
	26
	0.3

	Democratic Republic of the Congo (the)
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	27
	0.3

	Democratic Republic of the Congo (the)
	UNEP
	PHA
	HCFC
	Stage 2 - HCFC Phase-out Management Plan (implementation) 
	211
	2.4

	Democratic Republic of the Congo (the)
	UNEP
	PRP
	HCFC
	Stage 2 - HCFC Phase-out Management Plan (preparation) 
	68
	 

	Dominica
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	74
	0.0

	Equatorial Guinea
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	40
	0.2

	Equatorial Guinea
	UNIDO
	PHA
	HCFC
	REF-Servicing - HPMP - Stage I
	82
	0.5

	Gabon
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	57
	1.0

	Gabon
	UNIDO
	PHA
	HCFC
	REF-Servicing - HPMP - Stage I
	131
	2.4

	Guinea
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	73
	0.8

	Guinea
	UNIDO
	PHA
	HCFC
	REF-Servicing - HPMP - Stage I
	172
	2.0

	India
	UNDP
	DEM
	HCFC
	Demonstration project for development and evaluation of spray foam polyol systems for buildings using HFOs as blowing agent
	1,000
	33.0

	India
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	97
	1.4

	Kuwait
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	372
	8.0

	Kuwait
	UNIDO
	PHA
	HCFC
	FOA-XPS - HPMP - Stage I
	1,129
	25.5

	Kuwait
	UNEP
	PRP
	HCFC
	Stage 2 - HCFC Phase-out Management Plan (preparation) 
	68
	 

	Kuwait
	UNIDO
	PRP
	HCFC
	FOA-Rigid PU foam - Preparation of Stage II HPMP 
	86
	0.0

	Kuwait
	UNIDO
	PRP
	HCFC
	REF-Air Conditioning - Preparation of Stage II HPMP 
	86
	0.0

	Kuwait
	UNIDO
	PRP
	HCFC
	REF-Servicing - Preparation of Stage II HPMP 
	32
	0.0

	Marshall Islands (the)
	UNEP
	INS
	SEV
	Institutional Strengthening
	85
	 

	Mauritania
	UNDP
	PHA
	HCFC
	Stage I HPMP
	42
	0.9

	Mauritania
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	86
	1.7

	Mexico
	UNIDO
	INS
	SEV
	Institutional Strengthening
	338
	0.0

	Morocco
	UNEP
	INS
	SEV
	Institutional Strengthening
	200
	 

	Morocco
	Italy
	PHA
	HCFC
	REF-Servicing - HPMP Stage II
	150
	1.7

	Morocco
	UNIDO
	PHA
	HCFC
	REF-Servicing - HPMP Stage II
	467
	5.0

	Morocco
	UNIDO
	PHA
	HCFC
	FOA-Rigid PU foam - HPMP Stage II
	538
	7.9

	Mozambique
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	34
	0.2

	Mozambique
	UNIDO
	PHA
	HCFC
	REF-Servicing - HPMP - Stage I
	82
	0.5

	Myanmar
	UNEP
	INS
	SEV
	Institutional Strengthening
	85
	 

	Myanmar
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	21
	0.1

	Namibia
	UNEP
	INS
	SEV
	Institutional Strengthening
	85
	 

	Nauru
	UNEP
	INS
	SEV
	Institutional Strengthening
	85
	 

	Niger (the)
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	141
	1.3

	Niger (the)
	UNIDO
	PHA
	HCFC
	REF-Servicing - HPMP - Stage I
	97
	0.9

	Nigeria
	UNDP
	PHA
	HCFC
	Stage II HPMP (foam)
	545
	8.0

	Nigeria
	UNDP
	PHA
	HCFC
	Stage II HPMP (servicing)
	523
	5.6

	Nigeria
	UNIDO
	PHA
	HCFC
	REF-Manufacturing - HPMP Stage II
	1,634
	10.0

	Panama
	UNDP
	PHA
	HCFC
	HCFC-INV: Foams - HPMP Stage I
	327
	4.8

	Panama
	UNEP
	PHA
	HCFC
	Stage 2 - HCFC Phase-out Management Plan (implementation)
	22
	0.2

	Peru
	UNEP
	PHA
	HCFC
	Stage 2 - HCFC Phase-out Management Plan (implementation)
	14
	0.3

	Philippines (the)
	World Bank
	PHA
	HCFC
	REF-Air conditioning - HPMP Stage II
	789
	5.4

	Philippines (the)
	World Bank
	PHA
	HCFC
	REF-Commercial refrigeration - HPMP Stage II
	277
	3.0

	Qatar
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	170
	4.3

	Qatar
	UNIDO
	PHA
	HCFC
	REF-Servicing - HPMP - Stage I
	160
	4.2

	Saint Lucia
	UNEP
	INS
	SEV
	Institutional Strengthening
	85
	 

	Saint Vincent and the Grenadines
	UNEP
	INS
	SEV
	Institutional Strengthening
	85
	 

	Saudi Arabia
	UNEP
	INS
	SEV
	Institutional Strengthening
	256
	 

	Serbia
	UNIDO
	INS
	SEV
	Institutional Strengthening
	180
	0.0

	Serbia
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	16
	0.0

	Serbia
	UNIDO
	PHA
	HCFC
	REF-Servicing and REF-Manufacturing - HPMP - Stage I
	73
	0.2

	Somalia
	UNIDO
	PHA
	HCFC
	FOA-Rigid PU foam - HPMP - Stage I
	151
	0.8

	South Africa
	UNIDO
	PRP
	HCFC
	REF-Manufacturing - Preparation of Stage II HPMP 
	161
	0.0

	South Africa
	UNIDO
	PRP
	HCFC
	REF-Servicing - Preparation of Stage II HPMP 
	96
	0.0

	Suriname
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	40
	0.1

	Suriname
	UNIDO
	PHA
	HCFC
	REF-Servicing - HPMP - Stage I
	32
	0.1

	Swaziland
	UNEP
	INS
	SEV
	Institutional Strengthening
	85
	 

	The former Yugoslav Republic of Macedonia
	UNIDO
	PHA
	HCFC
	REF-Servicing, FOA & INS - HPMP - Stage I
	88
	0.2

	Timor-Leste
	UNDP
	PHA
	HCFC
	Stage I HPMP
	12
	0.0

	Timor-Leste
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	19
	0.0

	Timor-Leste
	UNEP
	PHA
	HCFC
	Stage 2 - HCFC Phase-out Management Plan (implementation)
	19
	0.0

	Togo
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	70
	0.7

	Togo
	UNIDO
	PHA
	HCFC
	REF-Servicing - HPMP - Stage I
	161
	1.7

	Trinidad and Tobago
	UNDP
	INS
	SEV
	Institutional Strengthening
	91
	0.0

	Tunisia
	UNEP
	PRP
	HCFC
	Stage 2 - HCFC Phase-out Management Plan (preparation)
	23
	 

	Turkey
	Italy
	PHA
	HCFC
	REF-Servicing - HPMP Stage II
	150
	1.7

	Turkey
	UNIDO
	PHA
	HCFC
	REF-Servicing - HPMP - Stage I
	1,711
	52.6

	Uganda
	UNEP
	INS
	SEV
	Institutional Strengthening
	85
	 

	Venezuela (Bolivarian Republic of)
	Italy
	PHA
	HCFC
	REF-Servicing - HPMP Stage II
	100
	1.4

	Yemen
	UNEP
	INS
	SEV
	Institutional Strengthening
	218
	 

	Yemen
	UNEP
	PHA
	HCFC
	HCFC Phase-out Management Plan (implementation) - Stage I
	186
	13.2

	Yemen
	UNIDO
	PRP
	HCFC
	REF-Manufacturing - Preparation of Stage II HPMP 
	41
	0.0

	Yemen
	UNIDO
	PRP
	HCFC
	REF-Servicing - Preparation of Stage II HPMP 
	73
	0.0
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Pre - session documents of the Executive Committee of the Multilateral Fund for the Implementation of the Montreal Protocol are  without prejudice to any decision that the Executive  Committee might take following issu ance   of the document.    

UNITED   NATIONS  EP  

 United Nations   Environment   Programme    Distr.   GENERAL       UNEP/OzL.Pro/ExCom/77/5   3 November 2016     ORIGINAL: ENGLISH  

EXECUTIVE COMMITTEE OF      THE MULTILATERAL FUND FOR THE      IMPLEMENTATION OF THE MONTREAL PROTOCOL   Seventy - seventh   Meeting   Montreal,  28 November  -   2 December 2016       UPDATE ON THE STATUS OF IMPLEMENTATION OF THE 2016 - 2018 CONSOLIDATED  BUSINESS PLAN OF THE MUL TILATERAL FUND     1.   At the 75 th   meeting, the Executive Committee endorsed the consolidated business plan of the  Multilateral Fund for 2016 - 2018. In response to decision 75/22(b) and (c), the Secretariat adjusted the  consolidated 2016 - 2018 business plan

1

, which was further adjusted pursuant to decision   76/3(c), as shown  in Table   1.    Table 1. R esource allocation of the 2016 - 2018 consolidated business plan of the Multilateral Fund  (US   $)  

Description  2016  2017  2018  Total  Approved  MYAs  after 2018  

Required  for compliance  

Approved multi - year agreements  (MYAs)  22,267,577  11,922,133  16,645,965  50,835,675  13,365,125  

HCFC production phase - out  management plan (HPPMP)  preparation  –   stage I  107,000  0  0  107,000     

HPPMP  –   stage I  0  0  532,500  532,500     

HPPMP  –   stage II  0  21,874,286  21,874,286  43,748,571     

HCFC phase - out management plan  (HPMP) preparation  –   stage   II  1,814,755  408,336  3,611,279  5,834,369     

HPMP preparation  –   stage III  0    0  22,600  22,600     

HPMPs and HPMP investment projects  –   stage I  564,098  2,453,989  330,800  3,348,887     

HPMPs and HPMP investment projects  –   stage II  114,913,217  109,823,665  158,190,630  382,927,512     

HPMP verification  588,600  588,600  588,600  1,765,800     

Low global - warming potential (GWP)  alternative demonstration projects  7,674,500  0  0  7,674,500     
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  The adjusted consolidated  2016 - 2018 business plan was sent to bilateral and implementing agencies on  8   December 2015.  

