| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/88/17 14 October 2021 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-eighth Meeting

Montreal, 15-19 November 2021

PROGRESS REPORT OF THE WORLD BANK AS AT 31 DECEMBER 2020

# This document presents the progress report of the World Bank as at 31 December 2020.

Introduction

# The progress report of the World Bank includes the status of implementation of projects, including five HFC-related projects that have been funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2020, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs which are measured in mt CO2-eq.

Scope of the document

# This document consists of the following parts:

## Part I:	Projects approved under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2020 and cumulative since 1991 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs); it contains a review on the status of implementation of each ongoing project at the country level; and it identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## Part II:	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down. It provides a summary on the status of implementation of HFC phase-down projects funded under the voluntary contributions.

Recommendation.

# The document also contains the following annexes:

Annex I: 	A summary status and a recommendation for each ongoing project with outstanding issues for consideration by the Executive Committee.

Annex II: 	An analysis of the progress report.

Part I: 	Projects approved under the regular contributions to the Multilateral Fund

Summary of progress in implementation of projects for 2020 and cumulative

# Implementation of projects and activities by the World Bank for 2020 and cumulative since 1991 up to 31 December 2020, is summarized as follows:

## Phase-out: In 2020, 675.1 ODP tonnes of consumption of controlled substances were phased out and an additional 808.8 ODP tonnes of consumption of controlled substances were approved for phase-out. Since 1991, 147,415 ODP tonnes of consumption of controlled substances and 187,996 ODP tonnes of production of controlled substances had been phased out, of an expected total of 305,406 ODP tonnes from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2020, US $12.52 million was disbursed and US $18.16 million was planned for disbursement based on the 2019 progress report, representing a rate of disbursement of 69 per cent of that planned. Cumulatively, US $1.15 billion had been disbursed out of the total US $1.16 billion approved for disbursement (excluding agency support costs), representing a rate of disbursement of 99 per cent. In 2020, US $2.07 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $5.45/kg and for the production sector was US $4.86/kg. The average cost-effectiveness of investment projects per ODP tonne was US $3.20/kg for completed projects and US $36.12/kg for ongoing projects;

## Number of projects completed: In 2020, one project was completed. Since 1991, 1,077 projects of the 1,090 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 99 per cent;

## Speed of delivery – investment projects: The World bank did not complete any investment project in 2020. Since 1991, the average time for completion of investment projects has been 40 months after their approval. First disbursements under these projects occurred, on average, 24 months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2020 were completed on average 13 months after their approval. Since 1991, the average time for completion of non-investment projects has been 36 months after their approval. First disbursements under these projects occurred, on average, 22 months after they had been approved;

## Project preparation: All of the 291 project preparation activities approved by the end of 2020 have been completed;

## Implementation delays: A total of 13 projects were under implementation at the end of 2020, experiencing, on average, a delay of 15 months. Two of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2020, five MYAs for HCFC phase-out management plans (HPMPs) and one HCFC production phase-out management plan (HPPMP) were under implementation. Since 1991, 40 MYAs have been approved and 34 MYAs have been completed, representing a completion rate of 85 per cent.

Project implementation progress in 2020

# Further to the review process, a number of issues were discussed and satisfactorily addressed, except for issues on two projects classified as projects with implementation delays that are related to components of MYAs that are subject to procedures for project cancellation, in line with decision 84/45(c). Annex I to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendation requesting the submission of a report to the 90th meeting.

# Details of progress in implementation of projects associated with the HPPMP for China and the HPMPs for China (polyurethane foam sector plan) and Indonesia have been submitted to the 88th meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. The issues relating to the HPMPs for Jordan and Thailand that were due at the 88th meeting but were not submitted, are addressed in the document on tranche submission delays.

# In line with decision 82/11(c)(ii), the Secretariat noted that renewal of the IS project for Jordan had not been submitted for the last two years; the main reason is lower disbursements during the period 2020-2021 as some of the planned meetings and workshops could not be undertaken due to restrictions imposed by the COVID-19 pandemic. The World Bank informed that it is planning to submit the renewal request by 2022.

# Of the 11 ongoing projects, excluding IS and project preparation, one project has revised its planned date of completion since the 2019 progress report.

# Part II:	PROJECTS APPROVED UNDER THE ADDITIONAL VOLUNTARY CONTRIBUTIONS FOR FAST-START SUPPORT FOR HFC PHASE-DOWN

# As of 31 December 2020, the Executive Committee had approved five HFC-related projects under the additional voluntary contributions amounting to US $963,514 (excluding agency support costs). A summary of the status of these projects is presented in Table 1.

# Table 1. Status of approved HFC-related projects as of the end of 2020

| Type | Number of projects* |  |  | Funding (US $)*** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 1 | 0 | 0 | 183,514 | 0 | 183,514 | 0 |
| Project preparation | 1 | 1 | 100 | 30,000 | 30,000 | 0 | 100 |
| Enabling activities | 3 | 1 | 33 | 750,000 | 365,451 | 384,550 | 49 |
| Total | 5 | 2 | 40 | 963,514 | 395,451 | 568,064 | 41 |

*Excludes transferred projects.

** 8.8 mt (12,555 mt CO2-eq.) of HFCs to be phased out.

**Excludes agency support costs.

# As of the end of 2020, of the five projects approved, one project preparation and one enabling activity had been completed. Extension of the completion dates of the two ongoing enabling activities was approved; these activities are at various stages of implementation. Further to the review process, one project for enabling activities and one investment project are classified as projects with implementation delays and are included in Annex I to the present document containing the Secretariat’s recommendation to request the submission of a report to the 90th meeting.

# In line with decision 82/11(b), the World Bank has requested further extension of the duration of one project for enabling activities as shown Table 2.

# Table 2. Project for which an extension of the completion date has been requested

| Country/Project code | Project title | Disbursement (%) | Status / Issues | Revised completion date | Date of completion requested |
| --- | --- | --- | --- | --- | --- |
| Thailand THA/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 39 | Due to COVID-19 restrictions, delays in completion of stakeholder workshops | Sep-2021 | Dec- 2021 |

# The investment project related to the phase-out of 8.8 mt (12,555 mt CO2-eq) of HFCs is currently under implementation The equipment for the production facility has been installed and the physical inspection has been delayed due to COVID-19 restrictions; completion of the project is expected by end of 2021.

# Of the total cumulative funding approved of US $963,514, US $395,451 had been disbursed, representing a disbursement rate of 41 per cent.

# Recommendation

# The Executive Committee may wish:

## To note the progress report of the World Bank as at 31 December 2020 contained in document UNEP/OzL.Pro/ExCom/88/17;

## To approve the extension of the completion date, to 31 December 2021, of the enabling activities for HFC phase-down for Thailand (THA/SEV/80/TAS/01+), to allow for completion of the remaining ongoing activities as reflected in Table 2 of document UNEP/OzL.Pro/ExCom/88/17; and

## To approve the recommendations related to ongoing projects with specific issues contained in Annex I to the present document.

Annex I

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR THE WORLD BANK

| Country/project code* | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Indonesia IDS/SEV/81/TAS/01+ | Enabling activities for HFC phase-down | 7% | 12 months delays | To request the World Bank to report to the 90th meeting on this project with implementation delays |
| Thailand THA/PHA/82/INV/179 | HCFC phase-out management plan (stage II, first tranche) (spray foam sector) | 0% | 18 months delays | To request the World Bank to report to the 90th meeting on this project with implementation delays |
| Thailand THA/PHA/82/TAS/177 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector and project management unit) | 0% | 18 months delays | To request the World Bank to report to the 90th meeting on this project with implementation delays |
| Thailand THA/REF/82/INV/03+ | Conversion from HFC to propane (R-290) and isobutene (R-600a) as a refrigerant in manufacturing commercial refrigeration appliances in Pattana Intercool Co. Ltd. | 0% | 18 months delays | To request the World Bank to report to the 90th meeting on this project with implementation delays |

*Codes ending with “+” are from the additional contributions.

# Annex II

ANALYSIS OF THE PROGRESS REPORT OF THE WORLD BANK

AS AT 31 DECEMBER 2020

# This Annex consists of the following two parts:

## Part I:	Projects approved under the regular contributions to the Multilateral Fund.

## Part II:	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down.

Part I: 	Projects approved under the regular contributions to the Multilateral Fund

# As of 31 December 2020, the Executive Committee had approved US $1.28 billion, consisting of US $1.16 billion for the implementation of investment and non-investment projects and US $120.21 million for agency support costs, as shown in Table 1. In 2020, two new projects and activities were approved. This level of funding is expected to result in the phase-out of 305,406 ODP tonnes of consumption and production of controlled substances.

# Table 1: Approved funding by sector for the World Bank as at 31 December 2020

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 22,984,030 |
| Destruction | 400,000 |
| Foam | 136,339,172 |
| Halon | 70,221,038 |
| Fumigants | 5,837,887 |
| Multiple sectors | 2,341,168 |
| Other | 5,059,360 |
| Phase-out plan | 202,645,157 |
| Process agent | 114,342,497 |
| Production | 378,930,190 |
| Refrigeration | 180,259,970 |
| Several | 28,969,731 |
| Solvents | 10,237,394 |
| Sterilant | 661,227 |
| Sub-total | 1,159,228,820 |
| Agency support costs | 120,209,090 |
| Total | 1,279,437,910 |

# A summary of the status of projects implemented by category is presented in Table 2.

Table 2: Status of project implementation by category

| Type | Number of projects* |  |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved |  | Disbursed | Balance | % disbursed |
| Country programme | 29 | 29 | 100 | 1,627,732 |  | 1,627,732 | 0 | 100 |
| Demonstration | 8 | 8 | 100 | 6,172,901 |  | 6,172,901 | 0 | 100 |
| Institutional strengthening (IS) | 50 | 48 | 96 | 9,569,981 |  | 9,063,388 | 506,593 | 95 |
| Investment | 634 | 625 | 99 | 1,099,167,100 |  | 1,089,082,549 | 10,084,551 | 99 |
| Project preparation | 291 | 291 | 100 | 26,623,320 |  | 26,623,320 | 0 | 100 |
| Technical assistance | 74 | 72 | 97 | 15,762,020 |  | 14,947,550 | 814,470 | 95 |
| Training | 4 | 4 | 100 | 305,766 |  | 305,766 | 0 | 100 |
| Total | 1,090 | 1,077 | 99 | 1,159,228,820 |  | 1,147,823,206 | 11,405,615 | 99 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

# Table 3 presents an overview of the status of project implementation by year. All projects and activities approved between 1991 and 2015, and 2017, have now been completed.

Table 3: Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US$)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 42 | 42 | 100 | 5,429,404 | 5,429,404 | 0 | 100 |
| 1992 | 76 | 76 | 100 | 28,047,705 | 28,047,705 | 0 | 100 |
| 1993 | 79 | 79 | 100 | 42,538,405 | 42,538,405 | 0 | 100 |
| 1994 | 91 | 91 | 100 | 41,081,267 | 41,081,267 | 0 | 100 |
| 1995 | 112 | 112 | 100 | 47,224,186 | 47,224,186 | 0 | 100 |
| 1996 | 55 | 55 | 100 | 29,319,479 | 29,319,479 | 0 | 100 |
| 1997 | 95 | 95 | 100 | 56,173,102 | 56,173,103 | -1 | 100 |
| 1998 | 59 | 59 | 100 | 35,959,418 | 35,959,417 | 1 | 100 |
| 1999 | 73 | 73 | 100 | 64,173,138 | 64,173,138 | 0 | 100 |
| 2000 | 67 | 67 | 100 | 36,982,134 | 36,982,133 | 1 | 100 |
| 2001 | 29 | 29 | 100 | 55,212,853 | 55,212,854 | -1 | 100 |
| 2002 | 32 | 32 | 100 | 64,357,778 | 64,357,778 | 0 | 100 |
| 2003 | 24 | 24 | 100 | 72,734,119 | 72,734,119 | 0 | 100 |
| 2004 | 29 | 29 | 100 | 77,111,770 | 77,111,770 | 0 | 100 |
| 2005 | 28 | 28 | 100 | 68,592,865 | 68,592,865 | 0 | 100 |
| 2006 | 22 | 22 | 100 | 64,473,260 | 64,473,260 | 0 | 100 |
| 2007 | 25 | 25 | 100 | 66,005,270 | 66,005,270 | 0 | 100 |
| 2008 | 28 | 28 | 100 | 40,214,774 | 40,214,774 | 0 | 100 |
| 2009 | 22 | 22 | 100 | 25,563,461 | 25,563,461 | 0 | 100 |
| 2010 | 16 | 16 | 100 | 1,148,623 | 1,148,623 | 0 | 100 |
| 2011 | 10 | 10 | 100 | 44,335,997 | 44,335,997 | 0 | 100 |
| 2012 | 10 | 10 | 100 | 11,698,145 | 11,698,145 | 0 | 100 |
| 2013 | 7 | 7 | 100 | 43,602,958 | 43,602,958 | 0 | 100 |
| 2014 | 13 | 13 | 100 | 28,336,509 | 28,336,509 | 0 | 100 |
| 2015 | 13 | 13 | 100 | 62,990,648 | 62,990,648 | 0 | 100 |
| 2016 | 18 | 15 | 83 | 12,601,632 | 12,320,351 | 281,281 | 98 |
| 2017 | 3 | 3 | 100 | 1,651,291 | 1,651,291 | 0 | 100 |
| 2018 | 7 | 1 | 14 | 26,408,870 | 19,350,245 | 7,058,625 | 73 |
| 2019 | 3 | 1 | 33 | 3,192,747 | 160,546 | 3,032,201 | 5 |
| 2020 | 2 | 0 | 0 | 2,067,012 | 1,033,506 | 1,033,506 | 50 |
| Total | 1,090 | 1,077 | 99 | 1,159,228,820 | 1,147,823,206 | 11,405,615 | 99 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

# Table 4 presents project implementation by country for 2020.

Table 4. Summary of project implementation by the World Bank for 2020

| Country | Phased out in 2020*(ODP tonnes) | Percentage of planned phase-out achieved in 2020 | Estimated funds disbursed in 2020 (US$) | Funds disbursed in 2020 (US$) | Percentage of funds disbursed over estimation in 2020 | Percentage of planned projects completed in 2020 |
| --- | --- | --- | --- | --- | --- | --- |
| China | 675.1 |  | 15,209,005 | 11,642,511 | 77 |  |
| Indonesia | 0.0 |  | 296,819 | 304,002 | 102 |  |
| Jordan | 0.0 |  | 425,349 | 278,156 | 65 | 0 |
| Thailand | 0.0 |  | 458,737 | 0 | 0 | 0 |
| Viet Nam | 0.0 | 0 | 1,769,783 | 295,934 | 17 | 0 |
| Global | 0.0 |  | 0 | 0 |  | 100 |
| Total | 675.1 | 0 | 18,159,693 | 12,520,603 | 69 | 25 |

* No phase-out in 2020 for HFC-related projects.

# Part II:	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2020, the Executive Committee had approved five HFC-related projects under the additional voluntary contributions amounting to US $963,514 (excluding agency support costs). A summary of the status of these projects is presented in Table 5.

# Table 5. Status of approved HFC-related projects as of the end of 2020

| Type | Number of projects* |  |  | Funding (US $)*** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 1 | 0 | 0 | 183,514 | 0 | 183,514 | 0 |
| Project preparation | 1 | 1 | 100 | 30,000 | 30,000 | 0 | 100 |
| Enabling activities | 3 | 1 | 33 | 750,000 | 365,451 | 384,550 | 49 |
| Total | 5 | 2 | 40 | 963,514 | 395,451 | 568,064 | 41 |

* Excludes transferred projects.

** 8.8 mt (12,555 mt CO2-eq.) of HFCs to be phased out.

** Excludes agency support costs.

# As of the end of 2020, of the five projects approved, one project preparation and one enabling activity had been completed. Extension of the completion dates of the two ongoing enabling activities was approved; these activities are at various stages of implementation.

# The investment project related to the phase-out of 8.8 mt (12,555 mt CO2-eq.) of HFCs is currently under implementation; equipment for the production facility with alternative technology is installed and the project is expected to be completed after physical inspection which is delayed due to COVID-19 restrictions. This project is expected to be completed by end of 2021.

# Of the total cumulative funding approved of US $963,514, US $395,451 had been disbursed, representing a disbursement rate of 41 per cent.

Online meetings and an intersessional approval process will be held in November and December 2021 due to coronavirus disease (COVID-19)

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database that is available upon request.

In line with decision 84/12(a)(iv), the measurement for HFCs in mt CO2-eq. is included in the progress reports submitted to the 88th meeting.

Ongoing projects are all projects that were under implementation as at 31 December 2020. Key indicators of progress include: percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

In line with decision 84/12(b), a detailed progress report providing an overview of the objectives, status of implementation, key findings and lessons learned, the amounts of HFC phased out where applicable, the level of funds approved and disbursed and potential challenges in completing the projects and activities, is presented in the consolidated progress report (UNEP/OzL.Pro/ExCom/88/12).

All the controlled substances under these projects were ozone-depleting substances.

All the controlled substances under these projects were ozone-depleting substances.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61) (as demonstration projects, project preparation, and institutional strengthening (IS) are not subject to those procedures).

UNEP/OzL.Pro/ExCom/88/79

UNEP/OzL.Pro/ExCom/88/43

UNEP/OzL.Pro/ExCom/88/51

UNEP/OzL.Pro/ExCom/88/21

Any request for an extension would have to be submitted for approval by the Executive Committee in advance of

the project completion date, noting that no new commitments were to be made before the extension had been approved.

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively-financed projects.