| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/95/14 30 October 2024 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-fifth Meeting

Montreal, 4-8 December 2024

Item 7(a)(i) of the provisional agenda

CONSOLIDATED PROGRESS REPORT AS AT 31 DECEMBER 2023

Introduction

# The consolidated progress report summarises progress and financial information provided by bilateral and implementing agencies as of 31 December 2023, in their respective progress reports submitted to the Secretariat.

# The consolidated progress report and the progress reports of the bilateral and implementing agencies include all controlled substances under the Montreal Protocol. Given that HFC-related projects and activities have been funded either under the regular contributions to the Multilateral Fund or under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment, the information related to these projects is presented separately, based on the funding source. The analysis contained in the present document is based on ODP tonnes for all controlled substances except for HFCs, which are measured in metric tonnes (mt) and CO2-eq tonnes.

Review process by the Secretariat

# The Secretariat reviewed each of the annual progress reports submitted by bilateral and implementing agencies separately. The review was based on the milestones established for investment and non-investment projects including, inter alia, signing of agreements; date of release of first disbursement; status of procurement and installation of equipment; status of services provided, including training of refrigeration technicians and customs officers; level of disbursement of approved funds; the operational and financial completion of the project; and the return of fund balances.

# During the review process, potential issues were identified, inter alia, cases where agreements had not been signed due to delays in administrative approvals; instances where a national ozone officer was not in place; lack of financial progress reports; delayed procurement process predominantly due to supply chain issues; lack of availability of alternative technologies in local markets; and security-related issues at the country level. All projects with outstanding issues had either low disbursement rates of approved funds or/and required an extension of planned completion dates.

# The Secretariat also had several exchanges with each bilateral and implementing agency on projects and activities with outstanding issues, where several of the issues were satisfactorily resolved. For those projects and activities where the issues could not be resolved, the proposed recommendations for consideration by the Executive Committee were discussed and agreed with the relevant bilateral or implementing agencies. The projects and activities for which an extension of the completion dates has been requested, are considered in the main documents, while the lists of projects with outstanding issues are contained in annex III of each progress report of bilateral and implementing agencies. The recommendations will be considered during the discussions of each agency progress report at the 95th meeting.

# In line with decision 84/45(c), the Secretariat identified all the multi-year agreement (MYA) components with implementation delays and informed the relevant bilateral and implementing agencies. The Secretariat’s recommendations are contained in annex III of each progress report of the bilateral and implementing agencies.

# This document consists of the following sections:

## I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2023 and cumulative since 1991 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs). It also contains a review on the status of implementation of each ongoing project at the country level. It identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## II.	Projects approved for Annex F substances (HFCs) under the additional voluntary contributions for fast-start support for HFC phase-down.

III.	Secretariat comments.

IV.	Recommendation.

# The progress reports of bilateral or implementing agencies did not include any policy issue for consideration by the Executive Committee. Also, no policy issues were identified during the Secretariat’s review of the progress reports.

I.	Projects approved for all controlled substances under the regular contributions to the Multilateral Fund

I.1	Progress in implementation of projects for 2023 and cumulative since 1991

# As of 31 December 2023, the Executive Committee had approved US $4.08 billion in projects for bilateral and implementing agencies, consisting of US $3.65 billion for the implementation of investment and non-investment projects, and US $430.17 million for agency support costs, as shown in table 1.

Table 1. Approved funding by sector and agency as at 31 December 2023 (US $)

| Sector | UNDP | UNEP | UNIDO | World Bank | Bilateral | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Aerosol | 26,054,837 | 882,689 | 34,397,921 | 22,984,030 | 2,051,914 | 86,371,391 |
| Destruction | 4,156,279 | 950,040 | 5,005,540 | 500,000 | 1,866,282 | 12,478,141 |
| Energy efficiency | 280,000 | 1,292,000 | 2,976,620 | 60,000 | 843,745 | 5,452,365 |
| Foam | 173,220,713 | 0 | 88,536,237 | 136,059,064 | 8,093,730 | 405,909,744 |
| Halon | 4,996,973 | 767,640 | 1,780,369 | 70,221,038 | 6,147,361 | 83,913,381 |
| HFC phase-down plan | 9,494,076 | 7,498,715 | 14,014,915 | 5,585,704 | 774,000 | 37,367,410 |
| Fumigants | 20,081,241 | 2,614,366 | 78,028,741 | 5,837,887 | 18,226,925 | 124,789,159 |
| Multiple sectors | 0 | 0 | 139,440 | 2,341,168 | 0 | 2,480,608 |
| Other | 0 | 0 | 11,317,246 | 5,059,360 | 0 | 16,376,606 |
| Phase-out plan | 408,275,770 | 79,498,943 | 401,924,677 | 222,655,585 | 76,082,047 | 1,188,437,022 |
| Process agent | 1,286,923 | 0 | 6,337,359 | 114,342,497 | 0 | 121,966,779 |
| Production | 1,056,000 | 0 | 50,638,105 | 400,943,496 | 10,000,000 | 462,637,601 |
| Refrigeration | 139,759,577 | 13,856,016 | 182,196,588 | 180,259,970 | 40,910,116 | 556,982,267 |
| Several | 76,382,273 | 304,266,763 | 24,058,832 | 29,413,466 | 4,759,718 | 438,881,051 |
| Solvents | 63,699,997 | 198,860 | 23,247,443 | 10,237,394 | 2,512,738 | 99,896,432 |
| Sterilant | 417,628 | 0 | 0 | 661,227 | 0 | 1,078,855 |
| Sub-total | 929,162,287 | 411,826,032 | 924,600,031 | 1,207,161,885 | 172,268,576 | 3,645,018,812 |
| Agency support costs | 128,988,679 | 33,545,445 | 123,185,415 | 127,723,299 | 16,730,516 | 430,173,354 |
| Total | 1,058,150,966 | 445,371,477 | 1,047,785,446 | 1,334,885,184 | 188,999,093 | 4,075,192,166 |

# In 2023, 354 new projects and activities were approved. This level of funding is expected to result in the phase-out of 481,255 ODP tonnes of consumption and production of ODS and 4,246 mt (8,446,038 CO2-eq tonnes) of consumption of HFCs. Annex I shows the status of project implementation per country in 2023.

# Table 2 shows the status of project implementation including fund disbursement per project type as at 31 December 2023. Annex II presents analytical information since 1991.

Table 2. Status of project implementation by type as at 31 December 2023

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 165 | 165 | 100 | 7,266,559 | 7,266,559 | 0 | 100 |
| Demonstration | 146 | 134 | 92 | 63,858,148 | 60,881,838 | 2,976,310 | 95 |
| Institutional strengthening (IS) | 1,462 | 1,320 | 90 | 186,598,928 | 158,762,674 | 27,836,253 | 85 |
| Investment | 3,349 | 3,063 | 91 | 2,849,038,351 | 2,676,944,051 | 172,094,301 | 94 |
| Project preparation | 1,994 | 1,785 | 90 | 109,210,730 | 94,508,766 | 14,701,964 | 87 |
| Technical assistance | 2,077 | 1,867 | 90 | 403,239,332 | 365,923,409 | 37,315,923 | 91 |
| Training | 324 | 324 | 100 | 25,806,763 | 25,806,763 | 0 | 100 |
| Total | 9,517 | 8,658 | 91 | 3,645,018,812 | 3,390,094,061 | 254,924,751 | 93 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

# Implementation of projects and activities by bilateral and implementing agencies for 2023 and cumulative since 1991 up to 31 December 2023, is summarized as follows:

## Phase-out: In 2023, 724 ODP tonnes of ODS were phased out and an additional 1,395 ODP tonnes of consumption of ODS and 3,861 mt (7,809,960 CO2-eq tonnes) of consumption of HFCs were approved for phase-out. Since 1991, 498,607 ODP tonnes had been phased out, of an expected total of 481,255 ODP tonnes of consumption and production of ODS and 213.3 mt (305,336 CO2-eq tonnes) had been phased out, of an expected total of 4,246 mt (8,446,038 CO2-eq tonnes) of consumption of HFCs from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2023, US $82.74 million was disbursed and US $102.3 million was planned for disbursement based on the 2022 progress report, representing a rate of disbursement of 81 per cent of that planned. Cumulatively, US $3.39 billion had been disbursed out of the total US $3.65 billion approved for disbursement (excluding agency support costs), representing a rate of disbursement of 93 per cent. In 2023, US $112.09 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $8.64/kg. The cost-effectiveness for the production sector was US $4.56/kg. The average cost-effectiveness of investment projects per ODP tonne was US $5.32/kg for completed projects and US $15.79/kg for ongoing projects;

## Number of projects completed: In 2023, 263 projects were completed. Since 1991, 8,658 projects of the 9,517 projects (excluding closed or transferred projects) financed by the Multilateral Fund were completed, representing a completion rate of 91 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2023 were completed on average 50 months after their approval. Since 1991, the average time for completion of investment projects has been 38 months after their approval. First disbursements under these projects occurred, on average, 14 months after they had been approved;

## Speed of delivery – non-investment projects: Projects that were completed in 2023 were completed on average 38 months after their approval. Since 1991, the average time for completion of non-investment projects has been 38 months after their approval. First disbursements under these projects occurred, on average, 12 months after they had been approved;

## Project preparation: Of the 1,994 project preparation activities approved by the end of 2023, 1,785 have been completed, leaving 209 ongoing activities. In 2023, 89 project preparation activities were approved and 60 were completed;

## Implementation delays: A total of 859 projects were under implementation at the end of 2023, experiencing, on average, a delay of three months. One hundred and fourteen of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation, as demonstration projects, project preparation and IS are not subject to those procedures; and

## MYAs: In 2023, one HPPMP, 141 MYAs for HCFC phase-out management plans (HPMPs), 24 MYAs for Kigali HFC implementation plan (KIP) and two MYAs for control and phase-out of HFC-23 emissions were under implementation. Since 1991, 480 MYAs have been approved and 312 MYAs have been completed, representing a completion rate of 65 per cent. Annex IV summarizes the total funding approved and disbursed for HPMP activities at the country level.

# Table 3 summarizes progress made by bilateral and implementing agencies since 1991.

## Table 3: Progress made by bilateral and implementing agencies since 1991

| Phase out achieved |  | Disbursement (US $) | Average CE (US$/kg) |  | Number of projects |  | Speed of delivery for completion (months) |  | Average project delays (months) | Number of MYAs |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ODP tonnes | CO2-eq tonnes |  | Consump- tion | Produc- tion | Approved | Completed | Investment | Non- investment |  | Approved | Completed |
| 498,607 | 305,336 | 3,390,094,061 | 8.64 | 4.56 | 9,517 | 8,658 | 38 | 38 | 3 | 480 | 312 |

HFC-related projects

# As of 31 December 2023, the Executive Committee had approved 292 HFC-related projects (including 11 demonstration projects, 57 investment projects, 175 project preparation activities and 49 technical assistance projects) under regular contributions amounting to US $51,973,252 (excluding agency support costs). A summary of the status of these projects is presented in table 4 and the respective data has already been included in paragraphs 9 to 13.

Table 4. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Demonstration | 11 | 0 | 0 | 2,532,365 | 0 | 2,532,365 | 0 |
| Investment** | 57 | 4 | 7 | 26,557,678 | 6,407,176 | 20,150,502 | 24 |
| Project preparation | 175 | 41 | 23 | 17,559,510 | 6,982,025 | 10,577,484 | 40 |
| Technical assistance | 49 | 29 | 59 | 5,323,699 | 3,030,169 | 2,293,530 | 57 |
| Total | 292 | 74 | 25 | 51,973,252 | 16,419,371 | 35,553,881 | 32 |

* Excludes agency support costs.

# ** 213.3 mt (305,336 CO2-eq tonnes) of 4,246 mt (8,446,038 CO2-eq tonnes) of HFCs had been phased out.

# As of the end of 2023, of the 292 projects, four investment projects, 41 project preparation activities and 29 technical assistance projects for enabling activities had been completed. Of the 20 ongoing technical assistance projects remaining, one is for enabling activities, for which extension of the completion date was approved and which is expected to be completed in 2024. The remaining 19 ongoing technical assistance projects are expected to be completed in 2024 and 2026. The remaining 53 ongoing investment projects are expected to be completed between 2024 and 2026. One hundred and twenty-six of the 134 ongoing project preparation activities are for KIPs and are expected to be completed between 2024 and 2025; five are for pilot projects on energy efficiency per decision 91/65 and are expected to be completed in 2025; two are for KIP investment projects and one is for an HFC demonstration project, and they are expected to be completed in 2024 and 2025. The 11 ongoing demonstration projects are expected to be completed in 2025 and 2026.

# Of the total cumulative funding approved of US $51,973,252 (excluding agency support costs), US $16,419,371 had been disbursed, representing a disbursement rate of 32 per cent.

# Annex III provides information on all HFC-related projects and activities under the Multilateral Fund, irrespective of the source of funding, at the country level, indicating the status of ratification of the Kigali Amendment and the status of the HFC licensing system.

I.2	Issues identified in project implementation in 2023

# Based on planned completion dates reported in the 2022 progress report, and the results reported in the 2023 progress reports, bilateral and implementing agencies completed 57 per cent of the projects they had planned to complete in 2023. One hundred and twenty-five of the 508 ongoing projects (excluding IS and project preparation) have revised their planned dates of completion since the 2022 progress report.

# Bilateral and implementing agencies achieved an overall rate of disbursement of 81 per cent in 2023. On a country/region basis, 59 countries (including regions) had a disbursement rate of over 85 per cent while 44 countries had a disbursement rate of below 50 per cent.

# In total, bilateral and implementing agencies are requested to report, at the 96th meeting, on 114 ongoing projects with implementation delays and 11 ongoing tranches of MYAs, renewal of IS projects, and preparation of HPMPs, recommended for status reports.

# At its 82nd meeting, the Executive Committee requested bilateral and implementing agencies, inter alia, to provide an update, prior to the last meeting of every year, on the countries for which requests for renewal of IS projects had not been submitted for two years (decision 82/11(c)(ii)). At its 91st meeting, the Committee decided to extend the duration of IS renewal implementation phases from the current two years to three years for IS renewal proposals submitted from the 92nd meeting onwards (decision 91/63(e)). In light of this, the time period referred to in decision 82/11(c)(ii) could also be extended from two years to three years. This change will help maintain continuity in monitoring the periodic submission of IS renewal proposals by Article 5 countries.

# The Executive Committee may wish to consider requesting bilateral and implementing agencies to provide an update, prior to the last meeting of every year, on the countries for which requests for renewal of IS projects had not been submitted for three years, instead of two years specified in decision 82/11(c)(ii).

II.	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2023, the Executive Committee had approved 144 HFC-related projects under the additional voluntary contributions amounting to US $22.75 million (excluding agency support costs). A summary of the status of these projects is presented in table 5.

# Table 5. Status of approved HFC-related projects as of the end of 2023

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 6 | 6 | 100 | 8,396,417 | 8,153,068 | 243,349 | 97 |
| Project preparation | 10 | 10 | 100 | 214,781 | 214,780 | 1 | 100 |
| Technical assistance | 128 | 128 | 100 | 14,140,333 | 13,843,589 | 296,744 | 98 |
| Total | 144 | 144 | 100 | 22,751,531 | 22,211,436 | 540,095 | 98 |

*Excludes agency support costs.

** 678.8 mt (970,373 CO2-eq tonnes) of 775.4 mt (1,108,442 CO2-eq tonnes) of HFCs had been phased out.

# All the 144 projects approved by the end of 2023 have been completed.

# Cumulatively, US $22,211,436 had been disbursed out of the total US $22,751,531 approved for disbursement (excluding agency support costs), representing a disbursement rate of 98 per cent.

# Since the projects approved under the additional voluntary contributions for fast-start support for HFC phase-down have all been completed and the remaining balances will be returned to the Secretariat, the Secretariat will no longer report on those projects in the future annual and financial progress report.

# III.	Secretariat comments

# The Secretariat noted that due to operational issues, some of the projects and tranches of HPMPs were delayed. In line with decision 82/11(b), extension for these projects to various dates up to 31 December 2025 need to be approved by the Executive Committee. The recommendations for the extension of completion dates of HPMPs for Thailand (World Bank) and the Sudan (UNIDO), and the cancellation of stage I of the HPMP for Haiti (UNEP) are addressed, as applicable, in the progress reports of the respective implementing agencies.

# The agencies have continued to provide information on specific steps taken to address delays in implementation of activities, including the analysis of the relevant root causes and information on how to avoid reoccurrence. Similar to the information reported in the 2022 progress report, the main issues identified include delays in procurement and distribution of equipment mainly due to the specialised technical nature of equipment; slower market uptake of low-global-warming-potential (GWP) technologies; structural changes in the Government including changes in national ozone unit (NOU); political/security situation; and delays in the submission of reports due to the lack of capacity of the NOU. The main actions taken by the agencies include defining procedures for timely procurement of equipment through long-term agreements with qualified suppliers; for promoting the adoption of low-GWP alternative technologies, close coordination with the NOU and industry and implementation of targeted programmes, and addressing technical and operational barriers through project activities; close coordination with Governments including consultations during the network and other meetings on specific country-level issues and defining plans of actions for addressing administrative issues; and training and capacity building of NOU staff and involving senior Government management staff on aspects relating to operational progress monitoring and reporting. At its 93rd meeting, the Executive Committee approved an increase in the funding support provided to implementing agencies to strengthen their capacities to provide technical and policy assistance to Article 5 countries during the triennium 2024-2026 (decision 93/95). This increase is expected to enable more effective implementation of various activities, particularly for low-volume-consuming countries.

Gender mainstreaming

# All agencies have undertaken different steps, at the agency level, NOU level and project level, in implementing the operational gender mainstreaming policy of the Multilateral Fund. The activities mainly include awareness and information outreach to NOUs and other stakeholders on the gender mainstreaming policy and actions needed for ensuring better gender balance during project implementation. The agencies closely work with the national counterparts and relevant project units to ensure that they have a good understanding of the gender mainstreaming policy, include provisions in all activities to encourage women participation at different levels (e.g., as consultants, project management personnel, trainees), work with the relevant stakeholders on collecting gender-disaggregated data during different activities and challenges faced in implementing the gender policy and plan and implement measures to address these challenges. UNEP, through its Compliance Assistance Programme’s regional network meetings, also includes sessions to promote the gender mainstreaming policy and actions that need to be taken to effectively implement the policy.

IV.	Recommendation

# The Executive Committee may wish:

## To note:

### The consolidated progress report of the Multilateral Fund as at 31 December 2023 contained in document UNEP/OzL.Pro/ExCom/95/14;

### With appreciation, the efforts undertaken by bilateral and implementing agencies in reporting their 2023 activities;

### That the bilateral and implementing agencies would report, at the 96th meeting, on 114 projects with implementation delays and 11 ongoing projects recommended for additional status reports, as contained in annex III of each individual progress report of bilateral and implementing agencies; and

## To request bilateral and implementing agencies to provide an update, prior to the last meeting of every year, on the countries for which requests for renewal of institutional strengthening projects had not been submitted for three years, instead of two years as specified in decision 82/11(c)(ii).

Annex I

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION

PER COUNTRY FOR 2023

# Table 1 of annex I presents the status of project implementation by country for 2023 in achieved phased out, planned and achieved disbursements and project completion.

Table 1. Status of project implementation for 2023

| Country | Phased out in 2023 (ODP tonnes) | Phased out in 2023 (CO2-eq tonnes)* | Estimated funds disbursed in 2023 (US$) | Funds disbursed in 2023 (US$) | Percentage of funds disbursed over estimation in 2023 | Percentage of planned projects completed in 2023** |
| --- | --- | --- | --- | --- | --- | --- |
| Afghanistan | 0.0 | 0 | 283,939 | 17,415 | 6 | 0 |
| Albania | 0.0 | 0 | 179,796 | 308,391 | 172 | 100 |
| Algeria | 0.0 | 0 | 165,316 | 81,725 | 49 |  |
| Angola | 0.0 | 0 | 530,404 | 257,437 | 49 | 0 |
| Antigua and Barbuda | 0.0 | 0 | 36,000 | 25,000 | 69 | 0 |
| Argentina | 18.0 | 0 | 949,837 | 1,260,563 | 133 | 17 |
| Armenia | 0.0 | 0 | 91,783 | 167,984 | 183 | 50 |
| Bahamas (the) | 0.0 | 0 | 185,575 | 141,011 | 76 | 100 |
| Bahrain | 0.0 | 0 | 166,576 | 289,743 | 174 |  |
| Bangladesh | 1.8 | 0 | 1,664,104 | 1,125,397 | 68 | 67 |
| Barbados | 0.0 | 0 | 212,587 | 61,586 | 29 | 100 |
| Belize | 0.0 | 0 | 141,285 | 144,880 | 103 | 100 |
| Benin | 1.6 | 0 | 140,550 | 150,358 | 107 | 100 |
| Bhutan | 0.0 | 0 | 79,413 | 29,735 | 37 | 0 |
| Bolivia (Plurinational State of) | 0.2 | 0 | 171,970 | 141,480 | 82 | 50 |
| Bosnia and Herzegovina | 0.3 | 0 | 133,012 | 124,900 | 94 |  |
| Botswana | 1.3 | 0 | 476,095 | 184,491 | 39 | 71 |
| Brazil | 0.0 | 0 | 3,845,830 | 1,468,793 | 38 | 50 |
| Brunei Darussalam | 0.0 | 0 | 169,179 | 80,663 | 48 | 0 |
| Burkina Faso | 0.5 | 0 | 82,068 | 52,057 | 63 | 75 |
| Burundi | 0.0 | 0 | 51,600 | 87,209 | 169 | 100 |
| Cabo Verde | 0.0 | 0 | 146,300 | 2,845 | 2 |  |
| Cambodia | 0.0 | 0 | 190,740 | 220,589 | 116 | 100 |
| Cameroon | 7.2 | 0 | 332,161 | 514,723 | 155 | 100 |
| Chad | 1.0 | 0 | 137,350 | 160,562 | 117 |  |
| Chile | 1.0 | 0 | 988,503 | 1,096,005 | 111 | 100 |
| China | 447.4 | 0 | 31,506,448 | 22,411,405 | 71 | 70 |
| Colombia | 0.0 | 0 | 1,253,274 | 798,270 | 64 | 75 |
| Comoros (the) | 0.0 | 0 | 73,089 | 7,438 | 10 | 50 |
| Congo (the) | 0.0 | 0 | 73,782 | 55,597 | 75 | 67 |
| Cook Islands (the) | 0.0 | 0 | 125,123 | 37,002 | 30 | 0 |
| Costa Rica | 0.0 | 0 | 442,376 | 242,924 | 55 |  |
| Cote d’Ivoire | 0.0 | 0 | 459,654 | 419,963 | 91 | 100 |
| Cuba | 0.0 | 0 | 361,705 | 334,474 | 92 | 0 |
| Democratic People's Republic of Korea (the) | 0.0 | 0 | 3 | 0 | 6 | 0 |
| Democratic Republic of the Congo (the) | 0.0 | 0 | 162,212 | 9,874 | 6 |  |
| Djibouti | 0.0 | 0 | 83,850 | 20,905 | 25 | 0 |
| Dominica | 0.0 | 0 | 171,814 | 105,895 | 62 | 0 |
| Dominican Republic (the) | 0.0 | 0 | 326,151 | 385,326 | 118 | 100 |
| Ecuador | 0.0 | 0 | 259,000 | 360,060 | 139 | 100 |
| Egypt | 13.3 | 0 | 3,061,953 | 3,353,252 | 110 | 40 |
| El Salvador | 0.0 | 0 | 320,600 | 118,507 | 37 |  |
| Equatorial Guinea | 0.0 | 0 | 92,404 | 0 | 0 | 50 |
| Eritrea | 0.0 | 0 | 90,000 | 63,759 | 71 | 100 |
| Eswatini (the Kingdom of) | 0.0 | 0 | 173,391 | 136,450 | 79 | 100 |
| Ethiopia | 0.0 | 0 | 223,605 | 101,315 | 45 |  |
| Fiji | 0.0 | 0 | 320,879 | 123,410 | 38 | 33 |
| Gabon | 0.0 | 0 | 144,161 | 76,949 | 53 | 67 |
| Gambia (the) | 0.0 | 0 | 226,852 | 167,971 | 74 | 50 |
| Georgia | 0.0 | 0 | 113,085 | 101,666 | 90 |  |
| Ghana | 5.0 | 0 | 549,176 | 730,806 | 133 | 100 |
| Grenada | 0.0 | 0 | 140,555 | 28,860 | 21 | 25 |
| Guatemala | 0.0 | 0 | 139,972 | 142,427 | 102 | 67 |
| Guinea | 0.0 | 0 | 106,028 | 71,600 | 68 | 100 |
| Guinea-Bissau | 0.0 | 0 | 91,922 | 42,520 | 46 | 50 |
| Guyana | 0.0 | 0 | 119,986 | 73,977 | 62 | 50 |
| Haiti | 0.0 | 0 | 97,751 | 58,570 | 60 |  |
| Honduras | 0.3 | 0 | 183,438 | 182,410 | 99 | 100 |
| India | 0.0 | 0 | 7,092,007 | 3,536,338 | 50 | 30 |
| Indonesia | 0.0 | 0 | 2,302,612 | 1,534,842 | 67 | 100 |
| Iran (Islamic Republic of) | 5.5 | 0 | 1,857,726 | 1,237,024 | 67 | 21 |
| Iraq | 0.0 | 0 | 203,663 | 409,374 | 201 | 100 |
| Jamaica | 0.0 | 0 | 145,401 | 30,433 | 21 |  |
| Jordan | 5.5 | 0 | 1,559,103 | 610,397 | 39 | 22 |
| Kenya | 0.0 | 0 | 233,343 | 174,076 | 75 |  |
| Kiribati | 0.0 | 0 | 181,084 | 35,091 | 19 | 50 |
| Kuwait | 3.0 | 0 | 2,153,680 | 1,909,627 | 89 | 100 |
| Kyrgyzstan | 0.0 | 0 | 156,818 | 148,965 | 95 | 100 |
| Lao People’s Democratic Republic (the) | 0.0 | 0 | 316,128 | 260,227 | 82 | 29 |
| Lebanon | 0.0 | 0 | 295,458 | 332,398 | 113 | 40 |
| Lesotho | 0.0 | 0 | 150,509 | 176,864 | 118 | 0 |
| Liberia | 0.0 | 0 | 148,083 | 121,751 | 82 | 50 |
| Libya | 1.2 | 0 | 267,551 | 232,974 | 87 | 100 |
| Madagascar | 0.0 | 0 | 54,101 | 53,726 | 99 |  |
| Malawi | 0.2 | 0 | 166,312 | 308,311 | 185 | 67 |
| Malaysia | 5.0 | 0 | 1,117,144 | 1,052,559 | 94 | 83 |
| Maldives | 0.0 | 0 | 120,124 | 46,476 | 39 | 0 |
| Mali | 0.0 | 0 | 20,728 | 15,150 | 73 | 0 |
| Marshall Islands (the) | 0.0 | 0 | 129,603 | 44,553 | 34 | 0 |
| Mauritania | 0.0 | 0 | 115,350 | 120,810 | 105 |  |
| Mauritius | 0.0 | 0 | 227,800 | 203,363 | 89 | 33 |
| Mexico | 22.5 | 0 | 1,644,064 | 2,973,216 | 181 | 100 |
| Micronesia (Federated States of) | 0.0 | 0 | 145,008 | 55,471 | 38 | 0 |
| Mongolia | 0.0 | 0 | 149,983 | 148,657 | 99 | 25 |
| Montenegro | 0.2 | 0 | 190,252 | 189,424 | 100 | 100 |
| Morocco | 0.0 | 0 | 179,000 | 104,637 | 58 |  |
| Mozambique | 1.2 | 0 | 232,604 | 78,798 | 34 | 67 |
| Myanmar | 0.0 | 0 | 127,172 | 33,256 | 26 | 0 |
| Namibia | 0.0 | 0 | 181,157 | 56,386 | 31 | 0 |
| Nauru | 0.0 | 0 | 90,270 | 2,660 | 3 | 0 |
| Nepal | 0.0 | 0 | 206,770 | 60,955 | 29 | 0 |
| Nicaragua | 0.1 | 0 | 233,983 | 302,307 | 129 | 100 |
| Niger (the) | 0.7 | 0 | 201,250 | 217,737 | 108 |  |
| Nigeria | 35.4 | 0 | 1,046,802 | 1,147,681 | 110 | 100 |
| Niue | 0.0 | 0 | 51,585 | 0 | 0 | 50 |
| North Macedonia | 0.4 | 0 | 140,000 | 261,616 | 187 | 100 |
| Oman | 2.4 | 0 | 162,052 | 224,134 | 138 | 100 |
| Pakistan | 2.8 | 0 | 1,036,954 | 1,489,841 | 144 | 60 |
| Palau | 0.0 | 0 | 131,715 | 43,525 | 33 | 50 |
| Panama | 0.0 | 0 | 329,546 | 333,493 | 101 |  |
| Papua New Guinea | 0.0 | 0 | 16,805 | 44,276 | 263 | 100 |
| Paraguay | 0.0 | 0 | 258,212 | 227,450 | 88 | 0 |
| Peru | 3.0 | 0 | 595,343 | 213,188 | 36 | 100 |
| Philippines (the) | 0.0 | 0 | 551,329 | 428,134 | 78 | 100 |
| Qatar | 0.0 | 0 | 138,697 | 92,346 | 67 |  |
| Republic of Moldova (the) | 0.0 | 0 | 113,953 | 85,085 | 75 | 100 |
| Rwanda | 0.0 | 0 | 206,100 | 155,420 | 75 | 40 |
| Saint Kitts and Nevis | 0.0 | 0 | 88,084 | 28,887 | 33 | 33 |
| Saint Lucia | 0.0 | 0 | 182,891 | 139,599 | 76 | 100 |
| Saint Vincent and the Grenadines | 0.0 | 0 | 158,264 | 80,484 | 51 | 33 |
| Samoa | 0.0 | 0 | 133,360 | 54,736 | 41 | 50 |
| Sao Tome and Principe | 0.0 | 0 | 114,508 | 90,828 | 79 | 67 |
| Saudi Arabia | 0.0 | 0 | 241,724 | 156,939 | 65 | 100 |
| Senegal | 0.0 | 0 | 295,895 | 174,685 | 59 | 50 |
| Serbia | 0.5 | 0 | 121,283 | 71,429 | 59 | 67 |
| Seychelles | 0.0 | 0 | 144,905 | 94,211 | 65 | 100 |
| Sierra Leone | 0.0 | 0 | 224,895 | 62,759 | 28 | 100 |
| Solomon Islands | 0.0 | 0 | 168,914 | 25,011 | 15 | 0 |
| Somalia | 0.0 | 0 | 135,850 | 152,469 | 112 | 67 |
| South Africa | 5.1 | 0 | 386,001 | 620,767 | 161 | 80 |
| South Sudan | 0.0 | 0 | 100,675 | 127 | 0 | 100 |
| Sri Lanka | 0.0 | 0 | 516,967 | 292,538 | 57 | 0 |
| Sudan (the) | 0.0 | 0 | 172,153 | 119,149 | 69 | 0 |
| Suriname | 0.0 | 0 | 60,837 | 45,350 | 75 | 50 |
| Syrian Arab Republic | 0.0 | 0 | 490,707 | 284,338 | 58 | 25 |
| Thailand | 0.0 | 0 | 867,004 | 1,070,787 | 124 | 25 |
| Timor-Leste | 0.0 | 0 | 104,884 | 147,279 | 140 | 100 |
| Togo | 0.0 | 0 | 101,651 | 123,888 | 122 |  |
| Tonga | 0.0 | 0 | 123,206 | 0 | 0 | 50 |
| Trinidad and Tobago | 0.0 | 0 | 384,918 | 234,909 | 61 | 100 |
| Tunisia | 0.0 | 0 | 163,000 | 249,069 | 153 | 33 |
| Türkiye | 0.0 | 0 | 717,000 | 2,087,774 | 291 | 100 |
| Turkmenistan | 0.0 | 0 | 282,369 | 347,197 | 123 | 100 |
| Tuvalu | 0.0 | 0 | 75,929 | 6,304 | 8 | 50 |
| Uganda | 0.0 | 0 | 164,250 | 171,712 | 105 | 50 |
| United Republic of Tanzania (the) | 0.0 | 0 | 173,850 | 53,110 | 31 | 0 |
| Uruguay | 0.0 | 0 | 616,829 | 277,813 | 45 | 100 |
| Vanuatu | 0.0 | 0 | 159,361 | 61,022 | 38 | 0 |
| Venezuela (Bolivarian Republic of) | 1.0 | 0 | 154,255 | 358,803 | 233 | 100 |
| Viet Nam | 129.1 | 0 | 2,850,847 | 3,898,908 | 137 | 100 |
| Yemen | 0.0 | 0 | 101,999 | 169,985 | 167 | 100 |
| Zambia | 0.4 | 0 | 224,100 | 270,730 | 121 | 50 |
| Zimbabwe | 0.0 | 0 | 491,802 | 571,153 | 116 | 67 |
| Region: ASP | 0.0 | 0 | 492,489 | 339,041 | 69 | 0 |
| Global | 0.0 | 0 | 9,888,417 | 9,277,368 | 94 | 100 |
| Grand total | 724.0 | 0 | 102,297,219 | 82,735,306 | 81 | 57 |

* No phase-out in 2023 for HFC-related projects.

** For projects that were planned to be completed in 2023.

Annex II

OVERVIEW OF STATUS OF PROJECT IMPLEMENTATION

AS AT 31 DECEMBER 2023

# Table 1 of annex II presents an overview of the status of project implementation by year. All projects and activities approved between 1991 and 2009 and in 2011 and 2013, have now been completed.

Table 1. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 68 | 68 | 100 | 7,950,771 | 7,950,771 | 0 | 100 |
| 1992 | 176 | 176 | 100 | 41,261,376 | 41,261,376 | 0 | 100 |
| 1993 | 217 | 217 | 100 | 73,198,586 | 73,198,586 | 0 | 100 |
| 1994 | 379 | 379 | 100 | 128,630,290 | 128,630,290 | 0 | 100 |
| 1995 | 355 | 355 | 100 | 111,188,309 | 111,188,309 | 0 | 100 |
| 1996 | 257 | 257 | 100 | 83,813,027 | 83,813,027 | 0 | 100 |
| 1997 | 532 | 532 | 100 | 154,314,938 | 154,314,940 | -2 | 100 |
| 1998 | 422 | 422 | 100 | 99,680,368 | 99,680,367 | 1 | 100 |
| 1999 | 546 | 546 | 100 | 152,710,736 | 152,710,736 | 0 | 100 |
| 2000 | 426 | 426 | 100 | 109,540,523 | 109,540,522 | 1 | 100 |
| 2001 | 427 | 427 | 100 | 130,139,750 | 130,139,752 | -2 | 100 |
| 2002 | 358 | 358 | 100 | 162,045,816 | 162,045,816 | 0 | 100 |
| 2003 | 247 | 247 | 100 | 157,043,468 | 157,043,468 | 0 | 100 |
| 2004 | 271 | 271 | 100 | 162,388,007 | 162,388,008 | -1 | 100 |
| 2005 | 255 | 255 | 100 | 180,276,023 | 180,276,021 | 2 | 100 |
| 2006 | 261 | 261 | 100 | 120,847,322 | 120,847,323 | -1 | 100 |
| 2007 | 213 | 213 | 100 | 120,084,047 | 120,084,047 | 0 | 100 |
| 2008 | 354 | 354 | 100 | 121,600,746 | 121,600,750 | -4 | 100 |
| 2009 | 320 | 320 | 100 | 73,691,484 | 73,400,556 | 290,929 | 100 |
| 2010 | 227 | 226 | 100 | 83,919,591 | 83,868,265 | 51,326 | 100 |
| 2011 | 264 | 264 | 100 | 201,764,495 | 201,898,540 | -134,045 | 100 |
| 2012 | 182 | 179 | 98 | 100,920,300 | 100,278,130 | 642,171 | 99 |
| 2013 | 184 | 184 | 100 | 125,235,353 | 125,077,165 | 158,187 | 100 |
| 2014 | 223 | 220 | 99 | 91,752,618 | 91,671,487 | 81,131 | 100 |
| 2015 | 377 | 370 | 98 | 156,179,504 | 153,559,454 | 2,620,050 | 98 |
| 2016 | 239 | 230 | 96 | 114,063,852 | 110,011,716 | 4,052,136 | 96 |
| 2017 | 124 | 115 | 93 | 63,854,227 | 62,426,894 | 1,427,333 | 98 |
| 2018 | 271 | 248 | 92 | 119,510,191 | 104,036,097 | 15,474,094 | 87 |
| 2019 | 224 | 184 | 82 | 48,834,278 | 38,630,067 | 10,204,211 | 79 |
| 2020 | 256 | 188 | 73 | 66,951,367 | 56,339,987 | 10,611,380 | 84 |
| 2021 | 292 | 133 | 46 | 84,484,901 | 52,952,575 | 31,532,326 | 63 |
| 2022 | 216 | 29 | 13 | 85,052,379 | 18,095,522 | 66,956,857 | 21 |
| 2023 | 354 | 4 | 1 | 112,090,169 | 1,133,498 | 110,956,671 | 1 |
| Total | 9,517 | 8,658 | 91 | 3,645,018,812 | 3,390,094,061 | 254,924,751 | 93 |

* Excludes closed and transferred projects.

** Excludes agency support costs.

Completed projects

# Since 1991, 8,658 projects of the 9,517 projects (excluding closed or transferred projects) financed by the Multilateral Fund were completed, representing a completion rate of 91 per cent. Tables 2 to 4 present information on completed investment, non-investment and project preparation activities.

Completed investment projects

# Table 2 presents information on investment projects that have been completed since 1991. The table presents the data in total, followed by data according to region, sector, implementation characteristics, and disbursement method.

Table 2. Cumulative completed investment projects

| Item | Number of projects | Approved funds plus adjustment (US $) | Per cent of funds disbursed (%) | Consumption phased out* | Production phased out* | Average number of months from approval to first disbursement | Average number of months from approval to completion | Overall cost-effectiveness to the fund (US$/kg.) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TOTAL | 3,063 | 2,564,570,299 | 100 | 277,555 | 204,189 | 14 | 38 | 5.32 |
| Region |  |  |  |  |  |  |  |  |
| Africa | 543 | 177,621,995 | 99 | 18,567 | 0 | 12 | 40 | 9.57 |
| Asia & Pacific | 1,600 | 1,898,940,810 | 100 | 216,055 | 184,239 | 16 | 38 | 4.74 |
| Europe | 169 | 73,078,473 | 100 | 8,051 | 175 | 10 | 34 | 8.88 |
| Latin America and Caribbean | 751 | 414,929,022 | 100 | 34,883 | 19,775 | 14 | 37 | 7.59 |
| Global | n/a | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Sector |  |  |  |  |  |  |  |  |
| Aerosol | 127 | 82,501,518 | 100 | 27,449 | 0 | 16 | 43 | 3.01 |
| Destruction | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Energy efficiency | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Fire fighting | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Foam | 1,006 | 378,858,556 | 100 | 69,471 | 0 | 15 | 34 | 5.45 |
| Fumigants | 123 | 99,900,005 | 100 | 7,993 | 0 | 10 | 49 | 12.50 |
| Halon | 39 | 71,476,177 | 100 | 42,111 | 41,958 | 17 | 30 | 0.85 |
| HFC phase-down plan | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Multiple sectors | 4 | 2,287,376 | 100 | 419 | 0 | 28 | 78 | 5.46 |
| Other | 8 | 16,059,360 | 100 | 1,574 | 0 | 12 | 20 | 10.20 |
| Phase-out plan | 916 | 839,693,940 | 99 | 57,056 | 10,988 | 12 | 42 | 12.34 |
| Process agent | 30 | 120,252,627 | 100 | 19,573 | 52,162 | 10 | 27 | 1.68 |
| Production | 62 | 416,148,243 | 100 | 0 | 99,081 | 9 | 20 | 4.20 |
| Refrigeration | 617 | 441,966,838 | 100 | 44,565 | 0 | 16 | 40 | 9.92 |
| Solvents | 128 | 94,351,804 | 100 | 7,285 | 0 | 19 | 32 | 12.95 |
| Sterilant | 3 | 1,073,855 | 100 | 60 | 0 | 15 | 34 | 17.78 |
| Implementation characteristics |  |  |  |  |  |  |  |  |  |
| Agency implementation | 1,909 | 981,377,455 | 100 | 97,440 | 17,381 | 11 | 37 | 8.55 |
| National implementation | 1,154 | 1,583,192,844 | 100 | 180,116 | 186,808 | 20 | 40 | 4.31 |
| Disbursement method |  |  |  |  |  |  |  |  |  |
| During implementation | 2,937 | 2,086,784,124 | 100 | 267,691 | 199,719 | 14 | 38 | 4.46 |
| After implementation | 50 | 17,166,608 | 100 | 2,512 | 0 | 23 | 25 | 6.83 |
| Retroactive funding | 37 | 14,635,851 | 100 | 2,100 | 500 | 15 | 11 | 5.63 |
| Country to final beneficiaries | 39 | 445,983,716 | 100 | 5,252 | 3,970 | 9 | 56 | 48.36 |

*Excludes closed and transferred projects.

# Overall, 99.7 per cent of the funds approved for completed investment projects have been disbursed. Since 1991, 3,063 investment projects have been completed at a total value of US $2.56 billion. The average time from approval to first disbursement for investment projects is 14 months. Investment projects have been completed, on average, 38 months after they were approved.

Completed non-investment projects

# Table 3 presents data on cumulative completed non-investment projects. Since 1991, 3,810 non-investment projects have been completed at a total value of US $605.58 million.

Table 3. Cumulative completed non-investment projects

| Item | Number of projects | Approved funds plus adjustment (US $) | Per cent of funds disbursed (%) | Average number of months from approval to first disbursement | Average number of months from approval to completion |
| --- | --- | --- | --- | --- | --- |
| TOTAL | 3,810 | 605,582,649 | 99 | 12 | 38 |
| Region |  |  |  |  |  |
| Africa | 1,173 | 103,169,943 | 99 | 12 | 37 |
| Asia & Pacific | 1,158 | 175,171,539 | 100 | 14 | 40 |
| Europe | 250 | 23,576,339 | 100 | 9 | 33 |
| Latin America and Caribbean | 906 | 108,035,313 | 100 | 13 | 41 |
| Global | 323 | 195,629,516 | 99 | 6 | 22 |
| Sector |  |  |  |  |  |
| Aerosol | 31 | 2,461,265 | 100 | 11 | 36 |
| Destruction | 17 | 8,695,865 | 100 | 11 | 65 |
| Energy efficiency | 0 | 0 | 0 | n/a | n/a |
| Fire fighting | 0 | 0 | 0 | n/a | n/a |
| Foam | 34 | 10,543,567 | 100 | 14 | 36 |
| Fumigants | 137 | 21,224,434 | 100 | 9 | 39 |
| Halon | 82 | 11,238,156 | 100 | 17 | 44 |
| HFC phase-down plan | 0 | 0 | 0 | n/a | n/a |
| Multiple sectors | 1 | 53,792 | 100 | 56 | 58 |
| Other | 1 | 76,499 | 100 | 7 | 38 |
| Phase-out plan | 804 | 81,884,991 | 100 | 14 | 40 |
| Process agent | 0 | 0 | 0 | n/a | n/a |
| Production | 1 | 40,000 | 100 | 4 | 4 |
| Refrigeration | 639 | 92,570,149 | 100 | 16 | 50 |
| Several | 2,029 | 373,395,149 | 99 | 10 | 32 |
| Solvents | 34 | 3,398,782 | 100 | 11 | 27 |
| Sterilant | 0 | 0 | 0 | n/a | n/a |
| Implementation characteristics |  |  |  |  |  |
| Agency implementation | 3,106 | 455,140,335 | 99 | 12 | 37 |
| National implementation | 704 | 150,442,314 | 100 | 14 | 41 |
| Disbursement method |  |  |  |  |  |
| During implementation | 3,775 | 593,179,682 | 99 | 12 | 38 |
| After implementation | 26 | 2,325,462 | 100 | 14 | 21 |
| Retroactive funding | 1 | 146,698 | 100 | 3 | 83 |
| Country to final beneficiaries | 8 | 9,930,807 | 100 | 7 | 38 |

# The average time from approval to first disbursement for non-investment projects is 12 months. Non-investment projects have been completed, on average, 38 months after they were approved. This figure is influenced by the large number of projects (2,029 of 3,810) in the sector called “several”, which had an average time from approval to completion of 32 months. Non-investment projects in the other sectors were completed between four and 65 months after they had been approved.

# Almost all projects were implemented by the agency concerned rather than through national implementation. Agency implementation of non-investment projects normally does not require legal agreements, which may explain the shorter period of time (37 months) compared with nationally-implemented non-investment projects (41 months).

Completed project preparation activities

# Table 4 presents data on cumulative completed project preparation activities. Since 1991, 1,785 preparation activities have been completed at a total value of US $90.88 million.

Table 4. Cumulative completed project preparation activities

| Item | Number of projects | Approved funds plus adjustment (US$) | Per cent of funds disbursed (%) | Average number of months from approval to first disbursement | Average number of months from approval to completion |
| --- | --- | --- | --- | --- | --- |
| TOTAL | 1,785 | 90,876,682 | 99 | 8 | 23 |
| Region |  |  |  |  |  |
| Africa | 471 | 16,615,234 | 97 | 9 | 26 |
| Asia & Pacific | 674 | 44,137,140 | 99 | 8 | 23 |
| Europe | 126 | 5,458,614 | 100 | 7 | 22 |
| Latin America and Caribbean | 495 | 23,055,269 | 99 | 7 | 21 |
| Global | 19 | 1,610,425 | 100 | 5 | 16 |
| Sector |  |  |  |  |  |
| Aerosol | 45 | 1,254,278 | 100 | 6 | 17 |
| Destruction | 18 | 818,719 | 100 | 13 | 40 |
| Energy efficiency | 0 | 0 | 0 | n/a | n/a |
| Fire fighting | 0 | 0 | 0 | n/a | n/a |
| Foam | 260 | 11,189,567 | 100 | 6 | 21 |
| Fumigants | 118 | 2,993,886 | 100 | 5 | 17 |
| Halon | 27 | 836,728 | 100 | 6 | 19 |
| HFC phase-down plan | 37 | 3,730,000 | 81 | 11 | 23 |
| Multiple sectors | 3 | 139,440 | 100 | 3 | 34 |
| Other | 2 | 240,747 | 100 | 11 | 35 |
| Phase-out plan | 527 | 29,640,261 | 99 | 11 | 31 |
| Process agent | 9 | 694,384 | 100 | 9 | 19 |
| Production | 12 | 1,402,145 | 100 | 7 | 15 |
| Refrigeration | 386 | 13,834,437 | 100 | 7 | 21 |
| Several | 283 | 21,969,992 | 100 | 4 | 15 |
| Solvents | 57 | 2,127,098 | 100 | 6 | 25 |
| Sterilant | 1 | 5,000 | 100 | 1 | 9 |
| Implementation characteristics |  |  |  |  |  |
| Agency implementation | 1,556 | 74,900,376 | 99 | 7 | 22 |
| National implementation | 229 | 15,976,306 | 97 | 11 | 30 |
| Disbursement method |  |  |  |  |  |
| During implementation | 1,775 | 89,275,221 | 99 | 8 | 23 |
| After implementation | 6 | 899,752 | 100 | 7 | 21 |
| Retroactive funding | 0 | 0 | 0 | n/a | n/a |
| Country to final beneficiaries | 4 | 701,709 | 100 | 5 | 29 |

# The average time from approval to first disbursement for project preparation activities is eight months. Preparation activities have been completed, on average, 23 months after they were approved. Overall, 99 per cent of the funds approved for completed preparation activities have been disbursed.

Ongoing projects

# A total of 859 projects were under implementation at the end of 2023. Tables 5 to 7 present information on ongoing investment, non-investment and project preparation activities.

## Ongoing investment projects

# Table 5 presents information on the status of investment projects under implementation by region, sector, and implementation characteristics.

Table 5. Cumulative ongoing investment projects

| Item | Number of projects | Approved funds plus adjustment (US $) | Per cent of funds disbursed (%) | Number of projects disbursing | Per cent of projects disbursing (%) | Average number of months from approval to first disbursement | Average number of months from approval to planned completion | Average length of delay in project planned completion | Overall cost-effectiveness to the Fund (US$/kg.)* |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TOTAL | 286 | 267,096,506 | 38 | 160 | 56 | 11 | 46 | 22 | 15.79 |
| Region |  |  |  |  |  |  |  |  |  |
| Africa | 79 | 38,631,819 | 35 | 55 | 70 | 13 | 50 | 27 | 37.55 |
| Asia & Pacific | 116 | 177,338,061 | 41 | 62 | 53 | 12 | 46 | 26 | 13.27 |
| Europe | 17 | 6,464,099 | 54 | 12 | 71 | 8 | 46 | 17 | 25.04 |
| Latin America and Caribbean | 74 | 44,662,527 | 29 | 31 | 42 | 9 | 41 | 13 | 19.80 |
| Global | 0 | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Sector |  |  |  |  |  |  |  |  |  |
| Aerosol | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Destruction | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Energy efficiency | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Fire fighting | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Foam | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Fumigants | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Halon | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| HFC phase-down plan | 45 | 18,865,695 | 0 | 1 | 2 | 5 | 35 | 1 | 5.31 |
| Multiple sectors | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Other | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Phase-out plan | 234 | 200,764,649 | 39 | 154 | 66 | 11 | 47 | 23 | 27.62 |
| Process agent | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Production | 2 | 44,997,213 | 51 | 1 | 50 | 16 | 63 | 72 | 7.57 |
| Refrigeration | 5 | 2,468,949 | 71 | 4 | 80 | 31 | 57 | 42 | 17.19 |
| Solvents | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Sterilant | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Implementation characteristics |  |  |  |  |  |  |  |  |  |
| Agency implementation | 194 | 146,604,037 | 37 | 126 | 65 | 10 | 48 | 22 | 23.90 |
| National implementation | 92 | 120,492,469 | 40 | 34 | 37 | 16 | 42 | 24 | 11.18 |
| Disbursement method |  |  |  |  |  |  |  |  |  |
| During implementation | 270 | 159,220,411 | 28 | 151 | 56 | 11 | 46 | 22 | 25.83 |
| After implementation | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Retroactive funding | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a | n/a |
| Country to final beneficiaries | 16 | 107,876,095 | 54 | 9 | 56 | 8 | 50 | 37 | 10.04 |

*Based on the ODS to be phased out according to the proposal.

# There are currently 286 investment projects under implementation at a total value of over US $267.1 million. Around 38 per cent of the funds have already been disbursed. The overall average cost-effectiveness of ongoing investment projects is US $15.79/kg ODP to be phased out. The average number of months from approval to first disbursement is 11 months. The average duration of an ongoing investment project is 46 months. Typically, ongoing investment projects are completed 22 months later than originally planned, which could be considered the average delay.

Ongoing non-investment projects

# Table 6 presents information on the status of non-investment projects under implementation by region, sector, and implementation characteristic.

Table 6. Cumulative ongoing non-investment projects

| Item | Number of projects | Approved funds plus adjustment (US $) | Per cent of funds disbursed | Number of projects disbursing | Per cent of projects disbursing | Average number of months from approval to first disbursement | Average number of months from approval to planned completion | Average length of delay in project planned completion |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TOTAL | 364 | 79,824,710 | 19 | 145 | 40 | 15 | 39 | 7 |
| Region |  |  |  |  |  |  |  |  |
| Africa | 115 | 15,026,030 | 12 | 30 | 26 | 13 | 35 | 3 |
| Asia & Pacific | 125 | 32,535,239 | 25 | 70 | 56 | 17 | 44 | 8 |
| Europe | 24 | 3,588,673 | 21 | 14 | 58 | 8 | 35 | 3 |
| Latin America and Caribbean | 95 | 17,250,168 | 23 | 30 | 32 | 16 | 41 | 9 |
| Global | 5 | 11,424,600 | 1 | 1 | 20 | 9 | 15 | 0 |
| Sector |  |  |  |  |  |  |  |  |
| Aerosol | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Destruction | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Energy efficiency | 42 | 5,302,365 | 0 | 3 | 7 | 4 | 35 | 1 |
| Fire fighting | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Foam | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Fumigants | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Halon | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| HFC phase-down plan | 18 | 1,391,715 | 0 | 0 | 0 | n/a | 37 | n/a |
| Multiple sectors | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Other | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Phase-out plan | 155 | 29,936,792 | 34 | 79 | 51 | 18 | 44 | 9 |
| Process agent | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Production | 1 | 50,000 | 0 | 0 | 0 | n/a | 12 | n/a |
| Refrigeration | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Several | 148 | 43,143,838 | 11 | 63 | 43 | 12 | 36 | 6 |
| Solvents | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Sterilant | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Implementation characteristics |  |  |  |  |  |  |  |  |
| Agency implementation | 316 | 62,803,259 | 18 | 116 | 37 | 16 | 40 | 6 |
| National implementation | 48 | 17,021,451 | 20 | 29 | 60 | 10 | 37 | 7 |
| Disbursement method |  |  |  |  |  |  |  |  |
| During implementation | 364 | 79,824,710 | 19 | 145 | 40 | 15 | 39 | 7 |
| After implementation | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Retroactive funding | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Country to final beneficiaries | 0 | 0 | 0 | 0 | 0 | n/a | n/a | n/a |

# There are currently 364 non-investment projects under implementation at a total value of US $79.8 million, with 19 per cent of the funds already disbursed. The average number of months from approval to first disbursement is 15 months. On average, ongoing non-investment projects are completed 39 months from the date of approval, which represents a delay of seven months.

Ongoing project preparation activities

# Table 7 presents information on the status of project preparation activities under implementation by region, sector, and implementation characteristic.

Table 7. Cumulative ongoing project preparation activities

| Item | Number of projects | Approved funds plus adjustment (US$) | Funds disbursed (US$) | Per cent of funds disbursed (%) | Average number of months from approval to first disbursement | Average number of months from approval to planned completion | Average length of delay in project planned completion |
| --- | --- | --- | --- | --- | --- | --- | --- |
| TOTAL | 209 | 18,045,000 | 4,303,290 | 24 | 11 | 32 | 8 |
| Region |  |  |  |  |  |  |  |
| Africa | 92 | 7,286,000 | 1,619,965 | 22 | 13 | 33 | 9 |
| Asia & Pacific | 47 | 4,284,000 | 900,299 | 21 | 11 | 32 | 8 |
| Europe | 19 | 1,665,000 | 423,898 | 25 | 7 | 27 | 3 |
| Latin America and Caribbean | 51 | 4,810,000 | 1,359,128 | 28 | 8 | 29 | 5 |
| Global | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Sector |  |  |  |  |  |  |  |
| Aerosol | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Destruction | 37 | 2,950,000 | 0 | 0 | n/a | 24 | 0 |
| Energy efficiency | 5 | 150,000 | 0 | 0 | n/a | 19 | 1 |
| Fire fighting | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Foam | 1 | 80,000 | 10,469 | 13 | 8 | 24 | n/a |
| Fumigants | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Halon | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| HFC phase-down plan | 127 | 13,380,000 | 3,763,305 | 28 | 10 | 31 | 6 |
| Multiple sectors | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Other | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Phase-out plan | 37 | 1,305,000 | 422,855 | 32 | 19 | 44 | 20 |
| Process agent | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Production | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Refrigeration | 2 | 180,000 | 106,660 | 59 | 6 | 34 | 10 |
| Several | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Solvents | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Sterilant | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Implementation characteristics |  |  |  |  |  |  |  |
| Agency implementation | 163 | 14,041,500 | 2,935,995 | 21 | 12 | 32 | 8 |
| National implementation | 46 | 4,003,500 | 1,367,295 | 34 | 10 | 32 | 7 |
| Disbursement method |  |  |  |  |  |  |  |
| During implementation | 209 | 18,045,000 | 4,303,290 | 24 | 11 | 32 | 8 |
| After implementation | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Retroactive funding | 0 | 0 | 0 | 0 | n/a | n/a | n/a |
| Country to final beneficiaries | 0 | 0 | 0 | 0 | n/a | n/a | n/a |

# There are currently 209 project preparation activities under implementation at a total value of US $18.05 million, with 24 per cent of the funds already disbursed. The average number of months from approval to first disbursement is 11 months. On average, ongoing preparation activities are completed 32 months from the date of approval, which represents a delay of eight months.

Closed projects

# Table 8 presents a summary of closed projects.  Since 1991, 284 projects have been closed at a total value of US $15.14 million.

Table 8. Closed projects summary

| Agency | Number of projects | Approved funding plus adjustment (US$) | Funds disbursed (US $) | Balances (US$) | Consumption ODP to be phased out | Consumption ODP phased out |
| --- | --- | --- | --- | --- | --- | --- |
| UNDP | 81 | 6,895,392 | 6,895,392 | 0 | 673 | 636 |
| UNEP | 16 | 195,325 | 195,325 | 0 | 12 | 12 |
| UNIDO | 68 | 6,446,674 | 6,446,674 | 0 | 1,808 | 367 |
| World Bank | 100 | 1,373,519 | 1,373,519 | 0 | 657 | 581 |
| Bilaterals | 19 | 227,901 | 227,901 | 0 | 223 | 0 |
| Total | 284 | 15,138,810 | 15,138,811 | -1 | 3,373 | 1,595 |

Annex III

AN OVERVIEW OF HFC-RELATED PROJECTS AND ACTIVITIES

# Since its 80th meeting, the Executive Committee has approved funding for the implementation of HFC investment projects (decisions 78/3(g) and 79/45), and enabling activities to help national ozone units fulfil their initial obligations with regard to HFC phase-down in line with the Kigali Amendment (decision 79/46).

# As of 31 December 2023, the Executive Committee has approved 436 HFC-related projects and activities in 144 countries and two regions, consisting of 185 requests for project preparation, 17 investment projects, 61 projects for Kigali HFC implementation plans (KIPs), one technical assistance project, 158 enabling activities, 11 projects for energy efficiency and three HFC-23 emission control projects, amounting to US $74.72 million (excluding support costs).

# Table 1 presents an overview of all HFC-related projects and activities under the Multilateral Fund, irrespective of their source of funding, at the country level, indicating the status of ratification of the Kigali Amendment and the status of the HFC licensing system.

Table 1. Overview of all HFC-related projects and activities under the Multilateral Fund

| Country | Group | Ratification of Kigali Amendment | Implemen- tation of licensing system | Funds approved for (US $) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Enabling activities | Energy efficiency | HFC-23 emission control | Investment projects | KIP | Project preparation | Technical assistance |
| Afghanistan | I |  |  | 136,888 |  |  |  |  |  |  |
| Albania | I | Yes | √ | 94,978 |  |  |  | 179,390 | 130,000 |  |
| Algeria | I |  |  | 150,000 |  |  |  |  |  |  |
| Angola | I | Yes | Pending | 150,000 |  |  |  |  | 170,000 |  |
| Antigua and Barbuda | I |  |  |  |  |  |  |  |  |  |
| Argentina | I | Yes | √ | 250,000 |  | 1,527,851 | 1,840,755 |  | 294,816 |  |
| Armenia | I | Yes | √ | 149,639 |  |  |  |  | 170,000 |  |
| Bahamas (the) | I | Yes | √ | 95,000 |  |  |  |  |  |  |
| Bahrain | II | Yes | Pending | 140,240 |  |  |  |  |  |  |
| Bangladesh | I | Yes | √ | 146,418 |  |  | 3,131,610 |  | 190,000 |  |
| Barbados | I | Yes | √ |  |  |  |  |  |  |  |
| Belize | I | Yes | √ | 95,000 |  |  |  |  |  |  |
| Benin | I | Yes | √ | 128,885 |  |  |  |  | 190,000 |  |
| Bhutan | I | Yes | √ | 49,654 |  |  |  |  | 100,000 |  |
| Bolivia (Plurinational State of) | I | Yes | √ | 150,000 | 96,000 |  |  | 194,000 | 170,000 |  |
| Bosnia and Herzegovina | I | Yes | √ | 94,920 |  |  |  |  | 130,000 |  |
| Botswana | I | Yes | √ | 96,648 |  |  |  |  | 170,000 |  |
| Brazil | I | Yes | √ |  |  |  |  |  | 230,000 |  |
| Brunei Darussalam | I |  |  | 150,000 |  |  |  |  |  |  |
| Burkina Faso | I | Yes | √ | 145,443 |  |  |  |  | 190,000 |  |
| Burundi | I | Yes | √ | 100,000 |  |  |  |  | 170,000 |  |
| Cabo Verde | I | Yes | √ | 79,038 |  |  |  |  | 130,000 |  |
| Cambodia | I | Yes | √ | 147,918 |  |  |  | 250,110 | 170,000 |  |
| Cameroon | I | Yes | √ | 149,324 |  |  |  | 355,500 | 190,000 |  |
| Central African Republic (the) | I |  |  |  |  |  |  |  |  |  |
| Chad | I | Yes | √ | 130,200 |  |  |  |  | 170,000 |  |
| Chile | I | Yes | √ | 137,279 |  |  |  | 876,507 | 220,000 |  |
| China | I | Yes | √ | 244,685 |  |  | 1,274,967 |  | 47,687 |  |
| Colombia | I | Yes | √ | 246,344 |  |  |  |  | 420,000 |  |
| Comoros (the) | I | Yes | √ | 45,242 |  |  |  |  | 100,000 |  |
| Congo (the) | I | Yes | √ | 149,841 |  |  |  | 81,500 | 170,000 |  |
| Cook Islands (the) | I | Yes | √ | 47,711 |  |  |  |  |  |  |
| Costa Rica | I | Yes | √ | 144,830 |  |  |  |  | 170,000 |  |
| Cote d’Ivoire | I | Yes | √ | 135,605 |  |  |  |  | 190,000 |  |
| Cuba | I | Yes | √ | 150,000 |  |  |  | 160,000 | 170,000 |  |
| Democratic People's Republic of Korea (the) | I | Yes | √ |  |  |  |  |  |  |  |
| Democratic Republic of the Congo (the) | I |  |  | 132,234 |  |  |  |  |  |  |
| Djibouti | I | Yes | Pending | 22,422 |  |  |  |  |  |  |
| Dominica | I |  |  | 50,000 |  |  |  |  |  |  |
| Dominican Republic (the) | I | Yes | √ | 149,518 |  |  | 129,801 | 535,930 | 201,572 |  |
| Ecuador | I | Yes | √ | 120,725 |  |  | 267,885 | 292,600 | 219,937 |  |
| Egypt | I | Yes | √ | 250,000 | 285,000 |  |  |  | 237,964 |  |
| El Salvador | I | Yes | √ | 150,000 |  |  |  |  | 170,000 |  |
| Equatorial Guinea | I |  |  | 113,154 |  |  |  |  |  |  |
| Eritrea | I | Yes | Pending | 92,822 |  |  |  |  | 130,000 |  |
| Eswatini (the Kingdom of) | I | Yes | √ | 94,509 |  |  |  |  | 130,000 |  |
| Ethiopia | I | Yes | √ | 94,208 |  |  |  |  | 130,000 |  |
| Fiji | I | Yes | √ | 147,699 |  |  |  |  | 130,000 |  |
| Gabon | I | Yes | √ | 134,202 |  |  |  |  | 190,000 |  |
| Gambia (the) | I | Yes | √ | 94,947 |  |  |  |  | 130,000 |  |
| Georgia | I | Yes | √ | 95,000 |  |  |  |  | 130,000 |  |
| Ghana | I | Yes | √ | 149,425 |  |  |  | 188,000 | 190,000 |  |
| Grenada | I | Yes | √ | 46,491 |  |  |  | 72,500 | 100,000 |  |
| Guatemala | I | Yes | √ | 128,267 |  |  |  |  |  |  |
| Guinea | I | Yes | √ | 100,000 |  |  |  |  | 190,000 |  |
| Guinea-Bissau | I | Yes | √ | 70,803 |  |  |  |  | 130,000 |  |
| Guyana | I |  |  | 55,000 |  |  |  |  |  |  |
| Haiti | I |  |  | 95,000 |  |  |  |  |  |  |
| Honduras | I | Yes | √ | 149,931 |  |  |  |  | 170,000 |  |
| India | II | Yes | √ | 250,000 | 273,745 |  | 846,326 |  | 150,000 |  |
| Indonesia | I | Yes | √ | 246,666 |  |  |  |  | 220,000 |  |
| Iran (Islamic Republic of) | II |  |  | 219,667 |  |  |  |  |  |  |
| Iraq | II |  |  | 168,030 |  |  |  |  |  |  |
| Jamaica | I |  |  | 145,083 |  |  |  |  |  |  |
| Jordan | I | Yes | √ | 127,708 |  |  | 1,637,610 | 2,540,680 | 190,000 |  |
| Kenya | I | Yes | Pending | 149,348 |  |  |  |  | 220,000 |  |
| Kiribati | I | Yes | √ | 32,898 |  |  |  |  |  |  |
| Kuwait | II |  |  | 138,000 |  |  |  |  |  |  |
| Kyrgyzstan | I | Yes | √ | 95,000 | 206,000 |  |  | 81,000 | 130,000 |  |
| Lao People's Democratic Republic (the) | I | Yes | √ | 54,082 |  |  |  |  | 130,000 |  |
| Lebanon | I | Yes | √ | 149,979 |  |  | 1,039,874 |  | 317,894 |  |
| Lesotho | I | Yes | √ | 94,532 |  |  |  |  | 130,000 |  |
| Liberia | I | Yes | √ | 95,000 |  |  |  |  | 130,000 |  |
| Libya | I |  |  | 147,508 |  |  |  |  |  |  |
| Madagascar | I |  |  | 115,554 |  |  |  |  |  |  |
| Malawi | I | Yes | √ | 149,954 |  |  |  | 68,000 | 170,000 |  |
| Malaysia | I | Yes | √ | 250,000 |  |  |  | 3,042,912 | 360,000 |  |
| Maldives | I | Yes | √ | 94,801 |  |  |  |  | 130,000 |  |
| Mali | I | Yes | Pending | 148,069 |  |  |  |  | 170,000 |  |
| Marshall Islands (the) | I | Yes | √ | 37,583 |  |  |  |  |  |  |
| Mauritania | I |  | √ | 102,338 |  |  |  |  |  |  |
| Mauritius | I | Yes | √ | 139,622 |  |  |  |  | 170,000 |  |
| Mexico | I | Yes | √ | 240,755 | 938,620 | 870,619 | 3,756,960 | 6,746,923 | 424,512 |  |
| Micronesia (Federated States of) | I | Yes | √ | 48,247 |  |  |  |  |  |  |
| Mongolia | I | Yes | √ | 92,866 |  |  |  |  | 210,000 |  |
| Montenegro | I | Yes | √ | 49,973 |  |  |  |  | 100,000 |  |
| Morocco | I | Yes | √ | 150,000 |  |  |  |  | 220,000 |  |
| Mozambique | I | Yes | Pending | 149,330 |  |  |  |  | 170,000 |  |
| Myanmar | I |  |  | 53,623 |  |  |  |  |  |  |
| Namibia | I | Yes | √ | 147,673 |  |  |  |  | 170,000 |  |
| Nauru | I | Yes | √ | 26,062 |  |  |  |  |  |  |
| Nepal | I |  | √ | 87,165 |  |  |  |  |  |  |
| Nicaragua | I | Yes | √ | 150,000 | 96,000 |  |  | 199,000 | 170,000 |  |
| Niger (the) | I | Yes | √ | 148,244 |  |  |  | 150,000 | 170,000 |  |
| Nigeria | I | Yes | √ | 245,868 | 145,000 |  |  |  | 220,000 |  |
| Niue | I | Yes | √ | 33,863 |  |  |  |  |  |  |
| North Macedonia | I | Yes | √ | 95,000 |  |  |  | 103,555 | 130,000 |  |
| Oman | II |  |  | 129,061 |  |  |  |  |  |  |
| Pakistan | II |  |  | 250,000 |  |  |  |  |  |  |
| Palau | I | Yes | √ | 25,000 |  |  |  |  |  |  |
| Panama | I | Yes | √ | 150,000 |  |  |  | 331,100 | 190,000 |  |
| Papua New Guinea | I |  |  | 95,000 |  |  |  |  |  |  |
| Paraguay | I | Yes | √ | 143,084 |  |  |  |  | 170,000 |  |
| Peru | I | Yes | √ | 147,582 |  |  |  | 283,140 | 190,000 |  |
| Philippines (the) | I | Yes | √ | 207,289 |  |  |  |  | 220,000 |  |
| Qatar | II |  |  | 150,000 |  |  |  |  |  |  |
| Republic of Moldova (the) | I | Yes | √ | 50,000 |  |  |  |  | 130,000 |  |
| Rwanda | I | Yes | √ | 91,190 |  |  |  |  | 130,000 |  |
| Saint Kitts and Nevis | I |  |  | 50,000 |  |  |  |  |  |  |
| Saint Lucia | I | Yes | √ | 95,000 |  |  |  |  | 130,000 |  |
| Saint Vincent and the Grenadines | I | Yes | √ | 50,000 |  |  |  |  | 100,000 |  |
| Samoa | I | Yes | √ | 49,018 |  |  |  |  |  |  |
| Sao Tome and Principe | I | Yes | √ | 83,915 |  |  |  |  | 130,000 |  |
| Saudi Arabia | II |  |  | 193,170 |  |  |  |  |  |  |
| Senegal | I | Yes | √ | 137,814 |  |  |  |  | 190,000 |  |
| Serbia | I | Yes | √ | 143,900 |  |  |  |  | 170,000 |  |
| Seychelles | I | Yes | √ | 95,000 |  |  |  |  | 130,000 |  |
| Sierra Leone | I | Yes | √ | 94,741 |  |  |  |  | 130,000 |  |
| Solomon Islands | I | Yes | √ | 88,655 |  |  |  |  |  |  |
| Somalia | I | Yes | √ | 144,313 |  |  |  |  | 170,000 |  |
| South Africa | I | Yes | √ | 193,367 | 350,000 |  |  |  | 220,000 |  |
| South Sudan | I |  |  | 94,791 |  |  |  |  |  |  |
| Sri Lanka | I | Yes | √ | 149,023 |  |  |  |  | 250,000 |  |
| Sudan (the) | I |  |  | 143,823 |  |  |  |  | 30,000 |  |
| Suriname | I |  |  | 65,650 |  |  |  |  |  |  |
| Syrian Arab Republic | I | Yes | √ | 218,235 |  |  |  |  | 220,000 |  |
| Thailand | I | Yes | √ | 247,414 |  |  | 183,514 |  | 250,000 |  |
| Timor-Leste | I |  |  | 46,669 |  |  |  |  |  |  |
| Togo | I | Yes | √ | 129,488 |  |  |  |  | 200,000 |  |
| Tonga | I | Yes | √ | 48,745 |  |  |  |  |  |  |
| Trinidad and Tobago | I | Yes | √ | 145,733 |  |  |  | 543,249 | 190,000 |  |
| Tunisia | I | Yes | √ | 149,990 |  |  |  |  | 190,000 |  |
| Türkiye | I | Yes | √ | 194,675 |  |  |  |  | 220,000 |  |
| Turkmenistan | I | Yes | √ | 148,955 | 142,000 |  |  | 116,000 | 170,000 |  |
| Tuvalu | I | Yes | √ | 25,631 |  |  |  |  |  |  |
| Uganda | I | Yes | √ | 49,763 |  |  |  |  | 100,000 |  |
| United Republic of Tanzania (the) | I | Yes | √ | 94,185 |  |  |  |  | 130,000 |  |
| Uruguay | I | Yes | √ | 149,987 |  |  |  |  | 190,000 |  |
| Vanuatu | I | Yes | √ | 46,845 |  |  |  |  |  |  |
| Venezuela (Bolivarian Republic of) | I | Yes | √ | 250,000 |  |  |  |  | 220,000 |  |
| Viet Nam | I | Yes | √ | 249,238 |  |  |  | 2,019,488 | 280,000 |  |
| Yemen | I |  |  |  |  |  |  |  |  |  |
| Zambia | I | Yes | Pending | 94,254 |  |  |  |  | 130,000 |  |
| Zimbabwe | I | Yes | √ | 140,551 |  |  | 426,954 |  | 189,909 |  |
| Region: ASP |  |  |  |  |  |  |  |  | 780,000 |  |
| Global |  |  |  |  |  |  |  |  |  | 793,400 |
| Grand total |  |  |  | 17,278,917 | 2,532,365 | 2,398,470 | 14,536,256 | 19,411,084 | 17,774,290 | 793,400 |

Annex IV

HCFC PHASE-OUT MANAGEMENT PLAN BY COUNTRY 
AS AT 31 DECEMBER 2023

| Country | Approved phase-out (ODP tonnes) | Funds approved (US$) | Funds disbursed (US$) | Balance (US$) | Funds disbursed (%) |
| --- | --- | --- | --- | --- | --- |
| Afghanistan | 8.4 | 946,363 | 567,426 | 378,937 | 60 |
| Albania | 4.1 | 661,413 | 475,750 | 185,663 | 72 |
| Algeria | 13.5 | 1,808,804 | 1,239,334 | 569,470 | 69 |
| Angola | 10.8 | 989,326 | 613,105 | 376,221 | 62 |
| Antigua and Barbuda | 0.0 | 27,235 | 27,235 | 0 | 100 |
| Argentina | 187.7 | 19,208,674 | 12,358,214 | 6,850,460 | 64 |
| Armenia | 3.5 | 675,496 | 675,496 | 0 | 100 |
| Bahamas (the) | 3.2 | 486,225 | 313,094 | 173,131 | 64 |
| Bahrain | 39.0 | 1,570,124 | 1,285,830 | 284,294 | 82 |
| Bangladesh | 39.1 | 6,194,621 | 4,575,287 | 1,619,334 | 74 |
| Barbados | 2.5 | 439,178 | 229,178 | 210,000 | 52 |
| Belize | 1.1 | 442,704 | 354,548 | 88,156 | 80 |
| Benin | 16.0 | 1,070,778 | 699,241 | 371,536 | 65 |
| Bhutan | 0.3 | 422,349 | 422,349 | 0 | 100 |
| Bolivia (Plurinational State of) | 4.2 | 784,659 | 410,176 | 374,484 | 52 |
| Bosnia and Herzegovina | 7.2 | 1,058,680 | 973,487 | 85,193 | 92 |
| Botswana | 3.8 | 752,892 | 444,138 | 308,754 | 59 |
| Brazil | 531.7 | 42,510,669 | 36,426,380 | 6,084,289 | 86 |
| Brunei Darussalam | 3.0 | 469,123 | 332,610 | 136,513 | 71 |
| Burkina Faso | 7.2 | 1,073,630 | 628,630 | 445,000 | 59 |
| Burundi | 1.0 | 329,579 | 296,379 | 33,200 | 90 |
| Cabo Verde | 0.1 | 332,834 | 160,074 | 172,760 | 48 |
| Cambodia | 7.8 | 1,350,000 | 1,176,816 | 173,184 | 87 |
| Cameroon | 34.7 | 2,441,520 | 1,608,851 | 832,669 | 66 |
| Central African Republic (the) | 0.0 | 45,000 | 45,000 | 0 | 100 |
| Chad | 10.9 | 887,542 | 621,049 | 266,493 | 70 |
| Chile | 77.1 | 5,431,854 | 5,017,344 | 414,511 | 92 |
| China | 9,724.3 | 448,831,523 | 405,606,705 | 43,224,818 | 90 |
| Colombia | 201.2 | 12,558,699 | 11,593,280 | 965,419 | 92 |
| Comoros (the) | 0.0 | 159,653 | 159,653 | 0 | 100 |
| Congo (the) | 3.6 | 342,030 | 282,180 | 59,850 | 83 |
| Cook Islands (the) | 0.0 | 258,381 | 102,098 | 156,283 | 40 |
| Costa Rica | 19.6 | 1,727,004 | 1,410,339 | 316,665 | 82 |
| Cote d’Ivoire | 22.3 | 1,823,722 | 1,673,228 | 150,494 | 92 |
| Croatia | 6.1 | 801,942 | 801,942 | 0 | 100 |
| Cuba | 19.3 | 2,267,320 | 1,989,241 | 278,079 | 88 |
| Democratic People’s Republic of Korea (the) | 19.4 | 794,182 | 281,520 | 512,662 | 35 |
| Democratic Republic of the Congo (the) | 9.4 | 832,524 | 481,033 | 351,491 | 58 |
| Djibouti | 0.2 | 164,405 | 164,405 | 0 | 100 |
| Dominica | 0.1 | 148,050 | 35,621 | 112,429 | 24 |
| Dominican Republic (the) | 26.6 | 4,902,859 | 3,772,398 | 1,130,461 | 77 |
| Ecuador | 35.6 | 3,076,425 | 2,543,319 | 533,106 | 83 |
| Egypt | 332.2 | 25,519,760 | 17,949,967 | 7,569,792 | 70 |
| El Salvador | 12.9 | 1,236,119 | 1,063,783 | 172,336 | 86 |
| Equatorial Guinea | 0.9 | 278,267 | 248,267 | 30,000 | 89 |
| Eritrea | 0.7 | 429,559 | 228,318 | 201,241 | 53 |
| Eswatini (the Kingdom of) | 8.3 | 971,931 | 891,931 | 80,000 | 92 |
| Ethiopia | 1.9 | 507,127 | 314,416 | 192,711 | 62 |
| Fiji | 2.0 | 607,700 | 325,276 | 282,424 | 54 |
| Gabon | 10.6 | 534,641 | 475,150 | 59,491 | 89 |
| Gambia (the) | 1.1 | 686,599 | 248,001 | 438,598 | 36 |
| Georgia | 3.5 | 691,739 | 600,791 | 90,948 | 87 |
| Ghana | 48.5 | 1,928,700 | 1,880,438 | 48,262 | 97 |
| Grenada | 0.5 | 481,289 | 207,049 | 274,240 | 43 |
| Guatemala | 7.0 | 911,712 | 575,019 | 336,693 | 63 |
| Guinea | 4.2 | 664,053 | 518,300 | 145,753 | 78 |
| Guinea-Bissau | 1.0 | 255,849 | 255,849 | 0 | 100 |
| Guyana | 1.1 | 681,602 | 329,352 | 352,250 | 48 |
| Haiti | 0.4 | 116,291 | 116,291 | 0 | 100 |
| Honduras | 12.2 | 1,162,082 | 832,015 | 330,067 | 72 |
| India | 1,151.3 | 67,277,161 | 55,487,933 | 11,789,228 | 82 |
| Indonesia | 275.1 | 20,396,281 | 14,163,747 | 6,232,535 | 69 |
| Iran (Islamic Republic of) | 312.5 | 18,737,927 | 15,526,406 | 3,211,522 | 83 |
| Iraq | 15.0 | 1,499,045 | 1,087,789 | 411,256 | 73 |
| Jamaica | 8.9 | 760,797 | 643,797 | 117,000 | 85 |
| Jordan | 60.7 | 6,438,035 | 5,235,706 | 1,202,329 | 81 |
| Kenya | 14.1 | 1,973,000 | 1,295,316 | 677,684 | 66 |
| Kiribati | 0.0 | 310,600 | 103,079 | 207,521 | 33 |
| Kuwait | 273.8 | 10,618,543 | 9,211,129 | 1,407,414 | 87 |
| Kyrgyzstan | 3.3 | 799,488 | 799,488 | 0 | 100 |
| Lao People's Democratic Republic (the) | 1.0 | 432,345 | 361,621 | 70,724 | 84 |
| Lebanon | 73.6 | 7,113,759 | 6,350,465 | 763,294 | 89 |
| Lesotho | 0.0 | 548,900 | 348,233 | 200,667 | 63 |
| Liberia | 3.7 | 666,595 | 329,496 | 337,099 | 49 |
| Libya | 37.6 | 2,137,328 | 917,583 | 1,219,745 | 43 |
| Madagascar | 12.8 | 865,923 | 611,726 | 254,197 | 71 |
| Malawi | 7.3 | 988,235 | 588,606 | 399,629 | 60 |
| Malaysia | 249.2 | 15,725,205 | 15,075,142 | 650,063 | 96 |
| Maldives | 0.6 | 1,081,613 | 1,081,613 | 0 | 100 |
| Mali | 5.2 | 542,523 | 486,523 | 56,000 | 90 |
| Marshall Islands (the) | 0.2 | 180,930 | 108,851 | 72,079 | 60 |
| Mauritania | 4.4 | 521,595 | 210,655 | 310,940 | 40 |
| Mauritius | 3.1 | 902,500 | 550,944 | 351,556 | 61 |
| Mexico | 599.2 | 27,694,586 | 25,488,409 | 2,206,177 | 92 |
| Micronesia (Federated States of) | 0.2 | 313,958 | 145,085 | 168,873 | 46 |
| Mongolia | 1.1 | 835,769 | 438,367 | 397,402 | 52 |
| Montenegro | 0.8 | 969,593 | 615,983 | 353,610 | 64 |
| Morocco | 35.6 | 2,299,926 | 1,389,158 | 910,767 | 60 |
| Mozambique | 3.9 | 702,361 | 268,751 | 433,610 | 38 |
| Myanmar | 0.4 | 280,000 | 174,042 | 105,958 | 62 |
| Namibia | 8.2 | 930,000 | 651,974 | 278,026 | 70 |
| Nauru | 0.0 | 129,304 | 66,514 | 62,790 | 51 |
| Nepal | 0.9 | 408,254 | 206,600 | 201,654 | 51 |
| Nicaragua | 5.2 | 774,572 | 491,057 | 283,514 | 63 |
| Niger (the) | 10.8 | 910,340 | 598,242 | 312,098 | 66 |
| Nigeria | 236.2 | 14,147,399 | 9,339,040 | 4,808,360 | 66 |
| Niue | 0.0 | 105,159 | 70,144 | 35,015 | 67 |
| North Macedonia | 2.6 | 1,441,950 | 1,196,730 | 245,220 | 83 |
| Oman | 24.1 | 1,636,375 | 1,113,502 | 522,873 | 68 |
| Pakistan | 177.8 | 12,944,169 | 10,333,106 | 2,611,063 | 80 |
| Palau | 0.2 | 303,000 | 134,000 | 169,000 | 44 |
| Panama | 19.7 | 1,715,241 | 1,207,238 | 508,003 | 70 |
| Papua New Guinea | 3.4 | 1,125,000 | 1,018,471 | 106,529 | 91 |
| Paraguay | 7.7 | 838,698 | 718,513 | 120,185 | 86 |
| Peru | 18.2 | 1,510,358 | 942,832 | 567,526 | 62 |
| Philippines (the) | 91.1 | 5,965,242 | 3,174,147 | 2,791,095 | 53 |
| Qatar | 23.9 | 1,635,441 | 1,146,996 | 488,445 | 70 |
| Republic of Moldova (the) | 0.6 | 384,056 | 284,159 | 99,897 | 74 |
| Rwanda | 1.9 | 437,166 | 352,299 | 84,867 | 81 |
| Saint Kitts and Nevis | 0.3 | 164,442 | 98,342 | 66,100 | 60 |
| Saint Lucia | 0.6 | 369,418 | 196,359 | 173,059 | 53 |
| Saint Vincent and the Grenadines | 0.2 | 421,951 | 318,951 | 103,001 | 76 |
| Samoa | 0.2 | 344,450 | 184,486 | 159,964 | 54 |
| Sao Tome and Principe | 0.1 | 154,727 | 154,727 | 0 | 100 |
| Saudi Arabia | 276.7 | 7,141,408 | 7,141,408 | 0 | 100 |
| Senegal | 3.6 | 872,663 | 614,076 | 258,587 | 70 |
| Serbia | 7.9 | 1,225,790 | 1,041,009 | 184,781 | 85 |
| Seychelles | 1.4 | 640,000 | 401,220 | 238,780 | 63 |
| Sierra Leone | 1.2 | 718,530 | 215,506 | 503,024 | 30 |
| Solomon Islands | 1.8 | 463,004 | 229,588 | 233,415 | 50 |
| Somalia | 1.8 | 385,574 | 377,781 | 7,793 | 98 |
| South Africa | 243.1 | 9,515,438 | 6,341,205 | 3,174,233 | 67 |
| South Sudan | 0.5 | 140,500 | 20,063 | 120,437 | 14 |
| Sri Lanka | 12.0 | 1,049,741 | 741,754 | 307,987 | 71 |
| Sudan (the) | 49.0 | 4,330,964 | 2,669,090 | 1,661,874 | 62 |
| Suriname | 1.3 | 426,709 | 175,859 | 250,850 | 41 |
| Syrian Arab Republic | 44.8 | 4,316,733 | 1,715,165 | 2,601,568 | 40 |
| Thailand | 284.5 | 20,540,540 | 17,992,292 | 2,548,248 | 88 |
| Timor-Leste | 0.2 | 504,170 | 431,739 | 72,431 | 86 |
| Togo | 13.5 | 952,823 | 702,899 | 249,924 | 74 |
| Tonga | 0.1 | 322,159 | 162,353 | 159,806 | 50 |
| Trinidad and Tobago | 31.2 | 2,596,444 | 1,743,386 | 853,058 | 67 |
| Tunisia | 29.7 | 2,284,799 | 1,635,134 | 649,665 | 72 |
| Türkiye | 564.4 | 13,264,790 | 11,719,823 | 1,544,967 | 88 |
| Turkmenistan | 4.6 | 916,112 | 873,542 | 42,570 | 95 |
| Tuvalu | 0.1 | 164,469 | 93,823 | 70,647 | 57 |
| Uganda | 0.0 | 283,875 | 255,705 | 28,170 | 90 |
| United Republic of Tanzania (the) | 1.1 | 462,271 | 219,041 | 243,230 | 47 |
| Uruguay | 22.7 | 2,281,080 | 1,359,948 | 921,132 | 60 |
| Vanuatu | 0.3 | 356,850 | 168,615 | 188,235 | 47 |
| Venezuela (Bolivarian Republic of) | 76.0 | 3,220,110 | 2,675,570 | 544,540 | 83 |
| Viet Nam | 317.3 | 18,027,461 | 14,144,434 | 3,883,027 | 78 |
| Zambia | 2.5 | 462,956 | 436,039 | 26,917 | 94 |
| Zimbabwe | 18.0 | 1,751,318 | 1,225,317 | 526,001 | 70 |
| Region: ASP | 0.0 | 940,000 | 573,924 | 366,076 | 61 |
| Total | 17,354.4 | 951,735,520 | 801,125,575 | 150,609,945 | 84 |

UNEP/OzL.Pro/ExCom/95/1

Progress reports were submitted by the following agencies: Australia, Canada, France, Germany, Italy, Japan, and Spain, UNDP, UNEP, UNIDO and the World Bank (documents UNEP/OzL.Pro/ExCom/95/15 to UNEP/OzL.Pro/ExCom/95/19).

The Executive Committee requested that detailed information on a project-by-project basis be made available to Committee members, with a printout available upon request (decision 19/23). The database for the Consolidated Progress Report is provided on the 95th meeting portal on the Multilateral Fund’s website, in the spreadsheet programme, Microsoft Excel.

At its 77th meeting, the Executive Committee accepted, with appreciation, the additional contributions announced by 17 non-Article 5 Parties to provide fast start support for implementation of the Kigali Amendment, noting that such funding was one-time in nature and would not displace donor contributions. The contributing parties are Australia, Canada, Denmark, Finland, France, Germany, Ireland, Italy, Japan, Luxembourg, Netherlands, New Zealand, Norway, Sweden, Switzerland, United Kingdom of Great Britain and Northern Ireland, and United States of America.

In line with decision 84/12(a)(iv), the measurement for HFCs in CO2-eq tonnes is included in the progress reports submitted to the 95th meeting.

Excluding those that are considered in the relevant project proposal documents, under reports on projects with specific reporting requirements (UNEP/OzL.Pro/ExCom/95/20 and UNEP/OzL.Pro/ExCom/95/21), or under tranche submission delays (UNEP/OzL.Pro/ExCom/95/24).

Ongoing projects are all projects that were under implementation as at 31 December 2023. Key indicators of progress include percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

Phase-out of ODS is expressed in ODP tonnes and of HFCs in mt and CO2-eq tonnes.

No phase-out for HFC-related projects in 2023.

Including 4,246 mt of HFC-related projects. Cost-effectiveness in CO2-eq is not included due to the limited number of projects approved.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies. The cost-effectiveness for MYAs of HCFC phase-out management plan (HPMP) is US $56.53/kg ODP, for stage I of HCFC production phase-out management plan (HPPMP) is US $23.93/kg ODP and for stage II of HPPMP is US $4.16/kg ODP.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61). Pursuant to decision 84/45(c), MYA components are subjected to procedure for cancellation.

The Executive Committee requested bilateral and implementing agencies to provide a brief report on key gender mainstreaming results achieved as part of their annual progress reports, as of 2023, on the basis of the information available to them (decision 90/48(d)).

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP tonnes/CO2-eq tonnes phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively financed projects.

Completed projects/activities are defined in decisions 17/22 and 19/23 as projects that have been commissioned and where the ODS addressed has been phased out. A further decision (decision 28/2) extends the definition to cover situations where no further use of CFCs in the sectors covered is in evidence, where an alternative product is being produced (and/or production has begun), and where the equipment using CFCs has been destroyed/dismantled/rendered unusable with respect to ODSs. Work programme activities without an ODS phase-out are considered completed when the activity is finished (e.g., for a workshop, when it has been conducted). This definition has been applied for HCFC-related projects.

The reason that 100 per cent of funds have not been disbursed for completed projects is that it may take from six months to one year to finalise accounting records.