| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/86/17 23 October 2020 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-sixth Meeting

Montreal, 2-6 November 2020

Postponed to 8-12 March 2021

PROGRESS REPORT OF UNDP AS AT 31 DECEMBER 2019

# This document presents the progress report of UNDP as at 31 December 2019.

Introduction

# The progress report of UNDP includes the status of implementation of projects, including 18 HFC-related projects that have been funded under the additional voluntary contributions by 17 non-Article 5 Parties to provide fast-start support for implementation of the Kigali Amendment.

# The Secretariat reviewed the status of implementation of each ongoing project on a country-by-country basis, taking into account implementation delays that have occurred with respect to planned completion dates that had been reported in 2019, the potential impact of these delays on the phase-out of controlled substances and the rate of planned disbursements. The analysis contained in the present document is based on ODP tonnes for all controlled substances (including HFCs which should be measured in mt CO2-eq).

Scope of the document

# This document consists of the following parts:

## Part I:	Projects approved under the regular contributions to the Multilateral Fund. It presents a summary of progress in implementation of projects for 2019 and cumulative since 1991 addressing all controlled substances under the Montreal Protocol, including Annex F substances (HFCs); it contains a review on the status of implementation of each ongoing project at the country level; and it identifies projects with implementation delays and the potential impact on the phase-out of controlled substances, and projects with outstanding issues for consideration by the Executive Committee.

## Part II:	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down. It provides a summary on the status of implementation of HFC phase-down projects funded under the voluntary contributions.

Recommendation.

# The document also contains the following annexes:

Annex I: 	A summary status and a recommendation for each ongoing project with outstanding issues for consideration by the Executive Committee.

Annex II: 	An analysis of the progress report.

# Part I: 	Projects approved under the regular contributions to the Multilateral Fund

Summary of progress in implementation of projects for 2019 and cumulative

# Implementation of projects and activities by UNDP for 2019 and cumulative since 1991 up to 31 December 2019, is summarized as follows:

## Phase-out: In 2019, 470.9 ODP tonnes of consumption of controlled substances were phased out and an additional 126.3 ODP tonnes of consumption of controlled substances were approved for phase-out. Since 1991, 67,480 ODP tonnes of consumption of controlled substances had been phased out, of an expected total of 68,407 ODP tonnes from projects approved (excluding cancelled and transferred projects);

## Disbursements/approvals: In 2019, US $23.14 million was disbursed and US $15.62 million was planned for disbursement based on the 2018 progress report, representing a rate of disbursement of 148 per cent of that planned. Cumulatively, US $768.69 million had been disbursed out of the total US $831.9 million approved for disbursement (excluding agency support costs), representing a rate of disbursement of 92 per cent. In 2019, US $10.39 million was approved for implementation;

## Cost-effectiveness (in ODP): Since 1991, the average cost-effectiveness of investment projects approved leading to a permanent reduction in consumption was US $10.65/kg. The average cost-effectiveness of investment projects per ODP tonne was US $9.38/kg for completed projects and US $78.78/kg for ongoing projects;

## Number of projects completed: In 2019, 56 projects were completed. Since 1991, 2,345 projects of the 2,475 projects approved (excluding closed or transferred projects) were completed, representing a completion rate of 95 per cent;

## Speed of delivery – investment projects: Projects that were completed in 2019 were completed on average 51 months after their approval. Since 1991, the average time for completion of investment projects has been 34 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;

## Speed of delivery – non investment projects: Projects that were completed in 2019 were completed on average 38 months after their approval. Since 1991, the average time for completion of non-investment projects has been 39 months after their approval. First disbursements under these projects occurred, on average, 13 months after they had been approved;

## Project preparation: Of the 539 project preparation activities approved by the end of 2019, 518 have been completed, leaving 21 ongoing activities. In 2019, one project preparation activity has been completed;

## Implementation delays: A total of 130 projects were under implementation at the end of 2019, experiencing, on average, a delay of 15 months. Five of these projects are classified as “projects with implementation delays” that are subject to the procedures of project cancellation (as demonstration projects, project preparation and IS are not subject to those procedures); and

## Multi-year agreements (MYAs): In 2019, 41 MYAs for HCFC phase-out management plans (HPMPs) were under implementation. Since 1991, 136 MYAs have been approved and 95 MYAs have been completed, representing a completion rate of 70 per cent.

Project implementation progress in 2019

# Further to the review process, a number of issues were discussed and satisfactorily addressed, except for five projects related to components of MYAs with implementation delays that are subject to procedures for project cancellation, in line with decision 84/45(c). Annex I to the present document presents those projects classified with implementation delays, and the Secretariat’s recommendation requesting the submission of a report to the 87th meeting.

# In addition, a number of issues were identified regarding projects or tranches of MYAs for the phase-out of HCFCs. These issues are also presented in Annex I to the present document. For each of these projects, a brief description on the status of implementation and the outstanding issues are presented and a recommendation is proposed for consideration by the Executive Committee.

# Details of progress in implementation of projects associated with the HPMPs for Armenia, Brazil, Brunei Darussalam, Cuba, the Dominican Republic, El Salvador, Eswatini, Fiji, India, the Islamic Republic of Iran, Jamaica, Lebanon, Nepal, Panama, Paraguay, Republic of Moldova (the), Sri Lanka, Trinidad and Tobago and Uruguay, and reports on projects with specific reporting requirements associated with Brazil (ODS disposal), Ghana (HPMP), and Mexico (HPMP), and China (HPMP), have been submitted to the 86th meeting. Recommendations for outstanding issues for these projects, including approval of extension requests, if any, are addressed in the relevant sections of those documents. The issues relating to the HPMPs for Bangladesh, Mali, Mauritania, Nigeria and South Sudan, are addressed in the document on tranche submission delays.

# Of the 86 ongoing projects, excluding IS and project preparation, 29 projects have revised planned dates of completion since the 2018 progress report.

# In line with decision 82/11(c)(ii), the Secretariat noted that renewal of the IS project for Brazil had not been submitted for the last two years. UNDP informed that it is planning to submit the renewal request in 2021.

Part II: Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2019, the Executive Committee had approved 18 HFC-related projects under the additional voluntary contributions amounting to US $6,053,676 (excluding agency support costs). A summary of the status of these projects is presented in Table 1.

# Table 1. Status of approved HFC-related projects as of the end of 2019

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 2 | 1 | 50 | 4,406,610 | 4,144,828 | 261,782 | 94 |
| Project preparation | 5 | 5 | 100 | 124,066 | 75,911 | 48,155 | 61 |
| Technical assistance - Enabling activities | 11 | 1 | 9 | 1,523,000 | 712,989 | 810,011 | 47 |
| Total | 18 | 7 | 39 | 6,053,676 | 4,933,728 | 1,119,948 | 81 |

* Excludes agency support costs.

** 480.6 mt (587,301 mt CO2-eq.) of HFCs to be phased out.

# As of the end of 2019, of the 18 projects approved, seven projects had been completed including one investment project, one enabling activity and five preparation activities, leaving 11 ongoing. Extension of the completion dates of the 10 ongoing enabling activities was approved at the 83rd meeting (nine projects) and at the 84th meeting (one project); these activities are at various stages of implementation.

# The remaining ongoing investment project approved at the 82nd meeting, with 80 per cent of the approved funds disbursed, is expected to be completed in 2021.

# Of the total cumulative funding approved of US $6,053,676, US $4,933,728 had been disbursed, representing a disbursement rate of 81 per cent.

Recommendation

# The Executive Committee may wish:

## To note the progress report of UNDP as at 31 December 2019 contained in document UNEP/OzL.Pro/ExCom/86/17; and

## To approve the recommendations related to ongoing projects with specific issues contained in Annex I to the present document.

Annex I

## ONGOING PROJECTS WITH OUTSTANDING ISSUES IN THE PROGRESS REPORT FOR UNDP

| Country/project code | Project title | Disbursement (%) | Status/Issues | Recommendation |
| --- | --- | --- | --- | --- |
| Bangladesh BGD/PHA/81/INV/51 | HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector) | 0 | No disbursement; delays in getting approvals by different departments for signing of agreement due inter alia to COVID-19 | To request a status report to the 87th meeting on the level of funds disbursement |
| Bangladesh BGD/PHA/81/TAS/49 | HCFC phase-out management plan (stage II, first tranche) (project management unit) | 0 |  |  |
| Colombia COL/PHA/75/INV/98 | HCFC phase-out management plan (stage II, first tranche) (foam sector) | 41 | 12 months delays | To request UNDP to report to the 87th meeting on this project with implementation delays |
| Democratic Republic of the Congo (the) DRC/PHA/79/PRP/42 | Preparation of a HCFC phase-out management plan (stage II) | 0 | No disbursement due to security situation in the country, and COVID-19 travel restrictions resulting in difficulties in field activities; submission of stage II delayed | To request a status report to the 87th meeting on the status of submission of stage II |
| Haiti HAI/PHA/76/INV/22 | HCFC phase-out management plan (stage I, second tranche) | 1 | Low disbursement; slow progress in equipment procurement and delivery | To request a status report to the 87th meeting on progress in implementation and the level of funds disbursement |
| Indonesia IDS/PHA/71/TAS/200 | HCFC phase-out management plan (project management and coordination) (stage I, second tranche) | 21 | 12 months delays | To request UNDP to report to the 87th meeting on this project with implementation delays |
| Indonesia IDS/PHA/76/INV/208 | HCFC phase-out management plan (stage I, third tranche) (refrigeration and air-conditioning sector) | 27 | 12 months delays | To request UNDP to report to the 87th meeting on this project with implementation delays |
| Indonesia IDS/PHA/76/INV/211 | HCFC phase-out management plan (stage II, first tranche) (fire fighting sector) | 0 | 18 months delays | To request UNDP to report to the 87th meeting on this project with implementation delays |
| Mauritania MAU/PHA/80/INV/25 | HCFC phase-out management plan (stage I, first tranche) | 0 | 18 months delays | To request UNDP to report to the 87th meeting on this project with implementation delays |

Annex II

ANALYSIS OF THE PROGRESS REPORT OF UNDP AS AT 31 DECEMBER 2019

# This Annex consists of the following two parts:

## Part I:	Projects approved under the regular contributions to the Multilateral Fund.

## Part II:	Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down.

Part I: 	Projects approved under the regular contributions to the Multilateral Fund

# As of 31 December 2019, the Executive Committee had approved US $945.34 million, consisting of US $831.9 million for the implementation of investment and non-investment projects and US $113.44 million for agency support costs, as shown in Table 1. In 2019, 41 new projects and activities were approved. This level of funding is expected to result in the phase-out of 68,407 ODP tonnes of consumption of controlled substances.

# Table 1. Approved funding by sector for UNDP as at 31 December 2019

| Sector | Funding (US $) |
| --- | --- |
| Aerosol | 26,054,837 |
| Destruction | 3,606,279 |
| Fire fighting | 2,170 |
| Foam | 173,331,969 |
| Halon | 4,996,973 |
| Fumigants | 20,081,241 |
| Multiple sectors | 0 |
| Other | 0 |
| Phase-out plan | 333,872,234 |
| Process agent | 1,286,923 |
| Production | 1,056,000 |
| Refrigeration | 139,612,399 |
| Several | 63,877,595 |
| Solvents | 63,699,997 |
| Sterilant | 417,628 |
| Sub-total | 831,896,245 |
| Agency support costs | 113,444,224 |
| Total | 945,340,469 |

# A summary of the status of projects implemented by category is presented in Table 2.

Table 2. Status of project implementation by category

| Type | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Country programme | 22 | 22 | 100 | 1,628,797 | 1,628,797 | 0 | 100 |
| Demonstration | 42 | 41 | 98 | 21,910,968 | 21,451,655 | 459,313 | 98 |
| Institutional strengthening (IS) | 249 | 226 | 91 | 53,614,738 | 48,248,611 | 5,366,127 | 90 |
| Investment | 1,275 | 1,223 | 96 | 682,547,982 | 635,467,983 | 47,079,999 | 93 |
| Project preparation | 539 | 518 | 96 | 22,365,067 | 21,645,479 | 719,588 | 97 |
| Technical assistance | 320 | 287 | 90 | 48,238,204 | 38,660,157 | 9,578,047 | 80 |
| Training | 28 | 28 | 100 | 1,590,489 | 1,590,489 | 0 | 100 |
| Total | 2,475 | 2,345 | 95 | 831,896,245 | 768,693,171 | 63,203,074 | 92 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

# Table 3 presents an overview of the status of project implementation by year. All projects and activities approved between 1991 and 2011, have now been completed.

Table 3. Status of project implementation by year

| Year | Number of projects* |  |  | Funding (US $)** |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| 1991 | 15 | 15 | 100 | 1,149,032 | 1,149,032 | 0 | 100 |
| 1992 | 67 | 67 | 100 | 8,619,002 | 8,619,002 | 0 | 100 |
| 1993 | 57 | 57 | 100 | 13,204,712 | 13,204,712 | 0 | 100 |
| 1994 | 148 | 148 | 100 | 49,481,581 | 49,481,581 | 0 | 100 |
| 1995 | 117 | 117 | 100 | 29,599,446 | 29,599,446 | 0 | 100 |
| 1996 | 83 | 83 | 100 | 27,838,805 | 27,838,805 | 0 | 100 |
| 1997 | 188 | 188 | 100 | 44,056,257 | 44,056,257 | 0 | 100 |
| 1998 | 172 | 172 | 100 | 31,305,010 | 31,305,010 | 0 | 100 |
| 1999 | 204 | 204 | 100 | 35,896,884 | 35,896,884 | 0 | 100 |
| 2000 | 149 | 149 | 100 | 31,268,361 | 31,268,361 | 0 | 100 |
| 2001 | 179 | 179 | 100 | 35,292,271 | 35,292,271 | 0 | 100 |
| 2002 | 117 | 117 | 100 | 44,316,422 | 44,316,422 | 0 | 100 |
| 2003 | 64 | 64 | 100 | 36,336,530 | 36,336,530 | 0 | 100 |
| 2004 | 69 | 69 | 100 | 24,802,714 | 24,802,714 | 0 | 100 |
| 2005 | 53 | 53 | 100 | 29,124,833 | 29,124,833 | 0 | 100 |
| 2006 | 62 | 62 | 100 | 15,753,459 | 15,753,461 | -2 | 100 |
| 2007 | 54 | 54 | 100 | 12,142,486 | 12,142,486 | 0 | 100 |
| 2008 | 84 | 84 | 100 | 22,873,866 | 22,873,866 | 0 | 100 |
| 2009 | 92 | 92 | 100 | 13,222,786 | 13,193,670 | 29,116 | 100 |
| 2010 | 43 | 43 | 100 | 19,567,970 | 19,567,970 | 0 | 100 |
| 2011 | 63 | 63 | 100 | 57,446,042 | 57,421,734 | 24,308 | 100 |
| 2012 | 29 | 28 | 97 | 33,889,850 | 32,979,174 | 910,676 | 97 |
| 2013 | 43 | 42 | 98 | 34,567,186 | 33,721,314 | 845,872 | 98 |
| 2014 | 67 | 65 | 97 | 22,714,330 | 22,292,594 | 421,736 | 98 |
| 2015 | 75 | 74 | 99 | 33,523,195 | 29,056,699 | 4,466,496 | 87 |
| 2016 | 52 | 37 | 71 | 42,508,656 | 33,144,050 | 9,364,606 | 78 |
| 2017 | 28 | 16 | 57 | 30,728,346 | 28,749,500 | 1,978,846 | 94 |
| 2018 | 60 | 3 | 5 | 40,274,486 | 5,469,512 | 34,804,974 | 14 |
| 2019 | 41 | 0 | 0 | 10,391,727 | 35,281 | 10,356,446 | 0 |
| Total | 2,475 | 2,345 | 95 | 831,896,245 | 768,693,171 | 63,203,074 | 92 |

*Excludes closed and transferred projects.

**Excludes agency support costs.

# Table 4 presents project implementation by country for 2019.

Table 4. Summary of project implementation by UNDP for 2019

| Country | Phased out in 2019* | Percentage of planned phase-out achieved in 2019 | Estimated funds disbursed in 2019 (US$) | Funds disbursed in 2019 (US$) | Percentage of funds disbursed over estimation in 2019 | Percentage of planned projects completed in 2019 |
| --- | --- | --- | --- | --- | --- | --- |
| Angola | 2.0 |  | 75,680 | 138,812 | 183 |  |
| Argentina | 0.0 |  | 113,619 | 110,653 | 97 |  |
| Armenia | 0.0 |  | 7,005 | 30,339 | 433 | 0 |
| Bangladesh | 0.0 |  | 475,871 | 187,628 | 39 | 100 |
| Barbados | 0.4 |  | 5,802 | 27,189 | 469 |  |
| Belize | 0.0 |  | 5,250 | 0 | 0 |  |
| Bhutan | 0.1 |  | 3,264 | 15,677 | 480 |  |
| Brazil | 92.4 |  | 2,590,760 | 3,934,029 | 152 |  |
| Brunei Darussalam | 0.0 |  | 11,520 | 34,600 | 300 | 100 |
| Cambodia | 1.0 |  | 10,000 | 50,000 | 500 | 100 |
| Chile | 23.0 |  | 348,129 | 1,009,701 | 290 |  |
| China | 5.9 |  | 1,072,665 | 5,100,642 | 476 | 100 |
| Colombia | 10.8 | 0 | 557,174 | 677,345 | 122 | 50 |
| Costa Rica | 0.0 |  | 65,985 | 185,239 | 281 |  |
| Cuba | 1.0 |  | 126,041 | 240,312 | 191 | 0 |
| Democratic Republic of the Congo (the) | 0.0 |  | 3,667 | 0 | 0 | 0 |
| Dominican Republic (the) | 2.3 |  | 149,255 | 403,053 | 270 |  |
| Egypt | 24.9 | 78 | 698,412 | 1,173,382 | 168 | 60 |
| El Salvador | 0.0 |  | 34,693 | 290 | 1 | 0 |
| Fiji | 1.0 |  | 21,809 | 48,374 | 222 |  |
| Georgia | 0.0 |  | 49,231 | 104,337 | 212 |  |
| Ghana | -5.5 |  | 75,243 | 147,057 | 195 |  |
| Guyana | 0.2 | 100 | 10,242 | 2,705 | 26 | 100 |
| Haiti | 0.0 |  | 19,424 | 1,250 | 6 |  |
| India | 35.0 |  | 4,578,702 | 3,162,037 | 69 | 100 |
| Indonesia | 0.0 |  | 847,675 | 371,366 | 44 | 33 |
| Iran (Islamic Republic of) | 23.8 | 100 | 340,013 | 621,656 | 183 | 100 |
| Jamaica | 0.0 |  | 24,810 | 28,345 | 114 |  |
| Kuwait | 0.0 |  | 68,600 | 0 | 0 | 0 |
| Kyrgyzstan | 0.0 |  | 35,035 | 70,429 | 201 |  |
| Lebanon | 6.0 |  | 268,127 | 492,085 | 184 | 100 |
| Malaysia | 73.6 |  | 504,611 | 1,385,155 | 274 | 100 |
| Maldives | 0.0 |  | 32,933 | 150,540 | 457 | 100 |
| Mali | 0.0 |  | 2,821 | 0 | 0 | 100 |
| Mauritania | 0.0 |  | 21,000 | 0 | 0 |  |
| Mexico | 131.5 |  | 779,300 | 1,622,125 | 208 |  |
| Nepal | 0.1 | 100 | 5,337 | 15,000 | 281 | 100 |
| Nigeria | 30.0 |  | 692,859 | 235,227 | 34 |  |
| Pakistan | 0.0 |  | 106,099 | 192,321 | 181 | 100 |
| Panama | 2.0 |  | 172,912 | 225,742 | 131 | 100 |
| Paraguay | 2.1 |  | 13,325 | 43,311 | 325 |  |
| Peru | 0.9 |  | 73,495 | 103,517 | 141 |  |
| Republic of Moldova (the) | 0.2 |  | 20,590 | 65,295 | 317 |  |
| Saint Kitts and Nevis | 0.1 |  | 8,000 | 39,942 | 499 |  |
| Sri Lanka | 1.1 | 100 | 50,451 | 104,604 | 207 | 100 |
| Timor-Leste | 0.0 |  | 14,540 | 6,050 | 42 |  |
| Trinidad and Tobago | 4.0 |  | 89,436 | 245,546 | 275 |  |
| Uruguay | 1.0 |  | 179,784 | 250,629 | 139 | 100 |
| Venezuela (Bolivarian Republic of) | 0.0 |  | 92,069 | 82,069 | 89 | 100 |
| Zimbabwe | 0.0 |  | 65,391 | 0 | 0 |  |
| Global | 0.0 |  | 0 | 0 |  | 100 |
| Total | 470.9 | 48 | 15,618,656 | 23,135,605 | 148 | 74 |

* 87.3 mt (125,000 mt CO2-eq.) phased out in 2019 for HFC-related projects.

# Table 5 presents a summary of HFC-related projects approved under regular contributions.

Table 5. HFC-related projects approved under regular contributions

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 3 | 1 | 33 | 2,491,791 | 1565244 | 926,547 | 63 |
| Technical assistance - Enabling activities | 5 | 0 | 0 | 384,000 | 50,919 | 333,081 | 13 |
| Total | 8 | 1 | 13 | 2,875,791 | 1,616,163 | 1,259,628 | 56 |

*Excludes agency support costs.

** 142.8 mt (204,332 mt CO2-eq.) was approved for investment projects.

# There are currently eight HFC-related projects (including three investment projects and five enabling activities). Of the eight projects, one investment project has been completed, leaving seven ongoing. Extension of the completion dates of three enabling activities was approved at the 84th meeting; these ongoing activities are at various stages of implementation.

# The remaining two ongoing investment projects are at various stages of implementation and are expected to be completed in 2021 and 2022.

# Of the total cumulative funding approved of US $2,875,791 (excluding agency support costs), US $1,616,163 had been disbursed, representing a disbursement rate of 56 per cent.

# Part II: Projects approved under the additional voluntary contributions for fast-start support for HFC phase-down

# As of 31 December 2019, the Executive Committee had approved 18 HFC-related projects under the additional voluntary contributions amounting to US $6,053,676 (excluding agency support costs). A summary of the status of these projects is presented in Table 6.

# Table 6. Status of approved HFC-related projects as of the end of 2019

| Type | Number of projects |  |  | Funding (US $)* |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Completed | % completed | Approved | Disbursed | Balance | % disbursed |
| Investment** | 2 | 1 | 50 | 4,406,610 | 4,144,828 | 261,782 | 94 |
| Project preparation | 5 | 5 | 100 | 124,066 | 75,911 | 48,155 | 61 |
| Technical assistance - Enabling activities | 11 | 1 | 9 | 1,523,000 | 712,989 | 810,011 | 47 |
| Total | 18 | 7 | 39 | 6,053,676 | 4,933,728 | 1,119,948 | 81 |

* Excludes agency support costs.

** 480.6 mt (587,301 mt CO2-eq.) of HFCs to be phased out.

# As of the end of 2019, of the 18 projects approved, seven projects had been completed including one investment project, one enabling activity and five preparation activities, leaving 11 ongoing. Extension of the completion dates of the 10 ongoing enabling activities was approved at the 83rd meeting (nine projects) and at the 84th meeting (one project); these activities are at various stages of implementation.

# The remaining ongoing investment project approved at the 82nd meeting, with 80 per cent of the approved funds disbursed, is expected to be completed in 2021.

# Of the total cumulative funding approved of US $6,053,676, US $4,933,728 had been disbursed, representing a disbursement rate of 81 per cent.

Due to coronavirus disease (COVID-19)

The progress report is attached to the present document. The data has been included in the Consolidated Progress Report database that is available upon request.

In line with decision 84/12(a)(iv), the measurement for HFCs in mt CO2-eq. would be included in the progress reports submitted from the 88th meeting. This issue is discussed in the consolidated progress report (UNEP/OzL.Pro/ExCom/86/15).

Ongoing projects are all projects that were under implementation as at 31 December 2019. Key indicators of progress include: percentage of funds disbursed and percentage of projects that have begun disbursing funds; funding expected to be disbursed by the end of the year as a percentage of the approved funding; the average length of projected delay in implementation; and information provided in the remarks column in the progress report database.

In line with decision 84/12(b), a detailed progress report providing an overview of the objectives, status of implementation, key findings and lessons learned, the amounts of HFC phased out where applicable, the level of funds approved and disbursed and potential challenges in completing the projects and activities, is presented in the consolidated progress report (UNEP/OzL.Pro/ExCom/86/15).

The phase-out includes approvals for HFC investment projects of 142.8 mt (204,332 mt CO2-eq.).

Including 142.8 mt of HFC investment projects.

The higher value of the cost-effectiveness for ongoing projects is largely due to the lower ODP values of HCFCs but also due to the means of assigning phase-out by agencies.

Projects approved over 18 months with disbursement less than 1 per cent, or projects that had not been completed 12 months after the proposed completion date in the progress report (decision 22/61) (as demonstration projects, project preparation, and institutional strengthening (IS) are not subject to those procedures).

UNEP/OzL.Pro/ExCom/86/38

UNEP/OzL.Pro/ExCom/86/41

UNEP/OzL.Pro/ExCom/86/42

UNEP/OzL.Pro/ExCom/86/45

UNEP/OzL.Pro/ExCom/86/46

UNEP/OzL.Pro/ExCom/86/48

UNEP/OzL.Pro/ExCom/86/49

UNEP/OzL.Pro/ExCom/86/50

UNEP/OzL.Pro/ExCom/86/54

UNEP/OzL.Pro/ExCom/86/55

UNEP/OzL.Pro/ExCom/86/56

UNEP/OzL.Pro/ExCom/86/59

UNEP/OzL.Pro/ExCom/86/63

UNEP/OzL.Pro/ExCom/86/68

UNEP/OzL.Pro/ExCom/86/69

UNEP/OzL.Pro/ExCom/86/71

UNEP/OzL.Pro/ExCom/86/74

UNEP/OzL.Pro/ExCom/86/77

UNEP/OzL.Pro/ExCom/86/80

UNEP/OzL.Pro/ExCom/86/21

UNEP/OzL.Pro/ExCom/86/21/Add.1

UNEP/OzL.Pro/ExCom/86/24

The data is presented according to the year when a project was approved by the Executive Committee. It treats all approvals (investment and non-investment projects) equally (i.e., an investment project or a funding tranche of an MYA of US $1 million is considered one project, same as a country programme preparation of US $30,000). Key indicators from the annual summary are: the percentage of projects completed, ODP phased out, and percentage of funds disbursed. There are three types of disbursements: during implementation, after implementation and for retroactively-financed projects.