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Corrigendum

PROGRESS REPORT OF UNDP AS AT 31 DECEMBER 2017
This corrigendum is being issued to provide clarification on projects recommended for cancellation in accordance with relevant Executive Committee policies and decisions as follows:
· Add paragraph 8(bis) as follows:
[bookmark: _GoBack]8(bis).	In addition, the Secretariat noted that no progress had been made for two projects due to different issues and circumstances noted in the table below. The Executive Committee may wish to consider cancellation of these projects and request remaining balances to be returned.

	Country/
Project code
	Project title

	Disburse-ment rate (%)
	Status/Issues

	Chile
CHI/PHA/73/INV/184
	HCFC phase-out management plan (stage I, third tranche)
	3
	Project completion date by decision is December 2017

	Cuba
CUB/REF/58/PRP/42

	Preparation for HCFC phase-out investment activities (manufacturing sector)
	0
	The enterprise indicated that it would not adopt low-global warming potential technologies



· Add sub-paragraph (c) to the recommendation in paragraph 10 as follows:
(c)	To cancel the following projects at the 82nd meeting and to request UNDP to return the remaining balances to the 83rd meeting:
HCFC phase-out management plan for Chile (stage I, third tranche) (CHI/PHA/73/INV/184); and
Preparation for HCFC phase-out investment activities (manufacturing sector) for Cuba (CUB/REF/58/PRP/42).
·  Delete the rows for Chile and Cuba in the table contained in Annex I. 
Pre-session documents of the Executive Committee of the Multilateral Fund for the Implementation of the Montreal Protocol are without prejudice to any decision that the Executive Committee might take following issuance of the document.
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