| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/82/16/Corr.1 29 November 2018 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-second Meeting

Montreal, 3-7 December 2018

Corrigendum

PROGRESS REPORT OF UNDP as at 31 december 2017

# This corrigendum is being issued to provide clarification on projects recommended for cancellation in accordance with relevant Executive Committee policies and decisions as follows:

# Add paragraph 8(bis) as follows:

8(bis).	In addition, the Secretariat noted that no progress had been made for two projects due to different issues and circumstances noted in the table below. The Executive Committee may wish to consider cancellation of these projects and request remaining balances to be returned.

| Country/ Project code | Project title | Disburse-ment rate (%) | Status/Issues |
| --- | --- | --- | --- |
| Chile CHI/PHA/73/INV/184 | HCFC phase-out management plan (stage I, third tranche) | 3 | Project completion date by decision is December 2017 |
| Cuba CUB/REF/58/PRP/42 | Preparation for HCFC phase-out investment activities (manufacturing sector) | 0 | The enterprise indicated that it would not adopt low-global warming potential technologies |

# Add sub-paragraph (c) to the recommendation in paragraph 10 as follows:

## (c)	To cancel the following projects at the 82nd meeting and to request UNDP to return the remaining balances to the 83rd meeting:

### HCFC phase-out management plan for Chile (stage I, third tranche) (CHI/PHA/73/INV/184); and

### Preparation for HCFC phase-out investment activities (manufacturing sector) for Cuba (CUB/REF/58/PRP/42).

# Delete the rows for Chile and Cuba in the table contained in Annex I.