| NATIONS UNIES |  | EP |
| --- | --- | --- |
|  | Programme des Nations Unies pour l’environnement | Distr. GÉNÉRALE UNEP/OzL.Pro/ExCom/98/4 25 mai 2026 FRANÇAIS ORIGINAL: ANGLAIS |

COMITÉ EXÉCUTIF

DU FONDS MULTILATÉRAL AUX FINS

D’APPLICATION DU PROTOCOLE DE MONTRÉAL

Quatre-vingt-seizième réunion

Montréal, 22-26 juin 2026

Point 4 b) de l'ordre du jour provisoire

# RAPPORT SUR LES SOLDES ET LA DISPONIBILITÉ DES RESSOURCES

# Introduction

# Ce document présente un résumé des ajustements financiers communiqués par les agences d’exécution et les agences bilatérales, et approuvés par le Secrétariat. Il comprend des données statistiques issues de tous les projets dont les soldes ont été détenus pendant plus de 12 mois après l’achèvement du projet, conformément aux décisions 28/7 et 56/2 c). Il examine les soldes à restituer provenant de projets au titre du suivi donné à des décisions pertinentes (appelés projets « soumis à décision » dans le présent document) et de transferts de projet. Il indique également au Comité exécutif le niveau des ressources disponibles en liquidités enregistrées dans le document État des contributions et des décaissements, conformément à la décision 41/92 b), et présente une recommandation. Les montants détenus par les agences d'exécution et les agences bilatérales pour les projets achevés et pour les projets soumis à décision figurent aux annexes I et II. L'annexe III présente les fonds restitués par les agences d'exécution provenant de projets achevés et financés par des contributions volontaires supplémentaires.

# Fonds à restituer à la 98e réunion

# Le montant total des fonds devant être restitués par les agences d’exécution s’élève à 1 417 152 $US provenant de projets achevés et financés par des contributions supplémentaires, comme indiqué au tableau 1.

# Tableau 1. Fonds devant être restitués à la 98e réunion par les agences d’exécution ($US)

| Agence | Coûts de projet | Coût d’appui d’agence | Coût total |
| --- | --- | --- | --- |
| PNUD | 105 125 | 7 918 | 113 043 |
| PNUE | 594 160 | 42 303 | 636 463 |
| ONUDI | 620 860 | 46 786 | 667 646 |
| Total | 1 320 145 | 97 007 | 1 417 152 |

# Fonds retenus par les agences d’exécution

# Les fonds totaux retenus s’élèvent à 5 125 184 $US par les agences d’exécution, comme indiqué au tableau 2.

Tableau 2. Soldes encore détenus par les agences d’exécution pour des projets achevés et des projets soumis à décision (coûts d’appui d’agence compris)

| Année d´achèvement | PNUD |  | ONUDI |  | Total |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Nombre | $US | Nombre | $US | Nombre | $US |
| Projets achevés depuis plus de 2 ans |  |  |  |  |  |  |  |
| 2021 | 0 | 0 | 1 | -367 | 1 | -367 |
| 2022 | 2 | 56 723 | 5 | 99 526 | 7 | 156 249 |
| 2023 | 7 | 629 753 | 5 | 468 332 | 12 | 1 098 085 |
| Du 1er janvier au 30 avril 2024 | 0 | 0 | 0 | 0 | 0 | 0 |
| Total partiel | 9 | 686 476 | 11 | 567 491 | 20 | 1 253 967 |
| Projets achevés depuis moins de deux ans |  |  |  |  |  |  |  |
| Du 1er mai au 31 décembre 2024 | 21 | 3 381 616 | 12 | 398 199 | 33 | 3 779 815 |
| Total partiel | 21 | 3 381 616 | 12 | 398 199 | 33 | 3 779 815 |
| Total | 30 | 4 068 092 | 23 | 965 690 | 53 | 5 033 782 |
| Projet avec contributions volontaires supplémentaires |  |  |  |  |  |  |  |
|  | 0 | 0 | 1 | 91 402 | 1 | 91 402 |
| Total général | 30 | 4 068 092 | 24 | 1 057 092 | 54 | 5 125 184 |

Disponibilité des ressources

# Le budget pour le Fonds multilatéral a été approuvé pour un montant de 965 millions de $US pour la période triennale 2024-2026, conformément à la décision des Parties (décision XXXV/1). Le document sur l’état des contributions et des décaissements indique, en date du 15 mai 2026, un solde disponible s’élevant à 652 281 816 $US. Le solde total restitué par les agences d’exécution à la 98e réunion s’élève à 1 417 152 $US. Ainsi, le solde total de ressources disponibles pour approbation à la 98e réunion s’élève à 653 698 968 $US.

# Observations du secrétariat

# Le Secrétariat a rappelé aux agences d’exécution que les soldes des projets achevés il y a un an ou plus, des projets soumis à décision et des projets financés par des contributions volontaires supplémentaires devraient être restitués au Fonds multilatéral dès que possible.

# Considérant que le montant total du financement pour des projets et activités soumis à la 98e réunion s’élève à 155 293 564 $US, les ressources disponibles sont suffisantes pour les approbations prévues lors de la 98e réunion.

Recommandation

# Le Comité exécutif pourrait envisager :

## a)	De prendre note :

### Du rapport sur les soldes et la disponibilité des ressources, figurant dans le document UNEP/OzL.Pro/ExCom/98/4 ;

### Du fait que le montant nt des fonds restitués à la 98e réunion par les agences d’exécution s’élève à 1 417 152 $US, constitué de 105 125 $US, plus des coûts d’appui d’agence à hauteur de 7 918 $US par le PNUD, de 594 160 $US, plus des coûts d’appui d’agence à hauteur de 42 303 $US par le PNUE; et de 620 860 $US, plus des coûts d’appui d’agence à hauteur de 46 786 $US par l’ONUDI ;

### Que le PNUD détenait des soldes d’un montant de 686 476 $US, coûts d’appui d’agence compris, pour neuf projets achevés depuis plus de deux ans ;

### Que l’ONUDI détenait des soldes d’un montant de 567 491 $US, coûts d’appui d’agence compris, pour 11 projets achevés depuis plus de deux ans; et 91 402 $US, coûts d’appui d’agence compris, pour un projet financé par les contributions volontaires supplémentaires ;

## b)	De prier le PNUD et l’ONUDI :

### De procéder au décaissement ou d’annuler les sommes engagées n’étant pas nécessaires aux projets achevés et de restituer les soldes correspondants à la 99e réunion ;

### De procéder au décaissement ou d’annuler les engagements pour les projets achevés depuis plus de deux ans, et de restituer les soldes à la 99e réunion ; et

## c)	De demander à l’ONUDI de procéder au décaissement ou de restituer à la 99e réunion le solde des projets financés par les contributions volontaires supplémentaires.

Annex I

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR COMPLETED PROJECTS

| Code | Project Title | Date Completed (Actual) | Approved funding plus adjustments as of 31 December 2024 (US $) | Funds disbursed as of 98th meeting (US $) | Balances committed as per 98th meeting (US $) | Balances not-committed as per 98th meeting (US $) | Support cost on balances committed and not committed as per 98th meeting (US $) | Why any balances could not be returned? | When they could be returned? | Project subject to decision |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |  |  |  |  |  |  |
| BGD/PHA/90/INV/59 | HCFC phase-out management plan (stage II, second tranche) (air-conditioning sector) | Dec-24 | 1,967,866 | 1,678,655 | 289,211 | 0 | 20,245 |  |  |  |
| BZE/PHA/87/INV/40 | HCFC phase-out management plan (stage II, first tranche) | Dec-24 | 73,854 | 41,316 | 32,538 | 0 | 2,928 |  |  |  |
| COS/KIP/87/PRP/63 | Preparation of Kigali HFC implementation plan | Dec-24 | 170,000 | 163,390 | 6,610 | 0 | 463 |  |  |  |
| CUB/KIP/87/PRP/65 | Preparation of Kigali HFC implementation plan | Aug-24 | 170,000 | 154,279 | 15,721 | 0 | 1,100 |  |  |  |
| DOM/KIP/87/PRP/73 | Preparation of Kigali HFC implementation plan | Aug-24 | 190,000 | 174,370 | 15,630 | 0 | 1,094 |  |  |  |
| EGY/PHA/79/TAS/132 | HCFC phase-out management plan (stage II, first tranche) (project management and monitoring) | Dec-22 | 75,000 | 39,629 | 35,371 | 0 | 2,476 |  |  |  |
| EGY/PHA/84/INV/144 | HCFC phase-out management plan (stage II, second tranche) (extruded polystyrene foam sector) | Dec-23 | 1,761,750 | 1,627,929 | 133,821 | 0 | 9,368 |  |  |  |
| ELS/PHA/87/INV/43 | HCFC phase-out management plan (stage II, first tranche) | Dec-24 | 169,000 | 66,702 | 102,298 | 0 | 7,161 |  |  |  |
| GHA/KIP/87/PRP/51 | Preparation of Kigali HFC implementation plan | Aug-23 | 130,000 | 126,468 | 3,532 | 0 | 247 |  |  |  |
| GRN/KIP/88/PRP/28 | Preparation of Kigali HFC implementation plan | Dec-24 | 40,000 | 14,163 | 25,837 | 0 | 1,809 |  |  |  |
| HAI/SEV/90/INS/25 | Extension of the institutional strengthening project (phase V: 7/2022-6/2024) | Dec-24 | 128,000 | 119,478 | 8,522 | 0 | 597 |  |  |  |
| IDS/PHA/81/INV/213 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Dec-24 | 753,500 | 158,983 | 594,517 | 0 | 41,616 |  |  |  |
| IDS/PHA/87/PRP/216 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | Dec-23 | 90,000 | 87,245 | 2,755 | 0 | 193 |  |  |  |
| IDS/PHA/88/INV/217 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector) | Dec-24 | 627,086 | 0 | 627,086 | 0 | 43,896 |  |  |  |
| IDS/PHA/92/INV/220 | HCFC phase-out management plan (stage II, fourth tranche) | Dec-24 | 433,300 | 0 | 433,300 | 0 | 30,331 |  |  |  |
| IND/PHA/86/TAS/482 | HCFC phase-out management plan (stage II, third tranche) (project management and monitoring) | Dec-24 | 800,000 | 0 | 800,000 | 0 | 56,000 |  |  |  |
| IRA/PHA/86/INV/243 | HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration sector) | Dec-24 | 576,090 | 551,597 | 24,493 | 0 | 1,714 |  |  |  |
| IRA/PHA/90/INV/262 | HCFC phase-out management plan (stage II, fourth tranche) (PMU) | Dec-23 | 92,000 | 69,877 | 22,123 | 0 | 1,549 |  |  |  |
| IRA/PHA/92/INV/264 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Dec-23 | 93,017 | 0 | 93,017 | 0 | 6,511 |  |  |  |
| IRA/PHA/92/INV/265 | HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration sector) | Dec-23 | 145,255 | 0 | 145,255 | 0 | 10,168 |  |  |  |
| MDV/KIP/87/PRP/36 | Preparation of Kigali HFC implementation plan | Dec-24 | 35,000 | 22,026 | 12,974 | 0 | 908 |  |  |  |
| NIR/KIP/87/PRP/156 | Preparation of Kigali HFC implementation plan | Dec-24 | 137,000 | 124,331 | 12,669 | 0 | 887 |  |  |  |
| NIR/PHA/81/TAS/150 | HCFC phase-out management plan (stage II, first tranche) (project management and coordination) | Dec-22 | 165,000 | 147,359 | 17,641 | 0 | 1,235 |  |  |  |
| NIR/PHA/88/INV/163 | HCFC phase-out management plan (stage II, second tranche) (project management and coordination) | Dec-24 | 75,000 | 41,581 | 33,419 | 0 | 2,339 |  |  |  |
| SRL/SEV/91/INS/61 | Extension of the institutional strengthening project (phase XIV: 1/2023-12/2024) | Dec-24 | 236,796 | 234,222 | 2,574 | 0 | 180 |  |  |  |
| TRI/KIP/87/PRP/40 | Preparation of Kigali HFC implementation plan | Dec-24 | 190,000 | 145,057 | 44,943 | 0 | 3,146 |  |  |  |
| TRI/PHA/86/INV/38 | HCFC phase-out management plan (stage II, first tranche) | Dec-23 | 498,756 | 310,706 | 188,050 | 0 | 13,164 |  |  |  |
| URU/KIP/87/PRP/77 | Preparation of Kigali HFC implementation plan | Dec-24 | 190,000 | 160,103 | 29,897 | 0 | 2,093 |  |  |  |
| URU/PHA/86/INV/76 | HCFC phase-out management plan (stage III, first tranche) | Dec-24 | 350,601 | 313,973 | 36,628 | 0 | 2,564 |  |  |  |
| ZIM/KIP/91/PRP/66 | Preparation of a Kigali HFC implementation plan | Dec-24 | 51,000 | 40,086 | 10,914 | 0 | 764 |  |  |  |
| Total UNDP |  |  | 10,414,871 | 6,613,525 | 3,801,346 | 0 | 266,746 |  |  |  |
| UNIDO |  |  |  |  |  |  |  |  |  |  |
| BOL/PHA/87/INV/50 | HCFC phase-out management plan (stage II, first tranche) | Aug-24 | 141,009 | 128,910 | 12,099 | 0 | 847 |  |  |  |
| BRA/PHA/82/INV/320 | HCFC phase-out management plan (stage II, third tranche) (commercial refrigeration and air-conditioning sector) | Dec-24 | 2,647,057 | 1,613,586 | 289,368 | 0 | 20,256 |  |  |  |
| CMR/KIP/88/PRP/49 | Preparation of Kigali HFC implementation plan | Dec-23 | 190,000 | 188,394 | 1,606 | 0 | 112 |  |  |  |
| CPR/PHA/88/INV/607 | HCFC phase-out management plan (stage II, fourth tranche) (extruded polystyrene foam sector plan) | Dec-23 | 4,400,000 | 4,405,665 | -5,665 | 0 | -397 |  |  |  |
| GAB/PHA/79/INV/34 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 119,900 | 60,409 | 59,491 | 0 | 5,354 |  |  |  |
| GAM/KIP/90/PRP/44 | Preparation of a Kigali HFC implementation plan | Dec-24 | 39,000 | 36,622 | 2,378 | 0 | 166 |  |  |  |
| IVC/PHA/84/PRP/47 | Preparation of a HCFC phase-out management plan (stage II) | Dec-24 | 20,000 | 16,024 | 3,976 | 0 | 278 |  |  |  |
| JOR/PHA/84/TAS/107 | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector, project management and coordination) | Dec-23 | 294,122 | 90,153 | 203,969 | 0 | 14,277 |  |  |  |
| LIB/PHA/75/INV/36 | HCFC phase-out management plan (stage I, first tranche) (foam sector) | Dec-23 | 1,690,627 | 713,112 | 229,982 | 0 | 16,099 |  |  |  |
| LIB/SEV/85/INS/44 | Renewal of the institutional strengthening project (phase VI: 7/2020-6/2022) | Jun-23 | 174,164 | 166,361 | 7,803 | 0 | 546 |  |  |  |
| MEX/PHA/90/INV/200 | HCFC phase-out management plan (stage II, fourth tranche) (cleaning agent phase-out in refrigeration servicing sector and project implementation and monitoring) | Dec-24 | 1,612,350 | 1,612,260 | 90 | 0 | 6 |  |  |  |
| MEX/PHA/92/INV/206 | HCFC phase-out management plan (stage II, fifth tranche) | Dec-24 | 450,600 | 448,181 | 2,419 | 0 | 169 |  |  |  |
| MOZ/PHA/66/INV/23 | HCFC phase-out management plan (stage I, first tranche) | Dec-22 | 75,000 | 72,133 | 2,867 | 0 | 258 |  |  |  |
| NER/PHA/84/INV/39 | HCFC phase-out management plan (stage I, second tranche) | Dec-22 | 90,000 | 76,492 | 13,508 | 0 | 946 |  |  |  |
| NER/PHA/88/INV/41 | HCFC phase-out management plan (stage I, third tranche) | Dec-22 | 20,000 | 19,002 | 998 | 0 | 70 |  |  |  |
| SAU/REF/86/PRP/35 | Preparation of a HCFC phase-out management plan (stage II) (air-conditioning) | Dec-24 | 150,000 | 141,442 | 8,558 | 0 | 599 |  |  |  |
| SEN/PHA/85/INV/41 | HCFC phase-out management plan (stage I, third tranche) | Dec-21 | 50,000 | 50,341 | -341 | 0 | -26 |  |  |  |
| SEN/PHA/85/PRP/43 | Preparation of a HCFC phase-out management plan (stage II) | Jun-22 | 20,000 | 5,015 | 14,985 | 0 | 1,049 |  |  |  |
| SIL/KIP/88/PRP/43 | Preparation of Kigali HFC implementation plan | Dec-24 | 39,000 | 39,014 | -14 | 0 | -1 |  |  |  |
| SIL/PHA/87/INV/40 | HCFC phase-out management plan (stage II, first tranche) | Dec-24 | 117,000 | 92,734 | 24,266 | 0 | 2,184 |  |  |  |
| SOM/PHA/88/PRP/17 | Preparation of HCFC phase-out management plan (stage II) (Overarching) | Dec-24 | 60,000 | 57,244 | 2,756 | 0 | 193 |  |  |  |
| TUR/KIP/90/PRP/113 | Preparation of a Kigali HFC implementation plan | Dec-24 | 120,000 | 108,720 | 11,280 | 0 | 790 |  |  |  |
| VEN/PHA/91/INV/137 | HCFC phase-out management plan (stage II, second tranche) (servicing sector) | Dec-24 | 261,444 | 246,924 | 14,520 | 0 | 1,016 |  |  |  |
| Total UNIDO |  |  | 12,781,273 | 10,388,738 | 900,899 | 0 | 64,791 |  |  |  |

Annex II

COMMITTED AND NOT-COMMITTED BALANCES HELD BY IMPLEMENTING AGENCIES FOR ADDITIONAL VOLUNTARY CONTRIBUTIONS PROJECTS

| CODE | Project title | Approved funding plus adjustments as of 31 December 2025 (US $) | Funds disbursed as of 98th meeting (US $) | Balances committed as per 98th meeting (US $) | Balances not- committed as per 98th meeting (US $) | Support cost on balances committed and not-committed as per 98th meeting (US $) | Why any balances could not be returned? | When they could be returned? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| UNIDO |  |  |  |  |  |  |  |  |
| ARG/SEV/81/TAS/02+ | Enabling activities for HFC phase-down | 250,000 | 164,578 | 85,422 |  | 5,980 |  |  |
| TOTAL UNIDO |  |  |  | 85,422 |  | 5,980 |  |  |

Annex III

DETAILS ON COMPLETED, ADDITIONAL VOLUNTARY CONTRIBUTIONS AND BY-DECISIONS PROJECTS WITH RETURNED BALANCES FROM IMPLEMENTING AGENCIES

| Code | Project title | Project costs returned (US $) | Agency support costs returned (US $) | Total (US $) |
| --- | --- | --- | --- | --- |
| UNDP |  |  |  |  |
| COL/KIP/87/PRP/110 | Preparation of Kigali HFC implementation plan | 75 | 5 | 80 |
| COL/PHA/88/INV/111 | HCFC phase-out management plan (stage II, fourth tranche) | 2,712 | 190 | 2,902 |
| COL/SEV/88/INS/115 | Extension of institutional strengthening project (phase XIII: 12/2021-11/2023) | 802 | 56 | 858 |
| COS/PHA/91/TAS/66 | Verification report on the implementation of stage II of the HCFC phase-out management plan | 3,841 | 346 | 4,187 |
| GHA/SEV/91/INS/54 | Extension of the institutional strengthening project (phase XV: 1/2023-12/2024) | 4 | 0 | 4 |
| HAI/PHA/91/PRP/26 | Preparation of HCFC phase-out management plan (stage II) (Overarching) | 7,233 | 506 | 7,739 |
| IDS/SEV/90/INS/219 | Extension of institutional strengthening project (phase XIII: 7/2022-6/2024) | 2 | 0 | 2 |
| IND/KIP/92/PRP/505 | Preparation of a KIP investment project in the refrigeration manufacturing sector for Mech Air Industries | 28,499 | 1,995 | 30,494 |
| KAM/KIP/88/PRP/40 | Preparation of Kigali HFC implementation plan | 10,027 | 702 | 10,729 |
| LAO/KIP/87/PRP/39 | Preparation of Kigali HFC implementation plan | 297 | 21 | 318 |
| LAO/PHA/86/INV/38 | HCFC phase-out management plan (stage II, first tranche) | 254 | 23 | 277 |
| LEB/KIP/87/PRP/98 | Preparation of Kigali HFC implementation plan | 3,886 | 272 | 4,158 |
| LEB/SEV/86/INS/96 | Extension of the institutional strengthening project (phase XII: 4/2021-3/2023) | 2,233 | 156 | 2,389 |
| MAL/PHA/87/PRP/189 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | 3,946 | 276 | 4,222 |
| MEX/FOA/90/PRP/198 | Preparation for HFC investment projects in the foam sector | 3,935 | 275 | 4,210 |
| MEX/KIP/87/PRP/195 | Preparation of Kigali HFC implementation plan | 3,883 | 272 | 4,155 |
| MEX/REF/92/INV/204 | Conversion of the manufacturing of commercial refrigerators from HFC-134a to propane (R-290) at the enterprise Friocima | 23,922 | 2,153 | 26,075 |
| PAK/SEV/87/INS/108 | Extension of the institutional strengthening project (phase XI: 7/2021-6/2023) | 1,257 | 88 | 1,345 |
| PAN/KIP/87/PRP/53 | Preparation of Kigali HFC implementation plan | 82 | 6 | 88 |
| PAR/KIP/87/PRP/42 | Preparation of Kigali HFC implementation plan | -65 | -5 | -70 |
| SRL/KIP/87/PRP/59 | Preparation of Kigali HFC implementation plan | -154 | -11 | -165 |
| SWA/KIP/87/PRP/33 | Preparation of Kigali HFC implementation plan | 284 | 20 | 304 |
| Total completed projects |  | 96,955 | 7,346 | 104,301 |
| FIJ/SEV/80/TAS/01+ | Enabling activities for HFC phase-down | 8,170 | 572 | 8,742 |
| Total “additional voluntary contributions” projects |  | 8,170 | 572 | 8,742 |
| Total UNDP |  | 105,125 | 7,918 | 113,043 |
| UNEP |  |  |  |  |
| CKI/SEV/88/INS/18 | Extension of the institutional strengthening project (phase VIII: 7/2022-6/2024) | 5,000 | 0 | 5,000 |
| ELS/PHA/87/TAS/42 | HCFC phase-out management plan (stage II, first tranche) | 1,419 | 184 | 1,603 |
| GLO/SEV/93/TAS/368 | Compliance Assistance Programme: 2024 budget | 468,485 | 37,479 | 505,964 |
| GUA/SEV/88/INS/60 | Renewal of the institutional strengthening project (phase IX: 12/2021-11-2023) | 13,315 | 0 | 13,315 |
| IND/PHA/86/TAS/483 | HCFC phase-out management plan (stage II, third tranche) (refrigeration servicing sector plan) | 7,246 | 878 | 8,124 |
| KYR/SEV/91/INS/48 | Extension of the institutional strengthening project (phase XI: 1/2023-12/2024) | 4,602 | 0 | 4,602 |
| NIC/PHA/92/TAS/47 | HCFC phase-out management plan (stage II, second tranche) | 26,312 | 3,421 | 29,733 |
| NIC/SEV/92/INS/51 | Renewal of institutional strengthening project (phase XI: 7/2023-6/2026) | 65,161 | 0 | 65,161 |
| PAK/PHA/88/TAS/109 | HCFC phase-out management plan (stage II, third tranche) | 2,539 | 330 | 2,869 |
| SEN/KIP/87/PRP/44 | Preparation of Kigali HFC implementation plan | 81 | 11 | 92 |
| Total completed projects |  | 594,160 | 42,303 | 636,463 |
| Total UNEP |  | 594,160 | 42,303 | 636,463 |
| UNIDO |  |  |  |  |
| BAH/PHA/93/INV/46 | HCFC phase-out management plan (stage II, second tranche) | 108 | 8 | 116 |
| BRA/PHA/75/INV/311 | HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector) | 1,699 | 119 | 1,818 |
| BRA/PHA/88/INV/327 | HCFC phase-out management plan (stage II, fifth tranche) (commercial refrigeration and air-conditioning sector) | 23,994 | 1,680 | 25,674 |
| CPR/PHA/75/INV/564 | HCFC phase-out management plan (stage I, fifth tranche) (room air-conditioner manufacturing sector plan) | -5,665 | -5,385 | -11,050 |
| GUA/KIP/94/PRP/69 | Preparation of a Kigali HFC implementation plan (stage I) | 216 | 15 | 231 |
| HON/KIP/90/PRP/55 | Preparation of a Kigali HFC implementation plan | 34 | 2 | 36 |
| JOR/PHA/92/PRP/115 | Preparation of HCFC phase-out management plan (stage III) (Overarching) | 15 | 1 | 16 |
| MEX/PHA/92/INV/205 | Destruction of emissions of HFC-23 generated in the production of HCFC-22 in Quimobasicos (second tranche) | 32 | 2 | 34 |
| MOR/KIP/92/PRP/79 | Preparation of a KIP investment project in the refrigeration manufacturing sector for MANAR | 471 | 33 | 504 |
| NIC/PHA/86/INV/40 | HCFC phase-out management plan (stage II, first tranche) | 1,505 | 105 | 1,610 |
| PAK/PHA/76/INV/94 | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | 16,483 | 1,154 | 17,637 |
| PAK/PHA/83/INV/102 | HCFC phase-out management plan (stage II, second tranche) (polyurethane foam sector) | 43,813 | 3,067 | 46,880 |
| PAK/PHA/83/TAS/100 | HCFC phase-out management plan (stage II, second tranche) (project management unit) | 34,237 | 2,397 | 36,634 |
| PAK/PHA/90/INV/110 | HCFC phase-out management plan (stage II, fourth tranche) (domestic air-conditioner manufacturing sector) | 1,882 | 131 | 2,013 |
| PHI/PHA/83/INV/104 | HCFC phase-out management plan (stage II, first tranche) (air-conditioning sector) | 188,014 | 13,160 | 201,174 |
| PHI/PHA/83/TAS/105 | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | 38,932 | 2,726 | 41,658 |
| PRC/KIP/91/PRP/38 | Preparation of a Kigali HFC implementation plan | 1,196 | 84 | 1,280 |
| RWA/KIP/88/PRP/38 | Preparation of Kigali HFC implementation plan | 6,238 | 440 | 6,678 |
| SOA/PHA/91/INV/16 | HCFC phase-out management plan (stage I, fifth tranche) (refrigeration servicing, custom training and monitoring) | 21,481 | 1,503 | 22,984 |
| Total completed projects |  | 374,685 | 21,242 | 395,927 |
| IRQ/PHA/74/INV/23 | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | 8,064 | 605 | 8,669 |
| NIC/EEF/92/TAS/49 | HCFC phase-out management plan (stage II, second tranche) (energy efficiency - related activities under decision 89/6) | 23,618 | 1,653 | 25,271 |
| NIC/KIP/93/INV/57 | Kigali HFC implementation plan (stage I, first tranche) | 137,870 | 17,923 | 155,793 |
| NIC/PHA/92/INV/48 | HCFC phase-out management plan (stage II, second tranche) | 56,623 | 3,963 | 60,586 |
| PAK/PHA/90/INV/111 | HCFC phase-out management plan (stage III, first tranche) (foam sector) | 20,000 | 1,400 | 21,400 |
| Total "by-decision" projects |  | 246,175 | 25,544 | 271,719 |
| Total UNIDO |  | 620,860 | 46,786 | 667,646 |

UNEP/OzL.Pro/ExCom/98/1

Les données présentées s’appuient sur le format de rapport élaboré conformément à la décision 31/2.

UNEP/OzL.Pro/ExCom/98/3

En date du 4 mai 2026