| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/86/41/Corr.1 10 November 2020 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Eighty-sixth Meeting

Montreal, 2-6 November 2020

Postponed to 8-12 March 2021

Corrigendum

Project Proposal: Brazil

This document is issued to:

- Replace Table 4 with the following:

Table 4. PMU costs under the first three tranches of stage I of the HPMP as of August 2020 (US $)

| Activity | Approved | Disbursed |
| --- | --- | --- |
| UNDP |  |  |
| Personnel (staff and international/national consultants) | 604,500 | 442,591 |
| Travel (including monitoring costs) | 185,250 | 133,412 |
| Awareness (workshops/meetings/communication) | 39,000 | 24,818 |
| Operational costs | 146,250 | 108,093 |
| Total UNDP | 975,000 | 708,914 |
| UNIDO |  |  |
| Personnel (staff and international/national consultants) | 412,000 | 297,187 |
| Travel (related to meetings with beneficiary enterprises, stakeholders, sector associations, training and awareness-raising campaign) | 70,000 | 60,927 |
| Operational costs (including office rental cost, computers, furniture office supplies, official translations, awareness campaigns) | 70,000 | 58,181 |
| Total UNIDO | 552,000 | 416,295 |

Due to coronavirus disease (COVID-19)