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Corrigendum

Project Proposal: Brazil

	This document is issued to:

· [bookmark: _GoBack]Replace Table 4 with the following:

Table 4. PMU costs under the first three tranches of stage I of the HPMP as of August 2020 (US $)
	Activity
	Approved
	Disbursed

	UNDP

	Personnel (staff and international/national consultants)
	604,500
	442,591

	Travel (including monitoring costs)
	185,250
	133,412

	Awareness (workshops/meetings/communication)
	39,000
	24,818

	Operational costs
	146,250
	108,093

	Total UNDP
	975,000
	708,914

	UNIDO

	Personnel (staff and international/national consultants)
	412,000
	297,187

	Travel (related to meetings with beneficiary enterprises, stakeholders, sector associations, training and awareness-raising campaign)
	70,000
	60,927

	Operational costs (including office rental cost, computers, furniture office supplies, official translations, awareness campaigns)
	70,000
	58,181

	Total UNIDO 
	552,000
	416,295
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