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PROGRAMA DE TRABAJO DEL PNUMA PARA EL AÑO 2022








OBSERVACIONES Y RECOMENDACIONES DE LA SECRETARÍA
El PNUMA solicita al Comité Ejecutivo aprobar la suma de 3.405.570 $EUA más gastos de apoyo de 166.530 $EUA para el programa de trabajo 2022 que se indica en el Cuadro 1. Se adjunta la respectiva presentación.
Cuadro 1: Programa de trabajo del PNUMA para el año 2022
	País
	Actividad/Proyecto
	Solicitado ($EUA)
	Recomendado ($EUA)

	SECCIÓN A: ACTIVIDADES RECOMENDADAS PARA APROBACIÓN GENERAL

	A1: Renovación de proyectos de fortalecimiento institucional

	Argelia
	Renovación de proyecto de fortalecimiento institucional (fase VII)
	329.472
	329.472

	Bahamas
	Renovación de proyecto de fortalecimiento institucional (fase VIII)
	85.000
	85.000

	Bahrein
	Renovación de proyecto de fortalecimiento institucional (fase XI)
	85.000
	85.000

	Barbados
	Renovación de proyecto de fortalecimiento institucional (fase VIII)
	149.760
	149.760

	Cabo Verde
	Renovación de proyecto de fortalecimiento institucional (fase VIII)
	85.000
	85.000

	Chad
	Renovación de proyecto de fortalecimiento institucional (fase X)
	85.000
	85.000

	Etiopía
	Renovación de proyecto de fortalecimiento institucional (fase IX)
	85.000
	85.000

	Guinea
	Renovación de proyecto de fortalecimiento institucional (fase XII)
	85.000
	85.000

	Honduras
	Renovación de proyecto de fortalecimiento institucional (fase X)
	85.000
	85.000

	Jamaica
	Renovación de proyecto de fortalecimiento institucional (fase XI)
	85.000
	85.000

	Lesotho
	Renovación de proyecto de fortalecimiento institucional (fase XI)
	85.000
	85.000

	Malawi
	Renovación de proyecto de fortalecimiento institucional (fase XIII)
	85.418
	85.418

	Maldivas
	Renovación de proyecto de fortalecimiento institucional (fase XII)
	85.000
	85.000

	Islas Marshall 
	Renovación de proyecto de fortalecimiento institucional (fase VIII)
	85.000
	85.000

	Níger 
	Renovación de proyecto de fortalecimiento institucional (fase XIII)
	85.000
	85.000

	Qatar
	Renovación de proyecto de fortalecimiento institucional (fase VI)
	113.920
	113.920

	Saint Kitts y Nevis
	Renovación de proyecto de fortalecimiento institucional (fase VIII)
	85.000
	85.000

	Arabia Saudita
	Renovación de proyecto de fortalecimiento institucional (fase III)
	256.000
	256.000

	Uganda
	Renovación de proyecto de fortalecimiento institucional (fase V)
	85.000
	85.000

	Total A1
	2.124.570
	2.124.570

	A2: Elaboración de planes de aplicación de la Enmienda de Kigali (PAEK)

	Bangladesh a
	Elaboración de un PAEK (etapa I)
	40.000
	40.000

	Benin b 
	Elaboración de un PAEK (etapa I)
	133.000
	133.000

	Botswana b 
	Elaboración de un PAEK (etapa I)
	119.000
	119.000

	Chad b 
	Elaboración de un PAEK (etapa I)
	119.000
	119.000

	Etiopía b 
	Elaboración de un PAEK (etapa I)
	91.000
	91.000

	Gambia b 
	Elaboración de un PAEK (etapa I)
	91.000
	91.000

	Guinea b 
	Elaboración de un PAEK (etapa I)
	133.000
	133.000

	Mozambique c
	Elaboración de un PAEK (etapa I)
	119.000
	119.000

	Santo Tomé y Príncipe
	Elaboración de un PAEK (etapa I)
	130.000
	130.000

	Serbia d
	Elaboración de un PAEK (etapa I)
	55.000
	55.000

	Seychelles e
	Elaboración de un PAEK (etapa I)
	81.000
	81.000

	Somalia d
	Elaboración de un PAEK (etapa I)
	51.000
	51.000

	Togo b
	Elaboración de un PAEK (etapa I)
	119.000
	119.000

	Subtotal A2
	1.281.000
	1.281.000

	Gastos de apoyo
	166.530
	166.530

	Total A2
	1.447.530
	1.447.530

	Total general (A1 + A2)
	3.572.100
	3.572.100


a Con el PNUD como principal organismo de ejecución.
b Con la ONUDI como organismo de ejecución cooperante.
c Con el PNUD como organismo de ejecución cooperante.
d Con la ONUDI como principal organismo de ejecución.
e Con el Gobierno de Alemania como organismo de cooperación bilateral.

SECCIÓN A: ACTIVIDADES RECOMENDADAS PARA APROBACIÓN GENERAL
A1: Renovación de proyectos de fortalecimiento institucional
Descripción
El PNUMA presentó sendas solicitudes de financiamiento para la renovación de proyectos de fortalecimiento institucional en los países que se indica en la sección A1 del Cuadro 1. Los proyectos se describen en el Anexo I al presente documento.
Observaciones de la Secretaría
La Secretaría analizó las solicitudes de renovación de 19 proyectos de fortalecimiento institucional presentadas a nombre de los respectivos Gobiernos a la luz de las pautas y decisiones pertinentes en cuanto a admisibilidad y niveles de financiamiento. Las solicitudes se confrontaron con los planes de trabajo de fortalecimiento institucional de la fase anterior, con los datos del programa país y del Artículo 7, con el último informe de ejecución del plan de gestión para la eliminación de HCFC (PGEH), con el informe de avance presentado por el organismo de ejecución y con las correspondientes resoluciones de la Reunión de las Partes. Se constató que cada país ha presentado los datos de sus programas país para el año 2021, que ha dado cumplimiento a las metas de control previstas en el Protocolo de Montreal, y que su consumo anual de HCFC no excede el máximo permitido en el Acuerdo con el Comité Ejecutivo. De acuerdo con la decisión 74/51 e), las solicitudes presentadas contenían además indicadores de desempeño para las actividades previstas en la siguiente fase de cada proyecto de fortalecimiento institucional.
Recomendación de la Secretaría
La Secretaría recomienda la aprobación general de las solicitudes de renovación de proyectos de fortalecimiento institucional para Argelia, Bahamas, Bahrein, Barbados, Cabo Verde, Chad, Etiopía, Guinea, Honduras, Jamaica, Lesotho, Malawi, Maldivas, Islas Marshall, Níger, Qatar, Saint Kitts y Nevis, Arabia Saudita y Uganda al nivel de financiamiento que se indica en la sección A1 del Cuadro 1 anterior. El Comité Ejecutivo podrá estimar oportuno remitir a los respectivos Gobiernos las observaciones formuladas en el Anexo II al presente documento.
A2: Elaboración de planes de aplicación de la Enmienda de Kigali (PAEK)
Descripción
Según consta en la sección A2 del Cuadro 1, el PNUMA solicitó fondos para preparar la etapa I de un plan de aplicación de la Enmienda de Kigali (PAEK) en un país del Artículo 5 en calidad de organismo de ejecución designado y en nueve en calidad de principal organismo de ejecución, con la ONUDI como organismo cooperante en siete de ellos; el PNUD, por su parte, solicitó fondos para un país y el Gobierno de Alemania para otro como organismo de cooperación bilateral; y solicitó además fondos para otros tres países en calidad de organismo cooperante, con el PNUD como principal organismo de ejecución en un caso y la ONUDI en dos. El Gobierno de Alemania, en calidad de organismo de cooperación bilateral en Seychelles, solicitó la suma de 49.000 $EUA más gastos de apoyo de 6.370 $EUA por concepto de cooperación bilateral;[footnoteRef:2] el PNUD, como principal organismo de ejecución en Bangladesh y cooperante en Mozambique, solicitó 201.000 $EUA más gastos de apoyo de 14.070 $EUA, y la ONUDI, en calidad de principal organismo de ejecución en Serbia y Somalia y cooperante en Benin, Botswana, Chad, Etiopía, Gambia, Guinea y Togo, solicitó 579.000 $EUA más gastos de apoyo de 40.530 $EUA, según se indica en los respectivos programas de trabajo para el año 2022.[footnoteRef:3] [2:  Documento UNEP/OzL.Pro/ExCom/90/14.]  [3:  Documentos UNEP/OzL.Pro/ExCom/90/15 y UNEP/OzL.Pro/ExCom/90/17.] 

Observaciones de la Secretaría
La Secretaría analizó las solicitudes en base a las pautas de financiamiento para planes de aplicación de la Enmienda de Kigali (PAEK) contenidas en la decisión 87/50, a las iniciativas propuestas y a su relación con las actividades de apoyo y demás proyectos relativos a los HFC en los respectivos países. Utilizando el formulario para planes de aplicación de la Enmienda, el PNUMA, como organismo de ejecución principal o designado, describió las actividades necesarias para la aplicación de la Enmienda de Kigali en Benin, Botswana, Chad, Etiopía, Gambia, Guinea, Mozambique, Santo Tomé y Príncipe, Seychelles y Togo, adjuntando los datos de consumo de HFC y sus mezclas para cada país. Entre las actividades de preparación de proyectos contempladas para estos 10 países se cuentan la evaluación de necesidades y el desarrollo de una estrategia transversal de reducción de los HFC, un estudio y recopilación de datos de consumo de HFC por país, un análisis del uso de HFC y sus alternativas, estadísticas de importación y exportación de alternativas a las SAO, reuniones consultivas con las contrapartes y reuniones de validación de datos. En el caso de nueve países (Benin, Chad, Etiopía, Gambia, Guinea, Mozambique, Santo Tomé y Príncipe, Seychelles y Togo) se contemplan además estudios del marco legislativo y de políticas sectoriales, una recopilación de datos y un análisis de las capacidades, necesidades de capacitación y equipamiento y sistemas de acreditación del sector servicio técnico y consideraciones sobre la integración de la perspectiva de género; en cinco países (Benin, Chad, Guinea, Santo Tomé y Príncipe y Togo) se realizará también un análisis de brechas de las normas y códigos, especialmente aquellos que regulan los refrigerantes inflamables; en tanto que en cuatro países (Botswana, Etiopía, Gambia y Mozambique) se contempla la elaboración de las primeras políticas y normas de regulación de los HFC con sus correspondientes planes de comunicación, y el desarrollo de una estrategia para las tecnologías ecoenergéticas existentes en el mercado.
El PNUMA aclaró que la preparación de las estrategias transversales para los PAEK de cada país se sustentará en las actividades de apoyo que sirvieron de punta de lanza para la reducción de los HFC y contribuyeron a la ratificación de la Enmienda de Kigali.
Tras el análisis, la Secretaría constató que los 10 países han ratificado la Enmienda de Kigali,[footnoteRef:4] que todos han manifestado por escrito su intención de adoptar medidas tendientes a la reducción de los HFC, y que el financiamiento solicitado es concordante con la decisión 87/50 c). [4:  Fechas de ratificación (o aceptación) de la Enmienda de Kigali: Benin, 19 de marzo de 2020; Botswana, 19 de septiembre de 2020; Chad, 26 de marzo de 2019; Etiopía, 5 de julio de 2019; Gambia, 5 de mayo de 2021; Guinea, 5 de diciembre de 2019; Mozambique, 16 de enero de 2020; Santo Tomé y Príncipe, 4 de octubre de 2019; Seychelles, 20 de agosto de 2019 y Togo, 8 de marzo de 2018.] 

[bookmark: _Hlk104444546]El PNUD y la ONUDI, en calidad de organismos de ejecución para los restantes países, más el PNUMA como organismo cooperante, describieron en sus respectivos programas de trabajo las actividades que requerirá la preparación de los PAEK, indicando los correspondientes costos y las observaciones de la Secretaría al respecto.
Recomendación de la Secretaría
La Secretaría recomienda la aprobación general de los fondos solicitados para elaborar los PAEK de Bangladesh, Benin, Botswana, Chad, Etiopía, Gambia, Guinea, Mozambique, Santo Tomé y Príncipe, Serbia, Seychelles, Somalia y Togo, al nivel de financiamiento que muestra la sección A2 del Cuadro 1.
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[bookmark: _Hlk105236325][bookmark: _Hlk105236326][bookmark: _Hlk105236634][bookmark: _Hlk105236635]Los documentos previos al período de sesiones del Comité Ejecutivo del Fondo Multilateral para la Aplicación del Protocolo de Montreal no van en perjuicio de las decisiones que el Comité pudiera adoptar después de la emisión de los mismos.
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Annex I

INSTITUTIONAL STRENGTHENING PROJECT PROPOSALS[footnoteRef:5] [5:  Data as at December 2020 are based on document UNEP/OzL.Pro/ExCom/88/15.] 

Algeria: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-93
	297,000

	Phase II:
	Mar-99
	90,010

	Phase III:
	Jul-02
	257,000

	Phase IV:
	Apr-06
	257,400

	Phase V:
	Apr-09
	257,400

	Phase VI:
	Nov-14
	257,400

		Total:
	1,416,210

	Amount requested for renewal (phase VII) (US $):
	329,472

	Amount recommended for approval for phase VII (US $): 
	329,472

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VII to the Multilateral Fund (US $):
	329,472

	Date of approval of country programme:
	1991

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex A, Group I (CFCs) (average 1995-1997)
	2,119.5

	(b)	Annex A, Group II (halons) (average 1995-1997)
	237.3

	(c)	Annex B, Group II (carbon tetrachloride) (average 1998-2000)
	20.9

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	5.8

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	62.12

	(f)	Annex E (methyl bromide) (average 1995-1998)
	4.7

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(a)	Annex A, Group I (CFCs)
	0.00

	(b)	Annex A, Group II (halons)
	0.00

	(c)	Annex B, Group II (carbon tetrachloride)
	0.00

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	39.33

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	39.33

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	21,638,547

	Amount disbursed (as at December 2020) (US $):
	19,347,083

	ODS to be phased out (as at December 2021) (ODP tonnes):
	2,733.2

	ODS phased out (as at December 2020) (ODP tonnes):
	2,798.3



1. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	16,326,211

	(b)
	Institutional strengthening:
	1,416,210

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	3,896,126

		Total:
	21,638,547

	(d)
	HFC activities funded from additional voluntary contributions
	0


Progress report
Despite an initial delay due to changes in the Ministry, the National Ozone Unit (NOU) of Algeria successfully implemented phase VI of the institutional strengthening (IS) project. The NOU collected ODS import data from the Customs department and importers and subsequently submitted Country Programme and Article 7 data to the Multilateral Fund and Ozone Secretariats, respectively. To ensure coordination with other stakeholders, meetings were held with the National Ozone Committee, and with industry association and refrigeration and air-conditioning (RAC) associations. The NOU supervised training of RAC technicians and customs and enforcement officers as part of the HCFC phase-out management plan (HPMP) project implementation. Awareness raising activities included the dissemination of information to consumers and importers on the availability of HCFC alternatives, information on laws such as the control or ban of HCFC‑based equipment, regulations and decisions of the Executive Committee and the Meetings of the Parties. Algeria celebrated the International Ozone Day in 2020 and 2021 and participated in regional network and Montreal Protocol meetings.
Plan of action
In phase VII of the IS project, the NOU is planning the following activities: information dissemination and awareness raising; implementation of the licensing and quota system for HCFCs, and providing information about annual quota to importers; monitoring and evaluation; organizing annual stakeholder workshops to raise awareness on low-GWP HCFC alternatives; data collection and reporting to the Ozone and Multilateral Fund Secretariats; and undertaking the communication at national level explaining the ratification of the Kigali Amendment by the country. The NOU has also planned specific activities for gender mainstreaming in the implementation of the Montreal Protocol activities and will collect, where possible, sex-disaggregated data for different activities organized as part of the project.
Bahamas: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	May-96
	50,000

	Phase II:
	Apr-03 & Apr-04
	43,333

	Phase III:
	Nov-06
	60,000

	Phase IV:
	Jul-10
	60,000

	Phase V:
	May-14
	60,000

	Phase VI:
	Dec-16
	85,000

	Phase VII:
	Dec-19
	85,000

		Total:
	443,333

	Amount requested for renewal (phase VIII) (US $):
	85,000

	Amount recommended for approval for phase VIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1996

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	4.8

	Annex E (methyl bromide) (average 1995-1998)
	0.2

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	2.1

		Annex E, (methyl bromide)
	0.00

		Total:
	2.1

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	1,909,553

	Amount disbursed (as at December 2020) (US $):
	1,514,882

	ODS to be phased out (as at December 2021) (ODP tonnes):
	80.3

	ODS phased out (as at December 2020) (ODP tonnes):
	78.8



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	711,420

	(b)
	Institutional strengthening:
	443,333

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	754,800

		Total:
	1,909,553

	(d)
	HFC activities funded from additional voluntary contributions
	95,000



Progress report
During phase VII of the IS project, the NOU of the Bahamas has enabled the country to maintain its strategic focus on the implementation of the Montreal Protocol activities. The Bahamas submitted Country Programme and Article 7 data to the Multilateral Fund and Ozone Secretariats, respectively, indicating its compliance with the Montreal Protocol. The NOU was able to continue: monitoring and prevention of illegal trade in ODS; data collection, processing and submission; offering a comprehensive public education and awareness programme about matters relating to the Montreal Protocol; and maintaining stakeholder confidence, support and collaboration [in its work?]. These activities have enabled the NOU to create a working relationship with government bodies, and in particular the Customs and Excise Department, RAC association and other relevant stakeholders, to support HCFC phase-out activities in the country. During the phase, the country fully achieved eight out of seventeen performance indicators, five were partially achieved, and four were not achieved. This was due to delays in implementation owing to the global COVID-19 pandemic and the effects of national elections and a change in Government, which essentially halted all Government activities.  
Plan of action
In the upcoming phase, the Government of the Bahamas will continue promotion of the issues related to the Montreal Protocol, in particular, securing ratification of the Kigali Amendment and adaptation of implementation due to the COVID-19 pandemic. The Government will continue to incorporate the work plan and budget of the NOU into the work plan of the Ministry and strengthen its relationships with stakeholders. Activities of the NOU will include: strengthening of the monitoring and enforcement mechanism through the licensing and quota system; strategic focus on the promotion of the transition to low-GWP, energy efficient alternatives; facilitation of ratification of the Kigali Amendment; data collection and verification; and maintaining participation in regional network meetings and the Montreal Protocol process.
Bahrain: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Oct-96
	66,000

	Phase II:
	Jul-00
	44,000

	Phase III:
	Dec-03
	57,200

	Phase IV:
	Nov-05
	60,000

	Phase V:
	Nov-07
	60,000

	Phase VI:
	Apr-10
	52,500

	Phase VII:
	Dec-12
	60,000

	Phase VIII:
	May-16
	85,000

	Phase IX:
	Jun-18
	85,000

	Phase X:
	Jun-20
	85,000

		Total:
	654,700

	Amount requested for renewal (phase XI) (US $):
	85,000

	Amount recommended for approval for phase XI (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XI to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1996

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	22.7

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	51.9

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	24.61

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	24.61

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	4,214,467

	Amount disbursed (as at December 2020) (US $):
	3,046,523

	ODS to be phased out (as at December 2021) (ODP tonnes):
	137.05

	ODS phased out (as at December 2020) (ODP tonnes):
	101.60



Summary of activities and funds approved by the Executive Committee:
	Summary of activities
	Funds approved (US $)

	(a)
	Investment projects:
	1,215,667

	(b)
	Institutional strengthening:
	654,700

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	2,344,100

		Total:
	4,214,467

	(d)
	HFC activities funded from additional voluntary contributions
	0



Progress report
During phase X of the IS project, the NOU of Bahrain, as part of the Supreme Council of Environment, was an integrated part of the national policy making and implementation structure. Bahrain submitted Country Programme and Article 7 data to the Multilateral Fund and Ozone Secretariats, respectively, indicating its compliance with the Montreal Protocol during the reporting period. New updated legislation on enhancing the environmental practices in installation and servicing of RAC equipment was issued and widely shared with stakeholders. During this phase, the NOU assisted in the following activities: upgrading the e-licensing system and including it on the government website; training of over 420 RAC technicians in good practices, and over 150 customs officers on ODS legislation, monitoring and prevention of illegal trade; and organizing regular coordination meetings with the Gulf Cooperation Council (GCC) countries to monitor and prevent illegal trade. The NOU also organized several awareness raising campaigns, including activities in observation of the Ozone Day. The National Ozone Officer (NOO) actively participated in Executive Committee meetings, as well as other Montreal Protocol meetings in 2020 and 2021. Of the 27 performance indicators selected, all were fully achieved, including four genders‑related indicators.
Plan of action
In the upcoming phase, the NOU will continue coordination and implementation of the activities planned under stage II of the HPMP as well as initial activities to prepare the country for ratification of the Kigali Amendment. Activities planned include: organization of a full inspection campaign to inspect local trade as a measure to ensure compliance with the legislation and the licensing system; continued collaboration with the GCC countries; collection and reporting of Article 7 and country programme data to the respective secretariats; organization of steering committee meetings and inclusion of gender and women’s empowerment issues; involvement of stakeholders in the NOU’s activities, awareness and outreach meetings and campaigns and celebrations of the Ozone Day; continued active participation of the NOO in the discussions and the decision-making process during Montreal Protocol meetings, as well as in deliberations of the Executive Committee, as the Chair of the Executive Committee in 2022.
Barbados: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Dec-94
	136,000

	Phase II:
	Nov-98
	90,000

	Phase III:
	Apr-04 & Jul-05
	117,000

	Phase IV:
	Jul-10
	117,000

	Phase V:
	Dec-12
	117,000

	Phase VI
	Nov-15
	149,760

	Phase VII:
	Dec-18
	149,760

		Total:
	876,520

	Amount requested for renewal (phase VIII) (US $):
	149,760

	Amount recommended for approval for phase VIII (US $): 
	149,760

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	149,760

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan:
	2013

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	3.7

	Annex E (methyl bromide) (average 1995-1998)
	0.1

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	0.87

	Annex E (methyl bromide)
	0.00

		Total:
	0.87

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	1,908,451

	Amount disbursed (as at December 2020) (US $):
	1,598,503

	ODS to be phased out (as at December 2021) (ODP tonnes):
	33.6

	ODS phased out (as at December 2020) (ODP tonnes):
	27.5



Summary of activities and funds approved by the Executive Committee:


	Summary of activities
	Funds approved (US $)

	(a)
	Investment projects:
	88,000

	(b)
	Institutional strengthening:
	876,520

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	943,931

		Total:
	1,908,451

	(d)
	HFC activities funded from additional voluntary contributions
	0



Progress report
Under phase VII of its IS project, Barbados maintained its regulatory and reporting compliance obligations under the Montreal Protocol. The country fully achieved 13 out of 17 performance indicators, two were partially achieved and two were not achieved. The performance indicators not achieved related to the submission of the country’s updated HPMP which was significantly affected by the COVID-19 pandemic, owing to national restrictions on gatherings and movement of persons. The activities implemented during this phase include: monitoring of the ODS phase-out to ensure compliance with the Montreal Protocol; implementation of the import/export licensing and quota system; reporting of data to the Ozone and Multilateral Fund Secretariats; execution of general public education and awareness activities which cover information on the status of implementation of Montreal Protocol‑related activities, local legislation and institutions, and the importance of the ozone layer; participation in regional and international meetings under the Montreal Protocol; and routine sensitization of national stakeholders on HCFC phase‑out and HFC phase-down issues.
Plan of action
Planned activities during the upcoming phase will ensure sustainability in Barbados’ commitment to the Montreal Protocol. These include a focus on preparation of the Kigali HFC implementation plan (KIP) including to access preparatory funding for the KIP. During the upcoming phase, a number of areas will be covered: monitoring the implementation of the HCFC licensing and quota system; sustaining the phase-out of ODS; maintaining and further strengthening the partnerships between the NOU and other country authorities, regional and international bodies, as well as with the Ozone and Multilateral Fund Secretariats and implementing agencies; monitoring implementation of the HPMP project and its deliverables; continuing public education activities to increase awareness about Montreal Protocol issues amongst stakeholders; and participating in regional and international Montreal Protocol negotiations and regional network meetings.
Cabo Verde: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02 and Dec-04
	75,000

	Phase II:
	Nov-06
	60,000

	Phase III:
	Apr-09
	60,000

	Phase IV:
	Dec-13
	60,000

	Phase V:
	Nov-15
	85,000

	Phase VI:
	Jun-18
	85,000

	Phase VII:
	Dec-20
	85,000

		Total:
	510,000

	Amount requested for renewal (phase VIII) (US $):
	85,000

	Amount recommended for approval for phase VIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	2001

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	1.1

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	0.04

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	0.04

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	1,492,400

	Amount disbursed (as at December 2020) (US $):
	1,136,372

	ODS to be phased out (as at December 2021) (ODP tonnes):
	2.4

	ODS phased out (as at December 2020) (ODP tonnes):
	1.3



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	0

	(b)
	Institutional strengthening:
	510,000

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	982,400

		Total:
	1,492,400

	(d)
	HFC activities funded from additional voluntary contributions
	95,000



Progress report
The NOU of Cabo Verde successfully implemented phase VII of its institutional strengthening project. Cabo Verde fully achieved 15 out of the 16 performance indicators selected and one was partially achieved. ODS import data was collected from the Customs department and the Government of Cabo Verde submitted Country Programme and Article 7 data to the Multilateral Fund and Ozone Secretariats, respectively, indicating its compliance with the Montreal Protocol during the reporting period. The NOU produced information and outreach materials and organized several activities in 2021 and 2022. The NOO actively participated in the regional and international Montreal Protocol meetings in particular those on HPMPs and HFC phase-down initiatives of the Africa network in 2020, 2021 and 2022.
Plan of action
The main objective of the IS project for the upcoming phase is to sustain the phase-out of 35 per cent of HCFC baseline consumption and to meet the next target as required by the Montreal Protocol. The main activities will include: ensuring sustainability of NOU activities; continuing effective cooperation with different stakeholders; continuing information dissemination and awareness raising to the decision makers, other stakeholders, and the public; coordinating the implementation of stage II of the HPMP activities; organizing two stakeholder workshops to raise awareness on phase-out of HCFCs and availability of low-GWP, energy-efficient and climate friendly alternatives; collecting and reporting data to the Fund and Ozone Secretariats; implementing the enabling activities for HFC phase-down and initiating preparation of the KIP.
Chad: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-98
	60,000

	Phase II:
	Dec-04
	60,000

	Phase III:
	Nov-06
	60,000

	Phase IV:
	Nov-08
	60,000

	Phase V:
	Nov-11
	60,000

	Phase VI:
	Dec-13
	60,000

	Phase VII:
	Nov-15
	85,000

	Phase VIII:
	Nov-17
	85,000

	Phase IX:
	Dec-19
	85,000

		Total:
	615,000

	Amount requested for renewal (phase X) (US $):
	85,000

	Amount recommended for approval for phase X (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1998

	Date of approval of HCFC phase-out management plan:
	2010

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	16.1

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.0

	(e)	Annex C, Group I (HCFCs)
	10.1

	(f)	Annex E (methyl bromide)
	0.0

		Total:
	10.1

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	2,605,748

	Amount disbursed (as at December 2020) (US $):
	2,293,339

	ODS to be phased out (as at December 2021 2021) (ODP tonnes):
	40.2

	ODS phased out (as at December 2020) (ODP tonnes):
	37.1



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	409,000

	(b)
	Institutional strengthening:
	615,000

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,581,748

		Total:
	2,605,748

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
The National Ozone Unit of Chad has implemented phase IX of its institutional strengthening project. During this phase, the NOU collected 2020 and 2021 HCFC import data from the Customs department and subsequently submitted country programme and Article 7 data to the Multilateral Fund and Ozone Secretariats, respectively. To ensure coordination with other stakeholders, meetings were held with the National Ozone Committee. The NOU also: held meetings with refrigerant importers and distributors; supervised training of 183 RAC technicians and 133 enforcement officers; and held awareness activities including the dissemination of information to consumers and importers on the availability of HCFC alternatives, information on ODS regulations and decisions of the Executive Committee and Meetings of the Parties. Chad celebrated International Ozone Day and participated in regional network and Montreal Protocol meetings. The country fully achieved 18 out of the 19 performance indicators selected for the phase, and one indicator was partially achieved.
Plan of action
In the upcoming phase, the NOU plans to implement the following activities: continue information dissemination and awareness raising; coordination of the implementation of the HPMP; continue implementation of the HCFC licensing and quota system and its enforcement, and provide information about annual quota to importers; organize meetings with the importers and distributors of refrigerants; submit the final report on the enabling activities project; and collect and report data to the Ozone and Multilateral Fund Secretariats. 
Ethiopia: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Oct-96
	60,500

	Phase II:
	Nov-99
	40,300

	Phase III:
	Apr-03 & Dec-03
	52,432

	Phase IV:
	Nov-06
	60,000

	Phase V:
	Nov-09
	60,000

	Phase VI:
	Nov-14
	60,000

	Phase VII:
	Dec-16
	85,000

	Phase VIII:
	Dec-20
	85,000

		Total:
	503,232

	Amount requested for renewal (phase IX) (US $):
	85,000

	Amount recommended for approval for phase IX (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase IX to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1996

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.5

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	5.5

	(f)	Annex E (methyl bromide) (average 1995-1998)
	15.6

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	3.41

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	3.41

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	1,827,757

	Amount disbursed (as at December 2020) (US $):
	1,032,868

	ODS to be phased out (as at December 2021) (ODP tonnes):
	30.7

	ODS phased out (as at December 2020) (ODP tonnes):
	11.6



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	200,000

	(b)
	Institutional strengthening:
	503,232

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,124,525

		Total:
	1,827,757

	(d)
	HFC activities funded from additional voluntary contributions
	95,000



Progress report
During phase VIII, the NOU of Ethiopia was involved in many activities centered on awareness raising, training and capacity building of refrigeration technicians, Customs and other law enforcement officers in the implementation of HPMP projects. In order to control the importation and consumption of HCFCs, a quota-based licensing system was operationalized. This system further put in place a mechanism to verify facilities handling HCFCs to ensure that they have adequate human capacity and equipment to manage HCFCs in an environmentally sound manner. These activities enabled the NOU to create a good working relationship with governmental bodies, industry associations and other relevant stakeholders. Ethiopia successfully implemented its programmes and activities under the Montreal Protocol for the phase‑out of ODS during this phase. Ethiopia fully achieved 18 of 22 performance indicators selected for this phase, and four performance indicators were partially achieved.
Plan of action
For the next phase, the NOU aims to sustain compliance with the Montreal Protocol and to implement programmes and strategies to achieve the gradual phase out of HCFCs leading to a complete phase out by 2030. The NOU will: conduct additional training for RAC technicians; strengthen the network between relevant institutions to collaborate in achieving the goals and objectives of the Montreal Protocol and its amendments; continue to carry out public awareness activities; coordinate and monitor programme activities under the HPMP; ensure integration of Montreal Protocol objectives into national environmental policy and regulations; and strengthen collaboration with different stakeholders in matters relating to the protection of the ozone layer.
Guinea: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-95
	50,000

	Phase II:
	Jul-99
	33,333

	Phase III:
	Jul-01
	33,333

	Phase IV:
	Dec-03
	43,333

	Phase V:
	Nov-06
	60,000

	Phase VI:
	Nov-08
	60,000

	Phase VII:
	Apr-11
	60,000

	Phase VIII:
	Jul-13
	60,000

	Phase IX:
	May-15
	60,000

	Phase X:
	Nov-17
	85,000

	Phase XI:
	Jun-20
	85,000

		Total:
	629,999

	Amount requested for renewal (phase XII) (US $):
	85,000

	Amount recommended for approval for phase XII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1995

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	22.6

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	1.65

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	1.65

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	2,319,669

	Amount disbursed (as at December 2020) (US $):
	1,826,433

	ODS to be phased out (as at December 2021) (ODP tonnes):
	54.5

	ODS phased out (as at December 2020) (ODP tonnes):
	53.0



Summary of activities and funds approved by the Executive Committee:
	Summary of activities
	Funds approved (US $)

	(a)
	Investment projects:
	485,000

	(b)
	Institutional strengthening:
	629,999

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,204,670

		Total:
	2,319,669

	(d)
	HFC activities funded from additional voluntary contributions
	0



Progress report
During phase XI, the NOU of Guinea collected ODS import data from the Customs department and subsequently submitted country programme and Article 7 data to the Fund and Ozone Secretariats, respectively. Guinea ratified the Kigali Amendment on 5 December 2019 and established an HFC licensing system on 8 July 2021. To ensure coordination with other stakeholders, annual meetings were held with the National Ozone Committee. Meetings were also held with refrigeration association and the major importers and consumer’s association. The NOU supervised training of 302 RAC technicians and 258 customs officers during the reporting period. Awareness raising activities included the dissemination of information to consumers and importers on the availability of HCFC alternatives, information on ODS regulations such as the import ban of HCFC-based equipment, and decisions of the Executive Committee and Meetings of the Parties. Guinea celebrated International Ozone Day and participated in regional network and Montreal Protocol meetings. To support women’s empowerment and gender‑responsive information dissemination, a gala match was organized between two female teams during the Ozone Day celebration. Guinea fully achieved 18 of 20 performance indicators selected for the phase, one indicator was partially achieved, and one was not assessed.
Plan of action
In phase XII, the NOU plans to implement the following activities: continue information dissemination and awareness raising; coordinate the implementation of stage I of the HPMP; promote the licensing and quota system and its enforcement and provide information about annual quota to importers; put in place the technician certification programme; continue monitoring and evaluation; organize annual stakeholder workshops to raise awareness on low-GWP HCFC alternatives; and collect and report data to the Ozone and Multilateral Fund Secretariats.


Honduras: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Oct-96
	66,000

	Phase II:
	Dec-00
	44,000

	Phase III:
	Jul-03
	57,200

	Phase IV:
	Apr-05
	60,000

	Phase V
	Nov-06
	60,000

	Phase VI
	Apr-09
	60,000

	Phase VII
	Dec-12
	60,000

	Phase VIII:
	Nov-15
	85,000

	Phase IX:
	May-19
	85,000

		Total:
	577,200

	Amount requested for renewal (phase X) (US $):
	85,000

	Amount recommended for approval for phase X (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase X to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1996

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	19.9

	(f)	Annex E (methyl bromide) (average 1995-1998)
	259.4

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.0

	(e)	Annex C, Group I (HCFCs)
	7.17

	(f)	Annex E (methyl bromide)
	0.0

		Total:
	7.17

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	7,120,105

	Amount disbursed (as at December 2020) (US $):
	6,494,730

	ODS to be phased out (as at December 2021) (ODP tonnes):
	681.16

	ODS phased out (as at December 2020) (ODP tonnes):
	675.30



Summary of activities and funds approved by the Executive Committee:
	Summary of activities
	Funds approved (US $)

	(a)
	Investment projects:
	4,699,255

	(b)
	Institutional strengthening:
	577,200

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,843,650

		Total:
	7,120,105

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During phase IX of the IS project, Honduras kept HCFC consumption below the established country baseline. The NOU (UTOH) of Honduras submitted country programme and Article 7 data to the Fund and Ozone Secretariats, respectively, indicating the country’s compliance with the Montreal Protocol during the reporting period. The NOU staff coordinated activities under the HPMP. Among other actions, the UTOH was responsible for: coordination of ODSs import/export controls with the general direction of Customs and other enforcement authorities; conducting awareness-raising activities among ODS importers, suppliers, end-users and general public; promoting the good practices in refrigeration and the certification of technicians, and training of the Custom officers. Additionally, UTOH participated in the regional and international meetings of the Montreal Protocol. During the reporting period, the UTOH fully achieved 30 out of 33 performance indicators selected for the phase and three were rated as partially achieved.
Plan of action
During the upcoming phase, the UTOH will continue activities such as revision of ODS legislation to fulfill the Kigali Amendment requirements and development of national capacities to allow the efficient implementation of all its provisions. The action plan also includes strict monitoring and control of the imports and use of HCFCs/HFCs, as well as facilitating access to and use of low-GWP alternative substances and technologies. The UTOH will continue coordination with the Customs to ensure an effective control of the international trade of all Montreal Protocol controlled substances, facilitating the involvement of main country stakeholders (importers, exporters, suppliers, technicians, and end-users) in the implementation of the HPMP. The UTOH will implement a digital database of trained and certified RAC technicians in the handling of alternative substances to HCFCs and HFCs. The UTOH will continue public awareness activities, especially in the education sector and with a gender focus during the World Refrigeration Day and World Ozone Day celebrations. The UTOH will also train service technicians in safe handling of flammable refrigerants.
Jamaica: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Oct-96
	66,000

	Phase II:
	Nov-99
	44,000

	Phase III:
	Dec-01
	44,000

	Phase IV:
	Jul-03
	57,200

	Phase V:
	Nov-05
	60,000

	Phase VI:
	Jul-08
	60,000

	Phase VII:
	Dec-10
	60,000

	Phase VIII:
	Dec-12
	60,000

	Phase IX:
	Nov-15
	85,000

	Phase X:
	Dec-19
	85,000

		Total:
	621,200

	Amount requested for renewal (phase XI) (US $):
	85,000

	Amount recommended for approval for phase XI (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XI to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1996

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	1.4

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	16.3

	(f)	Annex E (methyl bromide) (average 1995-1998)
	4.9

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	1.08

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	1.08

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	3,565,585

	Amount disbursed (as at December 2020) (US $):
	2,956,740

	ODS to be phased out (as at December 2021) (ODP tonnes):
	178.6

	ODS phased out (as at December 2020) (ODP tonnes):
	168.4



Summary of activities and funds approved by the Executive Committee:
	Summary of activities
	Funds approved (US $)

	(a)
	Investment projects:
	1,291,450

	(b)
	Institutional strengthening:
	621,200

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,652,935

		Total:
	3,565,585

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
Despite the challenges of the COVID-19 pandemic and its restriction, Jamaica maintained compliance with the Montreal Protocol during phase X of its IS project. The NOU adapted its work programme and deferred training until conditions have improved. The established relationship with the Jamaica Customs Agency facilitated the collection of ODS consumption data. Work continued towards ratification of the Kigali Amendment, which is in the final stages for ratification. Jamaica submitted country programme and Article 7 data to the Fund and Ozone Secretariats, respectively, indicating its compliance with the Montreal Protocol during the reporting period. Jamaica celebrated International Ozone Day through school activities, newspaper advertisements and social media and participated in virtual regional network meetings and webinars as well as Montreal Protocol related meetings. During the reporting period, Jamaica fully achieved 12 out of 16 performance indicators selected, two were partially achieved and two were not achieved. The two indicators not achieved were related to training and ratification of the Kigali Amendment which were affected by restrictions on gatherings due to the COVID-19 pandemic.  
Plan of action
The work plan for the upcoming phase includes: timely submission of Article 7 and country programme data; ongoing collaboration with Jamaica Refrigeration and Ventilation Association; organization of stakeholder workshops to raise awareness on the phase-out of HCFCs and the availability of low-GWP, energy-efficient and climate friendly alternatives; ongoing coordination and supervision of the HPMP implementation; participation in network meetings and Montreal Protocol related meetings and celebration of International Ozone Day. Jamaica will make progress in its national process towards ratification of the Kigali Amendment as soon as possible. The NOU will continue to adopt its modes of implementation to meet the evolving situation of the COVID-19 pandemic.
Lesotho: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Oct-96
	30,000

	Phase II:
	Nov-99
	20,000

	Phase III:
	Apr-05
	26,000

	Phase IV:
	Nov-07
	60,000

	Phase V:
	Dec-10
	60,000

	Phase VI:
	Dec-12
	60,000

	Phase VII:
	Nov-14
	60,000

	Phase VIII:
	Dec-16
	85,000

	Phase IX:
	Dec-18
	85,000

	Phase X:
	Jun-20
	85,000

		Total:
	571,000

	Amount requested for renewal (phase XI) (US $):
	85,000

	Amount recommended for approval for phase XI (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XI to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1996

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	3.5

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.1

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	0.44

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	0.44

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	1,713,295

	Amount disbursed (as at December 2020) (US $):
	1,250,627

	ODS to be phased out (as at December 2021) (ODP tonnes):
	6.18

	ODS phased out (as at December 2020) (ODP tonnes):
	7.0



Summary of activities and funds approved by the Executive Committee:
	Summary of activities
	Funds approved (US $)

	(a)
	Investment projects:
	576,200

	(b)
	Institutional strengthening:
	571,000

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	566,095

		Total:
	1,713,295

	(d)
	HFC activities funded from additional voluntary contributions
	95,000



Progress report
During the phase X, the NOU of Lesotho implemented the required activities in its IS project. Ozone Depleting Substances Regulation 2012 became fully operational with enforcement mechanisms such as the licensing and quota system in place, and a transition of the licensing and quota system to an electronic version started. The NOU further embarked on awareness-raising programmes during the phase, and trained Customs officers, clearing agents, border control agents, and RAC technicians. Ozone Depleting Substance Regulations are under review by the Government of Lesotho to include HFCs. Lesotho fully achieved 19 out of 21 performance indicators selected for the phase, and two performance indicators were partially achieved.
Plan of action
In the upcoming phase, Lesotho will implement its action plan to ensure sustained compliance with the Montreal Protocol. The NOU will ensure collaboration with stakeholders (customs, local technical institutions, and others) and implementing agencies to control ODS consumption in the country. The NOU will also continue with the training programme for RAC technicians and training of newly recruited and incumbent Customs officers to support the implementation and enforcement of ODS regulations including control measures of HCFCs. The NOU will continue with the awareness-raising programme on Montreal Protocol issues through mass media, interactions with non-governmental organizations (NGOs), workshops, and the distribution of materials such as newspapers, brochures, pamphlets and others to the industry and other stakeholders.
Malawi: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-94
	77,000

	Phase II:
	Jul-98
	51,350

	Phase III:
	Jul-00
	51,300

	Phase IV:
	Dec-03
	66,733

	Phase V:
	Nov-05
	66,733

	Phase VI:
	Nov-07
	66,733

	Phase VII:
	Nov-09
	66,733

	Phase VIII:
	Apr-12
	66,733

	Phase IX:
	May-14
	66,733

	Phase X:
	May-16
	85,418

	Phase XI:
	Dec-18
	85,418

	Phase XII:
	Jun-20
	85,418

		Total:
	836,302

	Amount requested for renewal (phase XIII) (US $):
	85,418

	Amount recommended for approval for phase XIII (US $): 
	85,418

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $):
	85,418

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan:
	2010

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	10.8

	(f)	Annex E (methyl bromide) (average 1995-1998)
	112.8

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	2.82

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	2.82

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	5,978,446

	Amount disbursed (as at December 2020) (US $):
	5,308,851

	ODS to be phased out (as at December 2021) (ODP tonnes):
	230.74

	ODS phased out (as at December 2020) (ODP tonnes):
	179.20



Summary of activities and funds approved by the Executive Committee:
	Summary of activities
	Funds approved (US $)

	(a)
	Investment projects:
	3,149,324

	(b)
	Institutional strengthening:
	836,302

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,992,820

		Total:
	5,978,446

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
During the phase XII, the NOU of Malawi implemented the required activities in its IS project. The NOU enforced the ODS regulations through the implementation of a licensing and quota system; further embarked on an awareness-raising programme; and trained Customs officers, clearing agents, border control police, and refrigeration technicians. Malawi incorporated the provisions of the Kigali Amendment into its draft legal framework on controlled substances under the Montreal Protocol which is in final stages for enactment. Malawi fully achieved all 16 performance indicators selected for the phase.
Plan of action
In the upcoming phase, Malawi will implement its action plan to ensure sustained compliance with the Montreal Protocol. The NOU will continue with the training programme for the RAC technicians and training of newly recruited and incumbent Customs officers to support the implementation and enforcement of ODS regulations including control measures of HCFCs. The NOU will continue with its awareness‑raising programme through mass media, interactions with NGOs, workshops, and distribution of awareness materials such as newspapers, brochures, pamphlets and others to the industry and other stakeholders.
Maldives: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-94
	41,250

	Phase II:
	Jul-02
	35,753

	Phase III:
	Dec-04
	60,000

	Phase IV:
	Nov-06
	60,000

	Phase V:
	Nov-08
	60,000

	Phase VI:
	Jul-10
	60,000

	Phase VII:
	Jul-12
	60,000

	Phase VIII:
	May-14
	60,000

	Phase IX:
	Dec-16
	85,000

	Phase X:
	Jun-18
	85,000

	Phase XI:
	Jun-20
	85,000

		Total:
	692,003

	Amount requested for renewal (phase XII) (US $):
	85,000

	Amount recommended for approval for phase XII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1993

	Date of approval of HCFC phase-out management plan:
	2010

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	4.6

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	0.09

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	0.09

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	2,773,003

	Amount disbursed (as at December 2020) (US $):
	2,400,834

	ODS to be phased out (as at December 2021) (ODP tonnes):
	5.21

	ODS phased out (as at December 2020) (ODP tonnes):
	2.90



Summary of activities and funds approved by the Executive Committee:
	Summary of activities
	Funds approved (US $)

	(a)
	Investment projects:
	505,000

	(b)
	Institutional strengthening:
	692,003

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,576,000

		Total:
	2,773,003

	(d)
	HFC activities funded from additional voluntary contributions
	95,000



Progress report
During phase XI of the institutional strengthening project, the NOU of Maldives enforced the licensing and quota system for HCFC import/export and the licensing system for HFCs. An online import licensing system was implemented through the Makudi system. Customs brokers and new Customs officers were regularly briefed and trained on the Montreal Protocol provisions and amendments including the Kigali Amendment. The NOU conducted training workshops for the RAC servicing sector in response to demand from the technicians and the market corresponding with the ratification of the Kigali Amendment. Due to the COVID-19 pandemic, some activities were organized in virtual mode during the phase. Maldives submitted country programme and Article 7 data to the Multilateral Fund and Ozone Secretariats, respectively, indicating its compliance with the Montreal Protocol. The country achieved its accelerated HCFC phase-out target in 2020 and continued to enforce the control measures. The NOU also participated in all network and regional workshops and meetings and international Montreal Protocol events. Among 17 performance indicators proposed for the phase, 15 performance indicators were rated as fully achieved, and two were partially achieved.
Plan of action
The action plan for the upcoming phase focuses on the development of a national overarching strategy for HFC phase-down, a quota allocation system for HFCs and the preparation of a KIP and its implementation. The NOU will continue to monitor the HCFC quota and enforce the online licensing system for HCFC and HFCs. The NOU will also focus on the data collection for HFCs and its sectoral distribution to better design the HFC phase-down activities and fulfill HFC phase-down obligations in coming years. In doing so, the NOU will closely cooperate with national stakeholders; build the capacity of Customs and enforcement officers on the trade control of the substances controlled under the Montreal Protocol; support the establishment of a RAC association and its activities; collect trade data of the controlled substances from various sources and cross-check them on regular basis and submit the necessary data reports to the Ozone Secretariat and the Fund Secretariat in a timely manner. The NOU will participate in all international and regional Montreal Protocol activities held during the phase and will organize awareness-raising activities to sensitize targeted and sector-specific audiences, as well as the general public on the Montreal Protocol issues.
Marshall Islands (the): Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-02
	34,000

	Phase II:
	Nov-06 & Nov-07
	60,000

	Phase III:
	Nov-09 
	60,000

	Phase IV:
	Jul-11
	60,000

	Phase V:
	Jul-13
	60,000

	Phase VI:
	Nov-17
	85,000

	Phase VII:
	Dec-19
	85,000

		Total:
	444,000

	Amount requested for renewal (phase VIII) (US $):
	85,000

	Amount recommended for approval for phase VIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	2002

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	0.2

	Annex E, (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	0.00

	Annex E (methyl bromide)
	0.00

		Total:
	0.00

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	825,200

	Amount disbursed (as at December 2020) (US $):
	532,280

	ODS to be phased out (as at December 2021) (ODP tonnes):
	1.2

	ODS phased out (as at December 2020) (ODP tonnes):
	0.0



Summary of activities and funds approved by the Executive Committee:
	Summary of activities
	Funds approved (US $)

	(a)
	Investment projects:
	0

	(b)
	Institutional strengthening:
	444,000

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	381,200

		Total:
	825,200

	(d)
	HFC activities funded from additional voluntary contributions
	50,000



Progress report
During phase VII of the IS project, the Marshall Islands sustained its compliance with Montreal Protocol obligations. During the implementation of phase VII, the management of the Environmental Protection Agency maintained NOU activities during a two-and-a-half-month gap where there was no sitting NOO. Despite the challenges imposed by high staff turnover and the COVID-19 pandemic, the NOU strategized and reprioritized activities. The Government of the Marshall Islands submitted country programme and Article 7 data to the Fund and Ozone Secretariats, respectively, indicating its compliance with the Montreal Protocol. The Marshall Islands also maintained zero ODS consumption during the reporting period. The NOU worked in close collaboration with all key stakeholders in the implementation of all Multilateral Fund projects. The NOU organized and delivered the 2020 International Ozone Day celebration in close collaboration with key stakeholders and participated actively in the regional network meetings. Following the ratification of the Kigali Amendment on 15 May 2017, a Ministerial Order put into place mandatory controls for HFC and its blends, while the amendment phase of the Ozone Layer Protection Regulation has begun to include the details of the HFC licensing system including a quota allocation process. Among the 21 performance indicators proposed for the phase, 11 were rated as fully achieved, six were rated partially achieved and four were not achieved.
Plan of action
The plan of action for the upcoming phase will include: enforcement of bans on the import of HCFC and implementing a licensing and quota system for HFCs; amendment of the Ozone Layer Protection Regulation to supplement the HFC licensing system through the Ministerial Order; timely submission of Article 7 data and country programme implementation reports; active engagement of stakeholders in the implementation of the Montreal Protocol; organization of the International Ozone Day celebration and development of awareness-raising materials; and participation in regional and international meetings relating to the Montreal Protocol. Gender mainstreaming will also be integrated into the IS project during the phase.
Niger (the): Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Dec-94
	74,800

	Phase II:
	Nov-98
	50,000

	Phase III:
	Mar-01
	50,000

	Phase IV:
	Dec-03
	64,827

	Phase V:
	Nov-05
	64,827

	Phase VI
	Nov-07
	64,827

	Phase VII:
	Nov-09
	64,828

	Phase VIII:
	Nov-11
	64,828

	Phase IX:
	Dec-13
	64,828

	Phase X:
	Nov-15
	85,000

	Phase XI:
	Nov-17
	85,000

	Phase XII:
	Dec-19
	85,000

		Total:
	818,765

	Amount requested for renewal (phase XIII) (US $):
	85,000

	Amount recommended for approval for phase XIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase XIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	15.98

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0.0

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	9.06

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	9.06

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	2,743,070

	Amount disbursed (as at December 2020) (US $):
	2,012,980

	ODS to be phased out (as at December 2021) (ODP tonnes):
	43.4

	ODS phased out (as at December 2020) (ODP tonnes):
	39.5



Summary of activities and funds approved by the Executive Committee:
	Summary of activities
	Funds approved (US $)

	(a)
	Investment projects:
	469,000

	(b)
	Institutional strengthening:
	818,765

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	1,455,305

		Total:
	2,743,070

	(d)
	HFC activities funded from additional voluntary contributions
	150,000



Progress report
Under phase XII of the IS, the NOU collected ODS import data from the Customs department and subsequently submitted country programme and Article 7 data for 2019, 2020 and 2021 to the Fund and Ozone Secretariats, respectively. To ensure coordination with other stakeholders, annual meetings were held with the National Ozone Committee and with the major importers and consumer’s association. The Government of the Niger also organized a workshop with the main stakeholders in the governmental and private sectors to discuss the implications of the Kigali Amendment, the necessary arrangements to facilitate and support its ratification, and activities that would assist the country in fulfilling its initial obligations with regard to the HFC phase-down. The NOU also supervised training of 245 RAC technicians and 212 customs and enforcement officers. Awareness-raising activities during the phase included the dissemination of information to consumers and importers on the availability of HCFC alternatives, information on laws such as the import ban of HCFC-based equipment, regulations and decisions of the Executive Committee and the Meetings of the Parties. The Niger celebrated International Ozone Day and participated in regional network and international Montreal Protocol meetings. Of the 16 performance indicators selected for the phase, 14 were fully achieved and two were not achieved.
Plan of action
In the upcoming phase, the NOU plans to implement the following activities: continue information dissemination and awareness-raising; promotion of the licensing and quota system and its enforcement, and sharing information about annual quota to importers; putting into place the technician certification programme; continue monitoring and evaluation; organizing annual stakeholder workshops to raise awareness on low-GWP HCFC alternatives; collection and reporting of data to the Ozone and Fund Secretariats; and undertaking communication at the national level explaining the ratification of the Kigali Amendment by the country.
Qatar: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Mar-99
	68,450

	Phase II:
	Dec-03 & Jul-06
	89,000

	Phase III:
	Nov-09
	89,000

	Phase IV:
	Jul-17
	113,920

	Phase V:
	Jun-20
	113,920

		Total:
	474,290

	Amount requested for renewal (phase VI) (US $):
	113,920

	Amount recommended for approval for phase VI (US $): 
	113,920

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VI to the Multilateral Fund (US $):
	113,920

	Date of approval of country programme:
	1999

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	86.9

	(f)	Annex E (methyl bromide) (average 1995-1998)
	0

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0

	(e)	Annex C, Group I (HCFCs)
	56.49

	(f)	Annex E (methyl bromide)
	0

		Total:
	56.49

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	3,357,197

	Amount disbursed (as at December 2020) (US $):
	2,550,092

	ODS to be phased out (as at December 2021) (ODP tonnes):
	115.88

	ODS phased out (as at December 2020) (ODP tonnes):
	122



Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	1,563,407

	(b)
	Institutional strengthening:
	474,290

	(c)
	Project preparation, technical assistance, training and other non-investment projects*:
	1,319,500

		Total:
	3,357,197

	(d)
	HFC activities funded from additional voluntary contributions
	0


* Includes US $150,000 for HFC phase-down enabling activities
Progress report
Phase V of the IS project was implemented as planned and provided the NOU with the required support to respond to Montreal Protocol-related challenges at all levels, including at the policy. Qatar implemented the applicable HCFC import control measures and the licensing and quota system, providing data in a timely manner. The NOU capacity was enhanced to ensure its role in data collection, processing and reporting. Qatar submitted country programme and Article 7 data to the Fund and Ozone Secretariats, respectively. The enabling activities project was completed and the process of ratification of the Kigali Amendment was initiated. During the implementation of this phase, Qatar fully achieved 26 out of 30 performance indicators selected, and four were partially achieved. 
Plan of action
In the upcoming phase, activities aim to sustain and further build the capacity of the NOU to undertake the assigned responsibilities and assist the country in meeting its obligations under the Montreal Protocol, including future commitments under the Kigali Amendment. The NOU will continue to work with all stakeholders; government and private sectors and ensure their full engagement in implementing the project activities. The NOU will continue the operation of the HCFC quota and licensing system to ensure full compliance with the agreed HCFC reduction steps, will update the system to include HFCs as required under the Kigali Amendment and will continue to pursue efforts to identify feasible alternatives suitable for high ambient temperature countries with an emphasis on the non-in-kind technologies. The NOU will also continue producing public and industry awareness-raising materials and preparing the necessary data reporting.
Saint Kitts and Nevis: Renewal of institutional strengthening
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Feb-97
	30,000

	Phase II:
	Apr-04
	13,000

	Phase III:
	Nov-05
	60,000

	Phase IV
	Nov-09 
	60,000

	Phase V:
	Dec-12
	60,000

	Phase VI:
	Nov-14
	60,000

	Phase VII:
	Jun-18
	85,000

		Total:
	368,000

	Amount requested for renewal (phase VIII) (US $):
	85,000

	Amount recommended for approval for phase VIII (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase VIII to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1997

	Date of approval of HCFC phase-out management plan:
	2011

	Baseline consumption of controlled substances (ODP tonnes):
	

	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	Annex C, Group I (HCFCs) (average 2009-2010)
	0.5

	Annex E (methyl bromide) (average 1995-1998)
	0.3

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	Annex B, Group III (methyl chloroform)
	0.00

	Annex C, Group I (HCFCs)
	0.04

	Annex E (methyl bromide)
	0.00

		Total:
	0.04

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	1,139,900

	Amount disbursed (as at December 2020) (US $):
	836,750

	ODS to be phased out (as at December 2021) (ODP tonnes):
	3.1

	ODS phased out (as at December 2020) (ODP tonnes):
	2.9



1. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	55,000

	(b)
	Institutional strengthening:
	368,000

	(c)
	Project preparation, technical assistance, training and other non-investment projects*:
	716,900

		Total:
	1,139,900

	(d)
	HFC activities funded from additional voluntary contributions
	50,000



Progress report
During phase VII of its IS project, Saint Kitts and Nevis fully achieved seven out of 24 performance indicators selected for the phase, eight were partially achieved and nine were not achieved. This was due to delays in the implementation of the HPMP owing to the COVID-19 pandemic and structural changes in the NOU. Additionally, during the latter part of implementation of the phase, the pandemic forced the NOU to adapt its mode of implementation to virtual, limiting the activities that it would normally implement. Despite these challenges, the NOU submitted its country programme and Article 7 data to the Fund and Ozone Secretariats, although it experienced delays with this activity. A number of activities were implemented with respect to: monitoring and prevention of illegal trade in ODS; data collection, processing and submission; public education and awareness programme; and maintaining participation at network meetings and international negotiations relating to the Montreal Protocol. These activities enabled the NOU to maintain compliance with the Montreal Protocol and achieve its HCFC phase-out targets.
Plan of action
During the next phase, the NOU will continue to monitor and enhance the existing licensing and quota system (LQS) by updating legislation to include HFCs in the licensing system while re-engaging the Customs Department to transition to an e-LQS. Upon completion, the NOU will be trained to utilize the ASYCUDA platform to issue licenses and monitor the import and export of ODS. Public education and awareness-raising activities will continue in order to ensure that all stakeholders understand their role in the HCFC phase‑out. Additionally, climate change and energy-efficiency will be taken into account when making decisions regarding alternative technologies, the establishment of any incentives, and in the general implementation of the ozone protection activities. The NOU hopes to complete the enabling activities project and see the ratification of the Kigali Amendment before the end of 2022. Saint Kitts and Nevis will continue to participate in regional and international meetings and negotiations relating to the Montreal Protocol; and will work to highlight challenges for very low-volume-consuming countries and the actions needed to assist them with the implementation of the Montreal Protocol.  
Saudi Arabia: Renewal of institutional strengthening
	Summary of the project and country profile

	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Nov-07
	300,000

	Phase II:
	Jul-12
	200,000

		Total:
	500,000

	Amount requested for renewal (phase III) (US $):
	256,000

	Amount recommended for approval for phase III (US $): 
	256,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase III to the Multilateral Fund (US $):
	256,000

	Date of approval of country programme:
	2007

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes):
	

	(a)	Annex A, Group I (CFCs) (average 1995-1997)
	1,798.5

	(b)	Annex A, Group II (halons) (average 1995-1997)
	1,064.0

	(c)	Annex B, Group II (carbon tetrachloride) (average 1998-2000)
	259.2

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	29.8

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	1,468.7

	(f)	Annex E (methyl bromide) (average 1995-1998)
	204.1

	Latest reported ODS consumption (2020) (ODP tonnes) as per Article 7:
	

	(a)	Annex A, Group I (CFCs)
	0.0

	(b)	Annex A, Group II (halons)
	0.0

	(c)	Annex B, Group II (carbon tetrachloride)
	0.0

	(d)	Annex B, Group III (methyl chloroform)
	0.0

	(e)	Annex C, Group I (HCFCs)
	880.5

	(f)	Annex E (methyl bromide)
	0.0

		Total:
	880.5

	Year of reported country programme implementation data:
	2021

	Amount approved for projects (as at December 2021) (US $):
	16,275,038

	Amount disbursed (as at December 2020) (US $):
	11,246,978

	ODS to be phased out  (as at December 2021) (ODP tonnes):
	1,158.79

	ODS phased out (as at December 2020) (ODP tonnes):
	1,026.90



2. Summary of activities and funds approved by the Executive Committee:
	Summary of activities

	Funds approved (US $)

	(a)
	Investment projects:
	10,699,588

	(b)
	Institutional strengthening:
	500,000

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	5,075,450

		Total:
	16,275,038

	(d)
	HFC activities funded from additional voluntary contributions
	0



Progress report
Under phase II of the IS project, the NOU established an e-system to manage ODS trade and a quota system for HCFCs. Issuance of an executive regulation gave the NOU more legal ground to implement and enforce all control measures. The NOU improved the permit requirement to include the "Certificate of Conformity for Exports to Saudi Arabia" provided by the Saudi Standards, Metrology and Quality Organization. This certificate ensures conformity with the Montreal Protocol. A desk study was undertaken on the Regulatory and Policies Impact Assessment in coordination with UNEP to facilitate the implementation of the Kigali Amendment. The NOU held workshops with governmental and private sector stakeholders to raise awareness and enhance compliance with the Protocol. 
Plan of action
In the upcoming phase, Saudi Arabia will continue coordination with all stakeholders to ensure full compliance with the Montreal Protocol and ensure their full engagement and facilitation of the ongoing funded projects. The NOU will continue enhancement of the e-system to improve control measures, include HFCs, and monitor quotas to ensure full compliance with the country’s phase out plans. The NOU will continue to hold workshops to train Customs officers in cooperation with Customs academy; industrial workshops to explore and evaluate the current challenges to adopt the HFC phase-down; and workshops to raise awareness of the Montreal Protocol. The NOU aims for a smooth implementation and early ratification of the Kigali Amendment. The NOU will also continue participation in all regional thematic and network meetings.
Uganda: Renewal of institutional strengthening 
	Summary of the project and country profile
	

	Implementing agency:
	UNEP

	Amounts previously approved for institutional strengthening (US $):
	

	Phase I:
	Jul-94
	64,515

	Phase II:
	Nov-14
	37,226

	Phase III:
	Dec-18
	85,000

	Phase IV:
	Jun-20
	85,000

		Total:
	271,741

	Amount requested for renewal (phase V) (US $):
	85,000

	Amount recommended for approval for phase V (US $): 
	85,000

	Agency support costs (US $):
	0

	Total cost of institutional strengthening phase V to the Multilateral Fund (US $):
	85,000

	Date of approval of country programme:
	1994

	Date of approval of HCFC phase-out management plan:
	2012

	Baseline consumption of controlled substances (ODP tonnes):
	

	(d)	Annex B, Group III (methyl chloroform) (average 1998-2000)
	0.0

	(e)	Annex C, Group I (HCFCs) (average 2009-2010)
	0.2

	(f)	Annex E (methyl bromide) (average 1995-1998)
	6.3

	Latest reported ODS consumption (2021) (ODP tonnes) as per Article 7:
	

	(d)	Annex B, Group III (methyl chloroform)
	0.00

	(e)	Annex C, Group I (HCFCs)
	0.06

	(f)	Annex E (methyl bromide)
	0.00

		Total:
	0.06

	Year of reported country programme implementation data:
	2020

	Amount approved for projects (as at December 2021) (US $):
	1,616,541

	Amount disbursed (as at December 2020) (US $):
	1,147,459

	ODS to be phased out (as at December 2021) (ODP tonnes):
	46.5

	ODS phased out (as at December 2020) (ODP tonnes):
	35.5



Summary of activities and funds approved by the Executive Committee:
	Summary of activities
	Funds approved (US $)

	(a)
	Investment projects:
	586,800

	(b)
	Institutional strengthening:
	271,741

	(c)
	Project preparation, technical assistance, training and other non-investment projects:
	758,000

		Total:
	1,616,541

	(d)
	HFC activities funded from additional voluntary contributions
	50,000



Progress report
During phase IV of the IS, the NOU of Uganda enforced the ODS regulations through the implementation of licensing and quota system. Uganda submitted its country programme and Article 7 data to the Fund and Ozone Secretariats, respectively. The Government of Uganda continued the process of incorporating the Protocol and Kigali Amendment provisions into the review of the new Chemicals Management Regulations. Uganda fully achieved eight out of 15 performance indicators selected for the phase, four performance indicators were partially achieved and three were not assessed (due to the inability to implement planned activities due to COVID-19-imposed restrictions).  
Plan of action
The NOU is committed to implementing the action plan during the upcoming phase to ensure sustained compliance with the Montreal Protocol and its Amendments. The NOU will continue with the training programme for technicians in the RAC sector. Training of Customs officers will be conducted to support the implementation and enforcement of ODS regulations and provisions under the National Environment Act of 2019, and the National Environment (Management of Ozone Depleting Substances and Products) Regulations of 2020. The NOU will also continue with awareness-raising programme through mass media, workshops, and distribution of awareness-raising materials including newspaper supplements, brochures, pamphlets, and factsheets, among others, to different stakeholders.
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Anexo II
CONSIDERACIONES PRELIMINARES DEL COMITÉ EJECUTIVO EN CUANTO A LA RENOVACIÓN DE LOS PROYECTOS DE FORTALECIMIENTO INSTITUCIONAL PRESENTADOS ANTE LA 90ª REUNIÓN

Argelia
1. Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Argelia (fase VII), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para los años 2014 a 2020 del programa país y del Artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata además que el Gobierno de Argelia ha adoptado medidas para eliminar el consumo de HCFC y controlar la importación de SAO por medio de un sistema de licencias y cuotas y de capacitar a funcionarios aduaneros y técnicos en refrigeración. El Comité valora los esfuerzos del Gobierno por reducir el consumo de HCFC y manifiesta su confianza en que durante el próximo bienio seguirá implementando con éxito las actividades que le permitan mantenerse en cumplimiento con el Protocolo de Montreal.
Bahamas
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para las Bahamas (fase VIII), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para los años 2020 y 2021 del programa país y del Artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata además que el Gobierno de las Bahamas ha cumplido en tiempo y forma con el calendario de eliminación de HCFC y que cuenta con un sistema operativo y bien estructurado de licencias y cuotas de importación de HCFC. El Comité también reconoce que el Gobierno ha adoptado medidas para ratificar la Enmienda de Kigali y manifiesta su confianza en que durante el próximo bienio seguirá implementando los proyectos y políticas sectoriales que le permitan cumplir con las metas de eliminación de HCFC y ratificar la Enmienda de Kigali.
Bahrein
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Bahrein (fase XI), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para los años 2019 y 2020 del programa país y del Artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata que el Gobierno de Bahrein ha adoptado medidas para optimizar la legislación y el sistema de licencias electrónicas, capacitar a técnicos de servicio y funcionarios aduaneros, y organizar actividades de extensión. El Comité observa con satisfacción los pasos que el Gobierno ha dado hacia la ratificación de la Enmienda de Kigali, valora sus esfuerzos y manifiesta su confianza en que durante el próximo bienio seguirá implementando las actividades que le permitan cumplir con las siguientes metas del Protocolo de Montreal.
Barbados
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Barbados (fase VIII), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para los años 2019 y 2020 del programa país y del Artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata que el Gobierno de Barbados ha cumplido en tiempo y forma con el calendario de eliminación de HCFC y que cuenta con un sistema operativo y bien estructurado de licencias y cuotas de importación de HCFC, por lo que manifiesta su confianza en que durante el próximo bienio seguirá implementando los proyectos y políticas sectoriales que le permitan cumplir con las metas de eliminación de HCFC y dar inicio a las actividades de reducción de los HFC.
Cabo Verde
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Cabo Verde (fase VIII), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para los años 2020 y 2021 del programa país y del Artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata además que el país cuenta con un sistema operativo de licencias y cuotas de importación y exportación de HCFC, saluda la ratificación de la Enmienda de Kigali en octubre de 2020 y manifiesta su confianza en que durante el próximo bienio el Gobierno de Cabo Verde seguirá adelante con las actividades de eliminación de HCFC y dará inicio a la reducción de los HFC.
Chad
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Chad (fase X), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para los años 2020 y 2021 del programa país y del Artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité observa además que el Gobierno de Chad ha adoptado medidas para eliminar el consumo de HCFC y controlar la importación de SAO por medio de un sistema de licencias y cuotas y de la capacitación de funcionarios aduaneros y técnicos en refrigeración. El Comité valora los esfuerzos del Gobierno por reducir el consumo de HCFC y manifiesta su confianza en que durante el próximo bienio seguirá implementando con éxito los proyectos que le permitan mantenerse en cumplimiento con el Protocolo de Montreal.
Etiopía
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Etiopía (fase IX), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para los años 2020 y 2021 del programa país y del Artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata que el Gobierno de Etiopía ha mantenido en vigor el sistema de licencias y cuotas de importación y exportación de HCFC, ha capacitado a funcionarios aduaneros y técnicos en refrigeración y desarrollado y organizado actividades de sensibilización, por lo que manifiesta su confianza en que durante el próximo bienio el Gobierno seguirá adelante con las actividades que le permitan cumplir con las obligaciones contraídas en virtud el Protocolo de Montreal.
Guinea
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Guinea (fase XII), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para los años 2020 y 2021 del programa país y del Artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité observa además que el Gobierno de Guinea ha adoptado medidas para eliminar el consumo de HCFC y controlar la importación de SAO por medio de un sistema de licencias y cuotas y de capacitar a funcionarios aduaneros y técnicos en refrigeración. El Comité valora los esfuerzos del Gobierno por reducir el consumo de HCFC y manifiesta su confianza en que durante el próximo bienio seguirá implementando con éxito las actividades que le permitan lograr lo previsto en el Protocolo de Montreal y mantenerse en situación de cumplimiento.
Honduras
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Honduras (fase X), el Comité Ejecutivo observa con satisfacción que el país ha dado cumplimiento a los requisitos de presentación de datos del programa país y del Artículo 7 del Protocolo de Montreal y a las obligaciones de eliminación de HCFC allí contempladas. El Comité constata además que el Gobierno de Honduras cuenta con un sistema operativo de licencias y cuotas de importación y exportación de HCFC al que se han integrado los HFC, que se ha capacitado a técnicos en refrigeración en buenas prácticas de refrigeración y manejo de sustancias alternativas, y que se han realizado reuniones consultivas y campañas de sensibilización pública sobre la protección de la capa de ozono. El Comité, por consiguiente, manifiesta su confianza en que durante el próximo bienio el Gobierno seguirá implementando satisfactoriamente las actividades que le permitan cumplir con las siguientes metas de control de HCFC previstas en el Protocolo de Montreal y preparar el inicio de la reducción de los HFC.
Jamaica
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Jamaica (fase XI), el Comité Ejecutivo observa con satisfacción que el país transmitió en marzo de 2022 -es decir, por adelantado- los datos para el año 2021 del programa país y del Artículo 7 que indican el cumplimiento con lo previsto en el Protocolo. Además de observar que el país cuenta con un sistema operativo de licencias y cuotas de HCFC, el Comité constata que, pese a la pandemia del Covid‑19, el Gobierno de Jamaica mantuvo su compromiso de eliminar los HCFC a través de las actividades que implementó en cooperación con sus contrapartes nacionales, por lo que manifiesta su confianza en que durante el próximo bienio el país alcance la reducción del 67,5 por ciento prevista para el año 2025 y ratifique la Enmienda de Kigali.
Lesotho
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Lesotho (fase XI), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para el año 2021 del programa país y del Artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité, además de constatar que el Gobierno de Lesotho cuenta con un sistema de licencias y cuotas para el control de las importaciones de SAO y que se ha capacitado a funcionarios aduaneros y a técnicos en refrigeración y climatización, saluda la ratificación de la Enmienda de Kigali en octubre de 2019 y manifiesta su confianza en que durante el próximo bienio el país seguirá implementando los proyectos y políticas sectoriales que le permitan cumplir con las metas de reducción del Protocolo de Montreal.
Malawi
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Malawi (fase XIII), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para los años 2020 y 2021 del programa país y del Artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata además que el Gobierno de Malawi ha adoptado medidas para eliminar el consumo de HCFC y controlar la importación de SAO por medio de un sistema de licencias y cuotas y de la capacitación de funcionarios aduaneros y de técnicos en refrigeración y climatización, por lo que manifiesta su confianza en que durante el próximo bienio el Gobierno seguirá implementando los proyectos y políticas sectoriales que le permitan cumplir con las metas de reducción del Protocolo de Montreal.
Maldivas
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Maldivas (fase XII), el Comité reconoce con satisfacción los esfuerzos realizados por el Gobierno de Maldivas en cuanto a la aplicación del sistema de licencias para HFC y la oportuna entrega de los datos del Artículo 7 y del programa país a las Secretarías del Ozono y del Fondo, respectivamente. El Comité observa además con satisfacción que Maldivas fue el primer país en culminar con éxito el plan acelerado de gestión para la eliminación de HCFC, y constata asimismo que mantiene un sistema en línea de licencias para HCFC y HFC que le permite cumplir con las obligaciones de eliminación e información, por lo que manifiesta su confianza en que durante el próximo bienio el Gobierno seguirá implementando los proyectos y políticas sectoriales que le permitan cumplir con las futuras metas del Protocolo de Montreal.
Islas Marshall
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Islas Marshall (fase VIII), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para los años 2019 y 2020 del programa país y del Artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata además que, durante la fase VII del proyecto de fortalecimiento institucional, el consumo de SAO de Islas Marshall fue igual a cero. El Comité valora los esfuerzos realizados por el Gobierno al disponer el control obligatorio de los HFC y sus mezclas y modificar las normas de protección de la capa de ozono, iniciativa que se espera concluir durante la siguiente fase. El Comité constata igualmente la activa participación del país en la red regional y los desafíos técnicos que la diferencia horaria y la limitada conectividad de internet plantean a su participación en las reuniones del Protocolo de Montreal. El Comité manifiesta su confianza en que durante el próximo bienio las Islas Marshall continuarán dando cumplimiento a las obligaciones contraídas en virtud del Protocolo de Montreal y velando por integrar la perspectiva de género en la implementación de las actividades.
Níger
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Níger (fase XIII), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para los años 2019, 2020 y 2021 del programa país y del Artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata además que el Gobierno de Níger ha adoptado medidas para eliminar el consumo de HCFC y controlar la importación de SAO por medio de un sistema de licencias y cuotas y de capacitar a funcionarios aduaneros y técnicos en refrigeración y climatización. El Comité valora los esfuerzos del Gobierno por reducir el consumo de HCFC y manifiesta su confianza en que durante el próximo bienio seguirá implementando con éxito las actividades que le permitan mantenerse en cumplimiento con lo previsto en el Protocolo de Montreal.
Qatar
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Qatar (fase VI), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para los años 2019 y 2020 del programa país y del Artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata además que, en el marco del proyecto de fortalecimiento institucional, Qatar logró durante el año 2020 reducir el consumo de HCFC en un 35 por ciento respecto de la base de comparación, que se encuentra en camino a cumplir con sus futuras obligaciones, y que contempla potenciar las iniciativas regulatorias en curso a fin de garantizar un control eficaz del consumo de HCFC. El Comité valora los esfuerzos del Gobierno por reducir el consumo de HCFC y manifiesta su confianza en que durante el próximo bienio superará los desafíos enfrentados durante la fase anterior y seguirá implementando las actividades que prepararán al país para cumplir con las metas del año 2025 y sentar las bases para la ratificación de la Enmienda de Kigali.
Saint Kitts y Nevis
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Saint Kitts y Nevis (fase VIII), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a la Secretaría del Fondo los datos de la ejecución del programa país 2021 y que se encuentra preparando los datos del Artículo 7 que deberá transmitir a la Secretaría del Ozono. El Comité constata además que el Gobierno de Saint Kitts y Nevis ha cumplido en tiempo y forma con el calendario de eliminación de HCFC y que cuenta con un sistema electrónico operativo y bien estructurado de licencias y cuotas de importación de HCFC. El Comité destaca que el Gobierno contempla ratificar la Enmienda de Kigali hacia fines de 2022 y manifiesta su confianza en que durante el próximo bienio seguirá implementando los proyectos y políticas sectoriales que le permitan cumplir con las metas de eliminación de HCFC y ratificar la Enmienda de Kigali.
Arabia Saudita
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Arabia Saudita (fase III), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para los años 2019 y 2020 del programa país y del Artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité valora los esfuerzos del Gobierno de Arabia Saudita por reducir el consumo de HCFC y manifiesta su confianza en que durante el próximo bienio seguirá implementando con éxito las actividades que prepararán al país para lograr las reducciones en el consumo de HCFC contempladas en el Protocolo de Montreal y culminar el proceso de ratificación de la Enmienda de Kigali.
Uganda
Tras tomar conocimiento del informe adjunto a la solicitud relativa al proyecto de fortalecimiento institucional para Uganda (fase V), el Comité Ejecutivo observa con satisfacción que el país ha transmitido a las Secretarías del Fondo y del Ozono, respectivamente, los datos para el año 2020 del programa país y del Artículo 7 que indican el cumplimiento con lo previsto en el Protocolo de Montreal. El Comité constata que el Gobierno de Uganda ha integrado las disposiciones de la Enmienda de Kigali al marco jurídico interno y que ha adoptado medidas para eliminar los HCFC y controlar la importación de SAO por medio de un sistema de licencias y cuotas y de capacitar a funcionarios aduaneros y técnicos en refrigeración y climatización. El Comité, por consiguiente, manifiesta su confianza en que durante el próximo bienio el Gobierno seguirá implementando los proyectos y políticas sectoriales que le permitan cumplir con las obligaciones contraídas en virtud del Protocolo de Montreal.
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