| UNITED NATIONS |  | EP |
| --- | --- | --- |
|  | United Nations Environment Programme | Distr. GENERAL UNEP/OzL.Pro/ExCom/93/25 17 November 2023 ORIGINAL: ENGLISH |

EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Ninety-third Meeting

Montreal, 15-19 December 2023

Item 8(c) of the provisional agenda

CONSOLIDATED BUSINESS PLAN OF THE MULTILATERAL FUND for 2024–2026

# Introduction

# This document presents the consolidated business plans of the Multilateral Fund for 2024–2026 and comprises the business plans for 2024–2026 of bilateral agencies, UNDP, UNEP, UNIDO and the World Bank submitted to the 93rd meeting.

# This business plan document presents the resource allocation plan for the next three years. The plan is expected to result in continued implementation of HCFC phase-out activities including energy efficiency related components pursuant to decision 89/6, implementation of HFC phase-down activities, continued implementation of HFC-23 emission control activities, pilot projects for energy efficiency pursuant to decision 91/65, project preparation for national inventories of banks of waste-controlled substances pursuant to decision 91/66 and continued implementation of other standard activities for the management of Montreal Protocol projects.

# This document consists of the following sections:

- Resource allocation in the business plan for 2024–2026

- Secretariat’s comments

- Adjustments to the consolidated business plan of the Multilateral Fund for 2024–2026

- Other policy issues

- Recommendation

- Resource allocation in the business plan for 2024–2026

# The Secretariat and the bilateral and implementing agencies began their collaborative efforts on the business planning of the Multilateral Fund for 2024–2026 on 22 September 2023 when the initial business plan tables were submitted. Subsequently, bilateral and implementing agencies revised their business plan tables and resubmitted them with the narrative sections. The total value of the revised business plan for 2024–2026 is summarized in table 1.

# Table 1 presents, by year, the value of activities included in the business plan for 2024–2026. At their Thirty-Fifth Meeting, the Parties to the Montreal Protocol adopted a budget for the Multilateral Fund for the 2024–2026 triennium of $965,000,000, with an annual budget of US $321,666,667 for each year of the triennium.

Table 1. Resource allocation in the business plan for 2024–2026 (US $)* – as submitted

| Description | 2024 | 2025 | 2026 | Total (2024–2026) | Total after 2026 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HCFC phase-out management plans (HPMPs) | 39,781,428 | 50,543,871 | 42,474,893 | 132,800,192 | 45,459,768 |
| Approved HCFC production phase-out management plan (HPPMP) | 23,232,000 | 0 | 0 | 23,232,000 | 0 |
| HPMP project preparation (PRP) – stage II | 167,700 | 44,300 | 0 | 212,000 | 0 |
| HPMP stage II | 4,970,041 | 7,491,681 | 11,175,056 | 23,636,779 | 59,785,401 |
| HPMP PRP – stage III | 522,900 | 65,400 | 0 | 588,300 | 0 |
| HPMP stage III | 15,849,471 | 13,725,497 | 26,174,094 | 55,749,063 | 58,617,796 |
| HPMP PRP – stage IV | 70,000 | 0 | 0 | 70,000 | 0 |
| HPMP stage IV | 0 | 0 | 3,691,000 | 3,691,000 | 5,537,000 |
| HPMP – energy efficiency | 4,279,812 | 3,416,240 | 303,300 | 7,999,352 | 0 |
| HPMP verification | 588,600 | 588,600 | 588,600 | 1,765,800 | 0 |
| HCFC activities subtotal | 89,461,952 | 75,875,590 | 84,406,943 | 249,744,485 | 169,399,964 |
| HFC activities |  |  |  |  |  |
| Enabling activities for HFC phase-down | 53,500 | 160,500 | 0 | 214,000 | 0 |
| Approved Kigali HFC implementation plan (KIP) | 0 | 0 | 434,420 | 434,420 | 481,500 |
| Approved HFC-23 emission control | 414,238 | 626,900 | 572,433 | 1,613,571 | 2,123,880 |
| KIP stage I – PRP | 3,140,814 | 1,167,771 | 211,280 | 4,519,864 | 0 |
| KIP stage I | 11,421,557 | 35,200,848 | 31,598,872 | 78,221,277 | 96,379,205 |
| KIP stage I – investment PRP | 32,100 | 0 | 0 | 32,100 | 0 |
| KIP stage I – investment | 3,712,616 | 0 | 0 | 3,712,616 | 0 |
| HFC-23 emissions control | 8,000,000 | 0 | 0 | 8,000,000 | 0 |
| HFC – technical assistance | 678,000 | 0 | 0 | 678,000 | 0 |
| HFC activities subtotal | 27,452,825 | 37,156,019 | 32,817,005 | 97,425,848 | 98,984,585 |
| Other activities |  |  |  |  |  |
| Pilot project for energy efficiency (demonstration, investment and preparation) | 4,764,200 | 1,248,600 | 0 | 6,012,800 | 0 |
| National inventories of banks of waste-controlled substances – PRP | 1,828,750 | 310,300 | 0 | 2,139,050 | 0 |
| Technical assistance – gender mainstreaming | 2,533,910 | 0 | 0 | 2,533,910 | 0 |
| Other activities subtotal | 9,126,860 | 1,558,900 | 0 | 10,685,760 | 0 |
| Standard activities |  |  |  |  |  |
| Institutional strengthening (IS) | 21,695,223 | 1,830,362 | 21,667,356 | 45,192,941 | 0 |
| Core unit | 6,011,529 | 6,053,609 | 6,095,985 | 18,161,122 | 0 |
| Compliance Assistance Programme (CAP) | 11,605,710 | 11,953,882 | 12,312,498 | 35,872,090 | 0 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 7,202,023 | 6,816,624 | 6,964,604 | 20,983,251 | 0 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 | 0 |
| Standard activities subtotal | 47,014,485 | 27,154,476 | 47,540,442 | 121,709,404 | 0 |
| Total | 173,056,123 | 141,744,985 | 164,764,390 | 479,565,498 | 268,384,550 |
| Indicative budget** | 321,666,667 | 321,666,667 | 321,666,667 | 965,000,000 |  |
| Difference | (148,610,544) | (179,921,682) | (156,902,276) | (485,434,502) |  |

* Including agency support costs where applicable.

** Based on the replenishment level for 2024–2026 pursuant to decision XXXV/1.

- Secretariat’s comments

II.1	HCFC activities

# Stage II of HPMPs

# The total level of funding for stage II of HPMPs for 17 low-volume-consuming (LVC) countries to meet 100 per cent reduction of the HCFC baseline amounts to US $6.45 million, including US $3.07 million for 2024–2026 and US $3.38 million for the period after 2026.

# The total level of funding for stage II of HPMPs for seven non-LVC countries amounts to US $76.97 million (including US $20.57 million for 2024–2026 and US $56.41 million for the period after 2026).

# A total of US $212,000 is included in the business plan for project preparation of stage II of HPMPs for five countries for 2024–2026.

# Stage III of HPMPs

# A total of US $114.37 million is planned for stage III of HPMPs for 25 countries (Albania, Angola, Argentina, Armenia, Brazil, Cameroon, China, Egypt, Iran (Islamic Republic of), Jordan, Kuwait, Lebanon, Malaysia, Mexico, Morocco, Peru, the Philippines, Qatar, Senegal, Serbia, Thailand, Timor-Leste, Tunisia, Turkmenistan, and Viet Nam), including US $55.75 million for 2024–2026 and US $58.62 million for the period after 2026..

# A total of US $588,300 is included in the business plan for project preparation for stage III of HPMPs for 11 countries for 2024–2026.

# Stage IV of HPMPs

# A total of US $9.23 million is planned for stage IV of the HPMP for one country (Nigeria) (including US $3.69 million for 2024–2026 and US $5.54 million for the period after 2026) and US $70,000 for project preparation in 2024, in line with decision 91/31(d).

# Energy efficiency for LVC countries

# Decision 89/6 allowed bilateral and implementing agencies, when submitting existing and future stages of HPMPs for LVC countries, to include the funding associated with the need for the introduction of alternatives to HCFCs with low- or zero-global-warming potential (GWP) and for maintaining energy efficiency in the refrigeration servicing sector.

# A total of US $8 million is included in the business plan for energy efficiency activities for 72 LVC countries for 2024–2026.

HPMP verification

# The Secretariat has included an amount of US $588,600 per year for verification reports, assuming that 18 reports, each at a cost of US $32,700, will be prepared (US $1.77 million for 2024–2026).

II.2	HFC activities

# Enabling activities

# HFC activities include enabling activities amounting to US $214,000 in 2024–2025 for two countries (Antigua and Barbuda and the Central African Republic). Both countries have submitted the required letter from their respective Government indicating their intent to make best efforts to ratify the Kigali Amendment as early as possible, in line with decision 79/46(d)(i).

# Project preparation for stage I of KIPs

# A total of US $4.52 million is included in the business plan for project preparation for stage I of KIPs for 26 countries in 2024–2026. In addition, one project preparation for stage I of KIP for an investment project for one country amounting to US $32,100 is included in 2024.

# Of the 27 countries for which project preparation for stage I of KIPs have been included, 20 countries have not yet ratified the Kigali Amendment but have submitted the required letter from their respective Government indicating their intent to make best efforts to ratify the Kigali Amendment.

# Stage I of KIPs

# A total of US $174.6 million is included in the business plan for stage I of KIPs for 100 countries (including US $78.22 million for 2024–2026 and US $96.38 million for the period after 2026). In addition, the business plan also included stage I of KIPs for investment projects for five countries amounting to US $3.71 million in 2024. One of these 100 countries (Thailand) has not yet ratified the Kigali Amendment and has been removed from the business plan.

# HFC-23 emissions control projects

# UNDP’s business plan included one HFC-23 emissions control investment project for one country amounting to US $8 million in 2024.

# HFC technical assistance

# UNEP has included one global HFC technical assistance project, twinning of ozone officers and national energy policymakers to support Kigali Amendment objectives, in the amount of US $678,000 in 2024. Phase I of this project was approved at the 91st meeting.

II.3	Other activities

Pilot projects for energy efficiency (decision 91/65)

# A total of US $6.01 million is included in the business plan under the funding window for pilot projects for energy efficiency (decision 91/65) for 2024–2025 (including US $2.87 million for demonstration projects, US $3.11 million for investment projects and US $34,000 for project preparation activities) for 12 countries (Armenia, the Gambia, Guatemala, Honduras, Jordan, Kenya, Malaysia, Maldives, Mauritania, the Republic of Moldova, Trinidad and Tobago and Viet Nam) and one global project on “demonstrating digital monitoring and management tools to enhance energy efficiency and reduce emission of greenhouse gases in the space cooling and cold chain sectors in Columbia, Lebanon, Panama, Sri Lanka, and Trinidad and Tobago”. The objective of the global project is to support the five countries to pilot digital tools for monitoring and managing air-conditioning and cold chain systems to reduce emission of the greenhouse gases, reduce energy consumption and associated electricity costs, and improve overall maintenance of cooling system proactively. The project preparation for this project is submitted to the 93rd meeting.

Project preparation for national inventories of banks of waste-controlled substances (decision 91/66)

# A total of US $2.14 million is included in the business plan for project preparation for national inventories of banks of waste-controlled substances (decision 91/66) for 2024–2025 for 22 countries (Bosnia and Herzegovina, Burkina Faso, Chile, Cuba, Egypt, Ghana, Indonesia, Jamaica, Jordan, Kyrgyzstan, Libya, Malaysia, Maldives, Mauritania, Nigeria, Panama, Paraguay, Peru, South Africa, Sri Lanka, Thailand, and Uruguay).

Gender mainstreaming technical assistance project

# UNDP and UNIDO’s business plans included two global technical assistance projects for “Increasing gender equality and economic empowerment of women in the refrigeration and air-conditioning (RAC) sectors” amounting to US $2.53 million in 2024. At present, there is no funding window for such technical assistance projects. Further, implementation of the operational gender mainstreaming policy and its associated relevant decisions should be included in each Article 5 country’s national plans to phase out controlled substances.  The issue is presented in section IV on policy issues.

- Adjustments to the consolidated business plan of the Multilateral Fund for 2024–2026

# The adjustments to the consolidated business plan for 2024–2026 were based on relevant decisions of the Executive Committee. In reviewing the revised business plan from the bilateral and implementing agencies for 2024–2026, the Secretariat noted that the following adjustments were not included:

Table 2. Adjustments to the consolidated business plan of the Multilateral Fund for 2024–2026 (US $)* – as proposed by the Secretariat

| Adjustment | 2024–2026 | After 2026 |
| --- | --- | --- |
| HPMP values to reflect the actual amounts approved under the Agreements including tranches of HPMPs that have been submitted to the 93rd meeting | (1,385,755) | (18,511,470) |
| HPMP values to reflect the draft Agreements submitted to the 93rd meeting | (623,686) | (356,373) |
| PRP for stage II of HPMPs pursuant to decision 71/42 | (33,300) | 0 |
| Stage II of HPMPs in non-LVC countries with the refrigeration manufacturing sector based on a maximum cost-effectiveness of US $8.40/kg | (357,683) | (2,692,047) |
| Energy efficiency for LVC countries pursuant decision 89/6 or submitted to the 93rd meeting | (857,001) | 0 |
| KIP values to reflect the draft Agreements submitted to the 93rd meeting | (50,372) | (39,240) |
| PRP for KIPs pursuant to decision 87/50 or submitted to the 93rd meeting | (60,365) | 0 |
| KIPs pursuant to decision 84/46(g) | (8,560,000) | (10,700,000) |
| Servicing sector for stage I of KIPs pursuant to decision 92/37 | (1,561,968) | (3,291,775) |
| Pilot projects for energy efficiency submitted to the 93rd meeting | (33,900) | 0 |
| Preparation for national inventories of banks of waste-controlled substances submitted to the 93rd meeting | (596,600) | 0 |
| Technical assistance (global project on gender mainstreaming) | (2,533,910) | 0 |
| IS pursuant to decision 91/63(d) | 3,184 | 0 |

# * Including agency support costs where applicable.

# Table 3 presents the results of the Secretariat’s proposed adjustments to the consolidated business plan for 2024–2026.

Table 3. Adjusted resource allocation for the business plan for 2024–2026 (US $)*

| Description | 2024 | 2025 | 2026 | Total (2024–2026) | Total after 2026 |
| --- | --- | --- | --- | --- | --- |
| HCFC activities |  |  |  |  |  |
| Approved HPMPs | 40,987,832 | 47,951,712 | 42,474,893 | 131,414,437 | 26,948,298 |
| Approved HPPMP | 23,232,000 | 0 | 0 | 23,232,000 | 0 |
| HPMP PRP – stage II | 134,400 | 44,300 | 0 | 178,700 | 0 |
| HPMP stage II | 4,970,041 | 7,133,999 | 11,175,056 | 23,279,096 | 57,093,354 |
| HPMP PRP – stage III | 522,900 | 65,400 | 0 | 588,300 | 0 |
| HPMP stage III | 15,849,471 | 13,725,497 | 25,550,408 | 55,125,376 | 58,261,422 |
| HPMP PRP – stage IV | 70,000 | 0 | 0 | 70,000 | 0 |
| HPMP stage IV | 0 | 0 | 3,691,000 | 3,691,000 | 5,537,000 |
| HPMP – energy efficiency | 3,726,111 | 3,305,040 | 111,200 | 7,142,351 | 0 |
| HPMP verification | 588,600 | 588,600 | 588,600 | 1,765,800 | 0 |
| HCFC activities subtotal | 90,081,355 | 72,814,548 | 83,591,157 | 246,487,060 | 147,840,075 |
| HFC activities |  |  |  |  |  |
| Enabling activities for HFC phase-down | 53,500 | 160,500 | 0 | 214,000 | 0 |
| Approved KIP | 0 | 0 | 434,420 | 434,420 | 481,500 |
| Approved HFC-23 emission control | 414,238 | 626,900 | 572,433 | 1,613,571 | 2,123,880 |
| KIP stage I – PRP | 3,080,448 | 1,167,771 | 211,280 | 4,459,499 | 0 |
| KIP stage I | 11,414,706 | 30,348,731 | 26,285,500 | 68,048,937 | 82,348,191 |
| KIP stage I – investment PRP | 32,100 | 0 | 0 | 32,100 | 0 |
| KIP stage I – investment | 3,712,616 | 0 | 0 | 3,712,616 | 0 |
| HFC-23 emissions control | 8,000,000 | 0 | 0 | 8,000,000 | 0 |
| HFC – technical assistance | 678,000 | 0 | 0 | 678,000 | 0 |
| HFC activities subtotal | 27,385,608 | 32,303,902 | 27,503,633 | 87,193,143 | 84,953,571 |
| Other activities |  |  |  |  |  |
| Pilot project for energy efficiency (demonstration, investment and preparation) | 4,730,300 | 1,248,600 | 0 | 5,978,900 | 0 |
| National inventories of banks of waste-controlled substances – PRP | 1,232,150 | 310,300 | 0 | 1,542,450 | 0 |
| Technical assistance – gender mainstreaming | 0 | 0 | 0 | 0 | 0 |
| Other activities subtotal | 5,962,450 | 1,558,900 | 0 | 7,521,350 | 0 |
| Standard activities |  |  |  |  |  |
| IS | 22,071,008 | 1,830,362 | 21,294,756 | 45,196,125 | 0 |
| Core unit | 6,011,529 | 6,053,609 | 6,095,985 | 18,161,122 | 0 |
| CAP | 11,605,710 | 11,953,882 | 12,312,498 | 35,872,090 | 0 |
| Secretariat, Executive Committee, and Monitoring and Evaluation costs minus Canadian counterpart | 7,202,023 | 6,816,624 | 6,964,604 | 20,983,251 | 0 |
| Treasurer | 500,000 | 500,000 | 500,000 | 1,500,000 | 0 |
| Standard activities subtotal | 47,390,269 | 27,154,476 | 47,167,842 | 121,712,588 | 0 |
| Total | 170,819,683 | 133,831,827 | 158,262,632 | 462,914,142 | 232,793,645 |
| Indicative budget** | 321,666,667 | 321,666,667 | 321,666,667 | 965,000,000 |  |
| Difference | (150,846,983) | (187,834,840) | (163,404,035) | (502,085,858) |  |

* Including agency support costs where applicable.

** Based on the replenishment level for 2024–2026 pursuant to decision XXXV/1.

- Other policy issues

Budget

# Following adjustments, the value of the activities put forward by the agencies and as reflected in the consolidated business plan is below the overall indicative budget by US $502.09 million for the period 2024–2026.

# It is noted that certain policy issues related to funding including the cost guidelines for HFC phase-down will be under discussions at the 93rd meeting. The adoption of the cost funding guidelines in the manufacturing sectors and other ongoing policy discussions at the Executive Committee, the recent decisions at the Thirty-Fifth Meeting of the Parties and the strengthening of the capacity of the Multilateral Fund institutions including that of the national ozone units, may lead to additional project submissions by the agencies from 2024 onward. The decisions related to all issues at the 93rd meeting could have an impact on the business plan values compared to the levels, as submitted, for the period of 2024–2026.

# Decision XXXV/1 (paragraph 3) of the Thirty-Fifth Meeting of the Parties decided inter alia that the Executive Committee should take action to ensure, to the extent possible, that the entire budget for the triennium 2024–2026 is committed by the end of 2026 […]. In view of the estimates of balance by the end of 2026 based on the business plans submitted by the agencies for the triennium 2024–2026, the Secretariat will take into account discussions and decisions at the 93rd meeting when preparing the financial planning for the triennium 2024–2026 to be presented to the 94th meeting as part of the update on the status of implementation of the 2024–2026 consolidated business plan of the Multilateral Fund.

Activities submitted to the 93rd meeting

# Activities included in the 2023 business plans of bilateral and implementing agencies but not submitted to the 93rd meeting have already been included in the business plan for 2024–2026. In addition, projects and activities submitted at the 93rd meeting after review by the Secretariat but subsequently deferred, would be included in the business plan for 2024–2026.

Further adjustments after the 93rd meeting

# The 2024–2026 business plan could be further adjusted based on the funding levels of new stages of HPMPs and KIPs that will be approved in principle at the 93rd meeting. The Executive Committee may wish to adjust the 2024–2026 business plan based on the level of funds for the HPMPs and KIPs approved in principle at the 93rd meeting.

Pilot projects for energy efficiency (decision 91/65)

# At the 91st meeting, the Executive Committee established a funding window for pilot projects in the amount of US $20 million with the possibility of augmenting that funding window at a future meeting to maintain and/or enhance energy efficiency in the context of HFC phase-down as specified in decision XXVIII/2. A total of US $6.01 million is included in the business plan for 2024–2025 for 12 countries. Taking into account approvals at the 92nd meeting of US $33,900 and submission to the 93rd meeting amounting to US $15,797,367, it is estimated that the funding window for pilot projects for energy efficiency will be exceeded by US $1,844,067; however, the exact value of the remaining balances under this funding window would be available after the 93rd meeting.

# The Secretariat will provide an update on the matter as part of the update on the status of implementation of the 2024–2026 consolidated business plan of the Multilateral Fund and financial planning for the triennium 2024–2026 to be presented at the 94th meeting.

Policy issues in agencies’ business plans

# UNDP raised the following policy issue. UNDP indicated that “The Multilateral Fund for the Implementation of the Montreal Protocol recognizes the need for its activities to address gender inequality and has adopted two recent decisions by the Executive Committee (decisions 84/92 and 92/40) to promote gender mainstreaming in its projects. While UNDP has developed the required tools, such as guidance on how to conduct gender analyses and action plans, promoting gender mainstreaming in its Montreal Protocol portfolio requires additional resources in order to recruit the expertise to conduct these country-specific gender analyses and action plans. Furthermore, the TEAP report assessing the funding requirements for the replenishment 2024-2026 analyzed the funding for gender mainstreaming of other global funds and recognizes that ‘without a requirement to earmark funding for those activities, not all countries will be able to properly respond to gender required actions and will not prioritize it’.”

# In line with this reasoning, UNDP and UNIDO have included in their respective 2024 business plan two global technical assistance projects for “Increasing gender equality and economic empowerment of women in the RAC sectors” amounting to US $2.53 million in 2024 (including US $32,250 for UNDP and US $2,501,660 for UNIDO). The objective of this proposal is to systematize and improve the delivery of actions targeted to gender mainstreaming in the UNDP and UNIDO portfolios, by analyzing the gaps in knowledge and addressing the needs of national ozone units, energy and environment counterparts and RAC sector beneficiaries. Recalling that implementation of the operational gender mainstreaming policy and its associated relevant decisions should be included in each Article 5 country’s national plans to phase out controlled substances, the Secretariat would like to seek guidance from the Executive Committee on whether to reinstate these activities back to the 2024–2026 business plan.

- Recommendation

# The Executive Committee may wish:

## To note the consolidated business plan of the Multilateral Fund for 2024–2026 contained in document UNEP/OzL.Pro/ExCom/93/25;

## To decide whether:

### To adjust the business plan as proposed by the Secretariat in document UNEP/OzL.Pro/ExCom/93/25;

### To further adjust the business plan:

By adding to the 2024 business plan projects and activities that had been deferred at the 93rd meeting;

By taking into account the values approved in principle for new HCFC phase-out management plans and Kigali HFC implementation plans at the 93rd meeting;

## To consider whether to reinstate the global HCFC technical assistance project for “Increasing gender equality and economic empowerment of women in the refrigeration and air-conditioning sectors” for UNDP;

## To consider whether to reinstate the global HCFC technical assistance project for “Increasing gender equality and economic empowerment of women in the refrigeration and air-conditioning sectors” for UNIDO; and

## To endorse the consolidated business plan of the Multilateral Fund for 2024–2026, as adjusted by the Secretariat [and the Executive Committee] taking into consideration relevant decisions taken at the 93rd meeting, while noting that endorsement did not denote approval of the projects identified therein or their funding or tonnage levels.

UNEP/OzL.Pro/ExCom/93/1

UNEP/OzL.Pro/ExCom/93/26

UNEP/OzL.Pro/ExCom/93/27

UNEP/OzL.Pro/ExCom/93/28

UNEP/OzL.Pro/ExCom/93/29

UNEP/OzL.Pro/ExCom/93/30

The total initial business plan values for 2024–2026 were US $482.91 million and the total after 2025, US $247.45 million.

Decision XXXV/1

To allow Nigeria to submit stage IV of its HPMP in 2025 and the request for the associated project preparation in 2023.

Decision 61/46(c) requires verification reports for a sample of 20 per cent of the LVC countries with approved HPMPs.

KIPs are allowed inclusion of such plans in the business plan only for countries that had ratified the Kigali Amendment (decision 84/46(g)).

As agreed at the Inter-agency coordination meeting.